## Chipsealing
Project | HAWKES BAY NOC CONTRACT | [6 empty] | ITP No.: |  | HB
Client | NZTA | [6 empty] | Revision : |  | 2
Description of Work | CHIP RESEALING
Prepared By | Arn Stone | [6 empty] | Date |  | 2022-09-14
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Inspection Point
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C or N |  |  |  | Y/N | Y/N
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
1. Procurement | Chipseal Resurfacing
What do we need to do to comply with the specification? e.g approval of materials such as concrete etc. | Binder - Penetration Grade | NZTA M01: 2020 | Table 6.1 | Property Test | per Bulk shipment/grade | Bitumen Supplier/ Surfacing Project Manager | IANZ Report's | C |  | C | N | N | Y
| Binder - Polymer Modified Emulsion | Higgins Internal Specification | % PMB Required, PH, Residue by Evaporation, Viscosity | Property Test | 1/100,000 litres supplied |  |  | C |  | C | N | N | Y
| Source Property -Coarse Aggregate - Crushing Resistance | NZTA M06: 2019 | <10% fines under 230kN minimum | Crushing Resistance | 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009) |  |  | C |  | C | N | Y | N
| Source Property -Coarse Aggregate - Weathering Resistance |  | AA or BA | Weathering Quality Index |  |  |  | C |  | C | N | Y | N
| Production Property - Skid Resistance | NZTA T/10 | Meet Skid performance Requirement | PSV | Each Site |  |  | C |  | C | N | Y | N
| Production Property - Cleaness Value | NZTA M06: 2019 | G2 - 89 min, G3 - 87 min, G4 - 85 min | Cleaness Value | Per Stockpile <100m3 - 1 Sample 100-500m3 - 2 Samples >500m3 3 Samples |  |  | C |  | C | N | Y | N
| Production Property - Particle Size/Shape |  | As per Table 2 and 3 | Particle Size/Shape |  |  |  | C |  | C | N | Y | N
| Production Property - Broken Faces |  | 98% | Broken Faces |  |  |  | C |  | C | N | Y | N
2. Construction | Chip Seal Resurfacing
What do we need to do to comply with the specification, drawings, and quality requirements during the construction process? e.g placement of materials such as concrete or fill material and required testing. | Chipseal Designs | HB NOC Design Report, Chipsealing in NZ, NZTA P/17 | Client Approval | Review | Annual | Surfacing Project Manager | HB NOC Design Report Acceptance | C |  | C | N | Y | N
| Finalise Sprayrate | HB NOC Design Report, Chipsealing in NZ, NZTA P/17 | N/A | Review | Per Site | Surfacing Project Manager | Site/Spray Instruction | C |  | C | C | N | Y
| Check weather | N/A | Not foggy or raining or wet surface. Base Temp ≥ 10ºC and rising. No rain forecast in next 24 hours | Weather Forecast | Prior to starting | Surfacing Project Manager | Daily Report, Chip Sealing Quality and Site Record | S |  | S | C | N | Y
| Ensure Limits of site are marked | HB NOC Design Report | Visual Inspection | Visual | Prior to start Sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Establish TTM | TMP | Comply with TMP | Visual | Per Site | Surfacing Supervisor / STMS | Daily Diary / STMS Record | C |  | C | C | N | Y
| Sweep surface clean of deleterious material | P/17 | Visual Inspection | Tractor Broom | Each site, prior to start of sealing | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Confirm correct treatment(s) and chip | HB NOC Design Report | Details/chip correct | Visual | Per Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Cutback Bitumen Blend | RNZ 9803_0513 | +/- 2PPH Cutter, +ve for Adhesion agent presence | Sample and test | 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed | Surfacing Project Manager, Surfacing Supervisor | IANZ Report's | C |  | C | C | N | Y
| Bitumen Application Rate | E/2 Certificate, Seal Design / Spray Instruction | Current E/2 Certificate +/- 4% per Spray Run | Test, Review | Per Sprayer, per Site | Surfacing Project Manager, Surfacing Supervisor | E/2 Certificate. Spray Sheets | C |  | C | C | N | Y
| Chip Application Rates | Chipsealing in NewZealand | As per Chipping Guide | Record | Daily | Surfacing Supervisor | Chip application check sheet. Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Rolling | Chipsealing in NewZealand | Mimimum as per CS in NZ - Bit volume / 3600 | Record | Per Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Cleanup | Chipsealing in NewZealand | Site including adjacent surfaces free of loose chip | Visual | Per Site | Surfacing Supervisor | Chip Sealing Quality and Site Record | C |  | C | C | N | Y
| Removal of TTM | TMP | Comply with TMP | Record | Per Site | STMS | STMS Record | C |  | C | C | N | Y
| RAMM Data | RAMM Xcel | Comply with NZTA format, contractor paid on completion of RAMM data | Record | Per Site | Project Manager | RAMM Xcel spreadsheet | C |  | C | C | Y | Y
| Resurfacing Construction Completion report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Per Site | Resurfacing Construction Completion report | STMS Record | C |  | C | C | N | Y
| Chipseal Post-Verification Testing and Report | NOC; MS 6.1.3 | Comply with Requirement of NOC MS 6.1.3 | Record | Per Site | Surfacing Manager | Chipseal Post-Verification Testing and Report | C |  | C | C | N | Y
S - Subcontractor |  | C – Contractor- Higgins |  |  | N – Client Representative (NZTA)

## TAC
Project | HB NOC CONTRACT | [6 empty] | ITP No.: |  | HB
Client | NZTA | [6 empty] | Revision : |  | 2
Description of Work | ASPHALT RESURFACING
Prepared By | Arn Stone | [6 empty] | Date |  | 2022-09-14
INSPECTION AND TEST PLAN (ITP)
Operation or Task Category | Task Description | Controlling Documents | Acceptance Criteria | Inspection or Test |  |  | Verifying Document | Inspection / Test Authority |  |  |  | Hold Point | Witness Point
| (e.g. procurement, temp works, construction activities) | (e.g. list specifications & clause, drawing) | (e.g. slump value, cylinder strength, etc.) | Method | Frequency | Responsible Person | (e.g. test result, pour record, material approval) | S, C or E |  |  |  | Y/N | Y/N
|  |  |  | (e.g. visual inspection, slump test) |  |  |  | Conduct | Witness | Produce Record | Approval
1. Procurement | Asphalt
What do we need to do to comply with the specification? e.g approval of materials such as concrete etc. | Binder - Penetration Grade | NZTA M01: 2020 | Table 6.1 | Property Test | Approvals are for a period of five years | Bitumen Supplier/Project Manager | IANZ Report | S |  | S |  | N | N
|  | TNZ P11: 2007 | Table 5.2 Lab Mix Design Volumetric and Physical requirements |  |  | Aggregate Supplier / Project Manager
| Source Property -Coarse Aggregate | TNZ P11: 2007 | 230kN minimum | Crushing Resistance | 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
|  |  | AA or BA | Weathering Quality Index
| Production Property -Coarse Aggregate | SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007 | ≥ 58. (At least 85% by mass of minimum PSV) | PSV
|  | RPT-21711902a-PVT-PV310-H01 | Table 3.13 for various sites
| Source Property -Fine Aggregate | TNZ P11: 2007 | 130kN minimum | Crushing Resistance | 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
| Production Property- Blended Coarse Agregateate |  | 2.25 max | Particle Shape | 1/500m³ (Section6 of RNZ 9805:2009)
|  |  | 98% | Broken Faces
|  |  | Report Value-5 minimum | Cleaness Value
| Design Mix | TNZ P11: 2007 | Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements |  | 10 days minimum prior to paving | Project Manager |  | S |  | S | E | Y | N | Note: Verify the type of mix specified in the contract and confirm with the laboratory-David Jones. Allow 6weeks for new desig mix.
3. Construction | Asphalt
What do we need to do to comply with the specification, drawings, and quality requirements during the construction process? e.g placement of materials such as concrete or fill material and required testing. | Production Property Test | SPC-2171902a-PVT-PV3006-H-01 | Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four | Grading | 1/>30mimutes production run and 2/>5 hours production run | Project Manager | IANZ Report | S |  | S |  | N | N
|  |  |  | Binder Content |  |  | IANZ Report | S |  | S |  | N | N
|  | TNZ TM6002:2006 | Report Value | Maximum Specific Gravity |  |  | IANZ Report | S |  | S |  | N | N
|  | TNZ P11: 2007 | ±10 oC from recommended mixing temperature | Ave temperature | Any truck load |  | IANZ Report | S |  | S |  | N | N
| Ensure accurate survey setting out is in place. | For Construction Drawing | Visual Inspection | Survey set out | Prior to start paving |  | Survey Record | S | C | S |  | N | Y
| Check weather |  | Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers) | Weather Forecast | Prior to starting |  | - | S |  | S |  | N | N
| Ensure previous layer is broomed clean. |  | Visual Inspection | truck broom | Prior to start paving | Supervisor-Paving | - | S | C | S |  | N | Y
| Layer Thickness | SPC-2171902a-PVT-PV3006-H-01 | ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications | As-built survey |  |  | IANZ Report | S |  | S |  | N | N
| Surface Shape | SPC-2171902a-PVT-PV3006-H-01 | ≤5mm | 5m straigt edge | During paving operation |  | Recod Sheet | S |  | S |  | N | N
| Surface Texture | NZTA M10: 2023 | Table 3 | Laser Profilometer | every 10m | Project Manager | IANZ Report | S |  | S |  | N | N
| Ride quality | 10. Appendices to Principal's Requirement | 50 NAASRA count as a 95%tile for every 100m rolling section | NAASRA | Upon 100% completion of OGPA layer and at expiry of defects liabilty period |  | IANZ Report | S |  | S |  | N | N
| As-Built |  | Visual Inspection | Survey | Upon completion |  | As-Built | S |  | S |  | N | N
S - Subcontractor -Higgins |  | C – Contractor- Fletcher Construction |  |  | E – Engineer/Client Representative (BECA+PB)