## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Asphalt Resurfacing - HAWKES BAY NOC CONTRACT | itp |  |  |  |  | ITP - Asphalt Resurfacing - HAWKES BAY NOC CONTRACT
section | 1. Procurement
checkpoint | Binder - Penetration Grade (1)
label | Controlling Documents - NZTA M01: 2020
label | Acceptance Criteria - Table 6.1
label | Method - Property Test
label | Frequency - Approvals are for a period of five years
label | Responsible Person - Bitumen Supplier/Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Binder - Penetration Grade (2)
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Source Property -Coarse Aggregate (1)
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - 230kN minimum
label | Method - Crushing Resistance
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Source Property -Coarse Aggregate (2)
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - AA or BA
label | Method - Weathering Quality Index
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property -Coarse Aggregate (1)
label | Controlling Documents - SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007
label | Acceptance Criteria - ≥ 58. (At least 85% by mass of minimum PSV)
label | Method - PSV
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property -Coarse Aggregate (2)
label | Controlling Documents - RPT-21711902a-PVT-PV310-H01
label | Acceptance Criteria - Table 3.13 for various sites
label | Method - PSV
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Source Property -Fine Aggregate
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - 130kN minimum
label | Method - Crushing Resistance
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property- Blended Coarse Agregateate (1)
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - 2.25 max
label | Method - Particle Shape
label | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property- Blended Coarse Agregateate (2)
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - 98%
label | Method - Broken Faces
label | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property- Blended Coarse Agregateate (3)
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - Report Value-5 minimum
label | Method - Cleaness Value
label | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | Responsible Person - Aggregate Supplier / Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Design Mix
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements
label | Frequency - 10 days minimum prior to paving
label | Responsible Person - Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
label | Approval - E
label | Note: Verify the type of mix specified in the contract and confirm with the laboratory-David Jones. Allow 6weeks for new desig mix.
holdpoint | HOLD POINT
section | 3. Construction
checkpoint | Production Property Test (1)
label | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
label | Acceptance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | Method - Grading
label | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | Responsible Person - Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property Test (2)
label | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
label | Acceptance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | Method - Binder Content
label | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | Responsible Person - Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property Test (3)
label | Controlling Documents - TNZ TM6002:2006
label | Acceptance Criteria - Report Value
label | Method - Maximum Specific Gravity
label | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | Responsible Person - Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Production Property Test (4)
label | Controlling Documents - TNZ P11: 2007
label | Acceptance Criteria - ±10 oC from recommended mixing temperature
label | Method - Ave temperature
label | Frequency - Any truck load
label | Responsible Person - Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Ensure accurate survey setting out is in place.
label | Controlling Documents - For Construction Drawing
label | Acceptance Criteria - Visual Inspection
label | Method - Survey set out
label | Frequency - Prior to start paving
label | Responsible Person - Project Manager
label | Verifying Document - Survey Record
label | Conduct - S
label | Witness - C
label | Produce Record - S
label | Witness Point - Y
checkpoint | Check weather
label | Acceptance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers)
label | Method - Weather Forecast
label | Frequency - Prior to starting
label | Responsible Person - Project Manager
label | Conduct - S
label | Approval - S
checkpoint | Ensure previous layer is broomed clean.
label | Acceptance Criteria - Visual Inspection
label | Method - truck broom
label | Frequency - Prior to start paving
label | Responsible Person - Supervisor-Paving
label | Conduct - S
label | Witness - C
label | Produce Record - S
label | Witness Point - Y
checkpoint | Layer Thickness
label | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
label | Acceptance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | Method - As-built survey
label | Responsible Person - Supervisor-Paving
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Surface Shape
label | Controlling Documents - SPC-2171902a-PVT-PV3006-H-01
label | Acceptance Criteria - ≤5mm
label | Method - 5m straight edge
label | Frequency - During paving operation
label | Responsible Person - Supervisor-Paving
label | Verifying Document - Recod Sheet
label | Conduct - S
label | Produce Record - S
checkpoint | Surface Texture
label | Controlling Documents - NZTA M10: 2023
label | Acceptance Criteria - Table 3
label | Method - Laser Profilometer
label | Frequency - every 10m
label | Responsible Person - Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | Ride quality
label | Controlling Documents - 10. Appendices to Principal's Requirement
label | Acceptance Criteria - 50 NAASRA count as a 95%tile for every 100m rolling section
label | Method - NAASRA
label | Frequency - Upon 100% completion of OGPA layer and at expiry of defects liabilty period
label | Responsible Person - Project Manager
label | Verifying Document - IANZ Report
label | Conduct - S
label | Produce Record - S
checkpoint | As-Built
label | Acceptance Criteria - Visual Inspection
label | Method - Survey
label | Frequency - Upon completion
label | Responsible Person - Project Manager
label | Verifying Document - As-Built
label | Conduct - S
label | Produce Record - S