## res_ITC 12 - R11 and R16 Stormw
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Chip Resealing - HAWKES BAY NOC CONTRACT | itp |  |  |  |  | ITP - Chip Resealing - HAWKES BAY NOC CONTRACT
section | 1. Procurement
checkpoint | Binder - Penetration Grade
label | Controlling Documents - NZTA M01: 2020
label | Acceptance Criteria - Table 6.1
label | Method - Property Test
label | Frequency - per Bulk shipment/grade
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
label | Inspection Point - Y
checkpoint | Binder - Polymer Modified Emulsion
label | Controlling Documents - Higgins Internal Specification
label | Acceptance Criteria - % PMB Required, PH, Residue by Evaporation, Viscosity
label | Method - Property Test
label | Frequency - 1/100,000 litres supplied
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
label | Inspection Point - Y
checkpoint | Source Property -Coarse Aggregate - Crushing Resistance
label | Controlling Documents - NZTA M06: 2019
label | Acceptance Criteria - <10% fines under 230kN minimum
label | Method - Crushing Resistance
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Source Property -Coarse Aggregate - Weathering Resistance
label | Controlling Documents - NZTA M06: 2019
label | Acceptance Criteria - AA or BA
label | Method - Weathering Quality Index
label | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Skid Resistance
label | Controlling Documents - NZTA T/10
label | Acceptance Criteria - Meet Skid performance Requirement
label | Method - PSV
label | Frequency - Each Site
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Cleaness Value
label | Controlling Documents - NZTA M06: 2019
label | Acceptance Criteria - G2 - 89 min, G3 - 87 min, G4 - 85 min
label | Method - Cleaness Value
label | Frequency - Per Stockpile
label | ○ <100m3 - 1 Sample
label | ○ 100-500m3 - 2 Samples
label | ○ >500m3 - 3 Samples
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Particle Size/Shape
label | Controlling Documents - NZTA M06: 2019
label | Acceptance Criteria - As per Table 2 and 3
label | Method - Particle Size/Shape
label | Frequency - Per Stockpile
label | ○ <100m3 - 1 Sample
label | ○ 100-500m3 - 2 Samples
label | ○ >500m3 - 3 Samples
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Production Property - Broken Faces
label | Controlling Documents - NZTA M06: 2019
label | Acceptance Criteria - 98%
label | Method - Broken Faces
label | Frequency - Per Stockpile
label | ○ <100m3 - 1 Sample
label | ○ 100-500m3 - 2 Samples
label | ○ >500m3 - 3 Samples
label | Responsible Person - Bitumen Supplier/ Surfacing Project Manager
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
section | 2. Construction
checkpoint | Chipseal Designs
label | Controlling Documents - HB NOC Design Report, Chipsealing in NZ, NZTA P/17
label | Acceptance Criteria - Client Approval
label | Method - Review
label | Frequency - Annual
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - HB NOC Design Report Acceptance
label | Conduct - C
label | Produce Record - C
label | Approval - N
holdpoint | HOLD POINT
checkpoint | Finalise Sprayrate
label | Controlling Documents - HB NOC Design Report, Chipsealing in NZ, NZTA P/17
label | Acceptance Criteria - N/A
label | Method - Review
label | Frequency - Per Site
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - Site/Spray Instruction
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Check weather
label | Controlling Documents - N/A
label | Acceptance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 10ºC and rising. No rain forecast in next 24 hours
label | Method - Weather Forecast
label | Frequency - Prior to starting
label | Responsible Person - Surfacing Project Manager
label | Verifying Document - Daily Report, Chip Sealing Quality and Site Record
label | Conduct - S
label | Produce Record - S
label | Approval - C
label | Inspection Point - Y
checkpoint | Ensure Limits of site are marked
label | Controlling Documents - HB NOC Design Report
label | Acceptance Criteria - Visual Inspection
label | Method - Visual
label | Frequency - Prior to start Sealing
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Establish TTM
label | Controlling Documents - TMP
label | Acceptance Criteria - Comply with TMP
label | Method - Visual
label | Frequency - Per Site
label | Responsible Person - Surfacing Supervisor / STMS
label | Verifying Document - Daily Diary / STMS Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Sweep surface clean of deleterious material
label | Controlling Documents - P/17
label | Acceptance Criteria - Visual Inspection
label | Method - Tractor Broom
label | Frequency - Each site, prior to start of sealing
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Confirm correct treatment(s) and chip
label | Controlling Documents - HB NOC Design Report
label | Acceptance Criteria - Details/chip correct
label | Method - Visual
label | Frequency - Per Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Cutback Bitumen Blend
label | Controlling Documents - RNZ 9803_0513
label | Acceptance Criteria - +/- 2PPH Cutter, +ve for Adhesion agent presence
label | Method - Sample and test
label | Frequency - 1 Sample per Per Sprayer load, tested at frequency of 1 per 100,000l sprayed
label | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
label | Verifying Document - IANZ Report's
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Bitumen Application Rate
label | Controlling Documents - E/2 Certificate, Seal Design / Spray Instruction
label | Acceptance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
label | Method - Test, Review
label | Frequency - Per Sprayer, per Site
label | Responsible Person - Surfacing Project Manager, Surfacing Supervisor
label | Verifying Document - E/2 Certificate. Spray Sheets
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Chip Application Rates
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - As per Chipping Guide
label | Method - Record
label | Frequency - Daily
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip application check sheet. Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Rolling
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Mimimum as per CS in NZ - Bit volume / 3600
label | Method - Record
label | Frequency - Per Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Cleanup
label | Controlling Documents - Chipsealing in NewZealand
label | Acceptance Criteria - Site including adjacent surfaces free of loose chip
label | Method - Visual
label | Frequency - Per Site
label | Responsible Person - Surfacing Supervisor
label | Verifying Document - Chip Sealing Quality and Site Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Removal of TTM
label | Controlling Documents - TMP
label | Acceptance Criteria - Comply with TMP
label | Method - Record
label | Frequency - Per Site
label | Responsible Person - STMS
label | Verifying Document - STMS Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | RAMM Data
label | Controlling Documents - RAMM Xcel
label | Acceptance Criteria - Comply with NZTA format, contractor paid on completion of RAMM data
label | Method - Record
label | Frequency - Per Site
label | Responsible Person - Project Manager
label | Verifying Document - RAMM Xcel spreadsheet
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
holdpoint | HOLD POINT
checkpoint | Resurfacing Construction Completion report
label | Controlling Documents - NOC; MS 6.1.3
label | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
label | Method - Record
label | Frequency - Per Site
label | Responsible Person - Resurfacing Construction Completion report
label | Verifying Document - STMS Record
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y
checkpoint | Chipseal Post-Verification Testing and Report
label | Controlling Documents - NOC; MS 6.1.3
label | Acceptance Criteria - Comply with Requirement of NOC MS 6.1.3
label | Method - Record
label | Frequency - Per Site
label | Responsible Person - Surfacing Manager
label | Verifying Document - Chipseal Post-Verification Testing and Report
label | Conduct - C
label | Produce Record - C
label | Approval - C
label | Inspection Point - Y