## Checklists
PROJECT NAME: Industry Central Land Swap
Client: Alder Constructions
type | name | values
checklist | ITP-003 - Installation of Stormwater Drainage (Completion)
section | Pre-Construction
Text | Date Works Commenced:
checkpoint | All materials delivered to site have been inspected thoroughly by RCC Earthworks and the Client and: a) Are free of damage/cracks b) Pipe class, type and size matches plans. (upload images of damaged materials here)
Section | Construction
Checkpoint | Pits/Trenches set out clearly & accurately
Checkpoint | Pits & Trenches excavated to depth and checked with laser (allowed for 100mm bedding)
Checkpoint | Pits Installed at correct height and orientation
Checkpoint | Trench bedding material installed as per specification
Checkpoint | Pipe laid to grade (as per drawings) ensuring socket faces upstream and is free of foreign materials prior to installation of adjoining pipe
Checkpoint | Each joint visually inspected (rubber rings, witness marks, etc) and lifting holes plugged
Checkpoint | Haunching compliant and accepted by the client.
Section | Backfill
checkpoint | Suitable material backfilled in compacted layers
Section | Quality Assurance
Text | Date Section Completed
Checkpoint | Compaction testing Completed and Complies (attach compaction test results)
Checkpoint | CCTV Carried out upon completion of works
Text | CCTV Link:
Checkpoint | Lean Mix / Concrete dockets attached (if applicable)
Checkpoint | Quarry / Material Certificates attached
Checkpoint | Pipe / Pit / Fitting Certificates attached
Checkpoint | Images of the works
Text | Additional Comments
signoff | Signatures