## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 87bbeb4f-4845-407d-8032-dc2c85176959 |  | checklist | Daily Pre Start - Date: |  |  |  |  | Yes | H&S - Daily Pre Start | 027fe9ca-73fd-4697-be4c-76e678d2df15
checkpoint-status | b28c82bd-59df-4067-9cee-caca688867c9 |  | checkpoint | Attendees documented
checkpoint-status | 50f9a964-ea42-4ee1-8561-8ab12aab3dc1 |  | checkpoint | Where is each person working and what are they doing?
checkpoint-status | c46c94c6-c047-4dc6-9e04-5397954f49b6 |  | checkpoint | Are any permits required?
checkpoint-status | d99aa5fd-0fa5-4640-9e00-8d3c8931cf1b |  | checkpoint | Are there any work Hazards?
checkpoint-status | 994640a6-7cdc-4831-a9e8-6e4fd4ad5e17 |  | checkpoint | A JSEA been completed & Approved?
checkpoint-status | 01d96c67-8fd3-4609-87ca-e024494d1529 |  | checkpoint | Are there any concerns; Safety or Production?
checkpoint-status | d13c9e3f-2384-4da4-b9f0-5492effb0394 |  | checkpoint | Everyone has got their minimum PPE for site and task related PPE
checkpoint-status | 019958d3-df80-4f44-9b77-87f54bc517ae |  | checkpoint | All plant tagged and in good condition
checkpoint-status | eb59b879-17ad-4af8-9a4d-f1735ac0a27b |  | checkpoint | All employees have attended this meeting and are aware of their roles in safety and the daily hazards
checklist-flat | ed7f8029-d180-44f3-9e3f-1dc567a16969 |  | checklist | Cedar Cladding |  |  |  |  | Yes | QA - Cedar Cladding | 14655bd6-2cdd-44b2-a409-da113d45a282
checkpoint-status | 0ac178e3-2d1e-4044-bae5-7da19c055cdb |  | checkpoint | Cavity Inspected and passed
checkpoint-status | 1acd0eef-33ff-4a8e-bed2-1cd1f46d7680 |  | checkpoint | Datums set correctly
checkpoint-status | ded67d86-01e9-4f34-9621-65692658466c |  | checkpoint | All flashings and penetrations set and sealed
checkpoint-status | 0c04e9dc-0061-4fa0-a8a8-64c29b2eaf2b |  | checkpoint | Corners formed correctly
checkpoint-status | 0f70f43e-e153-485d-b2e7-907b8b81b992 |  | checkpoint | Joints formed correctly
checkpoint-status | bb0781ec-664d-4965-a62d-d796b00009aa |  | checkpoint | Nailed in alignment
checkpoint-status | 2846ba48-fda7-408c-8193-31cf612c0903 |  | checkpoint | Drip Edges Straight
checkpoint-status | aea829a8-5f85-4a7e-97f8-311e718d26b5 |  | checkpoint | Painting to exposed edges
checkpoint-status | a8a6703e-e29c-4c16-a44f-f946d775467b |  | checkpoint | Cedar complete
checklist-flat | d5893a6c-67eb-4e4d-adc6-6af3ebdae06c |  | checklist | Trims |  |  |  |  | Yes | QA - Trims | 16f2ca6f-52cf-4905-a474-427f9eb1f1d4
checkpoint-status | 7416a583-77d9-4bf3-8961-f8bddfb76395 |  | checkpoint | Correct trim used
checkpoint-status | 123e2d53-670e-44f2-b76d-20aade6cfde8 |  | checkpoint | All internal comers scribed
checkpoint-status | 807e62ec-3a3c-47e6-8927-341b85a514b1 |  | checkpoint | Adhesive applied to skirting
checkpoint-status | 4cb12946-aa3f-424d-b9be-748c5698bec8 |  | checkpoint | All external comers neat
checkpoint-status | 834ab9dc-e6d2-4616-b665-04aa1d895e59 |  | checkpoint | Skirting fixed correctly and all edges sanded
checkpoint-status | 42bdc511-2699-4626-bea6-cbef55c0857f |  | checkpoint | Areas complete ready for paint
checklist-flat | 1a31280d-9d6c-4808-b5f7-e5037836840b |  | checklist | Wrapshield |  |  |  |  | Yes | QA - Wrapshield | 1c4bbdc2-4a94-4a42-b5b3-2deea31385a9
checkpoint-status | 32121524-e05e-4558-bcd1-1698e0de935d |  | checkpoint | Area tidy and accessible
checkpoint-status | 6e1033c4-7793-4b05-94d0-b074a30db510 |  | checkpoint | All surfaces clean of debris and dry at install
checkpoint-status | daf6cf11-abda-4ad9-b769-ac67e2074f5c |  | checkpoint | Method of direction ok
checkpoint-status | a3433b41-ddca-46e9-8d50-d319c9650eed |  | checkpoint | All laps 6 inches horizontally 3 inches vertically
checkpoint-status | 4e38f2df-307f-4cd8-b8e6-37b5168c8840 |  | checkpoint | Vertical Seams Staggered
checkpoint-status | 62808366-4e31-46a8-b817-21335ca8fc51 |  | checkpoint | Roller used for Adhesion at seams
checkpoint-status | df57b2de-d9e3-4f06-b341-82a5ffb71b46 |  | checkpoint | Penetrations sealed
checkpoint-status | 3c6e93fd-ecc8-4645-b96a-1fc30c66e36f |  | checkpoint | Handover
checkpoint-status | 4e936627-23a5-4b0c-9a3a-917f72c35991 |  | checkpoint | Area left tidy and accessible
checklist-flat | c103be75-bc70-4074-9839-449933e933b0 |  | checklist | Louvre Install |  |  |  |  | Yes | QA - Louvre Install | 1fe0b1f0-b010-4590-b6f3-a030245db35a
checkpoint-status | d968a6db-2971-4573-be5a-00782011aa88 |  | checkpoint | Correct Location
checkpoint-status | 8c90808c-83b7-49f6-9203-02e3f5c6eeb7 |  | checkpoint | Louvre fixed level
checkpoint-status | b0dc7b73-bc84-42b4-9ee0-2803267e0201 |  | checkpoint | Correct fixing / spacings as per manufacturer / engineer detail
checkpoint-status | 17e3bda0-b9a4-4141-bf30-714956402c8b |  | checkpoint | Sealant applied correctly
checkpoint-status | 08e6039f-f9c9-4f7c-84c4-fadbcfa4909b |  | checkpoint | Job complete and area left clean and tidy
checklist-flat | 56277bc6-4462-4db4-8482-40a9ae2ceb19 |  | checklist | Weatherboards |  |  |  |  | Yes | QA - Weatherboards | 321fb013-d2c6-44bb-8b53-374b70dd021b
checkpoint-status | e5be9eab-2547-4d8a-bb68-2cacf3b36d0a |  | checkpoint | Plans/Specs followed
checkpoint-status | 950f0dc2-3c4b-40ce-918a-00bec245cd24 |  | checkpoint | Datums for weatherboards set correctly
checkpoint-status | 98fd60f0-a0ad-42b2-96df-bdc626491804 |  | checkpoint | Weatherboards cut with primed ends
checkpoint-status | 9ee36807-a391-4255-b7eb-a6d9d25a7aa6 |  | checkpoint | Installed and Nailed to every Stud location with Stainless Stud R Jolt
checkpoint-status | 01aa52ce-bb20-45b7-aefc-30f15ae6c744 |  | checkpoint | Scribers/soakers installed
checkpoint-status | bb08eda1-771b-4455-923f-de82226e016b |  | checkpoint | Sealant applied
checkpoint-status | 522caa2a-f3bc-45ff-9c2f-0c00ef3280d6 |  | checkpoint | Area complete
checklist-flat | 18d6985c-0d5a-48b8-ba58-08e667e4d35a |  | checklist | External Framing |  |  |  |  | Yes | QA - External Framing | 39a67a08-e1df-415a-ae2f-ab3fcae58eb1
checkpoint-status | 90478d13-7c6d-4a10-aa48-fabd3a1268e5 |  | checkpoint | Plans / Specs followed and correct type of timber used
checkpoint-status | ae6be2d2-729b-41f7-b462-29653f5b676e |  | checkpoint | Check for location
checkpoint-status | 1c5c8902-62bf-4e4b-9cc2-2730164c112f |  | checkpoint | Bolted at correct centres (please indicate)
checkpoint-status | d9581e05-5d14-43e2-9d80-4a31e7d1ad0d |  | checkpoint | Studs installed (Plumb)
checkpoint-status | 1be596a6-9e7c-431a-8cb9-18bea84ff1d1 |  | checkpoint | Nogs installed (Level)
checkpoint-status | a2a26082-50fc-4a6c-9913-cff3e5fdfa56 |  | checkpoint | Correct head detail
checkpoint-status | dd6b8acb-5d0e-49d9-ac54-f8f453034795 |  | checkpoint | Correct centres (please indicate)
checkpoint-status | 97197417-1791-4e68-b36d-47d376fe5302 |  | checkpoint | Check for Straight
checkpoint-status | ea964046-b6b1-41da-8286-dee44634df37 |  | checkpoint | Check for Level
checkpoint-status | 599b0a39-94ab-4dbb-9c26-f5efe6275bdd |  | checkpoint | Seismic/Engineer details apply
checklist-flat | 73157479-d7bb-40ae-bb5f-7089e77e6f67 |  | checklist | Adhero wraps and tapes |  |  |  |  | Yes | QA - Adhero wraps and tapes | 41f01e8f-0990-4861-8142-cee406f7bde7
checkpoint-status | 3a48f536-071f-443f-b3c8-f4f0067da60f |  | checkpoint | Plans / Specs followed and correct type of paper/wraps used
checkpoint-status | 255da0f4-661c-45e8-90ee-6705a6366d3f |  | checkpoint | Paper install level
checkpoint-status | 06ba3036-c2f5-4702-ad6c-9749c07c55c5 |  | checkpoint | Packing tape applied
checkpoint-status | 6ac1ebe1-d0e1-4e27-b33a-4e281cc5335c |  | checkpoint | All Flashing Tape installed prior taped onto paper
checkpoint-status | 24c747d8-7544-48e7-a107-b1136f113535 |  | checkpoint | All tapes applied around window
checkpoint-status | 121c9b35-9247-40fe-8f21-63ec3391283d |  | checkpoint | Signoff prior to claddings
checklist-sectioned | b7b6f716-e3df-4141-a2ad-dcc11a0765ed |  | checklist | Weekly Site Inspection Checklist |  |  |  |  | Yes | H&S - Weekly Site Inspection Checklist | 4fae0305-358d-46e6-be23-4627d0cbaae0
checkpoint-group | e316bbe0-4b63-4d57-8add-32777b60ee0e |  | section | Weekly Site Inspection
checkpoint-status | 75378bbf-77ed-4d10-bbcf-708b18383795 |  | checkpoint | Weekly Site Inspection Checklist
text | cf63c585-5f3d-5bd4-9f42-871367e64f53 |  | textbox | Location:
text | 61cf1dc7-29c3-522b-9741-13df8db61348 |  | textbox | Date:
text | 426c7282-7f49-5112-a188-caaa2d77d082 |  | textbox | Name of Inspector:
checkpoint-group | 390da825-e46e-43a3-9dbd-784ee9c7d3a1 |  | section | Site Control
checkpoint-status | 74a7c53a-013e-4899-a37b-18b8183458f0 |  | checkpoint | Hazard board up to date
checkpoint-status | cd52fc2a-5cbe-4a3f-b4a4-f67b544ca98a |  | checkpoint | Toolbox talk
checkpoint-status | 025ff76e-6f2d-4fe1-965b-8ec747ed1ef5 |  | checkpoint | Inductions up to date
checkpoint-group | b6324a58-be0f-43d6-b022-b005bb2f4b30 |  | section | Site Facilities
checkpoint-status | f531a6e8-34e8-433e-8d08-5f5888c20678 |  | checkpoint | Offices Clean
checkpoint-status | 204f4fc4-35d6-40e0-99cd-2f0c6d9756d6 |  | checkpoint | Smoko Sheds
checkpoint-status | 30e12bd8-8a6f-40db-b710-82a175fc6ae0 |  | checkpoint | Fridge
checkpoint-status | 98bdf657-86f7-4355-b538-8a173a6345f1 |  | checkpoint | Toilets
checkpoint-status | c0cddf58-bb4f-48c9-adc2-edd2d572a209 |  | checkpoint | Containers
checkpoint-group | 8a5f93d3-a797-4a12-8a8a-5506999176c1 |  | section | General Site
checkpoint-status | e00585f6-317f-4c15-aaed-85f29a56d3d1 |  | checkpoint | Access Ways
checkpoint-status | ea3374f4-695b-4230-97e3-cd4144f4000a |  | checkpoint | Stairways Clear
checkpoint-group | 79c65603-59e5-42f3-9582-dc06183b3f01 |  | section | PPE
checkpoint-status | 27c2f5b4-5a07-42b5-9e34-43c7d7fdfdea |  | checkpoint | Signage Displayed
checkpoint-status | a5eab723-2ff0-43a8-93d4-0a242d5311fa |  | checkpoint | Hardhats
checkpoint-status | 54a827db-1965-4ac9-95a9-4e7f4a49be8b |  | checkpoint | Glasses worn
checkpoint-status | 26380e14-0641-4dd9-99bb-5a7e68c370b9 |  | checkpoint | Gloves
checkpoint-group | d8ba0aff-5ab4-4fae-879b-00a9e12e6f91 |  | section | First Aid
checkpoint-status | f30d32ed-7f26-40bc-9059-a68f71563b7f |  | checkpoint | Box Available and stocked
checkpoint-status | d8417919-49dd-4dc6-a98c-18a7100836f8 |  | checkpoint | Fire Extinguishers Available
checkpoint-group | 0bd5c251-8b6a-4498-b7e6-089465f2e742 |  | section | Cutting/Grinding
checkpoint-status | 0bf641b8-a95a-46bc-bfa7-d2de2e6ef608 |  | checkpoint | Hot work permits
checkpoint-status | 3910e437-72dd-4713-a8fc-2e1aac3093c3 |  | checkpoint | Fire Extinguishers on hand
checkpoint-status | a47a6907-85b6-495b-adbc-3faa6e1ecfda |  | checkpoint | Full Face Shield
checkpoint-group | 061d3eb8-0ecf-46ef-ad73-ce3133511ab7 |  | section | Electrical Equipment
checkpoint-status | ae0c0090-ce1a-417d-b4d2-0febb09b15b3 |  | checkpoint | Current Tags
checkpoint-status | bf5b12af-28b0-40dd-bbfe-46a27ba9f2f8 |  | checkpoint | Leads placed safely
checkpoint-status | 824919c1-b491-4291-bd99-dacce4b9f7cd |  | checkpoint | Equipment in good condition
checkpoint-status | 71176e39-d017-4b3b-bd28-b7d96274f483 |  | checkpoint | Adequate lighting
checkpoint-group | f0a66c49-8f8d-4461-8377-c6fb72dd0d74 |  | section | Chemicals
checkpoint-status | 9caf946d-e70e-4ca7-9201-71f65849be02 |  | checkpoint | Correctly stored
checkpoint-status | c0d1cf30-17ce-4ff1-bbda-362700d304fe |  | checkpoint | MSDS Available
checkpoint-status | 70d77adf-d62c-4496-a074-538b29d3ea54 |  | checkpoint | Operators using PPE
checkpoint-group | 9a053910-a49b-49b0-a0c1-7ae463c53e3d |  | section | PAT Tools
checkpoint-status | 81427172-04f7-4a08-bb85-727647e6e58b |  | checkpoint | PAT Tool WOF
checkpoint-status | 94b6f38d-e603-4aff-aad7-9e759060d11a |  | checkpoint | PAT signage
checkpoint-status | 2eea315d-aa67-494d-a7f7-5d98a3fb12f3 |  | checkpoint | Staff trained
checkpoint-group | b84a2b17-b01f-4032-af77-5b010a309dd0 |  | section | EWP
checkpoint-status | fd9a7174-9c24-40f9-9e6f-d24edb37c372 |  | checkpoint | Current WOF
checkpoint-status | da0cdbd0-3154-4ef6-86cd-0632c5902746 |  | checkpoint | Log Books being used
checkpoint-status | 13cb3125-6c59-4aa6-8df7-67c1ab666419 |  | checkpoint | Staff Competent
checkpoint-group | 4dbd0677-d715-4c69-a659-1f080167c2c0 |  | section | Scaffolding
checkpoint-status | aacf709e-72a9-4c93-92ed-e830f2f412b0 |  | checkpoint | Tags
checkpoint-status | 609e3c35-1d56-4adc-a0c0-53e980192771 |  | checkpoint | Midrails/Handrails
checkpoint-status | c7e9fc4e-fb36-4c55-9b03-a46a7ef44aae |  | checkpoint | Toe Boards
checkpoint-status | 8d4f1103-86ce-4905-a603-25fa58eefdde |  | checkpoint | Ladders
checkpoint-status | 460a66f8-5fd3-4f96-9b8d-fcd41f391647 |  | checkpoint | Platforms Clear
checklist-flat | d5ec42a3-def1-4a9f-825d-0c969f07579d |  | checklist | Accident & Incident Investigation Report |  |  |  |  | Yes | H&S - Accident & Incident Investigation Report | 55eeefc2-17c6-447a-ba9f-ea0471be0a6a
checkpoint-status | 9c53a95b-0c3f-419e-86c7-b05816168d62 |  | checkpoint | Particulars of Incident details completed
text | 92c6440e-32f3-53a9-bc45-b62a0e3a74c8 |  | textbox | Name of Investigator:
text | 598c01d1-863f-52a8-bbca-90bcf91c8698 |  | textbox | Date:
text | 0d5dc537-075b-5349-b3fe-57be760a15c0 |  | textbox | Time:
text | 62510ce5-163d-5548-b7db-2990461fa28a |  | textbox | Project/Site:
text | c8e9802f-af9c-5f8f-90c9-9deedac5e448 |  | textbox | Date Reported:
checkpoint-status | 8230b43c-2c84-475f-948c-740b6ac14d1d |  | checkpoint | Injured Person details completed
text | 02b1ed51-a492-5406-99c4-726d97b7e38f |  | textbox | Name:
text | 592c5d4a-7e4a-5652-ad5b-3f24e41dab5e |  | textbox | Age:
text | 5d80cd6a-d23d-54ac-b636-502c49ddd4ac |  | textbox | Phone Number:
text | 020bb86b-9935-52b8-b6ec-95f7cadd701d |  | textbox | Address:
text | bc004c4e-785d-5c4b-b784-4e92f882ea12 |  | textbox | Reported date of incident:
text | e592c15e-eed6-5d38-8dc3-287c68c0c7e3 |  | textbox | Length of employment:
text | 101547f6-1c7e-5849-afe3-e4a33554434d |  | textbox | Time on job:
checkpoint-status | 2506c171-edc3-42c4-99d3-df97ae6ec22a |  | checkpoint | Type Of Injury:
boolean | ac35ad50-02b6-587f-892f-ca8bee197990 |  | tickbox | Strain/sprain
boolean | 3ac491a5-a287-5c35-8fb0-254222f256d7 |  | tickbox | Fracture
boolean | f93e8867-5ba8-5632-b94d-0cd7aae5a424 |  | tickbox | Laceration/cut
boolean | 6518473f-faba-5408-bf72-5de9a61c33fb |  | tickbox | Bruising
boolean | 509785f7-6855-5da3-ba9d-54c649111122 |  | tickbox | Scratch/abrasion
boolean | 5475ff81-c9b7-5f0a-85fa-e1cf4e928a16 |  | tickbox | Amputation
boolean | 0f6af857-f9f4-51a7-b903-124ee3e487c2 |  | tickbox | Burn scald
boolean | 9483ca2f-f04c-561a-86d3-dadb28cdeb19 |  | tickbox | Dislocation
boolean | f0152076-64e1-550e-9c4d-767450bd9598 |  | tickbox | Internal
boolean | fb66efc3-cebb-5bd2-a099-f44b5679f97d |  | tickbox | Foreign body
boolean | 8711e3b7-00f6-5388-8d74-da58153d2132 |  | tickbox | Chemical reaction
boolean | fcc5253d-2cbf-5ce8-a0d3-8a8cf8a949d2 |  | tickbox | Other
text | 1632c488-6b40-5f0a-885d-de8ba46ec93f |  | textbox | If other please specify:
text | 2c3738bb-2694-5a12-80f8-b65860606243 |  | textbox | Injured Part of Body:
checkpoint-status | cbcaf396-98b2-46a4-abe4-1fd20081dd7e |  | checkpoint | Damaged Property details
text | 0cb4345d-c7b6-5052-a039-063de546d5ff |  | textbox | Property/material damaged:
text | 451ec297-69fc-5c47-a830-64e22cce4a6d |  | textbox | Nature of damage:
text | 6edb6e43-6785-5a7e-9dc4-94cbeace67aa |  | textbox | Object/substance inflicting damage:
checkpoint-status | 5ca2c711-27f3-4c68-b1e0-f15e53204dbd |  | checkpoint | Incident Details Complete
text | 85f308f0-6d36-5599-bbd0-d7d44abd50d2 |  | textbox | Describe what happened:
checkpoint-status | 5a3ad6e7-039f-49ca-b143-570e3e65098f |  | checkpoint | Analysis Details Completed
text | 020b2ef1-b8b4-5089-9b81-2901d1822851 |  | textbox | What were the causes (root and contributing causes) of the incident?
text | aaa23a44-7756-5be3-8e83-e92db2446aec |  | textbox | Root causes / safety system failures:
text | 787cb769-120c-5687-b533-af0e93997e05 |  | textbox | Contributing causes / unsafe acts and conditions:
checkpoint-status | 3678e0cb-a4da-47f4-99b6-4b095d17f9b0 |  | checkpoint | Prevention Details Completed
text | e7997fbe-3d6b-50b5-ac5f-c4bb851c7f07 |  | textbox | What action has or will be taken to prevent a recurrence?
text | c6253cb2-5d4a-5c03-9de7-dc9533878629 |  | textbox | By Whom:
text | 4525a5ad-c8b0-570e-ab1c-3297cde5e115 |  | textbox | When:
checkpoint-status | 6b0ea36d-3b1d-449c-a728-e090500c47c0 |  | checkpoint | Treatment and Investigation of Incident Details Completed
text | 172f45ef-1ab3-51d1-a87c-ce8ff964e946 |  | textbox | Treatment and Investigation of Incident :
text | 4d29b07a-89eb-5c99-8b03-c2b3ae5048b6 |  | textbox | Name of person giving First Aid:
text | 91120d0b-ab4e-5af1-b973-7f77ba315f24 |  | textbox | Doctor/Hospital:
text | b473f8b2-dfa9-5f0b-87cd-905e5d111528 |  | textbox | Incident investigated by:
text | c0a084ab-c3ff-5d41-922e-0bec0d44a0eb |  | textbox | Date:
select | 70645720-ba4c-5552-8070-8adc7cf66636 |  | dropdown | Worksafe NZ advised | Yes,No
text | be0adf35-2ff7-5d3a-af30-42ab38dd6021 |  | textbox | Date:
checklist-flat |  |  | checklist | Dayworks |  |  |  |  | Yes | Add Dayworks Checklist | 5e7ad85f-30c9-45cf-a697-062d1894d83b
checkpoint-status |  |  | checkpoint | Has an ATS / SI been received for this work
text | c202477a-d92d-4389-a502-b981fa335613 |  | textbox | Person requesting work:
text | dd7e962b-77f3-4dda-95d8-cc30ee0cf4db |  | textbox | Description of work
text | 439b0f70-210b-4082-b5de-02ed56114b70 |  | textbox | Labour / operative undertaking work
text | 0ac387b4-c483-4cbb-b1d7-04eff1209305 |  | textbox | Hours Worked:
text | fa2324f1-38d1-4614-8ef1-58a1393f1df9 |  | textbox | Materials Used:
checkpoint-status |  |  | checkpoint | Job Completed Satisfactorily
checkpoint-status |  |  | checkpoint | Signed Off
checklist-flat | 31d94598-a878-4c4f-853e-701caf9594be |  | checklist | [5 empty] | Yes | Z - SYS - Archived Checklist | 63b37dd0-b44f-464d-acf8-8f734ba47551
checkpoint-no-status | 405039d8-c7bd-4953-823b-fa9875a1e272 |  | checkpoint | Received Instruction
text | 17a29e53-7a38-5556-9946-d0a941b42156 |  | textbox | Reference/SI Number
date | 65b6d5f6-7f80-577f-bcf6-70ffa15492b8 |  | date | Date Instructed
text | 9326bb7c-b108-51ed-b460-fb81ce3e951a |  | textbox | Client
text | 6b8f3dc9-ad79-562c-b740-c655e2565570 |  | textbox | Scope of work
text | 6e9d2205-49b5-5777-bbf3-2b01c7d27bb5 |  | textbox | Agreed value
holdpoint | a7424b92-408b-4854-9324-6fb2f07dc65e |  | signoff | Approval
checkpoint-status | 9fd1df66-3b35-4df6-a1e5-8327922b251a |  | checkpoint | Job Complete
text | 5f9803dd-4ddb-5396-a747-a87eeac32be0 |  | textbox | Labour/Operative undertaking work
date | cf237804-e0b0-5c0c-ac2c-3198b14a3faf |  | date | Date Complete
text | bca9de81-fa5c-5d69-b99b-3ed738f4198d |  | textbox | Hours worked
text | f92029ac-e30d-5c10-a523-ce1db6700754 |  | textbox | Material used
holdpoint | d262f2ba-d396-4ae5-9b47-8ee93ee040fd |  | signoff | Attach Signature
checkpoint-no-status | b3c44d42-d3c6-4e34-a4ae-853b35decf32 |  | checkpoint | Values
number | 8d715a2e-0fd6-5933-9ac1-0c10f3ce4cbe |  | number | Labour value
number | 78f57cdd-9a00-565a-b18a-fb3d9797bf25 |  | number | Materials value
text | 1263931f-fb4f-5385-a392-c1707f3ae7e7 |  | textbox | Other items
number | 868889c6-ae82-5049-b982-99afe6605c45 |  | number | Total value
checklist-flat | 8fbdb103-2e25-4581-a5ab-c84959899ac8 |  | checklist | Cavity Installation |  |  |  |  | Yes | QA - Cavity Installation | 6aed254b-2000-4202-9f69-0d14c90c392d
checkpoint-status | c4562034-3f52-480f-bba7-e279c01101a2 |  | checkpoint | Spec followed for timber type
checkpoint-status | cb86b83e-82e3-4e9e-9977-64e7ff55dcd7 |  | checkpoint | Flashings Installed ( Tape with aluband)
text | cdc6480d-7b1d-586f-b7e1-b05250c0b057 |  | textbox | ( Please note flashings )
checkpoint-status | e249fd79-6421-469e-90bc-9d995d98cfcc |  | checkpoint | Ventstrip Install
checkpoint-status | 0429f715-2a1c-4596-a1e9-78b0aebacc87 |  | checkpoint | Cavity battens fixed plumb
checkpoint-status | 587e6427-66ec-4fc7-bacd-d5b9e23c6c01 |  | checkpoint | Cavity battens at correct Centres
checkpoint-status | db4cdf65-1472-4e31-a38f-44286a551053 |  | checkpoint | Signed off ready for Board/Cladding
checklist-flat | e27ecf30-5dcd-4f14-85a0-5741d31a7216 |  | checklist | Insulation |  |  |  |  | Yes | QA - Insulation | 6cf937db-e42a-4b3e-afae-911f5b64a989
checkpoint-status | 02b23658-cf0e-4ab7-854c-05e4dba1b2c2 |  | checkpoint | Area tidy and accessible
checkpoint-status | d96b846d-8be3-4ed0-91fb-7e47c1a4d12d |  | checkpoint | Plans / Specs followed
checkpoint-status | 4d64cec1-803b-4265-84f6-d8836b641ed2 |  | checkpoint | Friction fitted
checkpoint-status | 14e4d2d9-b02c-4613-bfad-985d8271d189 |  | checkpoint | No gaps in product
checkpoint-status | e7dcbe97-4d79-4bc9-a12c-b317f12bad37 |  | checkpoint | No bulging
checkpoint-status | 3eca3cc5-a677-4184-b0c3-334cff224415 |  | checkpoint | No Compression
checkpoint-status | 6a0614b1-1f15-4843-826d-edc09754fe8a |  | checkpoint | Signed off ready for linings
checkpoint-status | 8dd2d4e2-db17-4e86-93d7-797d459cee80 |  | checkpoint | Area left tidy and accessible
checklist-flat | f99485c7-11a2-405b-a189-27e81989ed02 |  | checklist | CLD Batten |  |  |  |  | Yes | QA - CLD Batten | 73dd99b2-2e29-42a8-ae7c-45e77b0d2624
checkpoint-status | b5dd3cd4-0467-4b21-ba40-b40be856c9e9 |  | checkpoint | Technical Literature followed
checkpoint-status | 3e87cf30-8a23-4582-9542-16b58c22a955 |  | checkpoint | Batten layout followed
checkpoint-status | d0352bc3-919b-4d26-b4c4-bcfcea059f2a |  | checkpoint | Head flashings installed/taped/level
checkpoint-status | f1b4df6c-9ab5-4c0c-b72e-1215cb16078f |  | checkpoint | Vermin strip installed
checkpoint-status | 248eb5d9-80d8-47cc-a4fd-ada0cc6a1b24 |  | checkpoint | Battens level and nailed at 200mm centres
checkpoint-status | 1d54952d-acc8-4237-a5bf-823184d7e864 |  | checkpoint | Area complete
checklist-flat | 72ca002f-f97d-4401-bbd9-8df29588411a |  | checklist | Dayworks |  |  |  |  | Yes | Add Dayworks Checklist | 7803a4ab-39c5-4275-824b-514a97ea28a7
checkpoint-status | 356a41f0-f4d1-4adb-a21b-f8b83cc652d2 |  | checkpoint | Has an ATS / SI been received for this work
text | 3eb0bd9b-556a-5af4-b57b-c0de24712613 |  | textbox | Person requesting work:
text | f7c13697-1517-528a-a0b2-e8548015a337 |  | textbox | Description of work
text | 123a1107-1149-5b52-8c9c-aa1b9347d9bf |  | textbox | Labour / operative undertaking work
text | eea8c8dd-7168-5782-874d-8ab739c95c45 |  | textbox | Hours Worked:
text | 223f7d2c-b494-5dcb-b6f1-ae598f0d64af |  | textbox | Materials Used:
checkpoint-status | bd01cb57-9cd3-4b8b-a5e8-3bf393b1caca |  | checkpoint | Job Completed Satisfactorily
checkpoint-status | 044678cb-0b23-4eb9-8853-01f3ddd348e0 |  | checkpoint | Signed Off
checklist-flat | 79aad6ec-800e-4b35-a9c7-6df7ba096ef5 |  | checklist | Plywood To Walls |  |  |  |  | Yes | QA - Plywood To Walls | 7e9f2897-6c83-4d01-b20b-969aba75b449
checkpoint-status | 2f8da80f-8005-4241-829e-7fa827c7feca |  | checkpoint | Plans / Specs followed and correct type of board used
checkpoint-status | 1c299e12-680b-4bf9-a72f-2afe27e513da |  | checkpoint | Wall signed off ready to line
checkpoint-status | 2b895087-9c91-4383-9eb2-454eb2b517d2 |  | checkpoint | Plywood Fixed at Correct centres - 200 Perimeter
checkpoint-status | c0367032-77e6-4e87-ab7d-2975298bc934 |  | checkpoint | All screws at correct depth
checkpoint-status | 688ff67b-e1ec-4ef4-bb7f-6709ed466609 |  | checkpoint | All screw imbedding substate
checklist-flat | 7f3dc87b-dd7f-4b1a-9b67-c76ed1782e99 |  | checklist | Sheet Linning |  |  |  |  | Yes | QA - Sheet Linning Checklist | 83a55f7b-ebe7-42a4-96cb-37dd352a9d9a
checkpoint-status | be8efb8e-cd78-4887-b95b-87c31180fc0e |  | checkpoint | Framing ready/signed off for linings
checkpoint-status | 394a6eaa-9fc0-413f-9906-78a61253a092 |  | checkpoint | Sheet linnings as per Specs
checkpoint-status | 49fa7937-6cc2-41fd-9f9d-33b35f2cfbf7 |  | checkpoint | Correct fixings and centers
checkpoint-status | 85374c43-f071-41fb-9112-828c0e4f0163 |  | checkpoint | Sheet joints/expansion joints or rebates formed correctly
checkpoint-status | 159ad904-529f-40b5-8415-d7c98339d5ea |  | checkpoint | Area ready for Wraps or plastering
checkpoint-status | 23bdcfe4-ed85-4777-bde5-0e5f7d742ab0 |  | checkpoint | Plastering complete and ready for paint
checklist-flat | 3f295892-22ce-4e69-9885-830d9af8259f |  | checklist | Nu-Wall |  |  |  |  | Yes | QA - Nu-Wall | 857f8738-43aa-42c6-9cb7-6bd0eed0b158
checkpoint-status | 5ad1e387-704f-4920-a91e-d3d8513a2166 |  | checkpoint | Cavity Batten
checkpoint-status | 39222745-7ada-48bd-89a2-8f751011f399 |  | checkpoint | All flashings/Mid floor flashing and penetrations set and sealed
checkpoint-status | 0aaa867c-2158-4ea6-9d70-3c2d180e8c32 |  | checkpoint | Cavity Inspected and passed
checkpoint-status | 1454be6f-8ad3-4da2-acfe-c1fb0afb912b |  | checkpoint | Corners formed correctly
checkpoint-status | c933f30c-b023-4376-b573-2e5286928459 |  | checkpoint | Datums set correctly
checkpoint-status | 2378d078-2719-4d50-9724-6aafdc70a12c |  | checkpoint | Screwed in alignment
checkpoint-status | f875f354-0369-4dfc-afc0-6e9b480a72b8 |  | checkpoint | Drip edges straight
checkpoint-status | 923f512b-d088-4bc4-9be3-aa35274419b9 |  | checkpoint | Finished Sealant complete
checkpoint-status | f9d48c8d-dce6-466b-9a67-e88d4d42343a |  | checkpoint | Nu-wall complete
checklist-flat | a2328814-e381-4976-a5de-34174f3bf281 |  | checklist | RAB |  |  |  |  | Yes | QA - RAB | 8e2724e6-cff2-4e04-9179-e3aa55a0d4e7
checkpoint-status | 3500e76a-89b1-4ce7-9e46-5f8ce5bedf58 |  | checkpoint | Plans / specs followed
checkpoint-status | efd9092c-c1a9-43d6-b0f5-e4d2ea6385f4 |  | checkpoint | Flashings in place
checkpoint-status | 13715835-7d2d-4d34-a12f-373a0103d017 |  | checkpoint | Sheet neatly cut and 1-2 mm gaps at join
checkpoint-status | aaa3251a-8054-44c4-8b7c-93284e7cda60 |  | checkpoint | Correct nails / nailing pattern
checkpoint-status | da675615-54d3-4cd9-a00f-bad1991095b4 |  | checkpoint | All nails flat and not puncturing board
checkpoint-status | bb100471-33bb-4f83-ad11-464b6d4dcc2a |  | checkpoint | Taped / Sealed
checkpoint-status | 58bf3c6d-9a11-491b-b7b4-73e11fd36850 |  | checkpoint | Area RAB complete
checklist-flat | 98f3273f-f014-4f73-a520-85c965f3ef35 |  | checklist | Soffits |  |  |  |  | Yes | QA - Soffits | 94c94032-bddf-4176-99a8-39ea568ef796
checkpoint-status | cf1aca42-7e63-45c7-9da1-f99fa827e47e |  | checkpoint | All Specs for timber followed
checkpoint-status | 357c4a75-5524-4596-b3fb-36fbd1efe2fd |  | checkpoint | Soffits to correct RL/Fascias installed neatly and pre primed
checkpoint-status | e1252180-c8df-4c1a-a24d-32f725ab1c03 |  | checkpoint | Bulkheads at correct location
checkpoint-status | e41f4943-bc02-4495-87a7-712474f171f6 |  | checkpoint | Soffits lined with correct board
checkpoint-status | 3a130888-610d-4382-9cb6-cf0ae7221187 |  | checkpoint | All plastering complete
checkpoint-status | a45f4ef8-269f-411f-9d50-f1103786b350 |  | checkpoint | Ready for paint
checklist-flat | 7baa34bd-3887-41e8-ae3e-a50db161a52b |  | checklist | Plywood Under Membrane |  |  |  |  | Yes | QA - Plywood Under Membrane | 9b93ad53-5214-45f9-b7a2-bf46e6fbdd08
checkpoint-status | cfeb7d8e-a227-4ebb-a62b-6c9ca6c2f10f |  | checkpoint | Plans / Specs followed and correct type of board used
checkpoint-status | faffb4cc-f978-469e-a98e-269f426dae42 |  | checkpoint | Plywood Fixed at Correct centres - 150 Perimeter.
checkpoint-status | f45f906a-ba19-42e5-a093-1b4e2a9111dc |  | checkpoint | Plywood Fixed at Correct centres - 200 Perimeter
checkpoint-status | 105d0f2b-2752-4945-b9a8-73f5cc066482 |  | checkpoint | 3mm gaps between ply joints
checkpoint-status | 6af3d3b2-97d3-4c5b-8709-62b3591df904 |  | checkpoint | Brick Format
checkpoint-status | 23a6291c-afe0-4e01-a674-1be36fae1165 |  | checkpoint | Screwed and complete for membrane
checkpoint-status | da77b23f-1ff3-4831-983d-76f5009e0d03 |  | checkpoint | Angle Fillets
checklist-flat | b8fe7d5b-3341-4a83-a491-d7052cbbb463 |  | checklist | Internal Framing |  |  |  |  | Yes | QA - Internal Framing | a326ddcc-9718-45ab-aa93-4ac374b412e0
checkpoint-status | 3122f74c-c4d0-4b6b-b22c-8819bc49e030 |  | checkpoint | Plans / Specs followed and correct type of timber used
checkpoint-status | 57058858-52c5-4ac0-8a20-b9530c9f83ef |  | checkpoint | Check for location
checkpoint-status | 23b92000-2760-4770-845e-2e863ef6aff1 |  | checkpoint | Bolted at correct centres (please indicate)
checkpoint-status | d2658a12-01f1-4e52-b9b5-623fd756ab1f |  | checkpoint | Studs installed (Plumb)
checkpoint-status | 07084693-13be-44d5-9d25-2abc43e6083a |  | checkpoint | Nogs installed (Level)
checkpoint-status | c05ae7eb-8605-424e-94db-45e035c65cd3 |  | checkpoint | Correct centres (please indicate)
checkpoint-status | 4d7a7d61-ac54-4248-a85f-5e979c1c3bcd |  | checkpoint | Check for Straight
checkpoint-status | 2fee6b8b-da2a-48ee-9b6d-d228ae9db270 |  | checkpoint | Check for Level
checkpoint-status | 8f2397e8-bef1-43b9-9b84-3b509eb46998 |  | checkpoint | Seismic/Engineer details apply
checklist-flat | 5168e364-24f3-4f50-86df-99442aadd4a5 |  | checklist | Steel Stud |  |  |  |  | Yes | QA - Steel Stud | a367a344-e5f0-41f7-ad38-004909917b93
checkpoint-status | 6bca604b-24bd-4e54-a227-4f3870dc45ca |  | checkpoint | Bottom tracks set-out to correct revision / Fixed correctly
checkpoint-status | 3c845004-4058-4617-a237-7357798e20b5 |  | checkpoint | Top tracks fixed correctly
checkpoint-status | 20c652eb-b1d4-4f1d-89bf-3cd5ea61ba49 |  | checkpoint | Studs at specified centres (fixed only at base, free at head)
checkpoint-status | 19a8444b-266c-48fe-9ebe-4e2da6797628 |  | checkpoint | Walls plumb and true
checkpoint-status | 9cdd1533-5d76-44f0-998c-eecac072b452 |  | checkpoint | All nogs installed notched correctly
checkpoint-status | 9ef02295-7537-47ec-b312-c603e33860ea |  | checkpoint | Area steel stud complete
checklist-flat | 5df93282-69df-4304-a9c2-c46d7b54ffc5 |  | checklist | Roof Subframe |  |  |  |  | Yes | QA - Roof Subframe | b4e6ec23-ab5d-447a-b677-8020b9327388
checkpoint-status | a9051790-a1f7-4c45-becf-94cb3a046059 |  | checkpoint | Area tidy and accessible
checkpoint-status | 25f54926-cf4d-4335-bd81-90d4a41d253f |  | checkpoint | Rafters at 400c / Nogs 400c
checkpoint-status | 39ce28f8-7cd6-4683-96ec-e559db244fd4 |  | checkpoint | Hexagon Mesh fixed
checkpoint-status | f0e0364f-8320-4fe4-8876-38131c155994 |  | checkpoint | All brackets / hold downs fixed
checkpoint-status | b4f89c67-389e-4165-8764-11455339aa87 |  | checkpoint | Insulation and friction fitted ready for ply. Photos must be taken
checkpoint-status | df2dc425-2c3e-4034-ab00-0b3bddbb9041 |  | checkpoint | Ply fixed for membrane following manufacturers recommendations
checkpoint-status | 8154a2d3-3448-47ad-bba4-2d023ebc2b9f |  | checkpoint | Area complete ready for taping
checkpoint-status | 55567d95-aa12-446d-9694-d8eb68ac07b3 |  | checkpoint | Area left tidy and accessible
checklist-flat | 2abe5bd3-5364-4e7a-97a2-6757c3708fb1 |  | checklist | AXON Panel |  |  |  |  | Yes | QA - AXON Panel | bbcbc3b1-bec3-495f-80b2-e3c87ea4c064
checkpoint-status | bfdf29c7-4d72-434a-93b3-e34782cbdbd2 |  | checkpoint | Technical Literature followed
checkpoint-status | 5758c484-1e5d-4eef-b2d0-7a0cb70e171d |  | checkpoint | Panel layout followed
checkpoint-status | 88ba7303-87b5-410b-8260-212d807659d3 |  | checkpoint | Panels cut neat / sanded / primed
checkpoint-status | e67b3591-1010-497d-aecb-6150c20b1f2a |  | checkpoint | All tapes / flashings installed
checkpoint-status | 4599ef3c-8ffc-4eb9-9a86-940d771f9d74 |  | checkpoint | Board nailed positively with 25 mm brads
checkpoint-status | 86772524-8e2c-4af6-9b21-7802ce2a975e |  | checkpoint | Sealants applied neatly
checklist-flat | 993063ae-1180-4188-bbfd-46c5fc4ade25 |  | checklist | Titan Facade on CLD |  |  |  |  | Yes | QA - Titan Facade on CLD | c6654c44-cd34-4cdf-a0b4-3363aa950bec
checkpoint-status | 9c2b3b76-cbd4-482c-a708-cad50a32a1b9 |  | checkpoint | Plans/Specs followed
checkpoint-status | 382cf0e1-540a-4c40-b0d4-a04ba9fb3e21 |  | checkpoint | Sheet layout correct
checkpoint-status | ec8aaed4-21e8-47bb-b097-6cf7c247565a |  | checkpoint | All cuts straight and primed
checkpoint-status | 414fbd79-bd0d-48e1-8aca-8ae615254e5c |  | checkpoint | Adhesive applied to CLD batten as per spec
checkpoint-status | cf797004-d0d0-497f-9f67-cb02cefed72b |  | checkpoint | Board countersunk screwed at 200mm centres
checkpoint-status | 59363b63-766f-4453-9cfb-b5211b8ea2dd |  | checkpoint | Sealants applied neatly to all joints
checkpoint-status | 6aac6b78-f676-40ee-b034-aece089048cf |  | checkpoint | Filling of screws ready for paint
checklist-flat | 963dd61d-c9d0-47f9-b1f2-0140c92fa30f |  | checklist | Roof & Gutter Framing |  |  |  |  | Yes | QA - Roof & Gutter Framing | c6af493f-0632-4344-91ca-ea0453d0dc20
checkpoint-status | c07c750a-a33e-4bda-ab6b-8d82027cce5e |  | checkpoint | Plans / Specs followed and correct type of timber used
checkpoint-status | deac6a67-facf-4d42-90f4-c515e31b3f16 |  | checkpoint | Rafters at correct locations
checkpoint-status | 209fa2e2-7735-46e5-9ee0-86211cf5d1b9 |  | checkpoint | Engineer details followed including brackets
checkpoint-status | c6c44a6f-8e42-4af1-b923-4b10bbde3f62 |  | checkpoint | Gutter Falls to correct location
checkpoint-status | f4efee65-8914-4faa-8247-512b125026f1 |  | checkpoint | 3mm gaps in Ply
checkpoint-status | af1925c7-6aa2-4478-bb99-6aabdf527556 |  | checkpoint | Sumps formed correctly
checklist-flat | a99933cd-dd3e-498c-b9d9-29051f7944d4 |  | checklist | Task: |  |  |  |  | Yes | H&S - JSEA Checklist | c7f2cccd-37b6-4206-afd4-b86866a11f10
checkpoint-status | 6f6576cc-1efa-4241-b8b3-e7fe97e4dbb3 |  | checkpoint | Form complete
text | b33a622f-614c-521d-8b04-ea998541a474 |  | textbox | TASK DESCRIPTION
label | a2f297cf-80ab-5005-b2b7-0bbb0573124a |  | note | WHAT COULD GO WRONG
boolean | 42af3f94-663e-52fc-9dc0-e86225a5c615 |  | tickbox | Falls
boolean | a48631cb-7805-5ca1-8b1f-9264e252c22a |  | tickbox | Falling objects
boolean | 7d265721-f033-5d03-af1e-d509c65462fa |  | tickbox | Working at heights
boolean | e6e58c32-859f-5e30-b4b0-8ef0b36a637e |  | tickbox | Plant malfunction
boolean | f218cb86-d85f-5a86-8619-a32a7d338433 |  | tickbox | Slip/Trip/Falls
boolean | b5e0e8b2-b0bc-5afd-bd55-022fc26beec8 |  | tickbox | Eye injury
boolean | ea783882-80e6-5558-8b41-e87a400184ef |  | tickbox | Hand injury
boolean | 21ea32bf-1e9c-5f51-a34d-0fa109f9f9b1 |  | tickbox | Inhalation
boolean | 0bddff7a-856f-5125-8d03-68820e0dd9ef |  | tickbox | Crush
text | 541e3351-122d-5d4d-8dc0-07a558e0080c |  | textbox | Other:
text | 0d24beab-5087-5829-90d4-fb9609a152f7 |  | textbox | HAZARD RATING (1-25)
label | 38e73a6b-ddee-5e31-80f4-cde497370719 |  | note | WHAT CAN I DO TO PREVENT INJURIES TO MYSELF AND OTHERS?
boolean | e5caabb4-757f-5db9-8a5e-7ae72963ad42 |  | tickbox | PPE
boolean | 0eb34ddb-acfa-5f07-a46f-f5e489219b6f |  | tickbox | Safe working procedures
boolean | e8e36235-f300-5cd8-81cb-5bd4d4c24307 |  | tickbox | Training
boolean | f9214372-b090-5bd8-839d-e888e4d48417 |  | tickbox | Safety checks on plant
boolean | 0f9fa1d6-2053-5084-adb4-2554e8f05345 |  | tickbox | 3 Points of contact
boolean | 669ead2e-1c6b-5103-82b2-7b9a882b44ce |  | tickbox | Housekeeping
boolean | c3147a02-f4f9-598d-9cff-3d6fb24285aa |  | tickbox | Correct mobile scaffold build and operation
boolean | 1a6d9a2c-a967-5dc3-9fb6-423adf9fc939 |  | tickbox | Working at heights
text | e643cc7a-a25d-5621-b5c0-d2026af22340 |  | textbox | Other:
text | 06e44938-cb96-5e01-8fac-d48baac9cf8d |  | textbox | WHAT'S THE NEW HAZARD RATING?
label | bfccecf2-82f4-5f3c-a8e8-58a1dc74a202 |  | note | If RED (18+) requires sign-off to proceed
text | d7d21337-0f1c-516c-b274-0013e087a5de |  | textbox | WHAT PERMITS DO I REQUIRE? IF ANY
label | 42047139-26e9-5bfd-85c5-9d76c2be648e |  | note | PPE REQUIRED
boolean | 2bf5438a-e2c6-5ecb-8c59-909b25b253ca |  | tickbox | Hi-Vis
boolean | 1717c17b-84a2-5a45-bd82-c2f321fdaf6d |  | tickbox | Hardhat
boolean | 68ba1487-485f-5628-9d32-efc5275c448d |  | tickbox | Steel Cap Work Boots
boolean | 0cd77e8f-d49a-5945-a99e-d2d3e73695a5 |  | tickbox | Gloves
boolean | fbc40e0c-7b3d-5cb3-b8b5-3d26b82da0d1 |  | tickbox | Glasses
boolean | 92169f7a-7a5f-5a38-9aa1-aa59f4ee40bc |  | tickbox | Earmuffs/Ear plugs
boolean | 763f0c86-562e-5d4c-a938-f3bac8a36016 |  | tickbox | Faceshield
text | edccb48f-9e5c-5bde-832f-48d1f3bc34cb |  | textbox | Other:
checkpoint-status | e5930186-bfc9-412b-b443-1052614f8f90 |  | checkpoint | Signed Off
checklist-flat | b1b253cd-c04c-4396-9105-eedb298ac906 |  | checklist | Site Toolbox - Date: |  |  |  |  | Yes | H&S - Site Toolbox | c9051534-7895-4acb-83b4-e2068b738d99
checkpoint-status | 32cf8cae-674a-47bb-bed2-10b929b8b315 |  | checkpoint | Employees Attending
checkpoint-status | e1d2d42e-b5f1-4a5b-a2eb-ae5e32716041 |  | checkpoint | Site Activity / Safe Work Practices / Accident-Incident Investigations Discussed
checkpoint-status | cce893ad-0577-4268-8476-b0c7cdc8d1be |  | checkpoint | Employee issue raised
checkpoint-status | 7e18e4b4-b67d-4def-9fa4-d6a37af7b45e |  | checkpoint | Safe Observations
checkpoint-status | 5c8ebbfd-2c5f-4812-bb84-b5cba3a7e478 |  | checkpoint | JSEA completed
checklist-flat | 1bc9b929-b2c0-4936-a5b5-7989bc273cf3 |  | checklist | Architrave |  |  |  |  | Yes | QA - Architrave | d1b7328b-50c5-4096-94bf-ebcba7953ff3
checkpoint-status | 4e093c54-09b3-4905-a384-960337e277c1 |  | checkpoint | Level and Flush with walls
checkpoint-status | f916225d-2183-488f-bb00-2567c1ef0df5 |  | checkpoint | Gaps and joints angle are acceptable
checkpoint-status | 6572838c-d028-43f0-94db-7acfc9a102ec |  | checkpoint | Silicon and finishing nails have been used correctly
checklist-flat | c0ea194c-b05b-4759-a551-4157d2728d77 |  | checklist | Timber Floors |  |  |  |  | Yes | QA - Timber Floors | d5f2157a-48ad-405b-a634-7c2b09b23cf9
checkpoint-status | 37c1dc61-92c7-4326-9e46-ae1aefb8ec4a |  | checkpoint | Bearers installed
checkpoint-status | 63fc7964-d3a9-433a-a156-20066652d1c2 |  | checkpoint | Floor Joists Installed
checkpoint-status | ca7ea6af-1f85-4606-ac59-fb8ef85e6b40 |  | checkpoint | Engineer Details followed
checkpoint-status | 57f7ced7-93e0-4a7b-9807-7bae6721e89e |  | checkpoint | Flooring Installed
checkpoint-status | 09d9b39f-c9e4-495e-95e6-08f8a14de25d |  | checkpoint | Flooring Complete
checklist-flat | 9c9c5d55-e109-4048-b4d7-ed86f17c47c3 |  | checklist | Lattice Frame |  |  |  |  | Yes | QA - Lattice Frame | e502e99a-1bb1-47a5-94ce-8c7b6515dd75
checkpoint-status | e3aa4b1c-5479-4e1c-acf1-bac87c78ec3d |  | checkpoint | Plans/Specs followed and correct type of timber used
checkpoint-status | 10f9f6d6-c8ba-46a3-bcdf-7ef112d37120 |  | checkpoint | Safety Mesh Installed as per manufacturers recommendations
checkpoint-status | 51b408ec-d0a2-4a62-979e-f74f8736f887 |  | checkpoint | Battens perpendicular to purlins at 600c
checkpoint-status | 4869df3f-9bee-495e-b1ed-f2d0814613d6 |  | checkpoint | Nogs Installed at 600c
checkpoint-status | ea79f289-dffc-4af0-a193-5056577e3d28 |  | checkpoint | Engineered plans followed
checkpoint-status | ba3af85a-6ce5-4b10-9946-06d413de668e |  | checkpoint | Complete ready for Ply
checklist-flat | 7b6a8dea-7e05-424f-95d4-8e39b2eac724 |  | checklist | Doors |  |  |  |  | Yes | QA - Doors | f223e6a7-bd8e-4edc-b388-32c6cfa221fe
checkpoint-status | 3d4a4c0f-af04-451a-a29d-3b81604be159 |  | checkpoint | Correct door to location
checkpoint-status | 9d3a4607-48ac-4add-b01d-19fd4b17f4a3 |  | checkpoint | Door fixed to location with correct undercut
checkpoint-status | e22283a2-953c-4804-b842-8b88abed1878 |  | checkpoint | Hinge Side Plumb and fixed at correct intervals
checkpoint-status | c53669ad-cf44-4c0c-8b58-50418f923d49 |  | checkpoint | All margins neat with no Wind in door frame
checkpoint-status | b681a9d9-e622-42a4-b315-83358b858d2b |  | checkpoint | Slider/Bifold/Wardrobe margins and closes correctly
checkpoint-status | 2cafa1ad-781b-473f-a543-880822abf035 |  | checkpoint | Door stop fixed correctly
checkpoint-status | 4fc5eaf8-201d-4616-b22c-2d4c462f525b |  | checkpoint | Door complete
checklist-flat | a77b081f-b90f-4ee1-9ae4-120c66028623 |  | checklist | Ortech Panel System |  |  |  |  | Yes | QA - Ortech Panel System | f2c1f7d4-6146-4384-b367-8b9bed9f9c56
checkpoint-status | 3e3837c7-8523-4213-b2f0-084e948d97fb |  | checkpoint | Area tidy and accessible
checkpoint-status | e3e15ae7-ede0-46ab-87c5-d971627e720e |  | checkpoint | Fixing of timber plate and neoprene at 600mm centres
checkpoint-status | 74ebd89a-f06c-4b3e-a7c9-f28aff78890c |  | checkpoint | Ortech Shop drawings followed
checkpoint-status | 6ae2752d-1e6b-425f-a060-d0eec408a412 |  | checkpoint | I purlins and tees fixed in location
checkpoint-status | 80622dfe-11d7-49d2-8fca-f9ced7a9d066 |  | checkpoint | Insulation / Durra fixed with wedges
checkpoint-status | db1164a4-ae8f-4205-9510-3f31a0a06219 |  | checkpoint | Edge protection in place
checkpoint-status | b7c8a905-4084-440f-8ba4-7f9b4753f415 |  | checkpoint | Ortech lifted and bolted into place
checkpoint-status | 267829d3-f6ee-4de2-b0da-fcda450c49d8 |  | checkpoint | Area left tidy and accessible