## Project Breakdown
Chisholm TAFE |  |  |  |  | Checklists
QA / ITP's
Roofing
Roof Fascia Capping Aluminium
Soffit Cladding
|  |  |  | Soffit Cladding | Soffit Cladding checklist
Roofing Zone 1
Roof 3
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | Insulation | Insulation checklist
|  |  |  | Roof Installation | Roof Installation checklist
|  |  |  | Flashing/Capping Installation Checklist | Flashing/Capping Installation Checklist
|  |  |  | Parapet Wall Cladding | Parapet Wall Cladding checklist
|  |  |  | Roof Penetrations | Roof Penetrations checklist
Roofing Zone 2
Roof 4
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | Insulation | Insulation checklist
|  |  |  | Roof Installation | Roof Installation checklist
|  |  |  | Flashing/Capping Installation Checklist | Flashing/Capping Installation Checklist
|  |  |  | Parapet Wall Cladding | Parapet Wall Cladding checklist
|  |  |  | Roof Penetrations | Roof Penetrations checklist
Roofing Zone 3
Roof 1
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
|  |  |  | parapet wall cladding | Parapet Wall Cladding checklist
|  |  |  | roof penetrations | Roof Penetrations checklist
Roof 2
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
|  |  |  | parapet wall cladding | Parapet Wall Cladding checklist
|  |  |  | roof penetrations | Roof Penetrations checklist
Roofing Zone 4
Roof 5
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
|  |  |  | roof penetrations | Roof Penetrations checklist
Roof 6
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
|  |  |  | roof penetrations | Roof Penetrations checklist
Roof 7
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
Roof 8
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
Roof 9
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
Roof 10
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
Roofing Zone 5
Level 3 Roof
|  |  |  | Box Gutter Installation | Box Gutter Installation checklist
|  |  |  | insulation | Insulation checklist
|  |  |  | roof installation | Roof Installation checklist
|  |  |  | flashing/capping installation checklist | Flashing/Capping Installation Checklist
Rainspan
Zone 2
|  |  | East Wall - MC01 | Eurobond Installation | Eurobond Installation checklist
|  |  | North Wall - MC01 | Eurobond Installation | Eurobond Installation checklist
|  |  | Terrace 3 Wall | Eurobond Installation | Eurobond Installation checklist
|  |  | Internal Wall | Eurobond Installation | Eurobond Installation checklist
|  |  | Airlock Soffit - MC01 | Eurobond Installation | Eurobond Installation checklist
|  |  | Ampitheatre - Soffit - MC01 | Eurobond Installation | Eurobond Installation checklist
Zone 3
|  |  | South Wall - MC01 | Eurobond Installation | Eurobond Installation checklist
|  |  | Terrace 1 - Wall | Eurobond Installation | Eurobond Installation checklist
|  |  | Teraace 2 - Soffit - MC03 | Eurobond Installation | Eurobond Installation checklist
|  |  | Terrace 2 - Wall | Eurobond Installation | Eurobond Installation checklist
|  |  | Section C - Wall | Eurobond Installation | Eurobond Installation checklist
|  |  | Section F - Wall - MC01 | Eurobond Installation | Eurobond Installation checklist
|  |  | Level 1 - Soffit | Eurobond Installation | Eurobond Installation checklist
Dridesign
Zone 3
|  |  | Section C - Wall | Dridesign | Dridesign Installation checklist
|  |  | Section F - Wall | Dridesign | Dridesign Installation checklist
|  |  | South -Wall | Dridesign | Dridesign Installation checklist
|  |  | Terrace 1 - Wall | Dridesign | Dridesign Installation checklist
|  |  | Terrace 2 - Soffit | Dridesign | Dridesign Installation checklist
|  |  | Terrace 2 - Wall | Dridesign | Dridesign Installation checklist
Zone 2
|  |  | East - Wall | Dridesign | Dridesign Installation checklist
|  |  | Internal - Wall | Dridesign | Dridesign Installation checklist
|  |  | North - Wall | Dridesign | Dridesign Installation checklist
|  |  | Terrace 3 - Wall | Dridesign | Dridesign Installation checklist
|  |  | West - Wall | Dridesign | Dridesign Installation checklist
|  |  | Airlock - Soffit | Dridesign | Dridesign Installation checklist
|  |  | Ampitheatre - Soffit | Dridesign | Dridesign Installation checklist
Variations
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
OH&S
Daily Prestart Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Weekly Toolbox Forms
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
SWMS
Onsite Material Install Form1
Foremans Diary Reports
Delivery Dockets | Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec

## Roofing
ROOF
Roof Fascia Capping Aluminium
checklist | Soffit Cladding checklist
section | Material Inspection
checkpoint | Soffit Cladding type: Mondoclad 3mm Aluminium
checkpoint | Insulation: Sarking
checkpoint | Wall Cladding Top Hat - 0.75mm - 15mm Top Hat / Junction Stud
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Installation
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Caulk done with no gaps
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
checkpoint | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
checkpoint | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
checkpoint | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
checkpoint | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
checkpoint | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
checkpoint | Client Representative:
Roof - Zone 1 / Roof 3
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Fix only Syphonic Outlet
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
Roof - Zone 2 / Roof 4
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
Roof - Zone 3 / Roof 1
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
Roof - Zone 3 / Roof 2
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Parapet Wall Cladding checklist
section | Material Inspection
checkpoint | Wall Cladding - 50mm ASKIN panel Parapet lining
checkpoint | Top hat support: 0.75mm Top Hat
checkpoint | Flashing Material: 0.61mm Colorbond Ultra Matt
section | Installation
checkpoint | Insulated Panel Wall Cladding - Butyl Tape to Side, Top, and Bottom
checkpoint | Is primary strucutre adequate to support cladding or secondary framing?
checkpoint | Top hats installed at correct spacings to meet Manufacturers recommendations.
checkpoint | Wall cladding fixed to sub frame as per Manufacturer's recommendations.
checkpoint | Wall cladding flashed to make watertight.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
text | Client Representative:
Roof - Zone 4 / Roof 5
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Roof - Zone 4 / Roof 6
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Penetrations checklist
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
section | Installation
checkpoint | Penetration: Hole cut to correct size to allow clearance.
checkpoint | Roof sheets whethered correctly
checkpoint | Soaker flashing lapped, sealed and fixed correctly.
checkpoint | Adequate support under soaker to prevent ponding.
checkpoint | Side and front aprons / upstands formed to correct size
checkpoint | to fit the purpose.
checkpoint | Adequate support around penetration to prevent roof
checkpoint | sheet from buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Roof - Zone 4 / Roof 7
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Roof - Zone 4 / Roof 8
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Roof - Zone 4 / Roof 9
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Roof - Zone 4 / Roof 10
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | Syphonic Outlet
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
checkpoint | Soaker Gutter
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Deletion of Valley Gutter replace with Apron & Soaker
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Roof - Zone 5 / Level 3 Roof
checklist | Box Gutter Installation checklist
section | Material Inspection
checkpoint | Box Gutter Brackets:
checkpoint | Box Gutter Insulation - 60mm Anticon
checkpoint | Box Gutter Insulation - 4mm Polyair - 1200mm
checkpoint | Box Gutter - Spandek gutterboard
checkpoint | Box Gutter: Stainless Steel 316
checkpoint | Gutter Flashing: Stainless steel to match 316
checkpoint | High Capacity Overflow
checkpoint | Overflow Outlet 0.70mm 316 Stainless Steel
section | Installation
checkpoint | Gutter Brackets installed with fall as per Specification.
checkpoint | Insulation installed under gutter board
checkpoint | Gutter Board installed
checkpoint | Box gutter installed to sizes as shown in specification and drawings.
checkpoint | Sumps installed to correct locations and sizes as specified and as shown on drawings
checkpoint | Pops installed under the sump
checkpoint | Outlets installed to correct sizes.
checkpoint | Overflow outlets installed at each downpipe location and to correct size as indicated.
checkpoint | Gutter flashing installed with minimum of 100mm off from the sole of the box gutter
checkpoint | Area clean and free of debris.
checkpoint | Fix only Syphonic Outlet
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checkpoint | Insulation checklist
checkpoint | Material Inspection
checkpoint | Insulation: Roof - Glasswool on Medium Sarking - 145mm
checkpoint | Thermal spacer: Ashgrid 1200mm - 120mm
section | Installation
checkpoint | insulation to entire roof area
checkpoint | correctly lapped and joined
checkpoint | No over hang into gutters
checkpoint | Manufacturers recommendations.
checkpoint | Thermal Spacer Located correctly
checkpoint | insulation below box gutter lapped at joins
checkpoint | insulation cut back at sumps
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition with no tears
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Roof Installation checklist
section | Material Inspection:
checkpoint | Roof Sheets: 0.48mm Colorbond Ultra - Klip-lok / Speed Deck Ultra
checkpoint | Coating Type: Standard Colorbond Ultra
checkpoint | Insulation: Anticon 145
checkpoint | Safety Mesh: Galvanised 2mm x 150mm x 300mm
checkpoint | Roofing - Profile Infill Strips
checkpoint | Roof Clips - Klip-lok / Speed Deck Ultra (incl screws)
section | Installation:
checkpoint | Safety Mesh Installed
checkpoint | Insulation installed
checkpoint | Roof clips installed
checkpoint | Roof installed with adequate fall to meet roof profile
checkpoint | Roof installed straight and perpendicular to Roof purlins
checkpoint | Roof has adequate overhang into box gutter / spouting
checkpoint | Roof sheet turned up at high end of roof
checkpoint | Roof sheet turned down at gutter end of roof
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
checklist | Flashing/Capping Installation Checklist
section | Material Inspection
checkpoint | Flashing Material: 0.61mm Colorbond Ultra
checkpoint | Compression Flashing
checkpoint | Capping Material 0.61mm Colorbond to match Ultra
section | Installation
checkpoint | Flashings / Cappings: Straight and in correct plane.
checkpoint | Fixed adequately to hold flashing in place and prevent vibration in strong winds.
checkpoint | Adequate Fixings for Compression Flashings (Max 100mm Nylon Anchors)
checkpoint | Adequate sealants applied with minimal dust in between wall and flashing
checkpoint | Adequate lap at joins.
checkpoint | Silicone sealed under laps and where necessary to make waterproof.
checkpoint | Rivets and fixings sealed where necessary
checkpoint | Adequate support to prevent buckling.
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Rainspan
Rainspan Zone 2 - East Wall - MC01
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | 100mm Mineral Wool Panel - MC01
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
checkpoint | Wall Penetration - Overflow slots through facade
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 2 - North Wall - MC01
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | 100mm Mineral Wool Panel - MC01
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 2 - Terrace 3 Wall
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 75mm Mineral Wool Panel - MC03
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
checkpoint | Wall Penetration - Overflow slots through facade
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 2 - Internal Wall
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | 75mm Mineral Wool Panel - MC01
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
checkpoint | Wall Penetration - Overflow slots through facade
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 3 - South Wall - MC01
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | 100mm Mineral Wool Panel - MC01
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Drip flashing at base of sheets - White to match panels
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 3 - Terrace 1 - Wall
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 75mm Mineral Wool Panel - MC03
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels (Including Tape)
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 3 - Terrace 2 - Soffit - MC03
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 75mm Mineral Wool Panel - MC03
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels (Including Tape)
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 3 - Terrace 2 - Wall
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 75mm Mineral Wool Panel - MC03
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels (Including Tape)
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Wall Flashing - White external with Tape
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 3 - Section C - Wall
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 100mm Mineral Wool Panel - MC01
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
section | Installation
checkpoint | Drip flashing at base of sheets - White to match panels (Including Tape)
checkpoint | External corner flashing - White to match panels - including tape
checkpoint | Wall Flashing - White external with Tape
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Rainspan Zone 3 - Section F - Wall - MC01
checklist | Eurobond Installation checklist
section | Material Inspection
checkpoint | Wall Cladding - 100mm Mineral Wool Panel - MC01
checkpoint | Wall Cladding - Ledger angle
checkpoint | Stainless Screws
section | Installation
checkpoint | Wall Flashing - White external with Tape
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:

## Dridesign
Dridesign - Zone 3 - Section C - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels - non perforated
checkpoint | Dri Design Panels - Aluminium panels - 80m2 only perforated to bleacher area
checkpoint | Insulation - Wall - Acoustic Black Perforated - 50mm
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Aluminium - Window Trim - 400mm
checkpoint | Aluminium - Foot Flashing - stepped to stairs
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 3 - Section F - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | Dridesign J extrusion & PVC tape
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Aluminium - Window Trim - 400mm
checkpoint | Aluminium - Foot Flashing - stepped to stairs
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 3 - South - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Dri Design Panels - Aluminium panels - 80m2 only perforated to bleacher area
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Wall Trim to Horizontal fins - small face
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Aluminium - Window Trim - 400mm
checkpoint | Aluminium - Foot Flashing - stepped to stairs
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Area clean and free of debris
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 3 - Terrace 1 - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels - MC03
checkpoint | Dri Design Panels - Aluminium panels - MC01
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Aluminium - Window Trim - 400mm
checkpoint | Aluminium - Foot Flashing - stepped to stairs
checkpoint | Wall Penetration - Overflow slots through facade
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 3 - Terrace 2 - Soffit
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | J extrusion & tape
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | 0.70mm Aluminium - Soffit Trim 200mm
checkpoint | Soffit Cladding - Custom on site panel cutting/raking
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 3 - Terrace 2 - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels - MC03
checkpoint | Dri Design Panels - Aluminium panels - MC01
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | J extrusion & tape
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Aluminium - Wall Trim - 600mm - Perimeter Channel Flashing
checkpoint | Aluminium - Window Trim - 400mm
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 2 - East - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | J extrusion & tape
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Wall Flashing - Aluminium - Window Trim - 400mm
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 2 - Internal - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | J extrusion & tape
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Wall Flashing - Aluminium - Window Trim - 400mm
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 2 - North - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | J extrusion & tape
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 2 - Terrace 3 - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Small face extrusion
checkpoint | Aluminium - Wall Trim - 400mm
checkpoint | Wall Flashing - Aluminium - Window Trim - 400mm
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 2 - West - Wall
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Aluminium - Wall Trim to Horizontal fins - small face
Aluminium - Small face extrusion
Aluminium - Wall Trim - 400mm
Aluminium - Window Trim - 400mm
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 2 - Airlock - Soffit
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | Wall Cladding - Dridesign J extrusion & PVC tape
checkpoint | Metal Wall Cladding - Custom On Site Panel
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Soffit Flashing - 0.70mm Aluminium - Soffit Trim 200mm
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative:
Dridesign - Zone 2 - Ampitheatre - Soffit
checklist | Dridesign Installation checklist
checkpoint | Dri Design Panels - Aluminium panels
checkpoint | J extrusion & tape
checkpoint | Soffit Cladding - Custom on site panel cutting/raking
checkpoint | PVC Tape to the rear of the Cassette Top Flanges
section | Installation
checkpoint | Soffit Flashing - 0.70mm Aluminium - Soffit Trim 200mm
checkpoint | Area clean and free of debris
checkpoint | Insulated Panel Wall Cladding - Drill weep holes in J extrusion
checkpoint | Materials in good condition
section | Signoffs
checkpoint | Inspected and accepted by S&H authorised representative as complying with relevant Australian Standard and legislation
text | Checked and Signed by:
checkpoint | Inspected and accepted by Authorized Representative
text | Checked and Signed by:
checkpoint | Reinspection requested by Subcontractor
text | Date:
checkpoint | Non-Conforming Items to be Rectified
checkpoint | Follow up work satisfactorily
text | Site Supervisor:
checkpoint | All items have been completed and demonstrated satisfactorily
text | Client Representative: