## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP002 - Site Establishment | itp |  |  |  |  | FH-ZU2-QU-ITP002 - Site Establishment
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – Using the correct and complete set of drawings.
label | – All drawings are the latest revision
label | Reference Documents - Work Pack
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.2 - Dilapidation Report
label | Frequency - Prior to works
label | Acceptance Criteria - A dilapidation report is to be completed and submitted prior to works on site. Dilapidation report to include photos and recordings of the condition of the site compounds areas prior to start.
label | Reference Documents - Dilapidation Report
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex & This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.3 - Existing Service Identification & Protection
label | Frequency - Prior to works
label | Acceptance Criteria - Hardstand area has current BYD plans, service scanned, and existing services has been proved. Services have been identified and protected prior to demolition.
label | Reference Documents - BYDA, Survey Maps
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Surveyor, Project/Site Engineer
date | Date Completed:
checkpoint | 1.4 - Implementation of control measures
label | Frequency - Prior to works
label | Acceptance Criteria - All necessary control measures are being implemented, which include PSP, ECP, TMP, SWMS and WP
label | Reference Documents - PSP, EMP, TMP, SWMS, WP
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.5 - Testing
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure PFAS testing has been completed. The results of the testing will be used to determine the appropriate disposal or re-use of the demolished materials.
label | Reference Documents - Aconex
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed and test report
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.6 - Excavation Permits
label | Frequency - Prior to works
label | Acceptance Criteria - Prior to works, check that excavation permit has been obtained from APAM prior to any ground penetrating works. Internal Fulton Hogan permit has been issued for excavation works and plant operators have a Go-Card.
label | Reference Documents - APAM Excavation permit, FH Permit, Go-Cards
label | Inspection/Test Method - Verify
label | Record of conformity - Excavation Permit
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 1.7 - Geotechnical Testing
label | Frequency - Prior to works
label | Acceptance Criteria - Ensure testing is carried out to obtain a Hardstand design that meets the requirements and suitable for use.
label | Reference Documents - APAM Excavation permit, FH Permit, Go-Cards, FH spec
label | Inspection/Test Method - Verify
label | Record of conformity - Excavation Permit
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Building Hardstands
checkpoint | 2.1 - Definition of a works area (survey)
label | Frequency - Each Hardstand
label | Acceptance Criteria - Work area has been cleaned and surveyed (marked on site). Limits of hardstands are clearly marked.
label | Reference Documents - Site Markups, Survey layouts
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer, Surveyor
date | Date Completed:
checkpoint | 2.2 - Preparing subgrade
label | Frequency - Each Hardstand
label | Acceptance Criteria - Ensure topsoil stripped as per hardstand temp design and subgrade compacted to meet design requirements from Geotechnical Engineer.
label | Reference Documents - Geotechnical temp design
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 2.3 - Disposal of Material
label | Frequency - As Required
label | Acceptance Criteria - Contaminated or PFAS materials are to be taken to Gate 11 to be stockpiled into their dedicated category and contaminant.
label | Reference Documents - Negri PFAS Permit
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed and Negri Permit
label | IP
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 2.4 - Building Hardstand
label | Frequency - Each Hardstand
label | Acceptance Criteria - Make sure hardstand is built according to the geotechnical temp design, no soft spots existing after proof rolling.
label | Reference Documents - Geotechnical temp design
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer, Foreman, Geotechnical Engineer
date | Date Completed:
checkpoint | 2.5 - Building Crossways
label | Frequency - As Required
label | Acceptance Criteria - Construct culvert crossing/driveway access where required as per the temporary design.
label | Reference Documents - Temporary Design
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 2.6 - Installing Fencing
label | Frequency - As Required
label | Acceptance Criteria - Fencing installation is done as per the temp design or Australian standards AS4687
label | Reference Documents - Temporary Design
label | Inspection/Test Method - Visual inspection & verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
section | 3.0 - Mobilization and Set Up
checkpoint | 3.1 - Landing and Levelling Sheds
label | Frequency - Each Hardstand
label | Acceptance Criteria - Sheds are level and as per the site management plan.
label | Reference Documents - Manufacturers specification
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 3.2 - Erecting Hayshed
label | Frequency - Each Hardstand
label | Acceptance Criteria - Hayshed has been constructed as per the verified temporary design provided by OPT
label | Reference Documents - Temporary Design
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | 3.3 - Connecting electrical and plumbing services and appliances
label | Frequency - Each Hardstand
label | Acceptance Criteria - All appliances and connections are functional and tested and tagged
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project/Site Engineer, Foreman
date | Date Completed:
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: