## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP010 - Cement Treated Base | itp |  |  |  |  | FH-ZU2-QU-ITP010 - Cement Treated Base - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - The current revision drawings are being used including subcontractors copy.
label | Frequency - Prior to works
label | Acceptance Criteria - Current revision drawing is being used including the subcontractors copy. Current Revision to be obtained via Aconex.
label | Reference Documents - Aconex
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project/Site Engineer, Superintendent, Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
label | Reference Documents - PSP, EMP, TMP, SWMS & WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Project/Site Engineer
date | Date Completed:
section | 2.0 - Cement Treated Base Documentation & Trial
checkpoint | 2.1 - Submission of Mix Design
label | Frequency - 21 days prior to works
label | Acceptance Criteria - CTB material and test results to be submitted to the Principal’s Representative for review to ensure that specifications are met and are compliant, prior to the initial placement of the material.
label | Mix design results will include:
label | ○ Cement sample should include a CTB material within +/-0.5% of the specified cement content.
label | ○ Aggregates comply with either Section 4.4 or VicRoads Class 2 or 3 material.
label | ○ Cement shall be Portland Cement Type GP or Type GB complying with AS 3972.
label | ○ 3% minimum Portland cement content by weight of the dry un-stabilised material.
label | ○ Mean seven-day unconfined compressive strength of CTB to be a minimum of 5MPa and a maximum of 15MPa. No single samples are to be below 5MPa.
label | ○ Water to be pot
label | Reference Documents - Spec cl. 5.4, Spec cl. 5.5 AS 3972 VicRoads Class 2, VicRoads Class 3
label | Inspection/Test Method - Verify
label | Record of conformity - Approved Mix Design Report
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
label | Principles Rep - Aconex: BecaCPL-GCOR-000790
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Supply of Information on Materials Source
label | Frequency - Prior to works
label | Acceptance Criteria - Principle Contractor to supply the Principal’s Representative with supply information regarding the source of the CTB material via Aconex.
label | ○ Material information will include the material brand, material type, material supply source, and a supporting test certificate from a laboratory registered by NATA to prove material suitability for the Works.
label | Reference Documents - Spec cl. 5.21.1, Spec cl. 5.21.1.1 AS3972
label | Inspection/Test Method - Verify
label | Record of conformity - Approved Supply of Information Material Source
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
label | Principles Rep - Aconex: BecaCPL-GCOR-000790
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Production and Construction Trial
label | Frequency - Prior to works
label | Acceptance Criteria - Construction Trial for CTB mix to be undertaken by Contractor and reviewed by the Principal’s Representative.
label | ○ Trial of CTB will be based on the first day of placement. Construction procedure to be reviewed and updated if there are any non-conformances associated with the initial trial.
label | ○ The size of the trial area shall be a minimum of 3.5m wide and 50m in length.
label | ○ The CTB trial area may form part of the completed works.
label | Reference Documents - Spec cl. 132, Spec cl. 5.6
label | Inspection/Test Method - Verify
label | Record of conformity - Approved Construction trial report
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Placement of CTB Methodology
label | Frequency - Prior to works
label | Acceptance Criteria - Prior to placement of CTB the Principles Representative shall review this Work Method Statement for proposed methods of placement, compaction and curing
label | Reference Documents - Spec cl 5.9
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Sign off
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
label | Principles Rep - Aconex: BecaCPL-GCOR-000810
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Provision of Material Samples
label | Frequency - At Least 5 Days Prior to works
label | Acceptance Criteria - Principal Contractor to physically handover reference samples to Principal’s Representative of the approved CTB material. To be truly representative, the reference samples will be taken straight from the supplier of the material.
label | ○ The reference samples shall be divided into two representative portions, with one being held by the Contractor and the second portion by the principal until completion of the Works.
label | Reference Documents - Spec cl. 5.21.1.2
label | Inspection/Test Method - Verify
label | Record of conformity - Handover of Reference Samples and Aconex sign off
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Placement of Cement Treated Base
checkpoint | 3.1 - Subgrade, Basecourse Preparation
label | Frequency - Each lot
label | Acceptance Criteria - Existing surface of subbase is maintained in compliance with tolerances on surface smoothness and level. The subbase is clean and clear of any foreign matter before the placing of the CTB.
label | ○ Principal’s Representative will be notified 24 hours prior to the placement of CTB to allow the subbase to be inspected prior to the placement of the CTB. This will be recorded in ITP009 – Unbound Pavements.
label | ○ Principles Representative to be notified of the intention to place CTB.
label | Reference Documents - Spec cl. 5.7, Spec cl 5.9
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Foreman, Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.2 - Layer Placement Parameters
label | Frequency - Every Lot
label | Acceptance Criteria - Summary of Parameters for each Lot;
label | ○ A lot is defined as one layer placed in a single days production of uniform material
label | ○ Max Layer is 200mm
label | ○ Min Layer is 100mm
label | ○ Final Surface Level +0mm, -10mm (excluding intermediate layers)
label | ○ Shape: every 10m intervals, <7mm deviation over 3.5m straight edge (excluding intermediate layers)
label | ○ Material is batched within 1% of OMC
label | Reference Documents - Spec Clause 5.9
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Foreman, Site Engineer, Principal’s
date | Date Completed:
checkpoint | 3.3 - CTB Placement – Weather
label | Frequency - Each lot
label | Acceptance Criteria - Weather to be check prior to placement, CTB shall not proceed when;
label | ○ Ambient temperature is below 5°C
label | ○ Temperature is over 35°C
label | ○ Heavy Rain fall is forecasted
label | Reference Documents - Spec cl 5.18
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | HP*
label | Responsibility - Foreman, Project/Site Engineer
date | Date Completed:
checkpoint | 3.4 - CTB Placement – Checks
label | Frequency - Each lot
label | Acceptance Criteria - During CTB placement Activities check;
label | ○ Placement starts on the high side or crown of the layer where practical
label | ○ Material is spread in the direction of Taxiway across full width
label | ○ Underlying layer is not disturbed during deliveries
label | ○ Inspect Material for any contamination through placement activities
label | ○ Adjoining layers are a clean face / vertical
label | ○ Segregation does not occur
label | ○ Placement to be completed within 120 minutes from time of batching and before concrete has obtained its initial set
label | Reference Documents - Spec cl. 5.9 AS1289.5.2.1
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This signed ITP
label | IP
label | Responsibility - Site Engineer, Foreman
date | Date Completed:
checkpoint | 3.5 - CTB Compaction – Checks
label | Frequency - Each Lot
label | Acceptance Criteria - During Compaction check;
label | ○ Heavy smooth drum roller of 15t to 20t is used for initial compaction
label | ○ Pneumatic roller of 27t will compact material for final consolidation.
label | ○ A heavy smooth drum roller (in static mode) may also be used for final consolidation
label | ○ Watercart present onsite for conditioning
label | ○ Materials are trimmed to required shape and level
label | Reference Documents - Cl 4.10
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 3.6 - Curing & Protection
label | Frequency - Each Lot
label | Acceptance Criteria - Curing to commence as soon as CTB has been placed, compacted and trimmed. No plant (other than curing) to track across CTB for minimum 24 hours.
label | Curing to follow one of the below methods;
label | 1. Wet Method: This will involve a watercart lightly spraying the CTB surface for minimum 7 days.
label | 2. Debonding Coat: The CTB will be covered with a bitumen curing compound. In locations of PCC, will be the C170 seal with 7mm aggregate.
label | Reference Documents - Spec cl. 5.15
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Foreman, Project Engineer, Site Engineer
date | Date Completed:
checkpoint | 3.7 - Post Placement CTB Inspection
label | Frequency - Every Lot
label | Acceptance Criteria - Prior to the application of the succeeding layer or installation of the de-bonding coat, CTB final surface is to be inspected with the Principle Representative
label | Reference Documents - Spec cl. 5.9
label | Inspection/Test Method - Verify
label | Record of conformity - ITP signed
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 - Acceptance, Compliance, Controls and Quality Assurance
checkpoint | Field Dry Density
label | Frequency - Each Lot One test every 500m2 (or 250T) or part thereof
label | ○ Minimum 4 tests for Lots under 800m2 (or 400t)
label | ○ Minimum 6 tests for Lots over 800m2 (or 400t)
label | Acceptance Criteria - Average of Specified Minimum Dry Density Ratio (SMDDR) of 97% of the Maximum Modified Dry Density
label | – Average Equals or Exceeds 96% with no individual result be less than 93%. The lot will be accepted.
label | – Average Equals or exceeds 96% with a result being less than 93% - an additional 4 tests will be taken
label | – Average is less than 94%, the lot will be rejected
label | – Average is in between 94% and 96% - an additional 4 tests will be taken
label | Reference Documents - Spec cl. 5.10, Spec cl 5.21.2.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, Test Report Attached
label | TP
label | Responsibility - Foreman, Project Engineer, Site Engineer
date | Date Completed:
checkpoint | Moisture Tests
label | Frequency - Each Lot One test every 500m2 (or 250T) or part thereof
label | ○ Minimum 4 tests for Lots under 800m2 (or 400t)
label | ○ Minimum 6 tests for Lots over 800m2 (or 400t)
label | Acceptance Criteria - Target Moisture content of +/-1% for information only. Production of CTB to be within 1% of OMC.
label | Reference Documents - Spec cl 5.21.2.5
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, Test Report Attached
label | TP
label | Responsibility - Foreman, Project Engineer, Site Engineer
date | Date Completed:
checkpoint | 4.1 - Strength Testing
label | Frequency - Each Lot, divided into four approx. equal sub-lots
label | Acceptance Criteria - A total of 4 sub-lots will be taken as samples, with 2 being used for the 7-day strength testing, and the remaining being used for the 28-day strength testing. 28 day results are for information only.
label | ○ The mean 7-day unconfined compressive strength of the CTB shall be a minimum of 5.0MPa and a maximum of 15.0MPa. No single sample shall be below 5.0 MPa.
label | Reference Documents - Spec cl 5.11, Spec cl. 5.21.2.6, AS1012.9, AS5101.4
label | Inspection/Test Method - Testing
label | Record of conformity - This ITP signed, Test results
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.2 - Process Control
label | Frequency - Each Lot
label | Acceptance Criteria - CTB production and process control test results to be supplied to the Principles Representative
label | Reference Documents - Spec cl. 5.21.2.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.5 - CTB Layer Thickness
label | Frequency - Once Every 30m2
label | Acceptance Criteria - CTB layer thickness to be measured, recorded, and included in the Quality Assurance records. No CTB layer thickness to be less than that shown on the drawings other than allowable construction tolerances
label | Reference Documents - Spec cl. 5.21.5, Spec cl. 5.21.7
label | Inspection/Test Method - Testing & verify
label | Record of conformity - Test results & this ITP signed
label | IP, SCP
label | Responsibility - Project/Site Engineer, Site Engineer
date | Date Completed:
checkpoint | 4.6 - Quality Assurance Records
label | Frequency - Each Lot
label | Acceptance Criteria - Provision of ITP test reports must be submitted within 60 days after the completion of the Works. Principal contractor to supply electronic copy of reports detailing the results of the quality control and testing undertaken.
label | ○ Reports to be transmitted on Aconex and Aconex Reference to be quoted as Hold Point Sign off.
label | Reference Documents - Spec cl. 5.21.3
label | Inspection/Test Method - Submission of ITP reports
label | Record of conformity - This signed ITP
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
textbox | Principles Rep - Aconex Ref:
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Survey As-Built Report
label | Frequency - Each Lot
label | Acceptance Criteria - The surface level at the top of the final CTB layer shall not deviate from design level at the specified points by -10mm or +0mm. Contractor to provide Survey Conformance report of completed CTB surface layers per Lot.
label | Reference Documents - Spec cl. 5.17, Spec cl. 3.14.2
label | Inspection/Test Method - Verify
label | Record of conformity - Completed drawings, survey report, & this ITP signed
label | IP, SCP
label | Responsibility - Surveyor, Project Engineer
date | Date Completed:
checkpoint | Surface Smoothness
label | Frequency - Every Lot
label | Acceptance Criteria - Surface smoothness to be checked every 10m by placing a 3.5m long straight edged on the ground a checking any deviations over 7mm. Complete within 7 days of completion of each section. Document results.
label | ○ Intermediate layers and shoulder pavements are not required to be checked.
label | Reference Documents - Cl 5.17
label | Inspection/Test Method - Verify
label | Record of conformity - Report
label | TP
label | Responsibility - Project/Site Engineer
date | Date Completed:
checkpoint | 4.8 - Correction of Nonconforming Work
label | Frequency - Each Lot (if required)
label | Acceptance Criteria - All CTB that do not meet all the specified requirements will be rejected by Contract Administrator. Materials to be removed full depth of the layer and reinstated, unless otherwise approved through the NCR process.
label | Reference Documents - Spec cl. 5.21.4
label | Inspection/Test Method - Verify
label | Record of conformity - This Signed ITP
label | HP
label | Responsibility - Project/Site Engineer, Principal’s Representative
label | Principles Rep - (if required)
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: