## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP038 - Native Grass Protection | itp |  |  |  |  | FH-ZU2-QU-ITP038 - Native Grass Protection - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to site establishment
label | Acceptance Criteria - Review whether a preliminary report has been completed for the project which will outline where the Significant native grasses are and what protection has been specified.
label | Reference Documents - Consultant reports
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
date | Date Completed:
checkpoint | 1.2 - Check the Google Earth Mapping
label | Frequency - During site establishment
label | Acceptance Criteria - Review the Google Earth / GIS mapping which outlines the boundary of the native grasses at the time they were mapped.
label | Reference Documents - Google Earth Mapping
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
date | Date Completed:
section | 3.0 - Implementation of Controls to Protect the Native Grasses
checkpoint | 3.1 - Mark out the exact Significant Native Grass Boundary area
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Work with the surveyor to mark out the Significant Native grass boundary. FH Project Engineer must verify the set out survey data file matches the ECP and GIS.
label | Reference Documents - CEMP & ECP
label | Inspection/Test Method - Inspect
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
date | Date Completed:
checkpoint | 3.2 - Use temporary fencing/bollards and signage to block access to the Significant native grasses where we are working in close proximity.
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - For works in close proximity to the native grasses, use temporary fencing or purple bollards to block access with signage stating “NO GO ZONE NATIVE GRASSES”. Where possible, this fencing will be installed at a distance (1-2m) away from the actual native grass boundary to act as a ‘buffer zone’ but still allows works to progress.
label | Reference Documents - CEMP & ECP
label | Inspection/Test Method - Inspect
label | Record of conformity - This Signed ITP
label | HP*
label | Responsibility - FH Project Engineer
date | Date Completed:
checkpoint | 3.3 - Implementation of control measures required to protect the significant native grasses around our project area
label | Frequency - Prior to commencing any activity
label | Acceptance Criteria - Inspected and validate native grass delineation has been installed correctly using GPS mapping and against the design drawings.
label | Reference Documents - CEMP & EMP
label | Inspection/Test Method - Inspect
label | Record of conformity - This signed ITP
label | HP
label | Responsibility - FH Project Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 - APAM Hold Point Release - Second Inspection
checkpoint | 4.1 - Release of Hold Point for Native grass Protection
label | Frequency - Prior to commencing construction
label | Acceptance Criteria - Arrange an APAM inspection to confirm that the native grasses are protected with the required temporary fencing or bollards and correct signage where required.
label | ○ All parties are to sign off on this Hold Point
label | ○ Release document
label | Reference Documents - CEMP and ECP
label | Inspection/Test Method - Visual
label | Record of conformity - This Signed ITP
label | HP
label | Responsibility - APAM, Fulton Hogan Environmental Manager or Project Manager
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed above have been reviewed and implemented in accordance with the Construction Environmental Management Plan and conform in all respects with the requirements of the Contract.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: