## Table 1
Inspection Plan Checklist
Speedpanel & Pre-hang Fire Rated Plasterboard Doc.Ref-ITC-001-Rev1
Project Information
Name: |  | Wellington St Student Accommodation | [5 empty] | Work: |  |  |  |  | All applicable
Address: |  | 325-335 Wellington Street, Perth, WA 6000 | [5 empty] | Location:
Head Contractor: |  | Built | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [9 empty] | STATUS
SPECIFICATION / DRW No. | [9 empty] | OK |  |  |  |  | N/A | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: SET OUT
Item 2: INSTALLATION
Item 3: CAULKING
Item 4: CLEAN UP
Item 5: PRE-HANG FIRE RATED PLASTERBOARD
Item 6: TAPING AND STOPPING
Item 7: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  | NAME |  |  |  | SIGNATURE |  | POSITION | [5 empty] | DATE
SUBCONTRACTOR: | [8 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Scope: Speedpanel & Pre-hang Fire Rated Plasterboard |  |  |  |  | ITP Document No.: 1 | [8 empty] | Revision No. A |  |  | Date of Revision: 15/03/2024
Project Name: Wellington St Student Accommodation | [13 empty] | Organization Name: Built
Project Address: 325-335 Wellington Street, Perth, WA 6000
Prepared by
Name: Austin Han |  |  |  |  | Position: Contract Administrator | [8 empty] | Signature: |  |  | Date: 15/03/2024
Approved by
Name: ShuHan Hong |  |  |  |  | Position: Site Foreman | [8 empty] | Signature: |  |  | Date: 16/03/2024
Level: | [13 empty] | Room No./Area:
Project Specification: AR-SPC01 ¦ Australian Standards: AS2589 ¦ Project Drawings: HB-AR-00, HB-AR-03, HB-AR-08, HB-AR-11 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  |  | Reference Documents |  | Acceptance Criteria | [5 empty] | Frequency |  |  |  | Verification Records/Comments | Inspection By
[17 empty] | Subcontractor | Built | Client
1 | Set out Speedpanel walls |  |  | HB-AR-00 HB-AR-03 Series |  | Light Weight Wall Plan approved by Built Speedpanel installation guide revision 1 | [5 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S | S
2 | Install Speedpanel |  |  | HB-AR-03 HB-AR-08 Series |  | Light Weight Wall Plan approved by Built. Speedpanel installation guide revision 1 | [5 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S | S
3 | Caulking |  |  |  |  | Speedpanel installation guide revision 1 | [5 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S | S
4 | Clean up |  |  |  |  | Waste all cleaned. Tools and materials placed well. | [5 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | R
5 | Pre-hang fire rated plasterboard |  |  | Architect drawings |  | Light Weight Wall Plan approved by Built. | [5 empty] | Each location |  |  |  | Visual Checklist | S | S
[6 empty] | GTEK Ceiling & Wall Solution Rev. Mar.2024 | [9 empty] | Attached marked off drawings and photos
6 | Taping and stopping |  |  | Architect drawings |  | GTEK Ceiling & Wall Solution Rev. Mar.2024 | [5 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S | S
7 | Clean up |  |  |  |  | Waste all cleaned. Tools and materials placed well. | [5 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | R
Comments:
Date of Inspection: | [10 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [14 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [14 empty] | Date: