## Table 1
Inspection Plan Checklist
Frame All Walls Doc.Ref-ITC-002-Rev1
Project Information
Name: |  | Wellington St Student Accommodation | [5 empty] | Work: |  |  |  |  | All applicable
Address: |  | 325-335 Wellington Street, Perth, WA 6000 | [5 empty] | Location:
Head Contractor: |  | Built | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [9 empty] | STATUS
SPECIFICATION / DRW No. | [9 empty] | OK | [5 empty] | N/A | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: SET OUT
Item 2: FURRING CHANNEL TO WALLS
Item 3: METAL STUD WALL FRAME
Item 4: INSTALLATION AND FIRE RATED PMDF
Item 5: NOGGINGS
Item 6: CHECK NO SCREWS IN DEFLECTION HEAD
Item 7: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  | NAME |  |  |  | SIGNATURE |  | POSITION | [6 empty] | DATE
SUBCONTRACTOR: | [8 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Scope: Frame All Walls |  |  |  |  | ITP Document No.: 2 | [6 empty] | Revision No. A | [6 empty] | Date of Revision: 15/03/2024
Project Name: Wellington St Student Accommodation | [11 empty] | Organization Name: Built
Project Address: 325-335 Wellington Street, Perth, WA 6000
Prepared by
Name: Austin Han |  |  |  |  | Position: Contract Administrator | [6 empty] | Signature: | [6 empty] | Date: 15/03/2024
Approved by
Name: ShuHan Hong |  |  |  |  | Position: Site Foreman | [6 empty] | Signature: | [6 empty] | Date: 16/03/2024
Level: | [11 empty] | Room No./Area:
Wall Type: | [11 empty] | DWG No: | [8 empty] | Rev:
Project Specification: AR-SPC01 ¦ Australian Standards: AS2589 ¦ Project Drawings: HB-AR-00, HB-AR-03, HB-AR-06 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  |  | Reference Documents |  | Acceptance Criteria | [7 empty] | Frequency |  |  |  | Verification Records/Comments |  | Inspection By
[20 empty] | Subcontractor |  | Built | Client
1 | Set out walls |  |  | HB-AR-00 HB-AR-03 HB-AR-06 Series |  | Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2 Dwg No: Rev: | [7 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
2 | Furring channel to walls |  |  | HB-AR-00 HB-AR-03 Series |  | Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2 | [7 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
3 | Metal stud wall frame |  |  | HB-AR-00 HB-AR-03 Series |  | Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2 | [7 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
Item | Activity |  |  | Reference Documents |  | Acceptance Criteria | [7 empty] | Frequency |  |  |  | Verification Records/Comments |  | Inspection By
[20 empty] | Subcontractor |  | Built | Client
4 | Install and fire rate PMDF |  |  | Architect drawings |  | Architect GA plan & door schedule approved by Built. PMDF installation guide provided by builder | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
5 | Noggins |  |  |  |  | As per scope of work. Studco Wall design & installation manual Volume 3.2 | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
6 | Check no screws in deflection head |  |  |  |  | No screws in deflection head | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
7 | Clean up |  |  |  |  | Waste all cleaned. Tools and materials placed well. | [7 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  |  |  | R
Comments:
Date of Inspection: | [10 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [14 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [14 empty] | Date: