## Table 1
Inspection Plan Checklist
Hang Ceilings and Stop, Sand Walls & Ceilings Doc.Ref-ITC-003-Rev1
Project Information
Name: |  |  | Wellington St Student Accommodation | [5 empty] | Work: |  |  |  | All applicable
Address: |  |  | 325-335 Wellington Street, Perth, WA 6000 | [5 empty] | Location:
Head Contractor: |  |  | Built | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [10 empty] | STATUS
SPECIFICATION / DRW No. | [10 empty] | OK |  |  |  |  | N/A | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: INSTALL INSULATION
Item 2: SHEETING
Item 3: STOPPING TO WALLS & CEILINGS
Item 4: SANDING TO WALLS & CEILINGS
Item 5: FIT ACCESS HATCH FRAME
Item 6: CUT OUTS
Item 7: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  |  |  | NAME |  |  | SIGNATURE |  | POSITION | [5 empty] | DATE
SUBCONTRACTOR: | [9 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Scope: Sheet All Walls & Frame Ceiling | [6 empty] | ITP Document No.: 3 | [8 empty] | Revision No. A |  |  |  |  | Date of Revision: 15/03/2024
Project Name: Wellington St Student Accommodation | [15 empty] | Organization Name: Built
Project Address: 325-335 Wellington Street, Perth, WA 6000
Prepared by
Name: Austin Han | [6 empty] | Position: Contract Administrator | [8 empty] | Signature: |  |  |  |  | Date: 15/03/2024
Approved by
Name: ShuHan Hong | [6 empty] | Position: Site Foreman | [8 empty] | Signature: |  |  |  |  | Date: 16/03/2024
Level: | [11 empty] | Room No./Area:
Project Specification: AR-SPC01 ¦ Australian Standards: AS2589 ¦ Project Drawings: HB-AR-00, HB-AR-03, HB-AR-06, HB-AR-14, HB-AR-15, HB-AR-16 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  |  | Reference Documents |  | Acceptance Criteria | [7 empty] | Frequency |  |  |  |  | Verification Records/Comments | Inspection By
[20 empty] | Subcontractor |  | Built | Client
1 | Install insulation |  |  | Architect drawings |  | Light Weight Wall Plan approved by Built. Fletcher insulation installation guide | [7 empty] | Each location |  |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
2 | Sheet fire walls |  |  | Architect drawings |  | Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solutions Rev. Mar 2024 | [7 empty] | Each unit |  |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | HP
3 | Caulking fire walls |  |  | Architect drawings |  | GTEK Ceiling & Wall Solutions Rev. Mar 2024 | [7 empty] | Each unit |  |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
4 | Sheet remaining walls |  |  | Architect drawings |  | Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solutions Rev. Mar 2024 Class 2-9 Building. Fletcher insulation installation guide | [7 empty] | Each unit |  |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | HP
Item | Activity | Reference Documents |  |  |  | Acceptance Criteria | [8 empty] | Frequency |  |  |  | Verification Records/Comments | Inspection By
[20 empty] | Subcontractor |  | Built | Client
5 | Frame ceiling | Architect drawings |  |  |  | Architect RCP drawings approved by Built. Studco Wall design & installation manual Volume 3.2 | [8 empty] | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
6 | Trim out access hatches | Architect drawings |  |  |  | Architect RCP drawings approved by Built. | [8 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos | S |  | S
7 | Clean up |  |  |  |  | Waste all cleaned. Tools and materials placed well. | [8 empty] | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  |  | R
Comments:
Date of Inspection: | [17 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [15 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [15 empty] | Date: