## Table 1
Inspection Plan Checklist
Patching Doc.Ref-ITC-005-Rev1
Project Information
Name: |  | Wellington St Student Accommodation | [5 empty] | Work: |  |  |  | All applicable
Address: |  | 325-335 Wellington Street, Perth, WA 6000 | [5 empty] | Location:
Head Contractor: |  | Buuilt | [5 empty] | Drawing Ref. :
Details
PECOMMENCEMENT | [9 empty] | STATUS
SPECIFICATION / DRW No. | [9 empty] | OK |  |  |  | N/A |  | DATE
DESIGN & COMPUTATIONS
SAMPLES
MATERIALS MEET SPECIFICATION REQUIREMENTS
CHECK FOR DAMAGE
MAINTAIN SUITABLE STORAGE
INSTALLATION REPORT
Item 1: CEILINGS
Item 2: WALLS
Item 3: CLEAN UP
N.C.N. / C.A.R.
FINAL INSPECTION
WITNESSED BY: |  |  | NAME |  |  | SIGNATURE |  |  | POSITION |  |  |  |  | DATE
SUBCONTRACTOR: | [8 empty] | Foreman
BUILDER:
OTHER:
COMMENTS:
Inspection and Test Plan
Scope: Patching |  |  |  |  | ITP Document No.: 5 | [8 empty] | Revision No. A |  |  |  | Date of Revision: 15/03/2024
Project Name: Wellington St Student Accommodation | [13 empty] | Organization Name: Multiplex
Project Address: 325-335 Wellington Street, Perth, WA 6000
Prepared by
Name: Austin Han |  |  |  |  | Position: Contract Administrator | [8 empty] | Signature: |  |  |  | Date: 15/03/2024
Approved by
Name: ShuHan Hong |  |  |  |  | Position: Site Foreman | [8 empty] | Signature: |  |  |  | Date: 15/03/2024
Level: | [12 empty] | Room No./Area:
Project Specification: AR-SPC01 ¦ Australian Standards: AS2589 ¦ Project Drawings: HB-AR-00, HB-AR-03, HB-AR-05 Series
W = Witness, HP = Hold Point, S = Surveillance, R = Review
Item | Activity |  |  | Reference Documents |  |  | Acceptance Criteria |  |  |  | Frequency |  |  |  | Verification Records/Comments |  | Inspection By
[17 empty] | Subcontractor |  | Built | Client
1 | Check ceilings |  |  | Architect drawings |  |  | Architect RCP drawings approved by Built. |  |  |  | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
2 | Check walls |  |  | Architect drawings |  |  | Architect GA plan & wall type drawings approved by Built. |  |  |  | Each unit |  |  |  | Visual Checklist Attached marked off drawings and photos |  | S |  | S
3 | Clean up |  |  | Architect drawings |  |  | Waste all cleaned. Tools and materials placed well. |  |  |  | Each location |  |  |  | Visual Checklist Attached marked off drawings and photos |  |  |  | R
Comments:
Date of Inspection: | [10 empty] | Carried out by:
Verification Statement This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s) | [13 empty] | Attachments  Checklists  Photos  Dockets  Sample Material  Drawings  Calibration Certificates  Test Results / Certificate  Others:  Inspection reports
Signed : | [13 empty] | Date:
Page 1 of 1