## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard | itp |  |  |  |  | ITC&ITP No.1 - Speedpanel & Pre-hang Fire Rated Plasterboard
section | Speedpanel & Pre-hang Fire Rated Plasterboard
checkpoint | 1 - Set out Speedpanel walls
label | Reference Documents - HB-AR-00 HB-AR-03 Series
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. Speedpanel installation guide revision 1.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 2 - Install Speedpanel
label | Reference Documents - HB-AR-03 HB-AR-08 Series
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. Speedpanel installation guide revision 1.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 3 - Caulking
label | Acceptance Criteria - Speedpanel installation guide revision 1
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 4 - Clean up
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Built - R
checkpoint | 5 - Pre-hang fire rated plasterboard
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solution Rev. Mar.2024.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 6 - Taping and stopping
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solution Rev. Mar.2024
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 7 - Clean up
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Built - R
checkpoint | Verification Statement
label | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
label | Attachments
bool | Checklists
bool | Photos
bool | Dockets
bool | Sample Material
bool | Drawings
bool | Calibration Certificates
bool | Test Results / Certificate
bool | Inspection reports
bool | Others:
textbox | Others
holdpoint | Signed:
checklist | ITC&ITP No.2 - Frame All Walls | itp |  |  |  |  | ITC&ITP No.2 - Frame All Walls
section | Frame All Walls
checkpoint | 1 - Set out walls
label | Reference Documents - HB-AR-00 HB-AR-03 HB-AR-06 Series
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2.
textbox | Dwg No:
textbox | Rev:
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 2 - Furring channel to walls
label | Reference Documents - HB-AR-00 HB-AR-03 Series
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 3 - Metal stud wall frame
label | Reference Documents - HB-AR-00 HB-AR-03 Series
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. Studco Wall design & installation manual Volume 3.2.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 4 - Install and fire rate PMDF
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect GA plan & door schedule approved by Built. PMDF installation guide provided by builder
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 5 - Noggins
label | Acceptance Criteria - As per scope of work. Studco Wall design & installation manual Volume 3.2
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 6 - Check no screws in deflection head
label | Acceptance Criteria - No screws in deflection head
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 7 - Clean up
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Built - R
checkpoint | Verification Statement
label | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
label | Attachments
bool | Checklists
bool | Photos
bool | Dockets
bool | Sample Material
bool | Drawings
bool | Calibration Certificates
bool | Test Results / Certificate
bool | Inspection reports
bool | Others:
textbox | Others
holdpoint | Signed:
checklist | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling | itp |  |  |  |  | ITC&ITP No.3 - Sheet All Walls & Frame Ceiling
section | Sheet All Walls & Frame Ceiling
checkpoint | 1 - Install insulation
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. Fletcher insulation installation guide.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 2 - Sheet fire walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Built. GTEK Ceiling & Wall Solutions Rev. Mar 2024.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - HP
holdpoint | HOLD POINT
checkpoint | 3 - Caulking fire walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar 2024
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 4 - Sheet remaining walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Light Weight Wall Plan approved by Built.
label | ○ GTEK Ceiling & Wall Solutions Rev. Mar 2024
label | ○ Class 2-9 Building.
label | ○ Fletcher insulation installation guide
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - HP
holdpoint | HOLD POINT
checkpoint | 5 - Frame ceiling
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Built. Studco Wall design & installation manual Volume 3.2.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 6 - Trim out access hatches
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Built.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 7 - Clean up
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Built - R
checkpoint | Verification Statement
label | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
label | Attachments
bool | Checklists
bool | Photos
bool | Dockets
bool | Sample Material
bool | Drawings
bool | Calibration Certificates
bool | Test Results / Certificate
bool | Inspection reports
bool | Others:
textbox | Others
holdpoint | Signed:
checklist | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings | itp |  |  |  |  | ITC&ITP No.4 - Hang Ceilings and Stop, Sand Walls & Ceilings
section | Hang Ceilings and Stop, Sand Walls & Ceilings
checkpoint | 1 - Insulation to ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Built. Fletcher insulation installation guide.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 2 - Sheets to ceiling
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Built. GTEK Ceiling & Wall Solutions Rev. Mar.2024.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - HP
holdpoint | HOLD POINT
checkpoint | 3 - Stopping to walls & ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 4 - Sanding to walls & ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - GTEK Ceiling & Wall Solutions Rev. Mar.2024
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 5 - Fit access hatch frame
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Built.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 6 - Cut out for lights
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Built.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 7 - Clean up
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Built - R
checkpoint | Verification Statement
label | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
label | Attachments
bool | Checklists
bool | Photos
bool | Dockets
bool | Sample Material
bool | Drawings
bool | Calibration Certificates
bool | Test Results / Certificate
bool | Inspection reports
bool | Others:
textbox | Others
holdpoint | Signed:
checklist | ITC&ITP No.5 - Patching | itp |  |  |  |  | ITC&ITP No.5 - Patching
section | Patching
checkpoint | 1 - Check ceilings
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect RCP drawings approved by Built.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 2 - Check walls
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Architect GA plan & wall type drawings approved by Built.
label | Frequency - Each unit
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 3 - Clean up
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist, Attached marked off drawings and photos
label | Inspection By: Built - R
checkpoint | Verification Statement
label | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
label | Attachments
bool | Checklists
bool | Photos
bool | Dockets
bool | Sample Material
bool | Drawings
bool | Calibration Certificates
bool | Test Results / Certificate
bool | Inspection reports
bool | Others:
textbox | Others
holdpoint | Signed:
checklist | ITC&ITP No.6 - Rigid Board | itp |  |  |  |  | ITC&ITP No.6 - Rigid Board
section | Rigid Board
checkpoint | 1 - Set out Rigid Board
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Reflected Ceiling Plan approved by Built
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 2 - Install Rigid Board
label | Reference Documents - Architect drawings
label | Acceptance Criteria - Reflected Ceiling Plan approved by Built. Kingspan Kooltherm K10 installation guide 2021.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 3 - Tape & Seal
label | Acceptance Criteria - Kingspan Kooltherm K10 installation guide 2021
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Subcontractor - S
label | Inspection By: Built - S
checkpoint | 4 - Clean up
label | Acceptance Criteria - Waste all cleaned. Tools and materials placed well.
label | Frequency - Each location
label | Verification Records/Comments - Visual Checklist
label | Inspection By: Built - R
checkpoint | Verification Statement
label | This is to confirm that the nominated representative of L&D Commercial Interiors Pty Ltd, responsible for overseeing the works, has carried out all necessary inspections as listed above, and will be able to verify with documented evidence that the work has been completed and confirms to the contract specification(s)
date | Date of Inspection:
textbox | Carried out by:
label | Attachments
bool | Checklists
bool | Photos
bool | Dockets
bool | Sample Material
bool | Drawings
bool | Calibration Certificates
bool | Test Results / Certificate
bool | Inspection reports
bool | Others:
textbox | Others
holdpoint | Signed: