## Sheet1
1.1 | Bonded Anchor System - Chemical Adhesive | IFC Drawings 680.05 (a) 680.05 (b) (i - vi) | Bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below: i. ATIC SPEC 38 ii. EOTA EAD 330499-00 or 01-0601 iii. ICC-ES (USA) Enter: Teambinder Material Approval number [free text box] | Document Review | Once, per product, prior to commencement of Works | WP | Superintendent | This ITP | 1.1 - Bonded Anchor System - Chemical Adhesive | Reference: IFC Drawings 680.05 (a) 680.05 (b) (i - vi) | - - - - - - - - - | Acceptance Criteria: Bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below: i. ATIC SPEC 38 ii. EOTA EAD 330499-00 or 01-0601 iii. ICC-ES (USA) Enter: Teambinder Material Approval number [free text box] | - - - - - - - - - | Method: Document Review | - - - - - - - - - | Frequency: Once, per product, prior to commencement of Works | - - - - - - - - - | WP | - - - - - - - - - | Responsibility: Superintendent | - - - - - - - - - | Verifying Documents: This ITP | 1.1 - Bonded Anchor System - Chemical Adhesive
1.2 | Bonded Anchor System - Reinforcement | IFC Drawings 680.05 (c) 611.05 (a) | Where applicable, current ACRS certification for materials and for bar processing. Anchor bars need to remain uncoated (black) for durability purposes in fatigue loading. Note: Galvanised steel dowels are only to be used where maximum design life is 25 years and only permanently dry conditions. Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery) Enter: Teambinder Material Approval number [free text box] | Document Review | Where applicable, once for each supplier, 14 days of award of contract | WP | Superintendent | This ITP | [14 empty] | Reference: IFC Drawings 680.05 (a) 680.05 (b) (i - vi)
1.3 | Bonded Anchor System - Stainless Steel Anchors | IFC Drawings 680.05 (c) | Where applicable, stainless steel grades 1.4401, 1.4404, 1.4362 and 1.4571 (marking A4) may not be used in conditions where the component is either permanently inundated in seawater or in the splash zone. Stainless steel grades 1.4529 (marking C) may be used in conditions where the component is either permanently inundated in seawater or in the splash zone. Enter: Teambinder Material Approval number [free text box] | Document Review | Where applicable, once, prior to commencement of Works | WP | Superintendent | This ITP | [14 empty] | - - - - - - - - -
Acceptance Criteria: Bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below: i. ATIC SPEC 38 ii. EOTA EAD 330499-00 or 01-0601 iii. ICC-ES (USA) Enter: Teambinder Material Approval number [free text box]
- - - - - - - - -
Method: Document Review
- - - - - - - - -
Frequency: Once, per product, prior to commencement of Works
- - - - - - - - -
WP
- - - - - - - - -
Responsibility: Superintendent
- - - - - - - - -
Verifying Documents: This ITP