## B04
Maersk - Plumbing and Drianage
Level | Area | Total of Apartments
Underslab and Drainage
Dispatch Office
Main Office
Water Main Grid H
Water Main Grid 1
Water Main Grid A
Wate Main Grid 16
Water Main Eastern Front Yard
Grid 16 Loading Bay
Weighbridge Drainge
RPZ Set Ups
Water Tanks and Pumps
Irrgation
1st Fix and 2nd Fix
Dispatch Office
Main Office
Coolstore
WaterTanks and Pumps

## Checklists
type | name | values
checklist | Underfloor check
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
checkpoint | Plans correct issue and construction set
checkpoint | Check set out from builders
section | Install QA
checkpoint | Hot Water System (relief drain)
checkpoint | Drains laid to correct falls
checkpoint | Pipes wrapped though floor
checkpoint | Pipes tested for inspection
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Inspection passed
checkpoint | Water needed in floor for 1st fix
checkpoint | Work completed as per spec and tidied up
Checklist | Inslab Pipe Work
checkpoint | Drains laid to correct falls
checkpoint | Pipes wrapped/ lagged though floor correctly
checkpoint | No denso showing on S/S clips in Raft Slab
checkpoint | Check Set out of all risers and inline with drawings
checkpoint | Pipe work clipped correctly to reo and fixed
checkpoint | Scala Testing done on Trenches
checklist | First Fix QA
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
checkpoint | Plans correct issue and construction set
checkpoint | Check Plans for correct sizing and pipe material
section | First fix checks
checkpoint | Sanitary fixtures and fittings specifications received for set out
checkpoint | Acoustic Wrap installed
checkpoint | All Pipes silicone though noggs
checkpoint | Vents install though roof
checkpoint | Floor Flanges installed and Capped
checkpoint | All stud stiffeners installed
checkpoint | Marshall flashings installed
checkpoint | All pipes pressure tested to 1500KPA (fusiotherm refer to test procedures)
checkpoint | Noggs installed for fixing of sanitary fixtures and fittings
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Inspection passed
checkpoint | Work completed as per spec and tidied up
checkpoint | Council Inspection Passed
checklist | Second Fix QA
section | Preinstall QA
checkpoint | Substrate acceptable
checkpoint | Area accessible and ok to begin work
section | Second fix checks
checkpoint | Fixtures and fittings checked for damage
checkpoint | Flanges installed on all penetrations
checkpoint | All fixtures sealed with silicone as required
checkpoint | All fittings checked for leaks
checkpoint | Hot Water system commissioned
checkpoint | System commissioned
checkpoint | Handover checks
checkpoint | Photos Taken & attached
checkpoint | Work completed as per spec and tidied up
Drainage
Check Point | Storm Water
Check Point | Plans correct issue and construction set
Check Point | Check set out from builders
Check Point | Check Plans for correct sizing and pipe material
Check Point | All Falls achieved as per plans
Check Point | All Manholes hauched as per code
Check Point | All Cesspits, Manholes installed to correct heights
Check Point | All Trenches compacted with compactor
Check Point | Pipes tested for inspection
Check Point | Photos Taken
Check Point | Inspection passed
Check Point | Engineer Inspected
Check Point | Mark up drawings Done
Check Point
Check Point | Sewer
Check Point | Plans correct issue and construction set
Check Point | Check Plans for correct sizing and pipe material
Check Point | All Falls achieved as per plans
Check Point | All Manholes hauched as per code
Check Point | All Manholes installed to correct heights
Check Point | All Trenches compacted with compactor
Check Point | All ORG and RE installed as per plan
Check Point | Pipes tested for inspection
Check Point | Inspection passed
Check Point | Mark up drawings Done
Check Point | Photos Taken
Check Point
Check Point | Water Mains and Infrastructure
Check Point | Plans correct issue and construction set
Check Point | Check Plans for correct sizing and pipe material
Check Point | Water Main flushed ready for connection
Check Point | Pipes tested for inspection
Check Point | Warning tape installed
Check Point | All Trenches compacted with compactor
Check Point | Inspection passed
Check Point | Mark up drawings Done
Check Point | Photos Taken