## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 49185ac1-9958-4e8b-90f2-639ac42da96a |  | checklist | Deck Handover |  |  |  |  | Yes | Deck Handover | 0fcbfb24-e137-46bf-b355-2544f6232bbb
checkpoint-status | c3e22587-2ad5-4483-bce6-010cfc6a0211 |  | checkpoint | Communication between all trades
checkpoint-status | c1d6d104-0417-4603-840e-111c0c364f1f |  | checkpoint | Signage and barricades in place
checkpoint-status | e52e3cda-5284-4757-86c4-c43d9f9a7022 |  | checkpoint | Deck clean and clear of materials
checkpoint-status | 2910f8c0-70d7-48de-8b00-00933430ee8a |  | checkpoint | Loose materials are stacked and secure
checkpoint-status | 57b80811-0b86-4075-861c-d1e650477543 |  | checkpoint | Any backpropping required to handle loads of reo and other equipment
checkpoint-status | 8e9e4e9f-17d4-4147-8cf7-4bc2fd7e9519 |  | checkpoint | Designated walkways established
checkpoint-status | 733513b6-1b69-49fa-8ffd-b3a9d968f8e5 |  | checkpoint | All loose materials removed from edge
checkpoint-status | 69b10ef4-4f20-43cd-8976-2278b3800a5f |  | checkpoint | Are all penetrations covered and secured
checkpoint-status | 372f2ea6-8d47-4f00-a75f-21776b6d8970 |  | checkpoint | Rubbish bin on Deck
checkpoint-status | 523f36f8-5402-4c03-a29a-5ab867e81a12 |  | checkpoint | Perimeter Screens / Edge protection installed
checklist-flat | 50b530bc-ef7e-4d19-9b03-739283cf0d9f |  | checklist | Daily Pre Start |  |  |  |  | Yes | Daily Pre Start | ba30be87-faa6-48fb-bee6-0aef7be973c2
checkpoint-status | 66a206a7-f35f-43de-9dea-441749cf6204 |  | checkpoint | Daily pre start meeting completed
text | 6ce31fee-f913-59c6-8688-53233e607fc7 |  | textbox | Date
text | c2223dff-f2d5-52b1-845f-6ba07ba5dc2b |  | textbox | Time
text | 6381875f-8b87-5a99-b136-b1c65ac73d38 |  | textbox | Location
text | 957a1062-4856-583d-a1d8-1c5360a1ebfb |  | textbox | Supervisor / meeting leader
text | e43b3c10-3137-50fd-9ec2-e833b31671ac |  | textbox | Project Manager & Construction Supervisor attending
select | b1ca700a-bd2c-57fc-9fdf-3da3b3204aa7 |  | dropdown | Current weather | Rain, Wind
text | 6ba390ff-d9b5-516c-81c7-ae05e20dd027 |  | textbox | Temp
select | 728338df-e535-554d-bd24-89aed112af00 |  | dropdown | Forecast | Rain, Wind
text | 9a1b1020-3b0c-5fb0-a7b6-baed86a50cdc |  | textbox | Temp
button | 5d050d24-8c37-565c-8c96-5247df2569bb |  | button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
button | c902f9cf-add1-50d5-988d-92339a97a251 |  | button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
text | 73bd1fb3-6003-5190-8c52-5589691cfa5b |  | textbox | Any issues from the previous day
button | c8710d0c-4637-5ec0-a691-db2f838705a2 |  | button | Do you need to change SWMS | Yes, No
text | be2e90f2-9757-502d-b53f-51deda77b86d |  | textbox | First aiders on site today
text | c4584b49-a371-5cda-b163-c9ec1d9f240c |  | textbox | Apprentice & who are they assigned to
text | 952a8d69-5cae-57da-ad8d-8cc505729130 |  | textbox | Apprentice & who are they assigned to
text | b2951485-f097-5388-9ea2-d821bbac6973 |  | textbox | Apprentice & who are they assigned to
text | c4806d51-d926-518a-ad09-8772b60b2f4d |  | textbox | Todays tasks / jobs
select | 3772c266-e00f-555c-bdd3-35c66ef3b066 |  | dropdown | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
button | 5a71c6f4-4be2-5f98-8661-434c866011ce |  | button | SWMS in place for all activities | Yes, No
button | b592e2d4-432c-55d0-a8da-c0ba12d5b6db |  | button | Hot works | Yes, No
button | fa52512e-5c0f-55a1-9bb4-767ed2443617 |  | button | Excavation | Yes, No
button | 383378bb-efe4-5a40-9221-f61d3d796504 |  | button | Ladder | Yes, No
button | c1b93fda-71ca-5e7d-bcf7-56fa6fb689e4 |  | button | Core | Yes, No
button | f840ea98-eab4-582d-aa2f-5eb43d5f92af |  | button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
text | 0d2cb15e-2ece-5be6-b5a2-28f4ce4acc66 |  | textbox | If yes, list the substances
text | 46f29235-f1a8-5d54-82c4-631d2f11598b |  | textbox | Attendees
checklist-flat | 89d6b487-ab16-4770-885b-eadd768b37b6 |  | checklist | Variation / Site Instruction |  |  |  |  | Yes | Variation / Site Instruction | 36ca3faa-ba73-437c-a4a3-25180325d975
checkpoint-status | 91d0b653-c7db-4b60-bdd3-e06c1bde065f |  | checkpoint | Variation / SI Details Entered
label | 907beb16-1886-52bd-905b-bb58c07bf397 |  | note | Please take before photos
select | d366dc36-d740-5915-9344-48d5a4d70861 |  | dropdown | Work type: | Site Instruction, Variation Work
text | 8437014f-c997-528b-b3b0-b4e41030d104 |  | textbox | Attention:
text | e3247325-ace5-5dd0-a52e-3838e2e456c3 |  | textbox | Area/Location
text | 32977f81-a249-515f-b629-c509d361de34 |  | textbox | Date
text | f7943d34-e2a0-5565-8945-60f8754dbcc9 |  | textbox | Scope of work
text | 708bdc6b-03ce-5c11-99a3-fb11ae117dec |  | textbox | Normal Hours
text | 50607b9d-5c0e-57f5-b5af-64f268e38e59 |  | textbox | Overtime Hours
text | f91848e7-59f3-52c3-b21d-4dd9bb269512 |  | textbox | Material to complete task
checkpoint-status | 280dcdf6-92cb-4fd7-b047-08fb2e938f56 |  | checkpoint | Reference/SI Number Entered
text | 1e8c7f2b-1486-557d-834f-b2d58f2db694 |  | textbox | Reference/SI Number
checkpoint-status | 35aae6b3-a0f2-4599-835b-d8bda7b2bc30 |  | checkpoint | Variation / SI Work Completed
checkpoint-status | 49963d43-c01f-40d6-a81c-098da757d830 |  | checkpoint | Values added (Office use only)
text | f4fe15a4-6752-5aa5-80b6-ed2e683fd672 |  | textbox | Labour Value
text | 4447216b-278e-53eb-940a-922b846a0950 |  | textbox | Material Value
text | 0c3c051c-ba15-5a6c-b127-38d3209243d5 |  | textbox | Measured Items
text | 6801d96e-8de1-50c3-bcce-31ba4c6bb01d |  | textbox | Total Variation Value
checklist-flat | cdb9d37c-cb3d-4f91-b033-309c4c6b4325 |  | checklist | Columns Checklist |  |  |  |  | Yes | Columns Checklist | 453d23da-7b7c-4e3b-835b-e782bcd57b8f
checkpoint-status | bb9dbb4e-23d7-42fa-bf92-3fea483ebf28 |  | checkpoint | Area accessible & ready
checkpoint-status | 03f685bc-df76-40f1-bc26-829e8c4cf108 |  | checkpoint | Drawing references entered
text | 09ff70ad-5a28-5f50-81cc-84b066e62a7b |  | textbox | Architectural
text | f8c7a93d-ac90-5bde-b3cf-8abdff1f2b07 |  | textbox | Structural
text | 615f83be-90cf-5ac1-9df3-3e0ce90b3164 |  | textbox | Other
text | 579ee70c-96eb-585b-a20e-f97f4667f154 |  | textbox | Column No
checkpoint-status | daa855b7-d7ad-4f57-88df-bd31eca39645 |  | checkpoint | Current plans in use / Latest drawings checked and referenced
checkpoint-status | df8404e8-8fbd-4823-8591-8e279317a049 |  | checkpoint | Survey points given for 2 points
checkpoint-status | b1d9bc15-41a6-49aa-ae58-fd204a7b9549 |  | checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint-status | 3f05bbe8-c2a1-4d6f-b5a0-deb7ca642551 |  | checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint | 97a98283-9621-49e3-abdc-11bce3ab1c99 |  | signoff | Inspection from site engineer
checkpoint-status | fe457675-3217-495c-90b8-06194355afe4 |  | checkpoint | Column box cleaned & oiled
checkpoint-status | c5ebb47a-9e50-4790-85ef-dd6cb3333361 |  | checkpoint | Placement of column box over cage
checkpoint-status | abc6aa14-4428-43bd-8eea-1f85c7935d1e |  | checkpoint | Bracing props secured
checkpoint-status | 466eb49a-1db7-49f3-9a2e-968ae592cdb2 |  | checkpoint | Column plumbed
checkpoint-status | d799af68-1597-4448-96df-4fc6d09ea98f |  | checkpoint | Correct class of finish
checklist-sectioned | af8d4ccf-2972-48be-a8e9-141d920ae078 |  | checklist | Core Lids Checklist |  |  |  |  | Yes | Core Lids Checklist | 9b168e73-b070-4fc1-8b11-fabcbd082912
checkpoint-group | 63e845a3-bf8c-457a-a2a7-e233ab5b0714 |  | section | Phase 1
checkpoint-status | 518f481c-6c85-4fa7-a340-5f1577b7daa2 |  | checkpoint | Area accessible & ready
checkpoint-status | 069efe80-9a8a-4811-975c-b1be6b61352e |  | checkpoint | Drawing references entered
text | 259b9a02-38f0-5228-8a01-152caf45720c |  | textbox | Architectural
text | 0c495220-be4b-55ce-8057-4bb1894e8cd3 |  | textbox | Structural
text | c05c9636-528c-5349-be5e-f071b3a19433 |  | textbox | Other
checkpoint-status | 8a8ea143-0ccf-43b8-a6d2-4cd8b1af2ad7 |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 3e435555-7f00-4e3a-8525-45c652ee22a7 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | 90d9b071-cc7b-40b6-961c-4080e121d497 |  | checkpoint | Grids marked by builder
checkpoint-status | 625cfe28-71a2-4b27-88c2-76166e1e3558 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | ed80c05f-6b66-4f3e-9be7-e11104b7210e |  | checkpoint | Fillet & drip mould installed
checkpoint-status | ac1577e2-9c46-4797-8c25-a0abf09443df |  | checkpoint | Check set down position & RL
checkpoint-status | dee2cb61-b566-4213-8709-0b20c8e8bdfa |  | checkpoint | Check penetrations installed
checkpoint-status | 8e794924-bbd2-4efc-9d0d-eeb5d1a14ff0 |  | checkpoint | Column blockouts installed
holdpoint | 17238e57-ab31-4b99-ba3e-e8b734dc4386 |  | signoff | Inspection by site engineer
checkpoint-group | 33e6251e-aae7-41d5-a242-8ca4f09be82a |  | section | Phase 2
checkpoint-status | ad1e7f17-5635-4348-ac8d-795f2f4cf37a |  | checkpoint | Check back propping as per design
checkpoint-status | 53a6d442-5dd3-44b2-b973-9dc480468d9c |  | checkpoint | Blow off deck
holdpoint | 2c7aff8e-1728-4e58-b203-b8212ba72437 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | 72a41cb2-1d5e-4bb8-93ae-1531cee0bb6b |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | e450d5e4-493d-4473-95cf-957ce7845462 |  | checkpoint | Correct Class of Finish
checkpoint-status | 569c4866-54a5-4625-b7db-9cc23cc73fb2 |  | checkpoint | Stripping, cleaning & materials removed
label | 8f022a65-b5c1-5098-b3e8-a19fddcabc6d |  | note | Take photos
checklist-flat | 5f5678fc-bfb1-49ae-bca3-d99fd7538500 |  | checklist | S.O.G Checklist |  |  |  |  | Yes | S.O.G Checklist | cc7f9e62-caa8-4554-b739-f12661058ac7
checkpoint-status | 47dee1b0-7ae4-48fa-b5fa-54363df365b5 |  | checkpoint | Area accessible & ready
checkpoint-status | 06d62d93-9b70-4c41-8c5a-d31b4d1f8909 |  | checkpoint | Drawing references entered
text | 693df90d-49a5-5363-91fd-35d74e3dd2f8 |  | textbox | Architectural
text | a6eb899f-1239-5a71-9004-aaa690f3556f |  | textbox | Structural
text | 4cce0084-f8e7-589d-87e4-17e9491275d3 |  | textbox | Other
checkpoint-status | a2a407de-1264-44cf-b008-d2ad442789e7 |  | checkpoint | Current plans in use
checkpoint-status | 16d8c9cf-d780-40fe-8e21-9ec36443db01 |  | checkpoint | Survey points give for grids
checkpoint-status | 71d9ca5d-0432-44ca-85e2-e4a12d925d08 |  | checkpoint | Surveyors points given for edge boards
checkpoint-status | 60cba7f2-c1b3-41fd-93b0-98e382e14d12 |  | checkpoint | Datum RL supplied by surveyor
checkpoint-status | d4caffb4-0d33-42dc-bb21-1caaf47c16f6 |  | checkpoint | Edge boards plumb & straight
checkpoint-status | 4cf3e229-c9e4-4158-95f3-fd0cc707b7d2 |  | checkpoint | Step downs secure & correct RL
checkpoint-status | b8c18254-8845-4b9f-97f1-23f1bcf350ef |  | checkpoint | Dowels installed on pour joins
checkpoint-status | 7b461949-3cf6-470a-9ae1-ae8dce6b7ec0 |  | checkpoint | Column blockouts installed
checkpoint-status | 732be133-332e-49ad-9c9d-60717de32465 |  | checkpoint | Correct Class of Finish
checklist-flat | e94d83f4-b038-491f-ac92-a988c58bbead |  | checklist | Toolbox Meeting |  |  |  |  | Yes | Toolbox Meeting | 130364b6-e103-4676-b66b-c7a0b2fc2d4c
checkpoint-status | 4315964d-9a4a-4065-bac9-e316a250d075 |  | checkpoint | Toolbox signed off - Attach an forms
text | 56ef6fd6-14de-58e0-a53f-83079b0db251 |  | textbox | Work area
text | 5311aef4-154a-58d5-ae57-bc28a5fd7932 |  | textbox | Supervisor
text | f2b9ec94-d7af-5d46-9e47-0e42a73a969e |  | textbox | Date
text | d4ab76ac-2e2c-58eb-b75a-e53a810aee36 |  | textbox | Time am / pm
text | c0f20adc-cbf9-5ad0-8e05-8c33808e13e5 |  | textbox | Actions from last meeting
text | 71ff5ac2-eee7-5fd5-8a8f-276648c4519f |  | textbox | Injuries last week
text | 19176fa1-8835-5719-8304-7afee93419b9 |  | textbox | Near misses last week
text | 4eb8d54d-f0de-5b31-9420-24194073383a |  | textbox | Safety Items discussed
text | efb9f2d7-2d41-5370-b103-1c9edcc19a8d |  | textbox | Comments from the floor
text | 1d52d54a-7fd3-5bb2-8a17-8392c8cc635d |  | textbox | New business
text | c1c38bef-afae-5b99-971f-d252fbdd5daf |  | textbox | Attendees
checkpoint-status | d9e53b8c-a5de-4c8c-aa85-a8be10a4c25f |  | checkpoint | Attendance verified
checklist-flat | 1b938329-3a31-4c0c-b521-79d46c0372ee |  | checklist | Walls Checklist |  |  |  |  | Yes | Walls Checklist | f6525a3e-9286-422c-9e12-773a2ce4be08
checkpoint-status | 4d2f8f7f-6624-46e2-9fe7-abfdaf800dd0 |  | checkpoint | Area accessible & ready
checkpoint-status | 42d5458f-29a3-4703-b171-0f9af64ec681 |  | checkpoint | Drawing references entered
text | 23f6a1a2-58b0-5cbf-a76d-1f15489c2672 |  | textbox | Architectural
text | bf4b53ed-840b-5c70-a7ed-18d60adaa4b5 |  | textbox | Structural
text | 19feb658-ba35-567e-aa2d-3a4024a643fe |  | textbox | Other
checkpoint-status | 1ce336c0-ca14-4ca5-a0fa-5ed2e3835b2a |  | checkpoint | Current plans in use
checkpoint-status | 57f8bef2-c789-41a6-ae02-53b8c3438d52 |  | checkpoint | Survey points given for 2 points
checkpoint-status | 46f88d5b-aa39-4940-a8f2-0b0c913c69bf |  | checkpoint | Land shutter bracing props secured plumb shutter
checkpoint-status | 1542583b-a770-4984-9f97-d43f9a31bf38 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 8dbb431b-3a64-42c9-8a70-6b15fcf6af90 |  | checkpoint | Blockouts steps penetrations marked & installed
checkpoint-status | f1b26079-8b8f-4ad2-b5cb-75485813f53d |  | checkpoint | Steel tied & clear from Z bar holes
checkpoint-status | cea2a301-67e8-4dd3-958c-fc07a6628728 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 68602eff-ef26-4de1-a339-3dbde2c09b3f |  | checkpoint | Base of walls cleaned
holdpoint | 63e667aa-5993-4271-96dd-22c2f89cd7ab |  | signoff | Inspection by site engineer
checkpoint-status | 72b1de7f-eb30-432d-876f-1b03e9ca9033 |  | checkpoint | Closing shutter installed
checkpoint-status | ed634f2c-21c7-4576-8fd0-585636e72470 |  | checkpoint | Z bars secured wall straight & plumbed
checkpoint-status | 420d9a94-4bef-4e99-a1fa-a22ad3b703ad |  | checkpoint | Correct Class of Finish
checklist-sectioned | 5401c82d-76f2-429b-ab8b-f17ef0879ff2 |  | checklist | Stairs Checklist |  |  |  |  | Yes | Stairs Checklist | 9827755e-35ca-4f6b-b48f-6ca6465e516c
checkpoint-group | 090142a5-8d1c-4304-ad19-7b4437352d47 |  | section | Phase 1
checkpoint-status | 9a8ec78d-9021-4f61-963f-6343d0920da7 |  | checkpoint | Area accessible & ready
checkpoint-status | 23532e24-423d-46a0-b8f4-802de16e185f |  | checkpoint | Drawing references entered
text | 135b53bb-5211-5315-9f7a-de2698dafc0e |  | textbox | Architectural
text | 08895884-17e5-5cfb-bd1a-3272870494e7 |  | textbox | Structural
text | f89fafe3-ac10-5a9e-acfb-a9563ad98d17 |  | textbox | Other
checkpoint-status | 4d1d500f-1cd5-421b-b468-adbcca58d2dc |  | checkpoint | Current plans in use
checkpoint-status | 6ede5137-d1af-485c-9197-c534f5e1068b |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | 005b8595-5d2a-4a73-a6ca-333f114de919 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 3d65af19-820a-4dab-bbb9-5d9d9eb06ab6 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 2b01ad0d-3eb7-489b-817d-e33d3becdd79 |  | checkpoint | Base of stairs cleaned
checkpoint-status | b55ab9d3-4c79-489b-ad2a-a5ee6c82cbaf |  | checkpoint | Riser heights confirmed
checkpoint-status | 03c7c861-853a-48c9-ae4f-8bb85b5be6f6 |  | checkpoint | Going lengths confirmed
checkpoint-status | 8e1aa89e-3236-4d49-839f-3c6fd94f2aa9 |  | checkpoint | Correct Class of Finish
checkpoint-group | 4ba0e628-b357-423d-9196-406ec88782b8 |  | section | Phase 2
checkpoint-status | 558d60a8-b271-4d76-b656-bc5a04c27710 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | b8b64e51-1ae5-41d8-8e2a-fe69fdb83d2b |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | e18119ac-0e7d-43c8-8897-95c6f9916636 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 660ada29-9387-4c6d-b42a-4f386cee979f |  | checkpoint | Riser heights confirmed
checkpoint-status | de70cf24-511c-4f1d-98c7-237418c53c07 |  | checkpoint | Going lengths confirmed
checkpoint-status | 9581daad-d81d-44f2-8695-a480a72f3d2c |  | checkpoint | Correct Class of Finish
checklist-flat | 9eb03a39-cb1a-4fbe-b308-f7fdec62b648 |  | checklist | Injury Form |  |  |  |  | Yes | Injury Form | 14f8aea9-32dd-44d1-a4ad-14fe4b1985db
checkpoint-status | 32e181a0-444e-4b15-b161-7bef39f71adc |  | checkpoint | Injury form completed
text | b8ff311e-387c-5272-bd60-acdef0eb2cbc |  | textbox | Date of incident
text | fb1bf9ec-fadc-507b-bdce-0a6d650434f9 |  | textbox | Time
text | 1fdad347-f489-5f55-aec9-b08d2a3e52f4 |  | textbox | Site location of the accident / incident
text | 6d0f3afc-7019-5fb0-9b53-e6ca5e80afc7 |  | textbox | Detail of how the accident / incident happened
label | 7aabbd33-f648-51a3-8b02-3245c215ea28 |  | note | Details of injured person
text | 11f2c8bc-c2a1-5b33-a806-32e561616005 |  | textbox | First name
text | a90ee3af-54f2-543c-a967-8669f7ed46ad |  | textbox | Last name
text | 299e2967-a9f8-5b04-b6f2-821701b057d3 |  | textbox | DOB
text | 03dad560-51d1-591f-a458-38468d43b756 |  | textbox | Contact No
text | 2f715bef-a0fd-579f-b8aa-b859d360daaa |  | textbox | Address
text | 2a4a91bb-fd61-5b7e-848c-7dd53662b967 |  | textbox | Company
text | eca7e776-496c-5cf9-bc85-65c2cad5941e |  | textbox | Trade
text | a9d0ff13-0daf-5f36-a06c-f53efb518cab |  | textbox | Date Inducted
select | 89c3d156-0880-5b55-b550-d6dd0f8771ef |  | dropdown | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
select | 26efda09-e27e-5ded-a962-a850fe12cf8d |  | dropdown | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
select | adbbae11-8c0b-5ae3-badb-04926fdebca0 |  | dropdown | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
text | d2a1732b-16ce-592c-9afb-edb127f9f228 |  | textbox | Initial treatment given
text | 6cf7efaf-8528-5261-a352-02e8327108d5 |  | textbox | Was follow up treatment provided
text | e3252c70-d210-5d58-95cb-6269d75f1dc1 |  | textbox | Medical centre / Doctor / Hospital attended
text | bf84160b-f6b5-56d8-902f-ec5000b9081f |  | textbox | Date / time attended
button | 0830c669-5701-5b7a-8e64-021fdff5f4b4 |  | button | Regulator notified | Yes, No
label | 4581b9b9-283c-54a5-bd7c-8aedf0738bff |  | note | Witness details
text | 018a4b78-1494-54d2-8f1f-2105c2ab5f53 |  | textbox | Witness name & contact details
text | b7cc32a3-8f17-529c-9a06-d2653cf601c2 |  | textbox | Witness name & contact details
select | faa427ad-8b07-5b78-9151-3252731e84ee |  | dropdown | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
text | 897f359d-12e1-57d8-9eea-9e3735d0ed37 |  | textbox | Other
label | 8ae11d3d-b521-5a52-9a8e-0496edfb896d |  | note | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
checkpoint-status | 9a8c8aaf-7331-4480-ae23-181e0d34c44a |  | checkpoint | Signature of injured worker
checkpoint-status | 8aeff213-94df-4695-ae00-f11830d3f502 |  | checkpoint | Person completing this form
checklist-flat | b6d70a53-a17a-4334-98c9-59a9b152a71c |  | checklist | Site Diary |  |  |  |  | Yes | Site Diary | 8d0dc3df-eabf-45cc-b76e-af6275496aa6
checkpoint-status | 1219b5ff-57fb-4680-82db-a41986166256 |  | checkpoint | Areas of work accessible for the day
select | 5f7e7bf8-4650-5ec3-abc2-621f350eb564 |  | dropdown | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | 011d4022-a08e-5d11-a0ec-358db7c99a06 |  | textbox | Date
text | cf1ff6d8-8da0-5b37-a720-62b52cc88a60 |  | textbox | Year
text | 63d26336-2297-5b3a-ba73-8aec798db1ba |  | textbox | Number of workers on site
text | efcd1ea2-40d6-51c0-84a1-821dbb4c9f9e |  | textbox | HSR on site today enter name
text | a66dccb6-667d-5c6d-93af-7777d111e591 |  | textbox | First Aider on site today enter name
text | f8ee8e15-02fc-5733-ba7b-c8a3224af0df |  | textbox | Injury on site today enter name
checkpoint-no-status | c347debe-d6a7-4f2b-a946-003538dc06e2 |  | checkpoint | Work area 1 details entered
text | 87d3cc57-ae13-5626-843c-0617d54edead |  | textbox | Area
select | 5569c00c-73ec-5b22-98d9-a56447d57994 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 721680c2-f3c7-5b43-9845-15f2b66639d6 |  | textbox | Comments
checkpoint-no-status | 5dbe77e0-0d2e-4c8b-9649-cc6b36b3a696 |  | checkpoint | Work area 2 details entered
text | c1eaf4c8-2ee6-5c3b-94d0-0ac002a11c92 |  | textbox | Area
select | 8493762b-32f5-5347-91ec-9886fd9d2892 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 003aa407-3dd7-58fe-8604-6e58b4e91390 |  | textbox | Comments
checkpoint-no-status | bb654501-e330-4a57-bdc8-4ffa03582a81 |  | checkpoint | Work area 3 details entered
text | 495f245f-f118-52a8-8b01-ea0309007f77 |  | textbox | Area
select | 995a2840-96aa-5e20-9f1f-8e0cda43881e |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | c6ac3c5c-57e8-5e21-a7c3-b1ae5c275612 |  | textbox | Comments
checkpoint-no-status | 595c6743-4439-4462-b592-a96b9e2dffd8 |  | checkpoint | Work area 4 details entered
text | 6cb04c43-c176-535e-93da-a249740acf21 |  | textbox | Area
select | d90cf8dd-e41d-50b8-b427-150780df6dd7 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 0f9b3671-2f2d-587c-80d1-8121c083ad2f |  | textbox | Comments
checkpoint-no-status | 2476bece-efc9-47af-a98b-bbcb31c7445c |  | checkpoint | Work area 5 details entered
text | 3e8cd345-c128-5ed1-bea5-e90883f6239e |  | textbox | Area
select | ef6a1891-c047-5dcb-844a-ac846d17608a |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 394b159b-775d-5446-b867-4f4f605ea3c1 |  | textbox | Comments
checkpoint-no-status | da389799-5faa-47f4-895b-fdecf66961ac |  | checkpoint | Work area 6 details entered
text | b2452870-1df2-5795-89d9-bc042c2dd01b |  | textbox | Area
select | 82b68d27-5029-5532-9f9c-eb9ee0fa8c93 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | fb6f6b78-d2c2-5ad3-8da4-65d31335fe9e |  | textbox | Comments
checkpoint-no-status | 01e626fa-e1ca-447f-a243-21d60563e8ae |  | checkpoint | Work area 7 details entered
text | 02076334-3847-5521-993a-ebde125c1cf8 |  | textbox | Area
select | b7339567-6bc8-578c-80a9-a1b458862188 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 6e0b6292-13ba-5c60-b617-8b02124a9be4 |  | textbox | Other
checkpoint-no-status | eda0b4b5-23eb-4889-8ea8-9db0870db8df |  | checkpoint | Work area 8 details entered
text | 27029970-45de-5a81-aca6-55904e55a6b0 |  | textbox | Area
select | 05f22d0b-8e16-565d-93e9-654977ba3165 |  | dropdown | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | 70e7b35d-fb13-5c6c-9b1e-d6c196e85585 |  | textbox | Comments
checkpoint-no-status | 70d9ce38-e1ca-4259-9a4b-5cf14d886627 |  | checkpoint | Weather conditions entered
select | c5b84bba-1001-54f9-b275-57c2368486f3 |  | dropdown | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | 606b34e8-1f96-5ed6-bd18-75dd79faddfd |  | textbox | Min temp predicted
text | 5824b0d7-0051-5a56-ab95-7c8fb21aa1b5 |  | textbox | Max temp predicted
checkpoint-no-status | e711291c-7ddb-4ac7-875f-5330712a1971 |  | checkpoint | Delays from inclemency
text | 0bd72ff6-c4b0-5b32-a8e5-30e886b7ff6b |  | textbox | Total Hours of delay
select | b9ccba52-b2cd-5a77-ad24-8b72716a5092 |  | dropdown | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | c3354957-7e86-45cb-bc20-118a83a57552 |  | checkpoint | Delays from Builders or Others
text | 513eca07-7e8a-5711-83c8-9ac139f0cb44 |  | textbox | Total Hours of delay
select | e47fe080-5031-5506-a333-c5ebce8b3669 |  | dropdown | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist-sectioned | bef43297-4216-4ac5-bf1a-880bf0185eae |  | checklist | Stairs (in-situ) Checklist |  |  |  |  | Yes | Stairs (in-situ) Checklist | 321d7f24-89bb-4c08-8f77-226774c1298e
checkpoint-group | 34e0dde4-afbb-4157-92d1-f213eecdfd1f |  | section | Phase 1
checkpoint-status | 08952a79-a2bd-4fe8-980a-6b91388102c7 |  | checkpoint | Area accessible & ready
checkpoint-status | edd599f4-0465-4e91-af33-467638d42942 |  | checkpoint | Drawing references entered
text | 6a52d902-9d8a-5f8c-aea5-c85e794ae317 |  | textbox | Architectural
text | be5a862f-f4f7-57dd-8ced-9ae404f43e25 |  | textbox | Structural
text | 5f380b5f-1b4a-5e04-acf5-595bada21445 |  | textbox | Other
checkpoint-status | 1a64b273-9880-4af3-96b3-b138fb7a37eb |  | checkpoint | Current plans in use
checkpoint-status | 204cd235-ba93-444b-852c-04360176c62b |  | checkpoint | Land stringers & backdrops secured
checkpoint-status | 1a8e52d5-59e4-4b4d-a245-8aa191b81fc0 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | 1288110c-557f-46bd-b999-ce16459874e6 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | f0c19f09-c528-468e-a7a3-8dc7b329d541 |  | checkpoint | Base of stairs cleaned
checkpoint-status | 1d727059-0dac-4317-867a-a213169400d1 |  | checkpoint | Riser heights confirmed
checkpoint-status | 11be79a8-f97d-4fc3-95e0-20f503a9c02a |  | checkpoint | Going lengths confirmed
checkpoint-status | fbb5e496-e747-4b41-acee-165ad178858a |  | checkpoint | Correct Class of Finish
checkpoint-group | f1cd325e-7445-4bf1-81e5-427ed03036e1 |  | section | Phase 2
checkpoint-status | 6837c0af-1c82-4449-9b28-28ee54954fd6 |  | checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint-status | e28c04e6-c50c-4aaa-aa3b-622494ca4525 |  | checkpoint | Couplers & rebate boards installed
checkpoint-status | 631c37a5-53b4-4458-92a7-0590f65db5c9 |  | checkpoint | Base of stairs cleaned
checkpoint-status | f91a1fb3-4346-4df7-af51-c14498bac7e3 |  | checkpoint | Riser heights confirmed
checkpoint-status | 86a4cd21-9177-444a-af79-812e734bfa56 |  | checkpoint | Going lengths confirmed
checkpoint-status | fb3c72a2-02b1-4822-a69d-25b0efc194b6 |  | checkpoint | Correct Class of Finish
checklist-flat | 7145ac8c-74d4-4838-b7ec-9842b6359b97 |  | checklist | Suspended Slab Checklist |  |  |  |  | Yes | Suspended Slab Checklist | 7e07bd0c-6231-45e2-8521-618919f138fb
checkpoint-status | 821ceb50-05cd-4772-85cc-01e8d30266b2 |  | checkpoint | Area accessible & ready
checkpoint-status | 3cf52ff2-ffa0-4709-b170-865c4c8a5af4 |  | checkpoint | Drawing references entered
checkpoint-status | bba3117a-f244-44b8-9f38-55ff732bb5fb |  | checkpoint | Materials used complies with design documentation
checkpoint-status | 61c3cf0c-0692-4884-8acc-8f00f7423962 |  | checkpoint | Datum point used & soffit RLs checked
checkpoint-status | e73724a5-c480-43c1-8187-9415acd472a3 |  | checkpoint | Grids marked by builder
checkpoint-status | 4f2aa7a6-d650-4648-95d1-a9460fd43b67 |  | checkpoint | Surveyor points given for outside of building
checkpoint-status | 717c4229-8db4-4cc1-ab0b-cd07dddc3211 |  | checkpoint | Fillet & drip mould installed
checkpoint-status | 08674862-1e3d-4ebc-bd00-1ea595f29ed7 |  | checkpoint | Check set down position & RL
checkpoint-status | a00c41ca-7525-40cd-8aff-2f74c5cd3436 |  | checkpoint | Check penetrations installed
checkpoint-status | cb7eaf46-6fd3-4cfd-b824-2360497f8103 |  | checkpoint | Prop drop head wedges are secure
checkpoint-status | c534ad9c-841f-4032-9a6b-d237bd279ced |  | checkpoint | Column blockouts installed
holdpoint | 88e51d0e-6ea9-423f-8808-b68718fa5d23 |  | signoff | Inspection by site engineer
checkpoint-status | a3cc13e6-69fc-4c79-99f1-4bcc3f226af7 |  | checkpoint | check back propping as per design
checkpoint-status | 53894715-bf21-4f90-888b-533f5b257256 |  | checkpoint | Blow off deck
holdpoint | 9fe85ed6-e2cf-4388-88b1-0e36c2901f15 |  | signoff | Do not commence concrete till all works agreed
checkpoint-status | cb8dcdd7-c07d-4fbd-acf8-37d076a204cb |  | checkpoint | Engage external consultant (engineer inspection)
checkpoint-status | f3a1602b-3127-4fe0-828b-626b27c36753 |  | checkpoint | Correct Class of Finish
checkpoint-status | 44bd12e8-fead-4cff-a52a-4da04d0b3ff7 |  | checkpoint | Stripping, cleaning & materials removed