## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITR-I-07A Entec - Transmitters / Gauges Pre-Installation | [5 empty] | ITR-I-07A Entec - Transmitters / Gauges Pre-Installation
section | Inspection
checkpoint | Tag No. correct
checkpoint | Hazardous Area Certificate
checkpoint | Area Classification correct
checkpoint | General condition satisfactory
checkpoint | Pneumatic/Elec. Connections
checkpoint | Operating range
checkpoint | Calibrated range
checkpoint | Indicator range correct
checkpoint | Shipping stops removed
checkpoint | Body material correct
checkpoint | Process connections correct
checkpoint | Supply Settings correct
textbox | Elec:
textbox | Pnue:
checkpoint | Output signal
section | Function Check
checkpoint | Input
textbox | 0%
textbox | 25%
textbox | 50%
textbox | 75%
textbox | 100%
textbox | 75%
textbox | 50%
textbox | 25%
textbox | 0%
checkpoint | Output
textbox | 0%
textbox | 25%
textbox | 50%
textbox | 75%
textbox | 100%
textbox | 75%
textbox | 50%
textbox | 25%
textbox | 0%
checkpoint | Error
textbox | 0%
textbox | 25%
textbox | 50%
textbox | 75%
textbox | 100%
textbox | 75%
textbox | 50%
textbox | 25%
textbox | 0%
checkpoint | Test Equipment
textbox | Test equipment:
textbox | Model
textbox | Serial No.
textbox | Calibration Expiry Date
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist | ITR-I-09A Entec - Temperature Elements Pre-Installation | [5 empty] | ITR-I-09A Entec - Temperature Elements Pre-Installation
section | Inspection
checkpoint | Tag No. correct
checkpoint | Hazardous Area Certificate
checkpoint | Area Classification correct
checkpoint | General condition satisfactory
checkpoint | Pneumatic/Elec. Connections
checkpoint | Operating range
checkpoint | Calibrated range
checkpoint | Body material correct
checkpoint | Process connections correct
checkpoint | Supply settings
button | Type of Element | RTD,T/C
checkpoint | Element
checkpoint | Output Signal
checkpoint | Indicator range
section | Thermowell Inspection (if applicable)
checkpoint | TE / TW Supplied correct
checkpoint | Material Correct
checkpoint | According to data sheet
section | Cal Check
checkpoint | Cal Check:
textbox | Input
textbox | Output
textbox | Output C / F
textbox | ERROR
checkpoint | Make (Test equipment)
textbox | Model
textbox | Serial No
textbox | Calibration Expiry Date
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist | ITR-I-10A Entec - Flow Meters Pre-Installation | [5 empty] | ITR-I-10A Entec - Flow Meters Pre-Installation
section | Inspection
checkpoint | Tag No. correct
checkpoint | Hazardous Area Certificate
checkpoint | Area Classification correct
checkpoint | General condition satisfactory
checkpoint | Pneumatic/Elec. Connections
checkpoint | Operating range
checkpoint | Calibrated range
checkpoint | Indicator range correct
checkpoint | Shipping stops removed
checkpoint | Body material correct
checkpoint | Process connections correct
checkpoint | Supply Settings correct
textbox | Elec:
textbox | Pnue:
checkpoint | Output signal
section | Functional Check (where possible)
checkpoint | Input
textbox | 0%
textbox | 25%
textbox | 50%
textbox | 75%
textbox | 100%
checkpoint | Output/Reading
textbox | 0%
textbox | 25%
textbox | 50%
textbox | 75%
textbox | 100%
checkpoint | Error
textbox | 0%
textbox | 25%
textbox | 50%
textbox | 75%
textbox | 100%
checkpoint | Test Equipment
textbox | Test equipment:
textbox | Model
textbox | Serial No.
textbox | Calibration Expiry Date
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist | ITR-I-13A Entec - Controller Pre-Installation | [5 empty] | ITR-I-13A Entec - Controller Pre-Installation
section | Inspection
checkpoint | Tag No. correct
checkpoint | Hazardous Area Certificate
checkpoint | Area Classification correct
checkpoint | General condition
checkpoint | Pneumatic/Elec. Connections
checkpoint | Operating range
checkpoint | Indicator range correct
checkpoint | Shipping stops removed
checkpoint | Body material correct
checkpoint | Process connections correct
checkpoint | Supply Settings correct
textbox | Elec:
textbox | Pnue:
checkpoint | Output signal
section | 1. Required Data
checkpoint | Required Data
textbox | Function
textbox | Type / Model
textbox | Service
textbox | Manufacturer
textbox | Test equipment used
textbox | Test fluid
textbox | Test pressure
textbox | Range
textbox | Serial No.
textbox | Manufacturer accuracy (±) |  |  | %
textbox | Process connection
textbox | Line / Equipment No.
textbox | Test Voltage
textbox | Ambient Temp. |  |  | °C
section | 2. Function check Results
checkpoint | Actual Input
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Output I
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Output II
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Error
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Set point
textbox | Set point:
textbox | Rising:
textbox | Falling:
checkpoint | Reset point
textbox | Reset point:
textbox | Rising:
textbox | Falling:
section | 3. Hart / Foundation Fieldbus Address
checkpoint | Make (Test equipment)
textbox | Test equipment:
textbox | Model
textbox | Serial No.
textbox | Calibration Expiry Date
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist-flat | ITR-I-14A Entec - Instrument Calibration | [5 empty] | ITR-I-14A Entec - Instrument Calibration
checkpoint | 1. Required Data
textbox | Type and size
textbox | Make
textbox | Serial no.
textbox | PID & Drawing no.
textbox | Instrument Designation / Equipment no.
textbox | Calibration Interval
textbox | Calibration Method
textbox | Acceptance Criteria
textbox | Instrument type:
textbox | a. Field Transmitter:
textbox | b. Field Actuator:
textbox | c. Panel Instrument:
textbox | Calibrated at:
textbox | Installed Location:
textbox | Workshop:
checkpoint | 2. Instrument Power Supply (State measured values)
textbox | VAC
textbox | 2 Wire DC
textbox | Other
textbox | None
checkpoint | 3. Calibration
textbox | Input Simulated by:
textbox | Output Measured by:
label | Input
textbox | 0% |  | Input
textbox | 25% |  | Input
textbox | 50% |  | Input
textbox | 75% |  | Input
textbox | 100% |  | Input
textbox | Units / Remarks |  | Input
label | Output
textbox | 0% |  | Output
textbox | 25% |  | Output
textbox | 50% |  | Output
textbox | 75% |  | Output
textbox | 100% |  | Output
textbox | Units / Remarks |  | Output
checkpoint | Identifiable Calibration Settings
textbox | Zero
textbox | Span
textbox | Other (Specify)
textbox | Remarks
checkpoint | Reconnection Details
label | Earth at Instrument
textbox | Instrument |  | Earth at Instrument
textbox | Input cable screen |  | Earth at Instrument
textbox | Output cable screen |  | Earth at Instrument
label | Not Earth at Instrument
textbox | Instrument |  | Not Earth at Instrument
textbox | Input cable screen |  | Not Earth at Instrument
textbox | Output cable screen |  | Not Earth at Instrument
label | Not Applicable
textbox | Instrument |  | Not Applicable
textbox | Input cable screen |  | Not Applicable
textbox | Output cable screen |  | Not Applicable
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist-flat | ITR-I-15B Entec - Instrument Loop Checks | [5 empty] | ITR-I-15B Entec - Instrument Loop Checks
checkpoint | Transmitting Instrument 1
textbox | Tag No.
textbox | Area Classification correct
textbox | Type
textbox | Installation and location correct
textbox | Signal type / data:
textbox | Transmitter j
textbox | Switch, PLC alarms
textbox | Local indicator, RTU, LL, HH
textbox | Other specify, LH, Telemetry
checkpoint | Transmitting Instrument 2
textbox | Tag No.
textbox | Area Classification
textbox | Type
textbox | Installation and location correct
textbox | Signal type / data:
textbox | Transmitter j
textbox | Switch, PLC alarms
textbox | Local indicator, RTU, LL, HH
textbox | Other specify, LH, Telemetry
checkpoint | Receiving Instrument
textbox | Tag no.
textbox | Area Classification
textbox | Type
textbox | Installation and location correct
textbox | Signal type / data:
textbox | DCS
textbox | Panel no.
textbox | Terminal block no.
textbox | I/O
textbox | Rack no.
checkpoint | End Device
textbox | Tag no.
textbox | Area Classification
textbox | Type
textbox | Installation and location correct
textbox | Control action type:
textbox | Direct reverse control valve
textbox | Other, specify
textbox | Signal type / data:
checkpoint-no-status | Checks
label | 1. Conduct continuity checks on all cables as per P&ID, and loop diagrams of a particular instrument loop.
label | 2. Check electrical power supply to a specific instrument to confirm correct voltage (ac/dc)
label | 3. Confirm earthing, shielding as per specifications and drawings
label | 4. Programmable instrument, and values shall be recorded on test sheets as well electronic form.
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist-flat | ITR-I-17A Entec - Field Mounted Instruments Installation | [5 empty] | ITR-I-17A Entec - Field Mounted Instruments Installation
checkpoint | 1. Equipment has been received from the store in good condition and is the Correct type as per the site drawings, specifications & data sheets.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 2. Check fixings/supports /clearances from other services, structures and de-mountable equipment are satisfactory
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 3. Check Instrument air / Impulse Tubing to spec is correct.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 3.1 Instrument Air ¦ Process Tubing
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 3.2 Air set installation correct
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 3.3 3 way manifold installed, positioned correctly
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 4. Check connection to correct process point/ instrument.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 5. Instrument position orientation correct, properly supported. i.e. Stainless, steel, rubber lined
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 6. Instrument Installed undamaged, properly secured.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 7. Instrument / cables correctly tagged, location as per drawings
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 8. Accessible from safe position, installed in correct height.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 9. Flow direction correct, level probe length correct
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 10. Earthing arrangement and connections correct
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 11. Mechanical cable installation / termination method correct - i.e. special instrument cable, armoured and un-armoured cable.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 12. All air regulation equipment installed.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 13. Moisture traps installed (if applicable)
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 14. Measuring element cable length within the maximum permissible length stated in the vendor data
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 15. Flange mounted / in line instrument correctly installed - i.e. gaskets, total no. of bolts, threaded elements fully screwed on.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 16. Maintenance access satisfactory
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 17. Conforms to Specification and Drawings & As-Built Complete
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 18. Nuclear sources locked with shutter on close position / padlocked keys available
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 19. Danger signs installed
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 20. Confirm Area classification Ex, IP for materials, and devices
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 21. Signal isolator, junction boxes, trip wires adequate and installed
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 22. Devices and instruments protected by weather hoods
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 23. Devices and Instruments should be cleared off sources of heat and excessive vibrations (if not design for)
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 24. Installation drawings, locations drawings, cable schedules marked up "as built"
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist | ITR-I-22A Entec - Instrument Transmitter Calibration | [5 empty] | ITR-I-22A Entec - Instrument Transmitter Calibration
section | 1. Required Data
checkpoint | Required Data
textbox | Function
textbox | Type / Model
textbox | Service
textbox | Manufacturer
textbox | Test equipment used
textbox | Test fluid
textbox | Test pressure
textbox | Range
textbox | Serial No.
textbox | Manufacturer accuracy (±) |  |  | %
textbox | Process connection
textbox | Line / Equipment No.
textbox | Test Voltage
textbox | Ambient Temp. |  |  | °C
section | 2. Calibration Results
checkpoint | Actual Input
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Output I
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Output II
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Error
textbox | Input: 0% |  | Rising
textbox | Input: 25% |  | Rising
textbox | Input: 50% |  | Rising
textbox | Input: 75% |  | Rising
textbox | Input: 100% |  | Rising
textbox | Input: 0% |  | Falling
textbox | Input: 25% |  | Falling
textbox | Input: 50% |  | Falling
textbox | Input: 75% |  | Falling
textbox | Input: 100% |  | Falling
checkpoint | Set point
textbox | Set point:
textbox | Rising:
textbox | Falling:
checkpoint | Reset point
textbox | Reset point:
textbox | Rising:
textbox | Falling:
section | 3. Input / Foundation Fieldbus Address
checkpoint | Input / Foundation Fieldbus Address
textbox | Address
textbox | Test equipment
textbox | Make
textbox | Model
textbox | Serial No
textbox | Calibration Expiry Date
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist-flat | ITR-I-25A Entec - Instrument Installation | [5 empty] | ITR-I-25A Entec - Instrument Installation
checkpoint | 1. Check Instrument Nameplate details are correct in accordance with the instrument index.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 2. Ingress protection is suitable for area. Instrument is suitably rated for area.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 3. Instrument correctly mounted, orientation correct, elevation correct and free from vibration.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 4. Instrument is accessible for maintenance and clear of obstruction and debris.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 5. Vent lines are directed into a safe area.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 6. Cable/s glanded and installed correctly
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 7. Impulse, hydraulic, pneumatics, lines, air headers, correctly installed and supported.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 8. In-line equipment installed and supported correctly.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 9. Spare entries plugged correctly, using certified plug.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 10. Instrument earthed in accordance with project specification.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 11. Aspirator tubes and test gas tubes are installed and supported correctly.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 13. EOL resistor fitted and correctly rated where applicable.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 14. Check all tag No’s.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint | 15. Spot check tubing has been reamed at connection points.
textbox | Results
textbox | Punch List Item No.
textbox | Remarks
checkpoint-no-status | Remarks
textbox | Remarks:
button | Outstanding Punch List attached? | Yes,No
checkpoint-no-status | Description
label | TEST/INSPECTION CARRIED OUT BY
textbox | Print Name
textbox | Date
label | TEST/INSPECTION APPROVED BY
textbox | Print Name
textbox | Date
label | CLIENT REPRESENTATIVE
textbox | Print Name
textbox | Date
checklist | ITR-I-051 Entec - Stainless Steel Tube and Fittings | [5 empty] | ITR-I-051 Entec - Stainless Steel Tube and Fittings
section | A. CHECKS PRE INSTALLATION
checkpoint | 01. Tubing connection drawings and details available
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 02. Client site specific changes noted, agreed and sketched
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 03. Tube material type, size, gauge and standard confirmed and available
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 04. Tube fitting size and type confirmed and available
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
section | B. CHECKS DURING AND POST INSTALLATION
checkpoint | 01. Correct thread compatibility and engagement
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 02. Correct thread tape and sealant used on fittings
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 03. Check fitting ferrule orientation and confirm prior to connection
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 04. Tube installation is in compliance with the client specification (Supports, Bracketry, Slope, Expansion, Vibration, Access, Cables)
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 05. Tube bent correctly, sufficient straight section into fitting
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 06. Tube cut clean and straight, de-burred, reamed, and blown through
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 07. Depth insertion tool used, witness mark visible at all stages of process
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 08. Tube fitting hex’s marked to ensure correct swage tightness
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 09. Random check with No Go gap gauge
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 10. In service leak test performed and passed
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | 11. Fitting completion tag completed and applied to each fitting
textbox | Tradesman |  | (Initials)
textbox | Supervisor |  | (Initials)
textbox | Client |  | (Initials)
checkpoint | Signoff
textbox | Tradesperson Name:
textbox | Date:
textbox | Supervisor Name:
textbox | Date:
textbox | Client Rep Name:
textbox | Date:
textbox | Comments:
holdpoint | Signature