## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | FHC-ITP-017 - Basin Construction | itp |  |  |  |  | FHC-ITP-017 - Basin Construction
section | 1 - Preliminary Works
checkpoint | 1.1 The current revision drawings/documents are being used including subcontractors copy.
note | FREQUENCY: Prior to commencing
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Current revision drawing/documents are being used including the subcontractors copy.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to placement
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.4 Excavation Permit
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
note | • Plant and equipment shall be appropriate for the task.
note | • Excavation operations shall not disturb areas outside the limit of excavation
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Excavation permit
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Survey set-out
note | FREQUENCY: Prior to commencing excavation
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Site Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Survey records & pegs on the ground
note | – – – – – – – – –
note | SCP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer/ Surveyor
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 In situ Material
note | FREQUENCY: Initial
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: In situ material ripped and re-compacted to provide a smooth, stable working surface. Material to be free of debris, roots, sticks and sharp rocks/ boulders larger than 50mm
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Bentofix GCL Installation
note | FREQUENCY: Prior to placement of Type A
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Geotextile clay liner (GCL) shall be installed in accordance with the manufacturer's requirements
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Type A Placement
note | FREQUENCY: Once GCL has been installed
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: A minimum 300mm thick Type A fill layer shall be placed over the Bentofix GCL that has been installed
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Base Construction
note | FREQUENCY: Once Type A fill layer has been installed
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Provide a compacted 400mm thick hard base. Approximately 50% 300mm size. The remaining 50% made up of 0-100mm graded rock, premixed with 300 dia rocks and spread and tracked so as to form a compated base.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Project Spec. Latest IFC Drawings
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Site Engineer / Site Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: