## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-STR-Grout Pedestals & Bearings
ITP Description: |  | Grout Pedestals & Bearings
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 0
Revision Date: |  | 2020-04-14
ITP created by: |  | Mike Freeman
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Camms Road Project
Inspection & Test Plan - Grout Pedestals & Bearings
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2020-04-14
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 610 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 610 March 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | VicRoads Section 610 June 2019 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries - Materials
2.1 | Product Selection | IFC Drawings 610.28 610.33 | Product to be selected based on the following criteria: i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar ii. have the required strength at 28 days as noted on the IFC drawings. iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings. Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | IP | Nominated Authority | This ITP
2.2 | Curing Compound | 610.23 (d) | Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority. Note: This may be the same product used for the concrete curing Enter: Teambinder Material Approval number [free text box] | Document Review | Once, for each product, prior to placement of product | IP | Nominated Authority | This ITP
3 | Preliminaries - Procedures & Documentation
3.1 | Curing Methodology (for Concrete, Grout and Mortar) | 610.23 (a) | Curing methodology/procedure to be submitted for review to the Nominated Authority. Note: This may be the same document used for the concrete curing. Enter: Teambinder Correspondence Approval number [free text box] | Document Review | Once, 4 weeks prior to placement of product | HP | Nominated Authority | ConQA Hold Point Release
4 | Pre-construction Activities
4.1 | IFC Drawings | MRPA Quality Management Plan | Check the revision of the IFC drawings are current as per the drawing register (on Teambinder) | Document Review | Prior to starting Works and at regular intervals | HP* | All | This ITP
4.2 | Survey Set-out | IFC Drawings 610.46 (a), Table 610.462 (Nov 2018) 610.47 (a) Table 610.472 (March/June 2019) | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element. Note: Different revisions of 610 have different clause numbers | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
4.3 | Construction Joint | IFC Drawings 610.20 | Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment. Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product. | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
5 | Construction Activities
5.1 | Formwork Construction & Placement | IFC Drawings | Dimensions in plan as per drawings (typically +50mm all around). Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks. Any cast in componentry (ferrules, conduit etc.) secure. | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
5.2 | Pre-pour Inspection | IFC Drawings 610.20 | Formwork location and RLs comply. Any reinforcement has the required cover. Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product. | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
5.3 | Weather Conditions | 610.17 610.17 (a) & (e) Table 610.171 | All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented. The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Record: Required information on the Grout Pour Record. | Measure Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.4 | Mixing Product | Product TDS 610.28 | Size of mixer should match the application. Only whole bags to be mixed with potable water. Volume of water matches the required amount for flowable consistency and accurately measured. Product poured into the mixer slowly. Mixing time as per TDS so that a smooth, even consistency is obtained. Enter: Required information on the Grout Pour Record. | Measure Visual | Each batch | IP | SE/PE/SPE | This ITP
5 | Construction Activities (Continued)
5.5 | Product Testing - Compressive Strength Cubes | 610.28 610.33 | Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products. Testing is be in accordance with the following frequencies: First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength) Enter: Required information on the Grout Pour Record. | Test | Each element | IP | Tester SE/PE/SPE | This ITP
5.6 | Placement & Compaction | Product TDS | All batches are traceable. Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water. Product should flow to all areas and self consolidate. Product that stiffens or is showing signs of stiffening shall not be used. Enter: Required information on the Grout Pour Record | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.7 | Surface Finishes | 610.28 | Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
5.8 | Curing | Curing Methodology 610.23 Table 610.231 | Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231. Curing methodology to be in accordance with the approved procedure and manufacturer's TDS. | Visual | Each element | IP | Foreman SE/PE/SPE | This ITP
6 | Post-construction Activities
6.1 | Compressive Strength Test Results | IFC Drawings Product TDS | 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly. 28 day compressive strength per sample comply with the design strength. Attach: Compressive Strength Test Results | Document Review | Each cube | IP | SE/PE/SPE | This ITP
6.2 | As-built Survey | IFC Drawings 610.46 (a), Table 610.462 (Nov 2018) 610.47 (a) Table 610.472 (March/June 2019) | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below: Reduced level ±2.5mm Variation from grade across the width of individual pedestals shall not exceed 1 in 200 Deviation from flat surface ±1mm Note: Different revisions of 610 have different clause numbers Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor PE/SE/SPE | This ITP
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | PE/SE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /