## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-033-STR-Grout Pedestals & Bearings | itp |  |  |  |  | ITP-033-STR-Grout Pedestals & Bearings Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-STR-Grout Pedestals & Bearings
note | ITP Description: Grout Pedestals & Bearings
note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
note | Discipline (e.g. CIV/STR/RAIL): STR
note | Revision Number: 0
note | Revision Date: 14/04/2020
note | ITP created by: Mike Freeman
note | ITP approved for use by: Victor Mira
note | 1.1 Non Dependent
note | Reference: VicRoads Section 610 November 2018
note | 1.2 Non Dependent
note | Reference: VicRoads Section 610 March 2019
note | 1.3 Non Dependent
note | Reference: VicRoads Section 610 June 2019
section | Preliminaries - Materials
checkpoint | 2.1 Product Selection
note | REFERENCE: IFC Drawings 610.28 610.33
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
label | ii. have the required strength at 28 days as noted on the IFC drawings.
label | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
label | Note: Pedestals 200mm or greater shall be constructed from concrete - use ITP-STR-Structural Concrete instead
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product, prior to placement of product
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 2.2 Curing Compound
note | REFERENCE: 610.23 (d)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
note | Note: This may be the same product used for the concrete curing
textbox | Enter: Teambinder Material Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, for each product, prior to placement of product
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 3.1 Curing Methodology (for Concrete, Grout and Mortar)
note | REFERENCE: 610.23 (a)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Curing methodology/procedure to be submitted for review to the Nominated Authority.
note | Note: This may be the same document used for the concrete curing.
textbox | Enter: Teambinder Correspondence Approval number
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, 4 weeks prior to placement of product
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Nominated Authority
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: ConQA Hold Point Release
textbox | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 4.1 IFC Drawings
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Prior to starting Works and at regular intervals
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: All
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.2 Survey Set-out
note | REFERENCE: IFC Drawings
label | 610.46 (a), Table 610.462 (Nov 2018)
label | 610.47 (a) Table 610.472 (March/June 2019)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
note | Note: Different revisions of 610 have different clause numbers
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 4.3 Construction Joint
note | REFERENCE: IFC Drawings 610.20
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Existing construction joint rebate is roughened / scabbled and set to 20mm minimum below top of the crosshead / abutment.
note | • Concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction Activities
checkpoint | 5.1 Formwork Construction & Placement
note | REFERENCE: IFC Drawings
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Dimensions in plan as per drawings (typically +50mm all around).
note | • Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
note | • Any cast in componentry (ferrules, conduit etc.) secure.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Pre-pour Inspection
note | REFERENCE: IFC Drawings 610.20
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Formwork location and RLs comply.
note | • Any reinforcement has the required cover.
note | • Area is clean, concrete substrate surface saturated with water for 3 hours minimum prior to pouring product.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.3 Weather Conditions
note | REFERENCE: 610.17, 610.17 (a) & (e), Table 610.171
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
note | • The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
note | Record: Required information on the Grout Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.4 Mixing Product
note | REFERENCE: Product TDS 610.28
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Size of mixer should match the application.
note | • Only whole bags to be mixed with potable water.
note | • Volume of water matches the required amount for flowable consistency and accurately measured.
note | • Product poured into the mixer slowly.
note | • Mixing time as per TDS so that a smooth, even consistency is obtained.
textbox | Enter: Required information on the Grout Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Measure, Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each batch
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Construction Activities (Continued)
checkpoint | 5.5 Product Testing - Compressive Strength Cubes
note | REFERENCE: 610.28, 610.33
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
note | • Testing is be in accordance with the following frequencies:
note | • First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
note | • Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
textbox | Enter: Required information on the Grout Pour Record.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Test
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Tester, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.6 Placement & Compaction
note | REFERENCE: Product TDS
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: All batches are traceable.
note | • Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
note | • Product should flow to all areas and self consolidate.
note | • Product that stiffens or is showing signs of stiffening shall not be used.
textbox | Enter: Required information on the Grout Pour Record
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.7 Surface Finishes
note | REFERENCE: 610.28
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Surface finish shall be flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.8 Curing
note | REFERENCE: Curing Methodology 610.23 Table 610.231
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
note | • Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Visual
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Foreman, SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
section | Post-construction Activities
checkpoint | 6.1 Compressive Strength Test Results
note | REFERENCE: IFC Drawings, Product TDS
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
note | • 28 day compressive strength per sample comply with the design strength.
note | Attach: Compressive Strength Test Results
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each cube
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: SE/PE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.2 As-built Survey
note | REFERENCE: IFC Drawings
note | 610.46 (a), Table 610.462 (Nov 2018)
note | 610.47 (a) Table 610.472 (March/June 2019)
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
note | • Reduced level ±2.5mm
note | • Variation from grade across the width of individual pedestals shall not exceed 1 in 200
note | • Deviation from flat surface ±1mm
note | Note: Different revisions of 610 have different clause numbers
note | Attach: Survey As-builts / Survey Report
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Each element
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: IP
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: Surveyor, PE/SE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 6.3 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | – – – – – – – – – – – – – – – – –
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
note | – – – – – – – – – – – – – – – – –
note | METHOD: Document Review
note | – – – – – – – – – – – – – – – – –
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | – – – – – – – – – – – – – – – – –
note | CATEGORY: HP*
note | – – – – – – – – – – – – – – – – –
note | RESPONSIBILITY: PE/SE/SPE
note | – – – – – – – – – – – – – – – – –
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP