## ITP
|  |  | Inspection and Test Plan - Coloured Surface Treatments | [7 empty] | Document # 1145-C200-FUL-QAC-ITP-0087
[11 empty] | Revision : 00 | Date : 23/09/2024
Client: | MRPV |  | Construction Process: | Coloured surface treatments |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Craigieburn Road Upgrade |  |  |  |  | Name: | Shaman Costa | Name: | Omar El-Khub |  | Name: | Dirk Slabbert
Contract No: | CONS-1145 |  | Specifications: | Project Specification Sections 1160, and 3070.7 VicRoads Specification Section 175, 721, 431, RDN 03-07 |  | Position: | Site Engineer | Position: | Project Engineer |  | Position: | Completions & Quality Manager
|  |  | Structure / Component: | Coloured surface treatments |  | Date : | 2024-05-01 | Date : | 2024-09-22 |  | Date :
Lot No: | ITP-087-AX-LOT-XXX |  | Lot Title: | ITP-087-AX-LOT-XXX - Desc | Location: From ( ) to ( ) |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check that current revision drawings are being used |  | Prior to commencing works | Issued For Construction (IFC) drawings, & latest available revision used. | IFC Project Drawings, PS3070.07 | Document review | ITP signed Latest revision IFC drawings | IP | Site Engineer / Site Foreman | N/A
2 | Preliminaries - Materials
2.1 | Material approval - Binder |  | Prior to commencing site preparation | The following primer and binder details shall be provided to the Superintendent at least 14 days prior to the start of works: (i) priming materials type and source (ii) binder type and source (iii) manufacturer's recommendations/instructions for priming material supply and placement (iv) manufacturer's recommendations/instructions for binder mix quantities and tolerances on mixing components (v) manufacturer's recommendations/instructions for mixing of binder and components (vi) manufacturer's recommendations/instructions for pot life of binder, i.e. time of mixing to time of spreading (vii) manufacturer's recommendations/instructions for placement of binder including application rates and tolerances and placement temperatures (viii) manufacturer's recommendations/instructions for curing (ix) manufacturer's recommendations/instructions for accelerants (if applicable) (x) manufacturer's recommendations/instructions for supply and placement of protective sealers (xi) type of coloured pigment. | IFC Project Drawings, PS3070.07 VR431.03 | Document review | ITP signed Latest revision IFC drawings | WP | Site Engineer/ Superintendent
2.2 | Material approval - Aggregate |  | Prior to commencing site preparation | The aggregate shall be clean, free from dirt, clay and organic matter, of uniform shape and quality, resistant to fuel and oils spills from traffic, able to withstand traffic stresses without damage, and able to be swept using a mechanical broom and cleaned with high pressure water equipment without damage. The aggregate may be pigmented to provide a colour match of the final product. The following aggregate details shall be provided to the Superintendent at least 14 days prior to the start of works: (i) aggregate type, source and gradation (ii) manufacturer's or Contractor’s recommendations/instructions for placement of aggregate including spread rate (iii) Polished Stone Value (PSV) – aggregates shall have a minimum PSV of 54 | IFC Project Drawings, PS3070.07 VR431.03 | Document review | ITP signed Latest revision IFC drawings | WP | Site Engineer/ Superintendent
2.3 | Material - Material safety data sheets |  | Prior to commencing site preparation | Copies of Material Safety Data Sheets (MSDS) for priming materials, binders, aggregate coatings, protective sealers and any other work materials shall be provided to the Superintendent prior to the start of works. Any requirements for environmental protection measures as recommended by the material manufacturer shall be undertaken. All materials shall be used and stored in accordance with the manufacturer’s instructions, and MSDSs. | IFC Project Drawings, PS3070.07 VR431.06 | Document review | ITP signed Latest revision IFC drawings | WP | Site Engineer/ Superintendent
3 | Coloured Surface Treatment - Application
3.1 | Site preparation |  | Per lot | All loose material, grit, stones, vegetative matter, and rubbish shall be removed from the area of works prior to placement of the coloured surface treatment. The site may be further cleaned and prepared as required. Cleaning and preparation shall not cause structural damage to the pavement. All cleaning agents and collected material shall be removed from site and disposed in accordance with Environment Protection Authority (EPA) Victoria requirements for the type of waste generated. Existing pavement markings shall be masked to ensure the coloured surface treatment is not applied to the markings. All Raised Reflective Pavement Markers (RRPMs) shall be removed from the area of works prior to any coloured surface treatment being placed. New RRPMs shall be reinstated after the application of the coloured surface treatment. | IFC Project Drawings, PS3070.07 VR431.07 | Document review & Site inspection | ITP signed | IP | Site Engineer/Foreman | N/A
3.2 | Site preparation - Service pits, valve covers |  | Per lot | Service pits and valve covers less than 0.03 m2, and drainage grates and frames shall also be masked. Larger pit and valve covers shall be covered with the coloured surface treatment. All lifting mechanisms and joins between the lid and frame shall be masked and protected such that the coloured surface treatment does not impede lifting and replacing lids. | IFC Project Drawings, PS3070.07 VR431.07 | Document review & Site inspection | ITP signed | IP | Site Engineer/Foreman | N/A
3.3 | Site preparation |  | Per lot | The Superintendent shall agree to the method of removal and any pavement repairs for pavement markings and raised refelctive markers (RRPMs) prior to these works occurring. | IFC Project Drawings, PS3070.07 VR431.07 | Document review & Site inspection | ITP signed | HP | Superintendent
3.4 | Placement - Coloured surface treatments |  | Per lot | Coloured surface treatments shall not be placed until the Superintendent agrees that the prepared road surface is ready for surfacing. | IFC Project Drawings, PS3070.07 VR431.08 | Document review & Site inspection | ITP signed | HP | Superintendent
3.5 | Placement - Coloured surface treatments |  | Per lot | Coloured surface treatments shall be applied to produce a visually uniform coloured and textured surface. The edges of the work shall provide a neat and clean line onto the adjacent surface. | IFC Project Drawings, PS3070.07 VR431.08 | Document review & Site inspection | ITP signed | IP | Site Engineer/Foreman | N/A
3.6 | Placement - Application rate |  | Per lot | All application rates for the work involving placement of priming materials, binder, aggregates and accelerants shall be provided to the Superintendent. | IFC Project Drawings, PS3070.07 VR431.08 | Document review & Site inspection | ITP signed | AP | Site Engineer/ Superintendent/FH's Sub-contractor
3.7 | Placement - Temperature |  | Per lot | The pavement temperature of the site shall be measured and recorded at least every 2 hours during the works. The temperature shall be measured using an infrared temperature gauge accurate to +/‑2˚C. The temperature results shall be provided to the Superintendent. All materials shall be placed within any temperature limits recommended by the manufacturer. | IFC Project Drawings, PS3070.07 VR431.08 | Document review & Site inspection | ITP signed | AP | Site Engineer/ Superintendent
3.8 | Clean up |  | Per lot | The Superintendent shall agree the site is neat, tidy and free of excess aggregate prior to opening to traffic. | IFC Project Drawings, PS3070.07 VR431.10 | Site inspection | ITP signed | HP | Superintendent
3.9 | Protection of works |  | Per lot | Work to be protected by appropriate means until it is trafficable. | VR721.A11 | Site inspection | ITP signed | IP | Site Engineer/Foreman | N/A
4 | Acceptance of works
4.1 | Acceptance of works - Surface texture & Testing |  | Per lot | Coloured surface treatments shall provide a visually uniform surface with uniform aggregate retention, and be free from delamination, stripping and areas of wear/scuffing. Any work that fails to meet the minimum requirements shall be rectified. Acceptance of work for surface texture shall be based on visual assessment, however in marginal cases the Superintendent may request that nominated areas be tested in accordance with the test method for assessment of surface texture testing as listed in Section 175. A lot will consist of a single batch or area of like work which has been constructed under uniform conditions and is essentially homogeneous with respect to material and appearance. A lot shall be the lesser of one day’s production or each 500 m2. The surface texture of each test site within the lot shall be a minimum of 0.6 mm. Discrete portions of a lot which are non-homogeneous with respect to material and appearance shall be excluded from the lot and either treated as separate lots, or replaced. Where the areas excluded from a lot as non-homogeneous exceed 20% of the total lot area, the whole of the lot shall be rejected. | VR431.11 | Site inspection | ITP signed Test report | IP | Site Engineer/Foreman | N/A
4.2 | Acceptance of colour |  | Per lot | SUP Pram Crossings to be installed as per RDN 03-07 with Golden Yellow (AS colour Y14). Bus Lanes to be installed as per AS 1742.12 Signal Red R13 Bicycle Lanes to be installed as per Table 4311.111 Emerald Green G13 | PS3070.07 VR RDN 03-07 VR431.11 | Document review & Site inspection | ITP signed | TP | Site Engineer | N/A
4.3 | Testing of Colour |  | Per lot | The colour of the finished surface shall be a Rating 3 Approximate Match (or better) with the approved colour as per item 4.2. The initial colour shall be measured in accordance with Australian Standard 1580.601.1:1995. Each lot of material shall be tested within 2 days of placement. Testing shall be undertaken onsite and under daylight conditions only. Each lot of coloured surface treatment shall provide a Rating 3 Approximate Match (or better) with adjacent lots. | VR431.11 | Document review & Site inspection | ITP signed | TP | Site Engineer | N/A
5 | Maintenance and repairs
5.1 | Repairs - Coloured surface treatment |  | Per lot | The Contractor shall be responsible for monitoring and maintenance of the coloured surface treatment from the time of placement, until the end of the defects liability period. The Contractor shall advise the Superintendent in writing of the proposed treatment for any repairs before undertaking the work. | VR431.12 | Site inspection | ITP signed | HP | Superintendent
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent