## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Defecting Checklist |  | Defect ID No: | 271f5cf6-09fe-4d3f-8641-76d7bafc939a
| section | Defect
| checkpoint | Defect Identification
8701a653-7e68-5322-ba34-8a5f05976416 | date | Identified on (date):
ad0e584e-2967-515c-bb00-a32501bc38da | textbox | Identified by:
2a79d577-24ae-5a78-8819-dc3b936e69e4 | textbox | Process:
41d2bc45-4ace-52e7-a408-de753f71d800 | textbox | Area:
7ef5a324-a4da-5bf2-988b-bce11d762973 | textbox | Location:
f803d49d-f1e2-59c1-ac35-c6fbb3dc0972 | textbox | Client Reference (if any):
ef28bbc8-add5-59ad-8e0f-420dac7424db | textbox | CAMS NO. (if applicable):
b6901938-66b6-53fa-aeaf-27ed24228be0 | textbox | Description
19517bc0-3d2a-50df-b1cc-61f59a027757 | tickbox | Photo Attached
| checkpoint | Defect Rectification
20db7d32-e57f-533e-891f-7e15943d5b49 | date | Completion Date:
| checkpoint | Defect rectification accepted and closed (signed off by FH & Client)
ebedc7aa-7f4b-5a8f-83e7-a75c26ee5b8f | date | Date Completed:
a8067a07-371a-564c-b8d1-c43fbd81b0c9 | textbox | Fulton Hogan Representative
f2af2fa7-dd05-5062-b6d4-3083dff06751 | textbox | Client Representative
4c47cb50-8bb9-5595-bdc0-1eb15f5e6501 | date | Date Signed off
| signoff | Request Approval
| checklist | ITP 0001 - Clearing & Grubbing | itp | ITP-001-AX-LOT-XXX - Desc | ca1dc026-f34c-4536-b6d3-7bba87ca97dc
| checkpoint | 1.1 Induction
c4f11de1-919e-5738-b7fb-4e069e1ba368 | note | FREQUENCY: Prior to Commencing Work
989d9817-4ff9-5791-b10f-2a862f4d2c44 | note | - - - - - - - - -
061f7494-bb92-5976-b354-f01fe478bcc8 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the CRG site
1800820d-f9bd-5805-9aee-589f9ec614e8 | note | - - - - - - - - -
c4d0fe11-f5d0-5361-a306-03ca9e265802 | note | REFERENCE DOCUMENTS: PMP, Inductions Register
f2e2104f-bf86-5ada-86a8-62f7c4d52ba4 | note | - - - - - - - - -
bf8fcd7e-0a8b-5d3f-9b7e-756c314006ca | note | INSPECTION/TEST METHOD: Document review
32e4a27f-7d80-55ef-88a4-ceb0cbec71d0 | note | - - - - - - - - -
c890c341-db19-565a-aac7-5f5b967251bb | note | RECORD OF CONFORMITY: Site induction signed
c360107d-1a4a-521c-8e5f-54056a7fbd66 | note | - - - - - - - - -
12570bba-1865-5002-b36c-e6b3c4fb90ff | note | AP
47b1f726-f242-5c9d-b2d7-9e2039495680 | note | - - - - - - - - -
e79daeae-313c-544b-a5df-b4d7adad0c66 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1f6dd113-58a4-52e6-927b-461c283e069a | note | - - - - - - - - -
90e7438f-5835-5aba-abd7-b8259691a644 | date | Date Completed:
| checkpoint | 1.2 Safety measures are in place, SWMS undertaken
47df3d5b-98fd-5e9a-bf26-08531d7cf43b | note | FREQUENCY: Prior to Commencing Work
685caeac-f3dc-5bcd-acdb-4dd7fc616c1e | note | - - - - - - - - -
1a8d7886-d830-56b0-ade8-4c232faa5a23 | note | ACCEPTANCE CRITERIA: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
087397d0-7176-535a-be3c-81cd88867fce | note | - - - - - - - - -
5dddf8f5-4215-59cf-a67c-da20fa8b6fd5 | note | REFERENCE DOCUMENTS: Health and Safety Coordination Plan
81302791-f2a8-53ba-8fe3-5dc081fc6409 | note | - - - - - - - - -
ba942d99-8f86-5149-ad49-cf494e618bce | note | INSPECTION/TEST METHOD: Document Review
61a6bb37-b542-5c4b-b8d8-36022d502898 | note | - - - - - - - - -
fb210188-ce6d-50dc-88f3-a91d22abd646 | note | RECORD OF CONFORMITY: SWMS(s) signed
2343c97b-e517-5536-9d38-f6dae99cdbe1 | note | - - - - - - - - -
5652b807-de81-5ee0-9d02-e4b3381c3ecd | note | HP
b5b87b88-4290-521c-b848-75ec07a122a0 | note | - - - - - - - - -
33f72896-8ed1-582e-bcab-b1cd088e6f51 | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
63007c6f-6c9b-54ef-8e75-84a609505f43 | note | - - - - - - - - -
d6146ef8-8ab9-5bec-adb3-c5dc7cba7489 | date | Date Completed:
| signoff | REQUEST HOLD POINT SIGN OFF
| checkpoint | 1.3 Check that current revision drawings are being used
37e470fe-d009-5111-9a0b-648f54756fa3 | note | FREQUENCY: Prior to Commencing Work
5513b31f-6561-5645-8895-67d0b341b6c3 | note | - - - - - - - - -
2b23fad8-dc35-53dd-b89c-fa96634dc0ac | note | ACCEPTANCE CRITERIA: refer to latest drawings and latest available revision used
2bfb413c-14c1-5491-82ee-768288f3a913 | note | - - - - - - - - -
f93a756b-3708-5bc5-bbb2-6f69a506f375 | note | REFERENCE DOCUMENTS: IFC Project Drawings/ Drawing Register
e785fa76-69ff-50bb-982e-053a599efdaf | note | - - - - - - - - -
c187c187-cb7b-5259-90c3-8233fe436adc | note | INSPECTION/TEST METHOD: Document review
721ce7bc-365e-5efe-b6c2-1b76669e6628 | note | - - - - - - - - -
82e1927b-2b8f-5e25-b810-e97c469bdd40 | note | RECORD OF CONFORMITY: Latest revision drawings
05ddbc4c-5a81-59bd-8617-ea16c9e3eee1 | note | - - - - - - - - -
1f2c3898-05f1-5f01-a9f2-c0f650515c06 | note | AP
b92d8e93-41dc-54c4-a112-7c635c3e2bbd | note | - - - - - - - - -
abd7f221-dc24-5815-acb2-94d830ff54c7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2d20c03e-cec9-5901-bf6f-356a0cddc3c7 | note | - - - - - - - - -
00e7297f-3a9b-506f-b8f6-34f5816442ed | date | Date Completed:
| checkpoint | 1.4 Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
18cf5d74-567d-5492-b751-871f18d48047 | note | FREQUENCY: Prior to Commencing Work
78e06ef4-1909-5916-916c-af6134132896 | note | - - - - - - - - -
b1f7bfee-71cd-52d3-9b02-6a5e2b1f5708 | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
f8d5a5f3-2beb-5a7a-a720-61e42f186239 | note | - - - - - - - - -
826a33ca-ff17-566a-a5f6-e3f3e4bff93e | note | REFERENCE DOCUMENTS: EMP, induction register Project Spec. Cl.1200.03
b514523e-4fb1-5c8a-ba8f-e82603eceac8 | note | - - - - - - - - -
09c689de-a22b-5f96-871a-588d5c735552 | note | INSPECTION/TEST METHOD: Document review & Site inspection
9a5ea761-5f76-514b-89b2-a0cc79cf14e6 | note | - - - - - - - - -
26716aa4-0851-5d76-90d4-f11c50eae7a3 | note | RECORD OF CONFORMITY: Site induction signed This ITP signed
270b9aec-5c75-5a84-b162-6bc3f7d0d9b3 | note | - - - - - - - - -
a38b4977-9b9a-50d4-b962-60ddd06dc154 | note | IP
a6a69ee7-5913-5341-9891-95f540123ae2 | note | - - - - - - - - -
10061cd0-dbba-587a-bba3-9102b092a864 | note | RESPONSIBILITY: Site Engineer
4f1277ba-402b-535d-82cb-a60d59f0901a | note | - - - - - - - - -
e5278eb5-7b55-5b9f-9adf-8a6950ac1689 | date | Date Completed:
| checkpoint | 1.5 Excavation Permit issued
f7d7d07b-f9c5-5899-97d6-967c15cd3051 | note | FREQUENCY: Prior to Commencing Work
09eb9ad8-ff7b-5eeb-b83f-d16895aa2eb6 | note | - - - - - - - - -
752078b5-ed78-5dc7-8d32-d4e4d36b5cb0 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
bc62f9df-a5b7-5e55-b0b6-d07b3d554513 | note | - - - - - - - - -
05fe117f-4851-5c65-92e6-e0cba36b3559 | note | REFERENCE DOCUMENTS: Excavation Permit
9c345cd7-1a95-5a3d-91b2-2bd25b9c32f0 | note | - - - - - - - - -
a094d286-cfc5-5e6f-804e-95615a980f8d | note | INSPECTION/TEST METHOD: Document review & Site inspection
84775944-5117-5552-8480-28112c2d7508 | note | - - - - - - - - -
4a4a8a5f-a3d2-51cf-9171-ff956500b4fc | note | RECORD OF CONFORMITY: Excavation Permit #
5d4ed0b0-aacc-5eb4-bab6-0a64ea60f6c3 | note | - - - - - - - - -
a0c4d8e7-65fe-5879-b470-43dc503856a3 | note | HP*
dae1258e-4094-56f5-80a2-b937d78055f3 | note | - - - - - - - - -
5b092f42-9b06-5c89-b235-98f0602a62a5 | note | RESPONSIBILITY: Site Engineer
2656c47a-5e80-5dc8-9a7c-6237fbe4a117 | note | - - - - - - - - -
7883f666-6c4a-5262-8b63-76d1a4be44d2 | date | Date Completed:
| checkpoint | 1.6 Traffic Management (When required)
b6d74629-784e-5e95-a1ea-68b079e61b80 | note | FREQUENCY: Prior to Commencing Work
6b5ce27e-449d-59c3-89f8-d2df76dd9040 | note | - - - - - - - - -
ff49fe57-1bc5-5cc8-a877-54cff0a9f44e | note | ACCEPTANCE CRITERIA: Approved TMP and MOA
a87507da-f0b8-5326-ae3c-e15222cb28bd | note | - - - - - - - - -
6a32c59d-3ff4-53c8-9744-35e9f9499442 | note | REFERENCE DOCUMENTS: TMP
e59afad9-a6f6-5c92-ba51-eb1877e588ed | note | - - - - - - - - -
4f465fd1-d16f-506a-a0b2-b1611f5f91f9 | note | INSPECTION/TEST METHOD: Document review & Site inspection
2686112d-1e53-526a-ba4b-82fefd1072cb | note | - - - - - - - - -
b5c50cb8-d2d8-5163-892b-2828aab37dcb | note | RECORD OF CONFORMITY: Approved TMP & MOA
2876205b-3b57-52be-ad21-fa77a5b755bd | note | - - - - - - - - -
924835f6-3272-50cd-ba48-4f65c939eea1 | note | AP
3cbfdf08-2865-5522-9ea9-4c19d012ab26 | note | - - - - - - - - -
5d71ba2f-2a42-5d18-908d-44382428c7f4 | note | RESPONSIBILITY: Site Engineer
54e42a1a-ea64-57f6-856b-54f319165e95 | note | - - - - - - - - -
3c6b3ec8-f2b3-5063-ab34-7c15b37ab196 | date | Date Completed:
| checkpoint | 1.7 Vegetation Removal Permit (if required)
1372731c-169d-5055-b816-0ff1686eb591 | note | FREQUENCY: Prior to Commencing
ecc1df76-3aad-5a1d-a4dc-65a68e655ba0 | note | - - - - - - - - -
eb27eefa-1d9f-547b-b672-cb7e9b839efd | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, FH shall: (a) arrange an on-site inspection with the Superintendent relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits. (b) fence and sign all sites nominated as No-Go Zones.
fec6596c-6bd2-5f53-a26a-201dd5cf3921 | note | - - - - - - - - -
11b066a7-a7ac-5093-ae41-851fa38a1eb8 | note | REFERENCE DOCUMENTS: Project Specs. Cl.1200.15
873db04e-1ea5-5681-af80-4610b82bdbf1 | note | - - - - - - - - -
783df4a5-b3ba-5bb0-8af8-90b7a9bad6c4 | note | INSPECTION/TEST METHOD: Document Review
7b23e025-3a75-5fec-a25c-8148a16e9441 | note | - - - - - - - - -
a5747482-704e-5ce5-a185-71f144213ce8 | note | RECORD OF CONFORMITY: Approved Veg Removal permit received.
4052daa1-f465-55e9-903e-7c35376a671b | note | - - - - - - - - -
f34f2277-9ad1-56d3-8529-e26b7023762b | note | HP
8489f418-8606-5f15-9f89-28b784fb7ef9 | note | - - - - - - - - -
2beff777-b4d5-5875-b922-921204d750b6 | note | RESPONSIBILITY: Site Engineer & Superintendent
2970bd85-5d99-5b18-8aa2-820b9977cc3a | note | - - - - - - - - -
dd3fcc3e-1874-58b1-9846-af5f51b652ab | date | Date Completed:
| signoff | REQUEST HOLD POINT SIGN OFF
| checkpoint | 1.8 Extent of Clearing and Grubbing
7b8bff1d-690d-5e9d-a289-08c414da1476 | note | FREQUENCY: Prior to Commencing Work
a1a2c34f-87e6-5552-8d10-fb8b6d4da9de | note | - - - - - - - - -
d8afd6c5-ccb6-530c-af46-4ee5b891f8b4 | note | ACCEPTANCE CRITERIA: Extent of Clearing and Grubbing shall be reviewed jointly by Superintendent and FH representative prior commencement of the Works
883d394f-eda1-5c47-93ad-ae4ef93c2e97 | note | - - - - - - - - -
1dd65c93-24c2-5e7b-ba53-0ff88be02975 | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(a)(ii)
59f1477b-9b46-531f-9876-6ca16575aa41 | note | - - - - - - - - -
70653a42-eefe-5a2b-8356-fb77212c79fa | note | INSPECTION/TEST METHOD: Site Inspection
d06a847a-e39e-5eba-ae57-cc8b8b25794f | note | - - - - - - - - -
1824ad63-c8d6-526a-a91e-d115c6168fd5 | note | RECORD OF CONFORMITY: Extent of Clearing and Grubbing reviewed by Superintendent
22e412fb-1fe5-50be-937e-6e86a626ff8c | note | - - - - - - - - -
9a007bda-d1b2-5f0d-8fd5-aad386637a5c | note | HP*
ce20a235-f25b-586f-aea3-e6777167edbc | note | - - - - - - - - -
b06a3bdd-ee35-51ce-9bfc-2c80af93ad3d | note | RESPONSIBILITY: Site Engineer
0d7fe5bf-1645-55ef-aaff-fd1eb9b8d90c | note | - - - - - - - - -
b85a6ba6-9d3f-5a93-ab2a-6a48f2408b76 | date | Date Completed:
| signoff | REQUEST HOLD POINT SIGN OFF
| checkpoint | 2.1 Identification of Cultural Heritage sites and areas of Cultural Significance
b7316e43-e415-530f-9c31-9f73ff528d51 | note | FREQUENCY: Prior to Excavation
4ca83726-11bc-5839-977a-c373d777e5ca | note | - - - - - - - - -
1b918ad0-0d0f-5062-b429-d80a5e0ab730 | note | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing. Immediately notify the Superintendent if any Cultural Heritage is discovered or identified during construction and work to be suspended. Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
3a30983d-f4d8-5a38-8630-bf2e78324eac | note | - - - - - - - - -
e8b7c9e3-dedf-5e44-9ca5-96ecb3ca5eea | note | REFERENCE DOCUMENTS: Relevant EMP Project Spec. Cl.1200.17 VicRoads Spec. Cl.201.10
886d5357-3153-5e80-8041-1e50397b6bd8 | note | - - - - - - - - -
c96e6f0b-20da-51c7-949c-e02ee6ea5eba | note | INSPECTION/TEST METHOD: Document review & Site inspection
1913d147-dc3c-5fe2-be33-f0e80894804e | note | - - - - - - - - -
3302f5f5-5dae-582a-b3cf-9cb48f9fb138 | note | RECORD OF CONFORMITY: Cultural Heritage approval (when required) Signed ITP
806015ca-587c-569e-92ef-e50d04ec70d5 | note | - - - - - - - - -
836ccce4-9658-506d-90ce-7d278c29a3ff | note | IP
9b40422d-256a-5009-ab35-0574ecb08081 | note | - - - - - - - - -
4d339ef6-91e1-51e1-83a4-6324e80894fe | note | RESPONSIBILITY: Site Engineer
bc450f20-e576-5824-a5b7-0d8f21ea2a91 | note | - - - - - - - - -
9e23c3e3-c627-5b8c-8bc6-dc0311293a70 | date | Date Completed:
| checkpoint | 2.2 Stockpiling
943cb1b7-eb5f-5968-8a56-4de356908b53 | note | FREQUENCY: Prior to Excavation
8480272d-e3b5-5906-bdc3-518781313eac | note | - - - - - - - - -
843858e1-3c47-56d3-ad6c-78d9fe60420b | note | ACCEPTANCE CRITERIA: Where soil is stockpiled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways. If this clearance is not possible, additional protection shall be provided. An area for stockpiling of topsoil has been designated and marked according Work Procedure WP-0009
56f653db-2e24-5cd6-b42a-20aa263a17c5 | note | - - - - - - - - -
5a023889-0b7a-584a-ba41-4843f1a607eb | note | REFERENCE DOCUMENTS: Project Spec. Cl.1200.09 (b)(i)(4)
4fd431c5-910d-5a3a-abae-5fdd23cdd00a | note | - - - - - - - - -
5e9490d9-9cdd-50a6-ac8c-736cf1c0c363 | note | INSPECTION/TEST METHOD: Document review & Site inspection
e0b5aa05-a4fa-51c8-bc64-79591408b82c | note | - - - - - - - - -
caae3ba3-f798-5c9c-ad68-81b037ab8ef7 | note | RECORD OF CONFORMITY: Signed ITP
ae67607b-7822-50cc-a7d5-b3aba034dfd8 | note | - - - - - - - - -
b7f016a7-475c-5877-aad1-b470a3c30fe9 | note | IP
5550a08b-e2a5-5014-b0ed-f3504fbda60e | note | - - - - - - - - -
8b4db1d9-bb76-5b73-89ba-399849d55bb3 | note | RESPONSIBILITY: Site Engineer
9d5ac07c-9024-549e-9378-fe83d2bd3bca | note | - - - - - - - - -
5d87a512-b0fa-5b1b-9700-99ef7e3e4d11 | date | Date Completed:
| checkpoint | 2.3 Stripping of topsoil
ebb0bbfb-a83c-5a29-8a0d-a0e53c7f1af7 | note | FREQUENCY: Prior and after commencement of any ground disturbing activities
81fb18a0-89ae-5d1b-b91a-484eed9d577a | note | - - - - - - - - -
8820c0a2-8350-5150-878f-c97c36d3574d | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation. Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site. Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re spread as soon as practicable.
22c3a156-385f-55b8-b2b3-1f2cd948ff0f | note | - - - - - - - - -
20b6f318-f750-5760-972c-3cd486d72be7 | note | REFERENCE DOCUMENTS: Relevant EMP Project Spec. Cl.1200.16 VicRoads Spec. Cl.204.05
f2c64cd0-477d-5199-a94e-5e2945959ed1 | note | - - - - - - - - -
516d9dd8-d683-5d65-b73d-9414a0aa8e3b | note | INSPECTION/TEST METHOD: Site Inspection
00b47367-5d9c-57f1-83f9-adf5880a7d15 | note | - - - - - - - - -
b7fd8d14-ac8d-588a-9e7c-3fe337986b0f | note | RECORD OF CONFORMITY: Signed ITP
edf8350d-964c-51a9-862e-d5a684f36ab4 | note | - - - - - - - - -
cbb3a0f0-f8fc-52b3-8c06-74dee4c92232 | note | IP
36749fd2-9f24-5790-9aed-66f0011a0e90 | note | - - - - - - - - -
7212fa20-eb70-57ee-908e-7ad3d8987b5f | note | RESPONSIBILITY: Site Engineer
bb744305-c06d-5eb8-a206-8b5c92aaa76c | note | - - - - - - - - -
59d889f0-8970-5cbc-a424-7c92d3bf0d49 | date | Date Completed:
| checkpoint | 2.4 Removal of abandoned services
ce3ae9eb-acc3-5885-ba62-fe58bbad778f | note | FREQUENCY: Prior to commencing this work
e4b0d4d5-af36-5678-a888-d29425f5d158 | note | - - - - - - - - -
30207abe-9bd6-5d45-8e66-76a726a58c90 | note | ACCEPTANCE CRITERIA: Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works has been done. Verify service is not likely to contain a hazardous material (sewage, asbestos pipe) Decommissioned services to be disposed of in a suitable manner. Decommissioned pits have been broken back to 0.3 metres below subgrade level.
a6e32f48-10ab-5152-97e6-9ed2d80e3757 | note | - - - - - - - - -
017009ad-e2bc-521f-b9f7-eaa1047a2df2 | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(a)(i) VicRoads Spec. Cl.201.05 Excavation Permit # IFC Drawings
3f6dc261-592d-519a-8c04-e8d81889ca7c | note | - - - - - - - - -
16078674-6c51-5d3e-bd8e-a4330b253026 | note | INSPECTION/TEST METHOD: Site Inspection
16170594-d091-5376-aab8-6c77016a17c7 | note | - - - - - - - - -
40e0927d-e3bc-54f5-8e32-8e30aab3d5cd | note | RECORD OF CONFORMITY: Signed ITP
fbc37c5a-7b41-5ba7-834f-31df9ed1d3e2 | note | - - - - - - - - -
3811d690-6319-5e49-82da-e37e78953e83 | note | HP*
ed25b0d4-e133-5853-be63-991e274b158f | note | - - - - - - - - -
e38da777-5652-5678-ab6b-951da417335c | note | RESPONSIBILITY: Site Engineer
d382151b-4bac-50cd-b356-42764954dd95 | note | - - - - - - - - -
a8f08116-3a85-5845-9e5d-b61f505a9bf0 | date | Date Completed:
| checkpoint | 2.5 Clearing of Trees and Vegetation
c95587a4-b326-5867-b6e5-24083370216a | note | FREQUENCY: During clearing works
7dd369c2-dca0-5fe4-b448-f7602a6918bf | note | - - - - - - - - -
3329a53d-2bb6-5d27-bdcf-9bf7ac90cb8f | note | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface.
8ca7c65a-f225-5787-9ea3-7cbbe7a1a114 | note | Where whole branches are to be removed, the three cut method shall be used.
0bc3edaf-ada1-582e-be8e-f3f4faf98a18 | note | - - - - - - - - -
deeea810-2d78-5e01-af2b-33c67aa3ee48 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
2978e412-784c-5812-8327-3204fb70e267 | note | - - - - - - - - -
469adcb1-65da-5afe-bf6d-a9f2be6e0c9e | note | INSPECTION/TEST METHOD: Site Inspection
69feb279-d6ef-5ce5-86d5-5ce78eb8cf37 | note | - - - - - - - - -
809baaf1-fe20-596d-a67b-49d46af3acd1 | note | RECORD OF CONFORMITY: Signed ITP
fcb8623e-1ecc-59fa-aa35-7fd8e07af77e | note | - - - - - - - - -
809a917e-d69c-5525-9b94-517c3efec1ab | note | HP*
5fd3e582-3440-56c2-849a-7af2323512cb | note | - - - - - - - - -
9d7206e7-87ad-5c4c-b7ed-5e3af089d8f5 | note | RESPONSIBILITY: Site Engineer
67a2d126-720a-53a9-9886-23c3cfb83efe | note | - - - - - - - - -
51830072-baa1-5d44-88a3-ede8d54d40cc | date | Date Completed:
| checkpoint | 2.6 Clearing Process
3bed75e7-72fc-5c7e-9892-6104b9f8ef84 | note | FREQUENCY: During clearing works
baeed6c5-9e06-5324-acef-0660e99b0190 | note | - - - - - - - - -
a3df9aef-3f53-50b0-a090-ea34cb3e6c81 | note | ACCEPTANCE CRITERIA: Tree Clearing shall be done in a 2 stages:
232d22e2-0fca-508e-b153-eebb46002066 | note | 1. only non-habitat trees as identified by the the ecologist are to be removed
323c331d-c352-5038-bf4b-9b1a5b35d3fc | note | 2. the removal of habitat trees must occur not less than 24 hours after the removal of non-habitat trees in the area
51bccd5c-0f1d-5b63-a66f-a959a781b4b9 | note | - - - - - - - - -
cbb45d85-4ebc-58cf-9002-94fc763471c9 | note | REFERENCE DOCUMENTS: Project Spec Cl. 1200.15.5.a
f6489a21-9797-5914-9fb5-c457c1ca5dce | note | - - - - - - - - -
5acb6a64-23a7-5b1d-ab42-ad981b0b3d96 | note | INSPECTION/TEST METHOD: Site Inspection
3b1df3ef-8dca-5965-8ecf-54ddef6ad866 | note | - - - - - - - - -
ed1cdb67-530b-5bb8-8520-15d7201bd6a5 | note | RECORD OF CONFORMITY: Signed ITP
cd99b396-150b-521c-82ef-ef75d7800857 | note | - - - - - - - - -
4d12be88-d991-5b10-b266-58071b1a925b | note | HP*
c3fdbe49-2217-53e7-9c8a-37ab6de8e428 | note | - - - - - - - - -
0a56b407-ca03-5a1b-89e6-97cf9b6b837e | note | RESPONSIBILITY: Site Engineer
20484fbe-4392-55ff-8aae-4dd4d7dcde81 | note | - - - - - - - - -
c6e2f4f3-2fd5-5129-a5c2-e235778fa196 | date | Date Completed:
| checkpoint | 2.7 Grubbing of vegetation
e0d9af69-2cbc-5af8-82d6-ca4c7167f5ba | note | FREQUENCY: Prior to commencing excavation
baf6a228-1f03-5c9e-9788-a447fd6b24cb | note | - - - - - - - - -
166c0d3d-895e-5dce-85bf-689bd394600f | note | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
9f613617-f954-523c-a27d-dd098d3556ff | note | In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment. Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
82b4d7c7-2a65-5313-b7f0-adcebc8be536 | note | - - - - - - - - -
ccded32a-2df3-5e00-bc62-52860088e4c0 | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(a) VicRoads Spec. Cl.201.05
adc6bec1-dd77-5ed5-92b6-9cb81ff1b484 | note | - - - - - - - - -
7ca51f69-a8a8-54f4-aada-09898deda17c | note | INSPECTION/TEST METHOD: Site Inspection
78f3b2fb-ee23-52e8-b4a7-9eb226bdc955 | note | - - - - - - - - -
6dbd7725-72fb-58ce-a75a-d677086fe828 | note | RECORD OF CONFORMITY: Signed ITP
de8d15e2-4ba6-587d-9f9d-fad8b1a90de4 | note | - - - - - - - - -
48346c78-ffda-5c81-b25c-cb4f37edf7db | note | IP
29418c49-89b3-5e1f-bb2a-8cd15aae731d | note | - - - - - - - - -
5b753012-8b3c-59b0-b3a4-b4057c638953 | note | RESPONSIBILITY: Site Engineer
47d5a813-fd0b-5338-ab8a-ba0f8354dca8 | note | - - - - - - - - -
dc896368-51dc-571d-a7ac-85e52b3d3d17 | date | Date Completed:
| checkpoint | 3.1 Disposal of vegetation
c12bd6c6-5b36-5df9-a373-c942601b4364 | note | FREQUENCY: At completion of works
c822cc3f-2322-5503-adfc-49249ee4abd0 | note | - - - - - - - - -
ae304dba-704c-5e7e-979b-3280d4fee8d5 | note | ACCEPTANCE CRITERIA: Tree trunks and large branches shall be removed from the site. Small tree branches, shrubs and leaves, excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
bc10d970-710c-5699-8cec-9dcb4e56fee5 | note | - - - - - - - - -
f06f4e84-d904-5369-85ad-61eb878f812b | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.07
6a373dd6-823c-5391-87f1-9b0b47df993c | note | - - - - - - - - -
25f0c274-fc5b-5158-9afa-03718d5a91c7 | note | INSPECTION/TEST METHOD: Site Inspection
c46ee826-28e3-5790-b065-6acf116d434f | note | - - - - - - - - -
6eaa9842-8349-5f4e-b40a-239e721b4ae1 | note | RECORD OF CONFORMITY: Delivery docket
76e0aa96-7186-58a9-b3fd-2c0f2a58c79f | note | - - - - - - - - -
b39dc6e4-2b4c-5638-8ebb-f757f80ad4cd | note | IP
23457e9f-911d-5547-af81-0b11a48046a9 | note | - - - - - - - - -
3dc88ecd-b765-5d79-b47a-e4e8fa197edd | note | RESPONSIBILITY: Site Engineer
ea860c3b-7f72-5cd7-b66c-5c8923fff701 | note | - - - - - - - - -
e464903b-0950-5f16-b470-a7d80f9dbe8d | date | Date Completed:
| checkpoint | 3.2 Topsoil Placement
720d905f-8bf1-535f-9d36-d01fb5f523c9 | note | FREQUENCY: At completion of works
66e07792-4e31-5b94-9bff-8de25ca22627 | note | - - - - - - - - -
162b2b5b-bb53-5add-bf51-af7f2d00c07b | note | ACCEPTANCE CRITERIA: All disturbed and/or not paved areas shall be topsoiled according to Section 204 of VicRoads Standard for Roadworks and Bridge works, to the following minimum depths - Batter slopes > 2:1 = 50mm -tree and shrub plantation bed areas= 100mm - Verge, 50mm outer edge / 20mm when within 100mm of the edge of seal or asphalt surface treatment - All other areas - 75mm Topsoil should be levelled and spread, but not compacted, except for verge areas.
6e01c51f-f8ae-5ef3-bd40-c3570342f546 | note | - - - - - - - - -
778be8a5-532f-54fb-883d-eb8da2c52dab | note | REFERENCE DOCUMENTS: Project Spec. Cl.3020.07(k), VicRoads Specification Cl.204.17
cc0271e9-f3e5-529d-856a-27b6c3a37e9e | note | - - - - - - - - -
1f5c2247-2112-5dfd-b2d7-89298cfc9f06 | note | INSPECTION/TEST METHOD: Site Inspection
b9fece64-432b-5de3-a496-6ad1b8d4f765 | note | - - - - - - - - -
e06f53d6-5767-5dea-afb0-159c6ba2b21b | note | RECORD OF CONFORMITY: Signed ITP
b5b26862-7082-5c39-b53a-1da2cb17c491 | note | - - - - - - - - -
428abe4e-759d-56a9-b49a-8953fe991b88 | note | IP
78a50f9e-d5d2-5d30-8a80-27cbdf43173d | note | - - - - - - - - -
c7963d1a-36c4-52dc-b734-e77c2325516e | note | RESPONSIBILITY: Site Engineer
1f60c2f6-7510-59df-abbc-7e0e3a45b5e0 | note | - - - - - - - - -
07ee862b-17f5-5aa3-a3f6-7d82fbc8ca40 | date | Date Completed:
| checkpoint | Final Inspection
28159cb7-5603-5ecf-a7b0-d2abd7d348a1 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
c616d978-c9a7-5f23-b804-091411a3b0ac | textbox | Print Name:
1ac82e1d-5894-537c-a9f7-5933de128122 | textbox | Position:
b2274fe4-bbc5-5b8e-8156-f20bce166ce4 | date | Date:
bfc7516d-93cf-5719-b2ef-b8cb2460dbd5 | date | Work Completed On
| checklist | ITP 0006 - Excavation, Fill With Type B & Subgrade Prep | itp | ITP-006-AX-LOT-XXX - Desc | fed3260c-d764-4fcc-9bf4-951e27921dd8
| section | 1 - Preliminaries
| checkpoint | 1.1 - Check that current revision drawings are being used
52b99de2-457b-51b8-a0c0-4ac3f1073cf2 | note | Frequency - Prior to Commencing
09a87971-f93d-5d36-8d6d-83d6c0a5b005 | note | - - - - - - - - -
bff6f962-1921-5e8d-8bb6-0e0222476d3e | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
b8db71ce-6f4e-5123-8b5f-c7236de26632 | note | - - - - - - - - -
5c687d1e-d440-5b34-bbcc-c177a268918d | note | Reference Documents - Project Drawings / Drawing Register
6e5ab086-53b0-5f55-9595-c8cf859edd9a | note | - - - - - - - - -
93f5d06e-bdd7-57e2-9dea-8786b2a7c306 | note | Inspection / Test Method - Document review
dcb2467f-a4e4-5db4-9804-3032a508d78e | note | - - - - - - - - -
4a812f64-5db6-556c-8952-6b0a96e24af1 | note | Record of conformity - Latest Revision Drawings
d0f90126-5405-5561-b456-2ddc599d9da3 | note | - - - - - - - - -
cc08e3c0-1e1b-567c-ad5b-b6b836e9de95 | note | AP
74ae7c25-e71d-5846-b318-911e77b4b67f | note | - - - - - - - - -
feebfb5b-cc84-5a55-9c30-61173d3baa81 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer / Site Foreman
1410f849-af46-5147-b2d0-669a5a3d6427 | note | - - - - - - - - -
db55dc1d-264b-5c4f-b159-8bbc446416d9 | date | Date Completed:
| checkpoint | 1.2 - Excavation Permit issued
20acdecd-c7ee-5cd9-a429-15b48e1609f9 | note | Frequency - Prior to Commencing
7fb36c4a-6a63-5444-acaa-1ab86f8e12b2 | note | - - - - - - - - -
29f9f26e-1c15-5d9d-8189-9b50ed023363 | note | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
f2cc3754-c3ff-506b-b644-e343e4daf8f7 | note | - - - - - - - - -
ba94c1ed-8786-527c-8162-c7b82ed06bb4 | note | Reference Documents - Excavation Permit
f03bb7d6-8d83-5483-ba04-1619625ef134 | note | - - - - - - - - -
e4d7ced0-1bc8-5a89-9d60-f86f82b005b6 | note | Inspection / Test Method - Document review
f9361967-4bac-5145-bcda-cdb55919110d | note | - - - - - - - - -
5379c27b-08db-5a07-a204-c0b696a7f4fa | note | Record of conformity - Excavation Permit #
64af4fff-5df2-51a5-801b-79d3a721ddc4 | note | - - - - - - - - -
b69f69ec-519d-5641-b20c-55372798c7f7 | note | IP
e5422eb9-abed-5b52-afc5-4c76ff7d2404 | note | - - - - - - - - -
ec87337a-4653-532c-8634-b36b4171d347 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
046adec3-1178-50f9-8ed2-6269d655db74 | note | - - - - - - - - -
51f3660a-e646-5f12-b703-a2d06fd65ee3 | date | Date Completed:
| checkpoint | 1.3 - Re-Use of insitu material
f91729f6-562a-5abc-8d8c-214c8bad9f53 | note | Frequency - Prior to Placing fill
83640849-cf24-5519-ac97-51c660b8da35 | note | - - - - - - - - -
8955f478-b17f-558b-9f79-47e25c114d3b | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04.
2b07192b-db48-5686-8c93-adb0f985329f | note | Type B Material shall meet the following requirements:
04237fb5-feec-53d6-9689-8086240511cf | note | CBR ≥ 1.5%
1d9bed20-6821-5155-9521-c86bb82de19c | note | Swell < 2.5%.
51d45f8c-a25e-5cb6-9a32-452517e15033 | note | Attach: Test Certificates
43fb8588-90de-54e0-92ae-47f92801a4d9 | note | - - - - - - - - -
7ace1632-e5f6-5664-8378-717bb98d3a86 | note | Reference Documents - VicRoads Specification
53f6b62c-ec2a-591d-9489-af70da887fd8 | note | Cl. 204.04
09459d68-4005-5749-86e1-fb967950f393 | note | Cl. 204.06
4a0e7ece-8f26-5a0d-9342-569447eb5818 | note | - - - - - - - - -
a4989cb9-c4b9-5cec-8300-a0320b3c33f7 | note | Inspection / Test Method - Site Inspection
aef017e1-178b-5035-a001-2432744d1f88 | note | - - - - - - - - -
b2b76cd2-ec97-5b7b-a29e-a063f1f00afd | note | Record of conformity - Test Results
bebc4673-cc12-5240-a2fc-8f09265151ab | note | - - - - - - - - -
c26e7f0e-07d3-5eb5-a4b9-7760093e8e5e | note | Material Category agreed with Superintendent
23a8f894-06af-505e-a56d-9684bbac6397 | note | - - - - - - - - -
ab53ebde-d9c1-5348-994e-de5c60157aea | note | HP*
9034ebd4-f7db-5074-acba-da7676d53e66 | note | - - - - - - - - -
a941b528-67c2-58f2-9d90-b0819a8ee741 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
80d4d42a-bef1-5959-8c28-3b0a9f630200 | note | - - - - - - - - -
e9014003-4f40-5770-992a-14fcd7192c86 | date | Date Completed:
| checkpoint | 1.4 - Type B Material Approval
771f711c-83a9-52d2-b59a-df5088510ae8 | note | Frequency - Prior to Commencing
4eabc439-2c97-5ac0-9ede-cee7e02eb6ed | note | - - - - - - - - -
1188112f-3109-526d-9e67-00d4b658bd12 | note | Acceptance Criteria - Prior to the import of Type B material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type B material complies with section 204 of the VicRoads Spec.
53be571f-f67d-55ff-9498-3c873110755d | note | Type B Material shall meet the following requirements:
618a22e4-1d2a-5f6f-82b4-333429847981 | note | CBR ≥ 1.5%
73387661-b40b-5534-894c-ccb9334e5400 | note | Swell < 2.5%.
8b216b0a-22fc-5e32-b8b1-d0dd2dbeabe0 | note | If parameters are not met, remove 400mm of material mm below Cut Floor Level and replace with conforming Type B material.
bee7407c-bcce-5be5-b344-345ef1a6992e | note | If removal and replacement of material below the Cut Floor Level is not required, surface shall be loosened to a depth of 150mm and re-compacted to meet the specified requirements.
579e2517-c5b1-5e35-94fa-fb6963cb2759 | note | Attach: Test Certificates, Sample Delivery Dockets
86b6c413-fa90-5388-9dbc-9fefb4c1bf03 | textbox | Teambinder Approval number
869f490d-1e35-582d-862a-69083e9a887f | note | - - - - - - - - -
b4af758a-35d8-51fd-b687-577e5a5d76a2 | note | Reference Documents - VicRoads Specification
d86ad905-bd64-5627-9c80-946ec1dacc50 | note | Cl. 204.04(c)
08b7c372-e2b7-592c-8aed-d2ce354f93f9 | note | Cl. 204.06(e)
251bb153-26ac-5e36-9848-8641fd46894e | note | Project Specification PS3020.05
a2116657-0615-5bb8-afd0-81f2914a6b41 | note | - - - - - - - - -
e6765902-1ce1-5b18-a3ff-0fb8b8c933af | note | Inspection / Test Method - Site Inspection/ Document Review
b308ce2c-c351-5e37-9acb-e6374a6339cb | note | - - - - - - - - -
c07a007e-7691-5d14-93cd-86cf518e7dc2 | note | Record of conformity - Geotechnical Report
15c0d773-6de1-5aea-a132-19b5d264f6af | note | - - - - - - - - -
3717671c-4793-50f8-b5a7-481b978950ec | note | HP*
02ccc9ed-ad98-5c41-858e-a0d369138f3b | note | - - - - - - - - -
2fbaab4c-954d-5229-aab6-5c71401f4c91 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
79524ce6-9992-5578-a080-1a3d49fe2243 | note | - - - - - - - - -
45c0a746-32a1-5169-a160-5ac812ab9f03 | date | Date Completed:
| section | 2 - Cut Activities - 400mm below
| checkpoint | 2.1 - Survey set-out
aba57e13-bb06-51ba-8688-473a9f463da2 | note | Frequency - Prior to Placing fill
79d9404b-d342-509f-9d34-1f67781a8263 | note | - - - - - - - - -
ba19d8e3-a41c-5c3a-aa5b-fd66e5ec4b85 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
35c75e65-e0af-5c4c-b623-8259814015e0 | note | The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
6c4dc1b3-2a27-55bc-8231-8383b1d5be4a | note | - - - - - - - - -
159e304f-b9dc-5e99-9825-8456acf5eb9a | note | Reference Documents - Project General Specification Cl.1190.06
5689c8d7-3df6-5830-96bc-373e14ad33fe | note | Latest IFC Drawings
9ccc94eb-f45d-52c4-8bbc-334c992c71f7 | note | - - - - - - - - -
b5e6596f-0c69-56d8-b96a-aa36e345d8e1 | note | Inspection / Test Method - Site Inspection
f707c908-e108-5fc1-a076-7d73e6743200 | note | - - - - - - - - -
75f41cf9-03a1-5768-8634-3fc82f2ef5de | note | Record of conformity - Survey records & pegs on the ground
ca41de6a-b99e-5395-867b-84edf14aa0c8 | note | - - - - - - - - -
ff33721d-8a8c-5030-8307-af5de04ac5e2 | note | SCP
4243a7e4-e519-57b0-ab3b-25e517006983 | note | - - - - - - - - -
e1e639d2-50ab-5836-8368-da84d7d72883 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
dc1c9c50-5834-5238-b30d-2119c0011874 | note | - - - - - - - - -
deb9150c-4feb-5423-8d95-c5805cc0c44b | date | Date Completed:
| checkpoint | 2.2 - Ground water
3b2b09ee-eee9-533e-a3d2-3fc6f926900b | note | Frequency - Prior to Commencing (if required)
4cf63c58-809e-5860-99fd-6ec20ce6d833 | note | - - - - - - - - -
2c915a01-feb8-5b87-b409-e97e8eabbb4d | note | Acceptance Criteria - Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review.
c9c7b02f-edca-5d85-9bf2-b348cafd353a | note | The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
88493277-a0cc-5bcf-92bd-a756c00d8c12 | note | - - - - - - - - -
846110b3-32d0-5810-8089-947b3e08bc92 | note | Reference Documents - VicRoads Specification
44b1da55-62ff-5007-ad9e-48eb7d568b58 | note | Cl. 204.06(h)
2313b230-cb0a-5968-ad91-8f7a5e2b9641 | note | - - - - - - - - -
daf5e2a8-168c-5dc9-8d5a-d4685c1c59c1 | note | Inspection / Test Method - Site Inspection/ Document Review
6d3af875-884c-5584-8286-7c3aeecb32d8 | note | - - - - - - - - -
420333ec-c29c-5399-9850-ecaf62bb73ae | note | Record of conformity - Area reviewed by Superintendent
abacb6f8-3941-5b79-8301-6196a50ed04d | note | Signed ITP
9e42d60b-1f11-5523-a566-2e6f7f2eacd9 | note | - - - - - - - - -
63bd9c50-e5b5-545b-b0c4-0b065a4c743e | note | HP
163aa600-3b5b-545c-a62a-12ca2910af28 | note | - - - - - - - - -
bc1d881a-457b-5237-ab19-bf899ed97fee | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
06c0ce09-f823-5f57-9030-381786a3e66c | note | - - - - - - - - -
caec21dd-42d4-5172-ac59-6bc1407a2d57 | date | Date Completed:
| signoff | Authority Holdpoint
| checkpoint | 2.3 - Acceptance of Rock Subgrade (when applicable)
4cf0f6b2-569d-52d7-84d8-1e0385085c3a | note | Frequency - Prior to construction of the regulating layer
568c36d6-b6a4-5d2c-95c2-21367b4152cf | note | - - - - - - - - -
f8091a3a-5234-540b-be88-a27f030a060a | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
0d81cc44-fac9-5ead-b155-08d0f79d9161 | note | Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
ddc9cc2e-7cae-5f63-b0f4-260219d25648 | note | - - - - - - - - -
376c637a-f3d9-57bc-99e6-970254e54747 | note | Reference Documents - VicRoads Spec. Cl. 204.06(f)
f7056eb3-a0fa-5cb1-af81-9b797a3b2a36 | note | - - - - - - - - -
ff3687c3-8611-5a9e-a2ea-ca9cb6c1d08d | note | Inspection / Test Method - Site Inspection/ Document Review
27063950-da6c-529d-be95-358c6a45af29 | note | - - - - - - - - -
8925af95-3b59-598c-901a-3e18b9078ee3 | note | Record of conformity - Superintendent acceptance
440fc01f-59b3-5a15-b1fb-11b20edd9b3c | note | Signed ITP
fec0bfa4-314e-5d6f-9003-8e444bcf2862 | note | - - - - - - - - -
b16df26d-f74b-5e0c-8364-eb6eacb5aaa5 | note | HP
66831aa9-3927-5bd3-ba3f-5a124a09de2d | note | - - - - - - - - -
53a48862-4e1f-512b-bda0-d92009ae74e2 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
e51ff7b0-002c-5b4e-b0e5-5d9fe2cd1627 | note | - - - - - - - - -
996dffe6-302b-547e-a53f-bdbfe1dff04a | date | Date Completed:
| signoff | Authority Holdpoint
| checkpoint | 2.4 - Proof Roll - Cut Floor
d5a4a052-4af4-5372-8c17-36f7840cc058 | note | Frequency - Prior to Placing fill
66a14103-0de7-5fee-af36-6ce2b32ff518 | note | - - - - - - - - -
d1c3e4a3-88d8-5447-8695-d7ee112c3300 | note | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
6d05c1ce-0c7f-59e5-b939-22b9a2023a72 | note | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
848a2827-4ec3-5a99-8952-a9118cd31368 | note | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
5bb44cf9-cc46-5fd1-b165-562ac3913d62 | note | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
f812672a-d552-5da5-81df-bdff960c6004 | note | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
71953589-300e-5313-a12b-09365d8cb3c6 | note | - - - - - - - - -
2466fef6-39f7-565a-94ed-56b96f8cbd0c | note | Reference Documents - VicRoads Spec. Cl. 204.12 Cl.173.03
5630e1d8-2feb-5f76-bc1b-7d1b32b77d44 | note | Cl. 204.10(b)
db4175c2-7815-547c-8038-d0df8c9d3b0d | note | Cl. 204.07(d)
9a3199d9-621f-5dc2-b89f-3b0283a23b3e | note | - - - - - - - - -
d3e7b214-448a-509c-8e36-3942e1822b30 | note | Inspection / Test Method - Site Inspection
00b5f2eb-aea8-5db3-ae0c-615da6c90872 | note | - - - - - - - - -
0c29de5e-5789-5122-8ee5-06073994d9ae | note | Record of conformity - Area visually reviewed by Superintendent
a48942ea-c5fb-5127-bcc4-b4feff630a99 | note | Signed ITP
581ce914-b20e-5cac-9dbd-b6c29ce5d983 | note | - - - - - - - - -
3f230f05-d3dc-5ebc-8b23-2d8f9af1bd13 | note | HP
7391713e-27fd-50c3-9be0-26f17c3d451e | note | - - - - - - - - -
abfab430-279e-50f1-89c5-a79e410021a0 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
72cd618f-74e6-5d75-9805-9d1953842047 | note | - - - - - - - - -
717fbf45-ced7-5e25-bfc4-cd9f6171bfe2 | date | Date Completed:
| signoff | Authority Holdpoint
| checkpoint | 2.5 - Compaction Testing
c7ddd09c-f73b-56b3-b9db-b56b54503532 | note | Frequency - Each Lot
8f7f3cc2-b8a6-59cd-871e-0784955751bd | note | - - - - - - - - -
6aaa477b-0a36-56b5-aa72-ec5bbe5e96cc | note | Acceptance Criteria - Frequency = 6 tests per lot
53ffb599-225f-5d1d-afe3-4517cec51f2f | note | Min Frequency (subject to approval) = every second lot
a9eff641-575c-529e-884b-e37288fd2b6a | note | Lot = One day's production or 4,000m2, whichever is the lesser
e47c0019-bbcd-58e2-b09b-b5c04a2d208c | note | Characteristic Density Ratio =
0459ea83-57ca-53ad-9c85-27d68431adf4 | note | 97% minimum when more than 400mm below top of Type B Fill
f9046df7-202b-5eee-955f-1d5ae13bc671 | note | 99% minimum when within 400mm of top of Type B Fill
d4f7bf57-8469-5f14-a435-1568ecf4e3ed | note | Attach: NATA Compaction Test Report
ce96cca6-7608-5611-8a4e-39aee2764cc8 | note | - - - - - - - - -
5cc8106b-3ce6-5295-aa0b-6b6a4eef9d8c | note | Reference Documents - Table 204.131
42883e37-e6d9-54c0-95c9-9bc4dab26dd1 | note | Section 204.13, 204.14
a926276f-d155-5495-a0de-0f35ec81adb6 | note | - - - - - - - - -
62bb9e01-b19d-5967-a074-c5d5f981c7bc | note | Inspection / Test Method - Document Review
3c1c69e5-5a31-5bd5-95a1-4fc15a9681d6 | note | - - - - - - - - -
63fa2302-68c2-5fef-91d2-5c189f68173c | note | Record of conformity - Sign ITP
2819ab9f-78b4-5691-a0b9-d7cbb4d1fab4 | note | NATA Compaction Test Report
73fae927-6831-547c-a910-5da13aaeb68a | note | - - - - - - - - -
2fa99057-60db-526c-be8e-b385acb262f6 | note | IP
f6a69f53-8b0e-57e8-8a4e-dbfcccfaacb6 | note | - - - - - - - - -
83d40932-bb50-5b48-a53b-c3f57bc2c238 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
05269e65-4d50-52fa-8b03-21d896f94544 | note | - - - - - - - - -
5fbb5439-5ae3-5966-9eae-df1b43871853 | date | Date Completed:
| checkpoint | 2.6 - Survey Pickup
c8a22e93-08c2-56f4-9a0f-76969826cf82 | note | Frequency - Prior to Placing fill
2233a407-bc54-507e-b5af-64fa08dd43dd | note | - - - - - - - - -
ce2c6be3-6dbd-5099-b8b2-78d6e006633e | note | Acceptance Criteria - Ensure the Cut Floor Level is recorded by survey
c2159531-eddd-5efd-83e2-3533254f7f1e | note | - - - - - - - - -
55426932-401f-593c-bc6b-adcf7fed44df | note | Reference Documents - VicRoads Specification
8a12981e-bfee-5ed3-81b6-96de52aab01d | note | Cl. 204.03(f)
8d2cdf22-fbf2-5f82-adc4-9f270b9dfa8f | note | Cl. 204.03(g)
c28954c2-bf83-5883-8e1f-43a2dcd9573e | note | Table 204.031
7588b61a-3fdb-52de-9239-7fe1008a04f6 | note | - - - - - - - - -
c347275a-4ac7-5b5c-8501-442b9b61e47a | note | Inspection / Test Method - Document Review
e28161f9-c222-5561-b27f-ffc57057cdf4 | note | - - - - - - - - -
9aa2f345-761a-5c7e-9da7-6420aa2612db | note | Record of conformity - Survey As-Built
51f56c63-0508-5220-a595-572b378afddb | note | - - - - - - - - -
9588679a-48ac-54f8-bd92-bf12469468d4 | note | SCP
0d56d12e-9184-53b6-ab1a-707571be088b | note | - - - - - - - - -
fc111b0e-5def-548b-855a-7fa0741a1ca5 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
1f21b328-a389-5be0-94c1-a182e259477b | note | - - - - - - - - -
3446f74c-1b9e-5373-b0fa-3f5c1093aae9 | date | Date Completed:
| section | 3 - Fill Activities
| checkpoint | 3.1 - Placement of Fill
c56354e3-10f3-5d1a-80d1-413f288a642a | note | Frequency - Each Lot
5430de97-0e4d-55fd-a5b4-2d616c47c603 | note | - - - - - - - - -
a7e4b2a6-2d11-55c8-a9af-ab74107e1258 | note | Acceptance Criteria - Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness.
987eaf12-2744-5182-82d8-0e6026bbd1bf | note | Each layer shall be keyed in to the layer above by means of a textured surface
fb273f4d-180d-5cfb-bc00-7f769950b65a | note | Any rocky material present must be uniform throughout the layer.
757f672a-6f04-544c-b68c-269fd1def8d5 | note | - - - - - - - - -
7c65c19b-0f52-5cea-a622-1179f2037c6b | note | Reference Documents - VicRoads Spec. Cl. 204.10(d)
bccbe9e7-d702-56df-8270-7b45addda70b | note | - - - - - - - - -
e4e57854-9874-5c45-b1c5-2ba2801f3a35 | note | Inspection / Test Method - Site Inspection
707202eb-0312-50b4-ad72-395c3b163ea7 | note | - - - - - - - - -
5efb8301-0533-53df-8c82-0dfac871962f | note | Record of conformity - Signed ITP
76b68889-ac9e-5d6e-8832-20535c373759 | note | - - - - - - - - -
cf616211-e9f5-5202-9200-605ef28f6a68 | note | IP
677bacf8-b32e-5888-9a0f-5c241889abc8 | note | - - - - - - - - -
78d7e042-e303-5a26-ac7d-84a5fa8ca2c0 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
6945d598-b3dd-5fe6-9069-4984339fc681 | note | - - - - - - - - -
79cd9850-6c9e-599e-bedb-654b88a66584 | date | Date Completed:
| checkpoint | 3.2 - Preparation of final surface - Subgrade
80eddd33-1283-5973-9964-66bacde29d55 | note | Frequency - Prior to construction of subgrade layer
930c2865-1787-55ef-b985-83544d474c59 | note | - - - - - - - - -
875f272e-8905-5672-aef0-16154e53a9fb | note | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water)
8af9fa4f-9154-5b63-a27e-7a58b81dc26d | note | - - - - - - - - -
5f47e04c-f7d9-5d9c-86b8-20428a74aaa0 | note | Reference Documents - VicRoads Spec. Cl. 204.15 Cl. 204.03
de24ce5e-efbb-5cee-80de-6c5bf873c321 | note | - - - - - - - - -
f3eaa212-7615-5596-9da8-01ee2091ad36 | note | Inspection / Test Method - Site Inspection
a5a20ab9-e2e6-5f93-8b62-75a11e8de4fe | note | - - - - - - - - -
6d21799b-e9b3-542c-af78-e7eddd069776 | note | Record of conformity - Signed ITP
e4687c34-7e5a-5c4c-9ad7-d3342b322a70 | note | - - - - - - - - -
1827c5d8-c055-57ea-b808-f3004479e48a | note | IP
b6002c97-e1f9-5204-acb9-03445b3650f2 | note | - - - - - - - - -
2dd54766-242b-567f-99d0-d0c01fcfa1cf | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
ce3c06db-df7d-56bc-9b7f-f476769f727a | note | - - - - - - - - -
07d5914c-f570-5fef-a194-a61201c8f28d | date | Date Completed:
| checkpoint | 3.3 - Trimming and level conformity
9d77a097-45d0-5dd6-a07f-fd849e5f23b7 | note | Frequency - Each Lot (one day's production) prior to Commencing
b6f1f0e0-cb26-5703-9109-1a97dfad06d9 | note | - - - - - - - - -
b2032647-532c-53f0-8fa3-d9e2451d19bb | note | Acceptance Criteria - Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping does not differ by the mean values of more than 5 mm above or 15 mm below the specified level.
ce2b6185-9d2f-5185-98f8-2f8f2fd1917a | note | The level at any point of the subgrade shall not lie more than 20mm below a 3m straightedge in any direction accepting crowns.
0780eede-ee18-5f31-bf6c-7c68090cfd11 | note | - - - - - - - - -
40038282-131c-5789-bc2a-0099c02d5780 | note | Reference Documents - VicRoads Specification
e8f196cc-a268-5735-b17e-c485f9c98bad | note | Cl. 204.03(f)
0f7468c7-3171-5df0-9d5d-2b4615c67fdd | note | Cl. 204.03(g)
afd23922-98be-5ba2-b715-a02dd4388418 | note | Table 204.031
55d09cad-5be8-53ab-9a15-8256b8ab9ce5 | note | - - - - - - - - -
71f19095-02a0-5560-8ea5-bfc00f858b09 | note | Inspection / Test Method - Survey Report
faefbbe9-4109-54be-beb5-1ed26448da31 | note | - - - - - - - - -
62f3d6dd-537d-548d-a322-55a2309c01f8 | note | Record of conformity - Survey Record
7684bb5a-00e0-5ae7-a988-861dc3df2c82 | note | - - - - - - - - -
e784891e-9321-5ffc-8140-3d62c784fa92 | note | SCP
8a0535b5-c14f-5ab8-b5d0-a5049ffebdef | note | - - - - - - - - -
410ab4ad-f503-54a3-a141-af752a0aa8f6 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
b032007e-7e47-57e0-89c0-813569154fc4 | note | - - - - - - - - -
f96522ca-a769-59ea-b062-4a203a02354b | date | Date Completed:
| checkpoint | 3.4 - Proof Roll - Top of fill layer
96d16c95-9469-5d1b-9741-35a04711a80c | note | Frequency - Prior to Placing fill
396454ca-0bf0-503c-a384-c5b53ff559bc | note | - - - - - - - - -
e6e07111-665b-5237-b8b5-389f2c78b6a3 | note | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
ed5ce5df-b2a1-57af-9623-d01eaed282e7 | note | Superintendent to be present during all test rolling.
812f86ec-b699-5dcc-bdbf-e28628ccf50c | note | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
f59d15ac-d014-5f77-be71-90f0c1838816 | note | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
82589977-d21f-50b6-8e52-5685e2542fd5 | note | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
c88cb93c-c615-5a04-aabc-cf8516d0f370 | note | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
a79430d6-c8ee-519f-9321-be7ed63bc0aa | note | - - - - - - - - -
209b9270-9bbc-573b-a996-e7edb504f868 | note | Reference Documents - VicRoads Spec. Cl. 204.12 Cl.173.03
ccce4a52-0e04-5666-ad5e-c8863fbceca6 | note | Cl. 204.10(b)
8db68e1a-d53f-56ab-8a54-546a4067af53 | note | Cl. 204.07(d)
0718e3bf-5744-533c-9380-9bb4210ab265 | note | - - - - - - - - -
43b180b0-b440-5e7d-b601-04fd3196801a | note | Inspection / Test Method - Site Inspection
a94a4be8-494b-599f-8f17-f2cdaae35f90 | note | - - - - - - - - -
c817f07d-a773-54a0-838f-a4ca248debf9 | note | Record of conformity - Area visually reviewed by Superintendent
b9841437-b0ec-5a12-8c7e-609c03ca7aa2 | note | - - - - - - - - -
654fdbb0-794e-57b2-94fb-389f6779470f | note | Signed ITP
a07f6371-5521-584c-8bfd-95c8aa11aa7e | note | - - - - - - - - -
c0ec6d33-37cb-5a6b-b6b7-e56b1dac306f | note | HP
8f808f5c-09cb-5cb5-b30e-666ac5c0a3f5 | note | - - - - - - - - -
d6f6c971-3f70-52a1-9d19-31fad2f80b08 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Superintendent
863a88eb-945d-5e00-9d7b-783fb01b1663 | note | - - - - - - - - -
42d30c7a-bfcb-57ae-b682-1528a25c9421 | date | Date Completed:
c8089d5f-0dcb-5dad-b8a1-6911617fe5ff | note | - - - - - - - - -
| signoff | Authority Holdpoint
| checkpoint | 3.5 - Post-compaction Testing
834a6fb4-2076-5ab5-be29-f2d3cc63c5f0 | note | Frequency - Each Lot
4f46e7f3-1302-571b-a9f4-eadcb9c65a99 | note | - - - - - - - - -
c156534a-3bd8-59c7-ae4a-7e0cdcb78b68 | note | Acceptance Criteria - Post compaction testing shall meet the following requirements:
6d51ca6e-339c-54d7-85f9-d2840a0ff320 | note | CBR ≥ 1.5%
fe9ebec8-ad67-50da-a2e5-1d48c5491d25 | note | Swell ≤ 2.5%
47ae84b6-508f-56ea-a45a-fdc743d8083d | note | Characteristic Density Ratio ≥ 99%
1da57883-a6c0-5edc-ba58-0be8a60054a4 | note | Moisture Ratio ≥ 70%
2f380aa7-8e03-578a-b1cc-9071c8540477 | note | Subject to approval min frequency testing as follows:
0f835d6b-85a4-59b0-9a08-11a40b08c619 | note | Compaction & Moisture: 1 test per 2 lots
e1fe78d8-01c7-5607-aed3-851dd9ea4901 | note | CBR & Swell: 1 test per 8 lots
916c9b1a-fa08-5d43-9ff5-626409e58856 | note | Attach: NATA Compaction Test Report
71a22cae-ecf3-5e4b-bab1-6e5516dc97b4 | note | - - - - - - - - -
2daba4a2-1365-5c73-b7ff-27e40d09e7b8 | note | Reference Documents - VicRoads Spec. Table 204.142
1e92706c-ceba-5891-89fd-91c18751d28a | note | - - - - - - - - -
83e8824c-62d1-5471-bf94-7b637af9eb19 | note | Inspection / Test Method - Site Inspection
d0f3ae4b-ee84-51f8-890d-2682ab976e18 | note | - - - - - - - - -
33a52401-7a06-5bf0-9584-32fb47934b28 | note | Record of conformity - Signed ITP
d09f226a-c979-52aa-be24-677334ef55ce | note | - - - - - - - - -
342d5442-ff8a-5855-b6a2-013805e246a1 | note | TP
56fab060-9635-59e7-867b-62c82d4b6174 | note | - - - - - - - - -
9995f9bb-a45e-527a-a7d8-1260fc63c6de | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
d9c73c51-715c-504e-a57f-7a711666bf46 | note | - - - - - - - - -
1424cd1c-c95c-5185-ad7d-d4a59fb5ec16 | date | Date Completed:
| checkpoint | 3.6 - Survey Pickup - Top of subgrade
64eb7af3-d263-5319-8536-dc5dcb56c152 | note | Frequency - Prior to Placing fill
abaf37c8-25ee-5543-b3f7-a845f9f8edd5 | note | - - - - - - - - -
db25d4ab-8f8b-5542-9ec1-fdbc8dde87d5 | note | Acceptance Criteria - Ensure the Top of subgrade is recorded by survey
ffc8b469-db35-510d-bafd-dce60f273252 | note | - - - - - - - - -
f76062a8-86a2-5e09-85b9-19da18de8769 | note | Reference Documents - VicRoads Specification
09eb2d03-4185-5a2e-b091-37471baab476 | note | Cl. 204.03(f)
66461e11-f145-502a-8607-15c451d10ef6 | note | Cl. 204.03(g)
c15caadb-5d4e-5093-a969-c5c13f84c3e1 | note | Table 204.031
27737314-4a50-571b-94aa-f2dcb4ced092 | note | - - - - - - - - -
771f2249-cb05-57f1-a9a2-aa38ce3691d5 | note | Inspection / Test Method - Document Review
4d384ffd-388e-5f9f-ae6b-17cddcff09ff | note | - - - - - - - - -
e6e7a052-35b0-5335-a743-58451fe84825 | note | Record of conformity - Survey As-Built
31d55730-9828-58d2-b25b-3c274b496f3e | note | - - - - - - - - -
93282110-e5f5-5243-922e-b68fdf88e04b | note | SCP
20138c37-9913-5a2c-84c5-793625130504 | note | - - - - - - - - -
cdd8ecd2-06f6-5262-b662-ede16dfc0350 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
962b089d-4237-5ca9-8f1b-e6b63fcf1b9b | note | - - - - - - - - -
6ace37aa-35cc-51df-a720-5406ecc51861 | date | Date Completed:
| section | 4 - LOT Closeout
| checkpoint | 4.1 - Survey As-Built
5a0b5f58-955d-5fbb-af35-ea9c7c67711c | note | Frequency - Each lot
9ffd5723-0926-5310-a7a7-15a5ba4c6262 | note | - - - - - - - - -
b97ad782-d2c7-594c-ab17-174682a74fce | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
e1cd0073-6d11-5ee9-a7e7-158ff25a6566 | note | Scale A:
e5926adc-a4aa-5385-a8d0-58ffa084a5d4 | note | Min. No. of Measurements Per Lot: 80
3679a4bb-5036-5d4c-bbcc-61e063b23d9d | note | Range x (mean) = +5, -15mm
fdd285a9-d843-5507-a525-d3715334928e | note | Max S (Standard Deviation) = 12 mm
f02cde2f-de49-5bb4-b9a3-ed67dbff6a38 | note | Attach: Survey As-builts / Survey Report
3578546d-cb5c-501e-8ec8-2013f99d3721 | note | - - - - - - - - -
5d2df183-bfb6-5472-a44e-bbd6c78c457d | note | Reference Documents - Section 204.03 (h), 204.16
e399f01d-0edd-50e0-a706-765a5a65d04c | note | - - - - - - - - -
89e21945-1204-5f8a-85b2-a226161dbe14 | note | Inspection / Test Method - Review Document
3051a3a3-c64c-57c6-b8df-fe011f62b883 | note | - - - - - - - - -
3f35654c-3fd8-550d-adff-67955d9d1301 | note | Record of conformity - Attach As-Built Report
d7676cb4-c7cd-5c4c-b034-5388fad9b67f | note | - - - - - - - - -
303878d4-ea38-5a40-9b99-da69eefef779 | note | SCP
ce7f51e3-1f71-5438-8b34-0b4ceec8bd85 | note | - - - - - - - - -
de63bd74-2c26-5e2f-b3fc-c458cd866e55 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer & Surveyor
b57088af-d42d-5e8a-b24a-aef244f742a8 | note | - - - - - - - - -
f36ee153-ddc3-5122-acf6-47da1cfec4da | date | Date Completed:
| checkpoint | 4.2 - Non-conformance Closure
5b21be91-940b-573d-82a0-1f87fe989c76 | note | Frequency - Each Lot
f87e2b7b-ab57-5722-8269-404e0d64a87e | note | - - - - - - - - -
894a8b16-51c1-5a6c-a731-e0052e84dd9f | note | Acceptance Criteria - Ensure All related Non-conformances are recorded and closed out.
a6e7c4bc-1de3-5940-ba7a-28a3ee6d05a1 | textbox | CAMS Case Number(s)
7f155554-3d69-5c08-bbe6-7cd51b7ff9a6 | note | Attach: Closed NCR Report
9fb4c979-ecf9-5ab1-a225-8a41abdff916 | note | - - - - - - - - -
603be8ab-d1d9-5256-b26d-a0f7237e01de | note | Reference Documents - Quality Management Plan
07db8abd-c166-524d-b427-3be0823a9767 | note | - - - - - - - - -
0a235093-3aab-52fc-8e90-281f95352d27 | note | Inspection / Test Method - Review Document
c3979d62-03e4-5e08-94ae-e0dc3e72dd62 | note | - - - - - - - - -
1030d54a-93f6-5e63-8fb2-503c9788820e | note | Record of conformity - This ITP
e3b36146-605d-5d64-87c3-af99de9cef02 | note | - - - - - - - - -
5e50a320-5698-5309-83c3-51fa92a7ae4d | note | IP
3b8613fb-42d3-5280-8a7b-d00ed240843d | note | - - - - - - - - -
937c10c0-252a-5a44-9a6c-64dcb553e7e9 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
8778b8b6-1769-5b5c-b3f4-6a59a77e0f8b | note | - - - - - - - - -
0e42983f-733a-5897-b8f9-35f73f1d99a7 | date | Date Completed:
| checkpoint | 4.3 - Red Line Markups
a091fad8-0ab1-5cc0-bbf2-59a5de7f5a79 | note | Frequency - Each Lot
3035acc9-e690-5a0c-a191-f348711935f6 | note | - - - - - - - - -
5c71e29c-5e28-5f9d-8678-98bd0aa46db5 | note | Acceptance Criteria - Ensure any changes from design are captured in red-line markup drawings
96370d39-15d3-5cbf-94a1-0ac773b469b9 | textbox | RFI References
517efae1-aaac-5ef8-aa15-769cc296f585 | note | - - - - - - - - -
eb53f2cd-a604-503b-9b81-0b31ab28e030 | note | Reference Documents - Quality Management Plan
e890054a-de99-5790-ba37-32aec96f139e | note | - - - - - - - - -
68a8fc13-7541-512a-963b-e326ea40beeb | note | Inspection / Test Method - Review Document
9cd372c8-6a1b-5718-9d05-811150a87d39 | note | - - - - - - - - -
078734c3-225a-5836-b525-21c3c1568398 | note | Record of conformity - This ITP
84fc9754-d0ee-526b-ba44-2a466151e8bc | note | - - - - - - - - -
a7f4a4d6-a83b-517b-be3c-4a7e6f02b837 | note | IP
6f7da54d-5cc6-5cda-b189-463130f53d04 | note | - - - - - - - - -
9c4b2538-8a26-5638-abab-5f07177e1b96 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Site Engineer
72fefe9e-daad-5f26-86c9-28fced0165ff | note | - - - - - - - - -
4892300d-1075-5530-8866-22eda6aa6ffb | date | Date Completed:
| checkpoint | 4.4 - Final Inspection
7ba7bc26-6e12-5266-806c-d5eecee9ed35 | note | Frequency - Each Lot
ad62c266-95e2-598a-ae4d-c0a91a765a0e | note | - - - - - - - - -
99670eb6-ec21-592f-9ea7-21169656007e | note | Acceptance Criteria - It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
ce71067b-aeef-5d02-abe6-721678b57fb2 | note | - - - - - - - - -
7fa0a4bc-6df1-5db0-af54-bedc795e4a6c | note | Reference Documents - Quality Management Plan
a69ecc9d-4d70-509e-a77d-2fe2def47c78 | note | - - - - - - - - -
07f8b19d-94b0-549e-8512-9c74d1bc8ce5 | note | Inspection / Test Method - Review Document
9eaf0010-a2d5-52c1-a812-29c08f84d632 | note | - - - - - - - - -
91626aca-9c5e-5c60-9db7-a1afa0bccb8c | note | Record of conformity - This ITP
25e2d672-6338-5e6b-a6b9-dbd131649de8 | note | - - - - - - - - -
e2f2e85f-02ed-56b8-b56f-c0a00ee93540 | note | IP
5a514f55-90ce-5600-a441-6ae45a1d02e9 | note | - - - - - - - - -
353f185b-7809-5995-9eab-a8fdaad25b62 | note | Project Engineer/Site Engineer/Superintendent/Surveyor/Foreman - Quality Manager
dad5bc38-cb82-574e-b9ec-6f84a4879845 | note | - - - - - - - - -
4441f733-fcbb-53cd-a65c-82ae1256dde8 | date | Date Completed:
| checkpoint | Final Inspection
fe45d8e1-bec9-5370-8296-123382a0c468 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
beb1187a-76dd-54f6-9a44-f4a8b0603d76 | textbox | Print Name:
9db0e91d-c423-5f26-b2e1-511ade7aa5b0 | textbox | Position:
982a105a-35df-59d5-84d5-9c588405e8dd | date | Date:
208ff665-d1c9-52f7-8d80-0c4d9c1fa5ac | date | Work Completed On
| checklist | ITP 0007 - Fill With Material Type A | itp | ITP-007-AX-LOT-XXX - Desc | 157354aa-edda-46f9-bf86-d614f331fe6f
| section | 1 - Preliminaries
| checkpoint | 1.1 - Check that current revision drawings are being used
83bf83b6-5313-54c6-bca9-bb217cb2ca37 | note | Frequency - Prior to Commencing
cdbd7dfb-03e1-587c-9f0e-15622cb5fa86 | note | - - - - - - - - -
afb73c94-ffe1-5ced-b0c0-5113432fff3e | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
813009c4-a4f4-58bd-b2b7-0c569e4ed7fa | note | - - - - - - - - -
4f6f0b3c-b3fa-5720-b349-f4d6f1d716dc | note | Reference Documents - Project Drawings / Drawing Register
a2ad2c74-dd2f-59a5-a55e-a57f96951968 | note | - - - - - - - - -
f24dcfe3-190e-5e4b-8772-001ee9910812 | note | Inspection / Test Method - Document review
f721a2e4-bb51-532b-90bc-d044963814d0 | note | - - - - - - - - -
3c760bab-682e-50c7-ae45-2dda767f6c6e | note | Record of conformity - Latest Revision Drawings
cfd356d3-38ba-5b24-80da-95f16f275ff7 | note | - - - - - - - - -
135d432f-7a4d-52eb-be19-f71d15883d85 | note | AP
5471accd-5218-516e-8e96-892c775bec37 | note | - - - - - - - - -
03d2321f-34d1-53a2-8861-988977c8176b | note | Responsibility - Site Engineer / Site Foreman
66b1b1a0-b9c8-55fe-b536-09971201a5c3 | note | - - - - - - - - -
5da60b87-28db-5a6f-ba3e-030b1811ff6c | date | Date Completed:
| checkpoint | 1.2 - Excavation Permit issued
cd690b8b-bdd4-582d-8978-fa077c7ed3b5 | note | Frequency - Prior to Commencing
15356cba-1d2a-55bb-ba1a-f6f294eaf3d5 | note | - - - - - - - - -
e7a98ece-d946-587c-8fa0-36230fec4440 | note | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
f24af4a1-ac6b-5e90-aa38-ca2f2a8e17fe | note | - - - - - - - - -
e786d3ba-8d82-5574-ba6e-1c9bf20d8970 | note | Reference Documents - Excavation Permit
c24885d7-6dc5-5b34-a663-b2cb2834a26c | note | - - - - - - - - -
6870c072-bca6-56cf-9b11-4f26e68c1b82 | note | Inspection / Test Method - Document review
8a717bd4-9617-5165-8ca2-52ac48a9202d | note | - - - - - - - - -
93f87df9-6109-526c-aec6-aa89ab631cef | note | Record of conformity - Excavation Permit #
3c883ee3-57ab-524d-9475-e28865b9912f | note | - - - - - - - - -
02314d18-ce56-5c07-8f15-763942ea235d | note | IP
db4d648e-d2f6-5615-8264-39278f41e2f3 | note | - - - - - - - - -
cd516425-fe21-5f4f-9367-3bba301506d1 | note | Responsibility - Site Engineer
aa4913b7-0287-598f-bf6c-3b264a284056 | note | - - - - - - - - -
2bde4be3-9d7d-513b-89a7-4813ad4111d8 | date | Date Completed:
| checkpoint | 1.3 - Type A Material Approval
d11ac373-50ac-51f2-b6f4-c18cf0b48791 | note | Frequency - Prior to Commencing
86e1f07e-3722-5bc9-ba2b-ba84e9825a14 | note | - - - - - - - - -
e6271a40-dca1-530e-9e7d-93ae504aaf0c | note | Acceptance Criteria - Prior to the import of Type A material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type A material complies with section 204 of the VicRoads Spec.
d48bd243-75f0-50a4-8d6e-413df7fc483b | note | Type A Material shall meet the following requirements:
5d3a1ba7-e4db-59dd-b7cf-c08cb0fb5032 | note | CBR ≥ 6%
aea6da92-b0ff-53e3-b601-61aae8c9c1aa | note | Swell ≤ 1.5%
42d8423b-8324-5d80-9cab-acca495012f9 | note | Permeability ≤ 5e-9
b10d6042-1eee-5354-8551-ba53cf0d231d | note | PI (LL) = 6 - 25
bfae04b7-2652-5710-b4b9-1e6f57e08ad3 | note | PI x 0.425 passing ≤ 1000
5fa7708c-7db4-5f01-a90a-6bd99dd58e3e | note | Grading:
a24133fd-0432-5491-9ef0-0175aeb01b1a | note | % passing 75.0mm sieve = 100
05eec73c-612f-5a6d-891b-6d067f8fad94 | note | % passing 4.75mm sieve = 40 - 80
c54a1ad9-d509-5234-bf1f-3c21f06b77fa | note | % passing 0.075mm = 10 - 40
aadd8fe7-5b77-5fcd-8669-1028c79f7f22 | note | Attach: Test Certificates, Delivery Dockets
ce4dcf11-03a9-5dd9-9cdb-170a8d1ccc7d | textbox | Teambinder Approval number:
31383765-1cc5-50ba-b2d0-672f3a83d064 | note | - - - - - - - - -
97f2fe52-af66-5260-b495-acea3f541302 | note | Reference Documents - Project Specification
a758b953-b726-5167-a111-cd6ca979c5c0 | note | Cl. 3020.05
bfe1240c-6059-5e14-ad67-087bf24c33bb | note | VicRoads Specification
31868038-4628-5bc7-958b-37607f10ff0f | note | Cl. 204.04(b)
2c85c4c0-5cd4-5037-b214-d655a474b879 | note | Cl. 204.06(c)
0df5340b-60ea-569a-9a57-f840904bc84f | note | Table 204.041
e24dc910-263b-5f88-a70a-ce08a24987c3 | note | - - - - - - - - -
ba5e0493-bacd-5a33-b7fa-0740e22ca458 | note | Inspection / Test Method - Site Inspection
7a65263e-ee0d-584c-b8d9-b342384618fe | note | - - - - - - - - -
6247e5c9-b059-5dba-9330-584072a25771 | note | Record of conformity - Teambinder Approval #
7089d272-60cc-5b0a-bb41-d2152cbe9ba8 | note | - - - - - - - - -
455e4bd7-a48b-5de2-bb50-66d313096f9e | note | HP*
a6a61373-0a55-5de3-b176-66513ab2e35e | note | - - - - - - - - -
e3c86d6e-7cc2-584a-bcae-7a9391b2be5e | note | Responsibility - Site Engineer & Superintendent
55b68f2f-62e4-5cf8-b3af-b2d296a4fa1d | note | - - - - - - - - -
60dc1f6a-1830-5d36-8e21-4678e2f5e4e1 | date | Date Completed:
| checkpoint | 1.4 - Review of Subgrade Test Roll
6e52faff-e5a2-5346-932b-26fa409d23cb | note | Frequency - Prior to Placing fill
59576aa3-9f3b-5dc8-8dc6-8730703fefa5 | note | - - - - - - - - -
17e7e24b-7381-55b1-92d3-243fecfe7943 | note | Acceptance Criteria - No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
56ad90b1-5473-5f87-9ffd-84544b04702a | textbox | Subgrade ITP Number:
134bfa0f-c1b3-50ef-9327-69311d65f903 | note | - - - - - - - - -
23f2a6f8-595d-5464-b94d-2e30f23eb95a | note | Reference Documents - VicRoads Spec.
35f49d8f-cf44-576d-90a4-7f7618f4af9e | note | Cl. 204.12
8539dc0c-eeda-52d8-a2d5-c9069fcfbccf | note | Cl.173.03
7518ded3-9855-51f7-9cb2-76bece985676 | note | Cl. 204.10(b)
94cc2bc0-80b9-5429-8968-1ebef5b7351a | note | Cl. 204.07(d)
9ff624c7-99e7-536c-b3c4-740fef20a5fc | note | - - - - - - - - -
e4f0d795-3124-5120-9685-bd46aa964507 | note | Inspection / Test Method - Site Inspection
08d98833-acbe-59a7-ba09-364712972ea1 | note | - - - - - - - - -
e15a9169-8af2-5caa-976b-717e1fca1c65 | note | Record of conformity - ITP visually reviewed by Engineer
ea76d49c-e151-528d-9d56-34ec936705f9 | note | Signed ITP
a63f2975-67bd-539f-b1f8-bde363edfad6 | note | - - - - - - - - -
f74e1c4b-382e-5d07-b8ec-c37523ad6217 | note | IP
6238300d-7553-5b79-a24a-279418e3ac9b | note | - - - - - - - - -
c6a3e715-f802-57c4-8b77-c4bd06c70b70 | note | Responsibility - Site Engineer & Superintendent
f20f5960-a8d4-5d2d-8cd9-65b60c6df350 | note | - - - - - - - - -
8aabd1d9-3efc-56ee-94e3-fc0525ed6a96 | date | Date Completed:
| section | 2 - Fill Activities
| checkpoint | 2.1 - Survey set-out
8570b0ce-897d-5e74-b27f-d7205411e9a6 | note | Frequency - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
b4a4ceca-930b-5042-927f-b3954737281c | note | - - - - - - - - -
28fd853d-b297-5560-aa9b-8cbf8268e5be | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used. The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line.
1e995fd2-3af0-5fc0-b1c3-4dd88af4d1dc | note | - - - - - - - - -
32604506-a4c7-5037-952c-d0e77b25e1eb | note | Reference Documents - Project General Specification Cl.1190.06 Latest IFC Drawings
7e57c400-7e25-534f-b22d-ae10ace35be0 | note | - - - - - - - - -
dd70dda4-31bf-56f4-a0c8-90494fca5378 | note | Inspection / Test Method - Site Inspection
49f32e1a-cb7f-52eb-8e9d-56812724fb3d | note | - - - - - - - - -
b4c24f1b-6299-5795-8689-c576abe44f3a | note | Record of conformity - Survey records & pegs on the ground
4145dc91-983b-56c0-957f-ff0bab870694 | note | - - - - - - - - -
d239827b-a749-5fa8-8505-cf9ccfa7d22e | note | SCP
ade66612-df92-592d-80d0-0abb7f0a9362 | note | - - - - - - - - -
9aa871b9-bc33-5b04-9369-a2a1ea61e9e5 | note | Responsibility - Site Engineer & Surveyor
94438e71-0f19-514f-998c-70602f4a1a26 | note | - - - - - - - - -
fc9d927d-6c32-5ea7-a620-5a5650747a59 | date | Date Completed:
| checkpoint | 2.2 - Placement of Fill
521d4940-230d-52eb-84f0-84de30011331 | note | Frequency - Prior to Fill
9f4dbabf-88e0-5c40-89b3-4c37ce641d18 | note | - - - - - - - - -
7220a2ef-8779-58f3-9902-cdd83028f59d | note | Acceptance Criteria - Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Layers with a compacted thickness >200mm may be placed subject to approval from the Superintendent.
ddb78c05-cbd6-58c9-8c58-ab5b47438584 | note | Each layer shall be keyed in to the layer above by means of a textured surface
1c4c78c9-4d98-5870-b480-149c132423d0 | note | Any rocky material present must be uniform throughout the layer.
42d12f43-7823-55eb-b8c7-4d62bf0d9302 | textbox | RFI Number:
97daf980-d04c-560f-b0ff-32ce0ee7b5a4 | note | - - - - - - - - -
1f631b1b-020f-5ca2-beda-fe55f4b68049 | note | Reference Documents - VicRoads Spec. Cl. 204.10(d)
34eb497c-7f42-53fa-9fe0-fc9d2f6b3d2b | note | - - - - - - - - -
799dbeb2-3e95-5749-80c9-ce618c1108b9 | note | Inspection / Test Method - Site Inspection
76edaef3-548f-5653-bac9-81d109045964 | note | - - - - - - - - -
e33b007a-c707-5c06-8481-dfecd2b145b4 | note | Record of conformity - Signed ITP
a5af0ab8-2613-58a1-afc8-7d5b090fbb65 | note | - - - - - - - - -
2ca1ecbf-3639-5900-92cf-77fcd9885834 | note | HP*
e7fe6a17-cbe2-56b1-808a-4d392cf0e208 | note | - - - - - - - - -
97b1d149-875c-5942-bb7b-fdb118cf1f62 | note | Responsibility - Site Engineer
f7bc22d1-4540-5032-a356-1e1c1293a7b0 | note | - - - - - - - - -
3d2073ff-c6aa-5f46-b5ac-325b376a9cf3 | date | Date Completed:
| checkpoint | 2.5 - Preparation of final surface
36a66939-323c-5b98-88d0-a988ae468bf4 | note | Frequency - Prior to placement of next layer
a94ebf57-f90d-522a-b3d6-d1b6a23a7e27 | note | - - - - - - - - -
7276807a-06a4-557d-82b6-4f41bc3ffac4 | note | Acceptance Criteria - The level tolerances at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
60ed2202-0d66-5d5d-b978-6f2ced0d5021 | note | Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings
f1f6b5f0-41b7-5c05-947d-2f3b3cd63cd1 | note | - - - - - - - - -
0cb23375-1f58-57be-b2ab-9e547036b02f | note | Reference Documents - VicRoads Specification
95ac1ecb-3954-592b-9c23-bdc503c9e93f | note | Cl. 204.15
95ff81d8-985f-5c0d-8512-6abd8030a564 | note | Cl. 204.03(g)
ad9b631f-5047-519d-88ee-66305fbfabc9 | note | Cl. 173
8366c479-429a-53d1-8d30-87065191af1d | note | VicRoads Specification Table 204.03(f)
952acc90-188f-5e4b-93ef-cfecffc8add4 | note | - - - - - - - - -
32afc82c-507a-57de-8c75-46477b4d20fc | note | Inspection / Test Method - Site Inspection
881f2024-c751-5b35-a675-767ad1ed19e2 | note | - - - - - - - - -
90926b15-a221-55c9-857f-64e02294dbd3 | note | Record of conformity - Signed ITP
888e708e-676f-52e8-b4e8-a1e4440c3343 | note | - - - - - - - - -
5c2759ed-64a3-5234-a7d1-ba5815539da6 | note | IP
f890e337-a2f3-53ef-97b3-9bbb4fa5df23 | note | - - - - - - - - -
6f2215a9-0230-5d07-82b9-d160315497d1 | note | Responsibility - Site Engineer
579332e4-5365-57cc-994a-8ab5b3c540c8 | note | - - - - - - - - -
2d57878a-18c3-5e57-bf01-0ecf92359fa1 | date | Date Completed:
| checkpoint | 2.7 - Proof Roll - Top of placed layer
629a0dac-7478-5202-bbee-1084ecf0d2d8 | note | Frequency - Proof Roll - Top of placed layer
34bca4cb-8873-53c7-af7c-05ef9d276a9d | note | - - - - - - - - -
41411319-d3d0-58a1-8845-8570d7a8f95a | note | Acceptance Criteria - Superintendent to be present during all test rolling.
ae97efb5-fb27-5df6-b88a-4e39fc819a4a | note | Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling.
2d063e62-da54-5f23-b3a7-e4f29ef2621d | note | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent.
9851c363-f837-5760-b3bc-01a143f003c2 | note | Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review.
a1d4049f-5af5-5c61-a049-5ee31262b9f7 | note | Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
0878e10b-cd05-52de-969a-86931852e096 | note | - - - - - - - - -
79dec4b7-889e-54f7-a0c2-45a780a3e78c | note | Reference Documents - VicRoads Specification
3683c44c-6a8f-5826-bfa6-802f6b2ab357 | note | Cl. 204.12
d3f5929b-78fd-58a6-9514-bcea7bbcfee3 | note | Cl.173.03
79214783-cbe3-5612-92ba-29ee1a837f30 | note | - - - - - - - - -
403c111a-efc5-5e45-bc68-bb36dffa52d8 | note | Inspection / Test Method - Site Inspection
6d696017-6cdd-5c0f-923f-5f119e433175 | note | - - - - - - - - -
c36bdbdf-04a5-54b8-9633-4507d0d1fd36 | note | Record of conformity - Proof Roll Form signed.
7843a348-6257-55be-8188-bede13bb65ff | note | - - - - - - - - -
3f2b9785-5f87-50a0-8a7b-68c8c4e54d4c | note | HP
2e749f51-6560-5db6-b3e5-04273632baf0 | note | - - - - - - - - -
c5bf3b75-2973-539f-a587-c432e0b4fe0b | note | Responsibility - Site Engineer & Superintendent
b83dde77-11dc-5f15-b0a9-ad55474268fd | note | - - - - - - - - -
ae7b27b3-e253-5791-b6aa-3cdce97f4bde | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Post-compaction Testing
1600cf48-d409-533e-b136-a7f503f5d0ad | note | Frequency - Post-compaction Testing
e4a81ef8-08ae-5a26-ba4c-5e61062aa3b7 | note | - - - - - - - - -
c44b585d-926a-5f95-b9e3-1acfb80aaca3 | note | Acceptance Criteria - Type A Material shall be tested for the following:
bf944f1c-282d-53cf-bbfd-4cae6268967d | note | Characteristic Density Ratio ≥ 99%
cf13c945-83b9-55c1-9b77-376603642a35 | note | CBR ≥ 6%
7c24a723-7397-57e9-bf48-44d919e3ece1 | note | Swell ≤ 1.5%
7b1b7067-80db-539c-97c5-ce63bbe560ea | note | Permeability ≤ 5e-9
60a4c7ba-cad4-571d-a75e-9a114ba57a93 | note | PI (LL) = 6 - 25
c119a248-3286-5141-bde6-ec26cb126abb | note | PI x 0.425 passing ≤ 1000
e0c573bc-3287-5fcb-b8f5-712dfa14de85 | note | Grading:
c294ad31-810c-504a-8789-484538a90c0e | note | % passing 75.0mm sieve = 100
a5a0d604-d32f-5cf4-82d6-51e3994218f2 | note | % passing 4.75mm sieve = 40 - 80
34e7c92b-8ddd-58a4-b742-de1fbe54fa6f | note | % passing 0.075mm = 10 - 40
ee15df3a-0ff0-5862-a9a0-9a151bd7c76d | note | Subject to approval min frequency testing as follows:
49d10102-1672-5c5d-b96a-3ba7ce0ba34b | note | Compaction & Moisture: 1 test per 2 lots
056b3e52-3325-56f9-983b-e0507c20b3df | note | CBR & Swell: 1 test per 2 lots
7074bfff-04f6-57be-95e9-5fcacb2cc9a9 | note | Grading: 1 test for every second lot tested for compaction
266bba19-9b02-5d66-8f3b-a2b366627a09 | note | PI (LL): 1 test every 4 lots
3727b5ab-dfa9-5348-a02e-acd05365a647 | note | Permeability: 1 test every 4 lots
f65d6495-4c90-560c-94da-d16fcca5ec5b | note | Attach: Test Reports
4d64320f-3ebf-5318-ad56-31c1594ec4d6 | note | - - - - - - - - -
b5b7eee0-b440-5119-b05d-ff47d1b8ac93 | note | Reference Documents - Table 204.131
16f33654-71c6-58d3-9a24-fcaf7bb50153 | note | Section 204.13
249b2afa-cd10-521e-a3c2-7d0824588d5e | note | Section 204.14
2377c77e-7ffe-55d5-9276-0927bd3c2a11 | note | - - - - - - - - -
6374eac9-9426-5fe5-9d31-9bc42e970f79 | note | Inspection / Test Method - Site Inspection
037b1983-6835-5997-896b-efd3bfcbc248 | note | - - - - - - - - -
dea53898-1801-5b8c-af4b-0b542c88b876 | note | Record of conformity - Attach Test Results
6e0d74b9-d7ab-5460-b259-b7e62723f324 | note | - - - - - - - - -
f42d33a1-e85c-5f8c-98cc-4d9a1009b77e | note | TP
cc8ee653-861a-57ab-a29d-188c44582fc0 | note | - - - - - - - - -
7cb25fb5-ef14-5659-aade-040853d96bbe | note | Responsibility - Site Engineer
3e47ce3e-1375-5d67-a979-007b95059d5d | note | - - - - - - - - -
a676bcb9-f14e-5e4c-9a4f-7db7961bfe8a | date | Date Completed:
| section | 3 - LOT Closeout
| checkpoint | 3.1 - Survey As-Built
c3ebb6d2-1528-51b9-9e4b-bd753d82b0a0 | note | Frequency - Each lot
dfed8f42-1b18-5472-9503-4dd349c05047 | note | - - - - - - - - -
de197211-34b8-558f-91f2-19585627d382 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
fa67f69b-be3c-5b8f-a5e9-718214a40664 | note | Scale A:
45be3e26-a0be-529a-9f8c-a59d0a6a1819 | note | Min. No. of Measurements Per Lot: 80
c2ad4a3b-8d2b-564c-aab9-4f365ac651d2 | note | Range x (mean) = +5, -15mm
24969940-e89c-56e4-95b3-48aa0868c1f9 | note | Max S (Standard Deviation) = 12 mm
647d3971-e6f5-5a31-a2c0-9fff2ecac3e7 | note | Attach: Survey As-builts / Survey Report
9e05c90d-247c-5460-a663-29498a480b2e | note | - - - - - - - - -
2b79f704-cfc6-5df8-8116-2b346b961250 | note | Reference Documents - Section 204.03 (h), 204.16
bb400183-5c53-5637-9e15-b57956972bb4 | note | - - - - - - - - -
ba2e00a5-865a-5f42-baac-0720177099c9 | note | Inspection / Test Method - Review Document
37c45d09-d78e-561c-a330-9ee732267f8e | note | - - - - - - - - -
c3f13828-52e7-585c-acbb-3bff7e59e52c | note | Record of conformity - Attach As-Built Report
e4c9389e-408a-5f87-89fd-7fd3344b89ef | note | - - - - - - - - -
877829e6-d176-5d70-ba69-6d892812b242 | note | SCP
7a8cebdc-5880-5638-9251-001ae02aa03b | note | - - - - - - - - -
25dfee29-5062-5025-acde-5f9f97024768 | note | Responsibility - Site Engineer & Surveyor
f9cc090b-7c5b-50fb-8b4d-1a7cd438563b | note | - - - - - - - - -
00590504-c9ce-5cb6-9e02-53ae93804cc3 | date | Date Completed:
| checkpoint | 3.2 - Non-conformance Closure
bca8cee7-b2bd-541d-a266-14ead3ac4065 | note | Frequency - Each Lot
cf9a2439-604d-5286-8385-251081b88643 | note | - - - - - - - - -
04d768b5-1fd9-5cab-a31b-c51f6ea90f98 | note | Acceptance Criteria - Ensure All related Non-conformances are recorded and closed out.
9d10d40f-05cd-504d-94f6-4e57aa27eb4d | textbox | CAMS Case Number(s):
11f102a7-f81b-52b1-80d0-98a31104cf71 | note | Attach: Closed NCR Report
7d86770e-40ab-5358-b800-5a7b91a3654a | note | - - - - - - - - -
d749b54b-9d83-594c-82d1-0debe2c972a7 | note | Reference Documents - Quality Management Plan
3f822681-e60f-53e6-81f7-e718b2072f55 | note | - - - - - - - - -
e635094c-4b47-517a-a0e7-3b76292f59c2 | note | Inspection / Test Method - Review Document
a67f60ff-8108-5fa5-aa26-82d824a4cfa7 | note | - - - - - - - - -
33285110-e613-5c0d-ba01-6ae9910846e2 | note | Record of conformity - This ITP
8f9f1e54-26e9-50bc-bc60-66c3ce900ceb | note | - - - - - - - - -
3e0a6302-ea0a-5810-b8e9-ab467fa4df80 | note | IP
60bd3e85-5d65-555a-946d-65e9a7086e4e | note | - - - - - - - - -
54803571-8cd6-5acb-bf9b-c64f35a4896f | note | Responsibility - Site Engineer
46244b3c-596f-5e73-a387-d1682a005124 | note | - - - - - - - - -
b7666894-de23-53e8-b494-228a1bdb9bed | date | Date Completed:
| checkpoint | 3.3 - Red Line Markups
358f17e3-0627-53c2-b268-81b75c321b8c | note | Frequency - Each Lot
9a076d2e-4e61-544b-a9b0-fc1041e6bf0b | note | - - - - - - - - -
c51b788d-dedc-5c7d-8dd5-e0d8bcb0bdee | note | Acceptance Criteria - Ensure any changes from design are captured in red-line markup drawings
745ce23d-c573-5d4e-acdd-78abd0abfbef | note | RFI References
e51b6f59-f9ef-5a77-b9cc-19695c0b06cf | note | - - - - - - - - -
17fb19d2-b8ec-5736-b13e-5ffaea7b2283 | note | Reference Documents - Quality Management Plan
9074e078-048e-5bdd-a4b6-b4643af3f103 | note | - - - - - - - - -
2fd7b5e1-9f6d-5d11-a1c2-2abe8d897408 | note | Inspection / Test Method - Review Document
b3ab5612-bdb0-5167-af9e-8737b097bbbb | note | - - - - - - - - -
5749580b-d514-54ae-99b8-7bee3cb110c8 | note | Record of conformity - This ITP
e78811e0-8abb-578b-9998-38f8f9927461 | note | - - - - - - - - -
23c951b9-6a82-5013-8346-8255359d657f | note | IP
1d599f63-4757-551c-8d15-747e6f9fe908 | note | - - - - - - - - -
c9f1f2f2-7440-5a30-96c5-009784a7f74c | note | Responsibility - Site Engineer
ee52bb9c-be82-51e2-8a58-a5305f229aab | note | - - - - - - - - -
61d3a786-566c-51de-b9d7-8eff6b878fed | date | Date Completed:
| checkpoint | 3.4 - Final Inspection
febe7265-73cd-5943-8792-5505585fed14 | note | Frequency - Each Lot
7d4c4d43-2e48-59f4-8c77-0289a7d9326b | note | - - - - - - - - -
b23f01d1-d427-5433-836d-80f6f910b0c9 | note | Acceptance Criteria - It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
18d4a835-5da8-55df-8003-d797a3ed6541 | note | - - - - - - - - -
c77d48f2-bfb9-5343-aaa0-fb0655d264df | note | Reference Documents - Quality Management Plan
38ba96b3-a4e8-578b-b6a9-658d2b6ebd53 | note | - - - - - - - - -
626025e8-239a-5a98-aed0-a190c080ee4a | note | Inspection / Test Method - Review Document
7edd147c-e632-54e5-b946-11a5062fc9f1 | note | - - - - - - - - -
92439361-bd2a-57a7-8f75-d1ec0e146196 | note | Record of conformity - This ITP
1692b4d8-a698-5e33-a792-8bee5a0ead02 | note | - - - - - - - - -
5b14fa86-578c-56ac-95db-07fb3ce24535 | note | IP
8ad9b5b5-6858-5a5e-8790-5bb4f566bcb1 | note | - - - - - - - - -
8e07488e-37d7-54a5-9c1c-2a40c26337c3 | note | Responsibility - Quality Manager
c1f2655a-bcfb-5918-b2f6-ee3e6f66f15a | note | - - - - - - - - -
601e5faf-e1d2-54a5-a1ce-599e96806d3d | date | Date Completed:
| checkpoint | Final Inspection
1a07f000-d067-5d03-9800-9b60056ff94b | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
6cbf7655-1316-581c-8b00-915bb53e0ed9 | textbox | Print Name:
c771afb8-ba5f-5030-b1b7-ead3f43f1055 | textbox | Position:
cf106833-0ed9-5389-9cd6-b6a3d7149842 | date | Work Completed On
d094b1ba-67fd-5a25-84e5-c80309ef80a1 | date | Date:
| checklist | ITP 0009 - Unbound Pavements | itp | ITP-009-AX-LOT-XXX - Desc | e44afadc-bff3-4d47-8ccd-48323eccced5
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
155fecea-b516-51a3-bff5-c857e0687a31 | note | Frequency: Prior to Commencing
0cd76498-d71d-5adb-ad11-37880d18a3da | note | - - - - - - - - -
3305cc29-bb8f-5fa5-bcd7-83cf6c5bd537 | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
b0e57b3b-1228-5560-a1c0-7efc5ab8f668 | note | - - - - - - - - -
93b1b75a-fc43-55d7-b91f-4edf8217e8fa | note | Reference Documents: PMP Inductions Register
fe92ced2-a032-581e-a84a-cf74d83694a1 | note | - - - - - - - - -
754b62c5-597e-56db-85b9-41e3eaa6b034 | note | Inspection / Test Method: Document review
5d1456eb-5246-5ba3-81c1-b704901efb31 | note | - - - - - - - - -
234a4a93-4321-591e-ab48-485345714764 | note | Record of conformity: Site induction signed.
8a3eac3c-c7cd-5c8a-aa2e-3451c7801ee4 | note | - - - - - - - - -
ee89da63-37f3-5895-aa34-43218a9462bd | note | AP
1239ba0c-54f2-56f9-8f53-be191f0e193d | note | - - - - - - - - -
f93d0ed2-402d-5c56-b5e2-9f94b9d87fbf | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Check that current revision drawings are being used
7275c377-46f5-5c59-8a6f-6ce6074a49f3 | note | Frequency: Prior to Commencing
bdf806b2-0cbb-5754-87ab-89d4b6383098 | note | - - - - - - - - -
13f151f2-0c8e-557a-a036-e77de3310c6d | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
e9f39d34-9020-5aaf-9f71-72a0338911e9 | note | - - - - - - - - -
ab9d4ebe-7764-574a-8110-2e96db93ad5f | note | Reference Documents: Project Drawings / Drawing Register
27cb3298-2c0f-5f1a-8767-8d5832cbdf92 | note | - - - - - - - - -
504f68e7-3f08-5f03-b7e9-3813f1b88161 | note | Inspection / Test Method: Document review
13707d7d-1c26-5c9c-841a-be6eae5ebaf4 | note | - - - - - - - - -
e4c9adc3-deb0-503b-85e6-0dace6098e7c | note | Record of conformity: Latest Revision Drawings
2afac19b-9f6a-512d-ac95-48d0df890357 | note | - - - - - - - - -
169b6ac1-e76e-5812-8740-3c03481a8016 | note | AP
b79dcbe8-13db-5789-aaa9-863810a58b2c | note | - - - - - - - - -
2da345af-cc08-54da-9d78-ec26ffdadc36 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
f9510fd9-d8a3-51cb-86f7-a94844ef3bc5 | note | Frequency: Prior to Commencing
38222f77-248c-5c31-b008-49766ad68164 | note | - - - - - - - - -
177541fe-4697-53c6-ac6b-4a989cb9511f | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
ad7c4292-4ff5-5005-bcfb-74b0a1150e11 | note | - - - - - - - - -
cf111375-3936-577f-89aa-2ab39db3e02a | note | Reference Documents: EMP, Site induction, Project Specification Cl. 1200.03
8a6cad2e-f902-5cf9-9e45-f1c1dc00089c | note | - - - - - - - - -
a768a14c-62f1-5f70-92aa-46ccf9388411 | note | Inspection / Test Method: Document review & Site inspection
61e2704e-2c8b-5f2d-a61b-43272e434c6b | note | - - - - - - - - -
7360990f-0b31-5ec2-8bbc-8d5c6689fd36 | note | Record of conformity: Signed ITP
9d6395c1-d146-50db-85ed-19b74994b75f | note | - - - - - - - - -
0e8471a6-0ea6-535f-8793-af4d84aebee2 | note | IP
c1055175-995d-5c63-bf5c-e61058b1956b | note | - - - - - - - - -
a72b719d-4a1b-5243-ad95-e35a82bb7a62 | note | Responsibility: Site Engineer
| checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
3a6b08ca-dea7-5387-a19a-d0084eb9d5da | note | Frequency: Prior to commencing
2b7ed412-119f-57c0-aa13-3373b08b0dff | note | - - - - - - - - -
f5ea5692-35b8-5b58-a72e-c3763413ee08 | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
c58bd600-d51f-5747-90f3-fb809d5d335c | note | - - - - - - - - -
de05973e-a1ae-58d6-8733-e0fd598329a6 | note | Reference Documents: Project General Specification Cl.1125.07 Health and Safety Coordination Plan
5bab0d7d-3f04-5d7a-b581-512ec20d488c | note | - - - - - - - - -
c559ed95-fe1e-5c64-9cea-a5b22ca34c53 | note | Inspection / Test Method: Document Review
0a499822-1673-5663-b360-5917ea507332 | note | - - - - - - - - -
a6b20431-0bd1-589f-a188-ebbc47eed4a6 | note | Record of conformity: SWMS(s) signed
0a2a935b-1a34-5080-b1e8-9961c072f903 | note | - - - - - - - - -
9176df7f-8086-5e58-8368-20b8ec6008ef | note | HP*
0f7d056a-494d-5396-aeb8-40541d21bac0 | note | - - - - - - - - -
d4cfd172-fcbe-592c-831a-af1b892eaa8b | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Crushed Rock Mix design
ba9d7dec-41ed-54ff-a99c-72eacfe1f9fa | note | Frequency: Prior to Commencing Work
fe5bd6d9-c5e7-561b-8f4a-2493c388c3f5 | note | - - - - - - - - -
4cd8e562-40a0-5ab8-97e8-cf18a42d3de8 | note | Acceptance Criteria: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
21bb1c18-01db-586c-b20f-1313ac31a18e | note | - - - - - - - - -
c35675c1-5f0a-55ee-9375-3c75f870432f | note | Reference Documents: VicRoads Specification Cl.812.04
6dff1c43-da97-5853-b856-357e16db30c0 | note | - - - - - - - - -
d016fcde-748b-56a0-86fc-d94177738e8d | note | Inspection / Test Method: Document Review
0ffd2867-3591-5ce7-8e05-81335564ac14 | note | - - - - - - - - -
acebac35-e25e-57a1-83b3-7fc2469b9011 | note | Record of conformity: Mix Design VicRoads Approval
f7a924fa-64f6-536f-86c7-a7045c776cbb | note | - - - - - - - - -
aecd8dad-ce23-55be-a7a6-1079010dddf9 | note | HP
cdc89a5c-33ae-5206-b961-3c36498e8417 | note | - - - - - - - - -
1da7f209-cc8d-5e9b-8263-20955b18437f | note | Responsibility: Superintendent
| signoff | HOLD POINT AUTHORITY
| checkpoint | 1.6 - Excavation Permit issued
461436a5-a44b-5f68-9d4b-81f4edd5d086 | note | Frequency: Prior to Commencing Work
8d61249e-f2eb-5afe-b216-e7de23fa53d0 | note | - - - - - - - - -
404309d4-03f2-5131-afa1-e26d15385b21 | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
212fae2b-f96a-598e-b4e0-09bd221e6feb | note | - - - - - - - - -
7866ced4-df1a-5299-80ce-5bff610a2519 | note | Reference Documents: Excavation Permit
7f06400a-280a-5689-ab01-78668d22b7a9 | note | - - - - - - - - -
c96503e7-1e2c-5275-9daa-e966e4fe9180 | note | Inspection / Test Method: Document review & Site inspection
ad0af753-955e-530c-b083-2dc7b6a1c4a6 | note | - - - - - - - - -
c02eddf0-71a8-5c3c-b81e-c30b65a528cd | note | Record of conformity: Excavation Permit #
d897fe5b-1ef5-5393-ac70-39f2a1d48fe9 | note | - - - - - - - - -
ee0624db-aeb3-5448-b8cf-3538d88ddd6f | note | HP*
10c5c365-e24f-5b67-b60c-13ff02c3f7fd | note | - - - - - - - - -
0f189fe0-7923-584a-be41-e4301b1da09f | note | Responsibility: Site Engineer
| checkpoint | 1.7 - Traffic Management (When required)
421df136-1fd8-53ec-b56f-abce9705086a | note | Frequency: Prior to Commencing Work
59815c68-619f-5fa4-b307-b63ff6d1be7a | note | - - - - - - - - -
30615eda-f483-5343-86fe-5b9374a9dcb4 | note | Acceptance Criteria: Approved TMP and MOA
823ce0c4-7bf1-54c2-9189-feb34f0db5a8 | note | - - - - - - - - -
23679220-32e1-5f10-8a31-0fd4be8592dd | note | Reference Documents: TMP
96fc4f24-b5fd-5f33-98bf-c59a5b363e99 | note | - - - - - - - - -
4eb478a4-13c9-5e98-8e49-2d7f5ffb0d95 | note | Inspection / Test Method: Document review & Site inspection
61199d88-023d-5771-99c4-db511c426d1d | note | - - - - - - - - -
f5e2272e-79c3-5af3-834c-78d450df5558 | note | Record of conformity: Approved TMP & MOA
990e3c78-7b4e-52a6-9400-132ef6dbf9d5 | note | - - - - - - - - -
7811c2e1-880a-509b-9db8-b1cc0815f7ab | note | AP
0b8d8413-3273-53c5-8f64-b2f07f168879 | note | - - - - - - - - -
f90965a0-f920-5dc2-9bb9-d7359c7e0dad | note | Responsibility: Site Engineer
| section | 2 - Placing Fill
| checkpoint | 2.1 - Transverse Joints
33ac20bf-00f8-5bef-a992-f626fb4974f9 | note | Frequency: Check prior to placing material
fd805a08-b2f1-5c5e-ab69-f71955b24715 | note | - - - - - - - - -
ca0214fd-12ab-5130-8231-ae9fc4481b63 | note | Acceptance Criteria: * Material should be spread to minimize number of joints. * Transverse joints shall be offset from one layer to next by not less than 2 metres * Transverse joints shall be offset from one layer to the next by not less than 2 m.
9c6f39ca-7fd7-5597-8fb1-093988a5ecf4 | note | - - - - - - - - -
b28ffcda-a74a-52f0-83c7-cb31d9689980 | note | Reference Documents: VicRoads Specification Cl.304.07 (a, b & c)
ec81b593-fffb-5cbb-ae3c-a8fb5198e30a | note | - - - - - - - - -
2d0afae8-08a3-55d1-9c25-fe90e6be6fb7 | note | Inspection / Test Method: Site Inspection
3a12e153-d23b-5cd1-a2bc-31c9ba9c589e | note | - - - - - - - - -
33770eae-73ac-522e-9bae-2cb46fef7a8d | note | Record of conformity: Signed ITP
5b9c46a5-9202-5485-9b32-aceec9ec822a | note | - - - - - - - - -
16df53f7-1a11-5b70-af85-6be5ef5fa5ff | note | IP
705ec533-5651-5697-8e32-bbe238364d21 | note | - - - - - - - - -
3bd88636-8974-54ae-b557-cf53ef24af09 | note | Responsibility: Site Engineer
| checkpoint | 2.2 - Longitudinal Joints
1e403ea1-a9aa-5f54-9d4c-faee0585e0c4 | note | Frequency: Check prior to placing material
e8ee5c60-97e8-57df-b66e-9b75a45b233b | note | - - - - - - - - -
204f4747-18c4-585c-8a92-644ebe220245 | note | Acceptance Criteria: * Material should be spread to minimize number of joints. * longitudinal joints shall be offset from one layer to the next by not less than 150 mm. * longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
d765c6e9-32d5-5dcb-9f5c-c3cc7351ca4a | note | - - - - - - - - -
eabc172c-1821-5f50-a1f3-f265388cb2e1 | note | Reference Documents: VicRoads Specification Cl.304.07 (a, d & e)
cdee0f9f-b1df-522e-a58b-53f78c371f3f | note | - - - - - - - - -
8dbcb750-aac8-5cc8-b301-11fd634803c2 | note | Inspection / Test Method: Site Inspection
b8652e51-4547-5215-959b-396cf3c187cd | note | - - - - - - - - -
36ad6514-df90-5c88-9c6f-cb741dd06053 | note | Record of conformity: Signed ITP
ef770102-8070-5b68-a7be-1295a080d307 | note | - - - - - - - - -
3aa10ef3-f332-51a2-a154-51a9e9a661b0 | note | IP
b9df3a3f-b6c0-5c44-bee6-d9f313fff857 | note | - - - - - - - - -
ef60c3ae-4fcf-582e-bf83-30c4f8924ecc | note | Responsibility: Site Engineer
| checkpoint | 2.3 - Lot Size
647bb5db-6f21-5118-bd80-41ff0eb4e9df | note | Frequency: Check prior to placing material
21b8b527-1c31-5d9a-99b1-68ff74a8b7df | note | - - - - - - - - -
2577976a-b5e0-5887-82b8-60b593340f16 | note | Acceptance Criteria: A single lot shall be considered a single layer of 4000m2 or one day's production in a single layer, whichever is lesser. For pavement construction, any lot that has a surface area less than 500 m2 may be treated as a small area and tested in accordance with Section 173.
fffdf6c0-1429-50ac-8a29-52dc6917723c | note | - - - - - - - - -
ec2da191-16c3-5087-96bd-ebe02654a096 | note | Reference Documents: VicRoads Specification Cl.304.08 (b)(ii & iv) Table 304.111
76ddaddb-45f6-5586-8bd8-8e71a2833c20 | note | - - - - - - - - -
e38230a3-1a13-56be-9a03-028ab69d591c | note | Inspection / Test Method: Site Inspection
98afb2d8-82f0-5586-a210-5d2ce33a1f7f | note | - - - - - - - - -
a18c1899-4aef-587f-85c7-f28de257ea91 | note | Record of conformity: Signed ITP
9fffd593-8058-55e6-93ec-a0aafd139415 | note | - - - - - - - - -
37bbb6fa-7655-578b-8322-deaa81f976a7 | note | IP
d3446d84-e10b-5010-a553-b54ddc51fcee | note | - - - - - - - - -
588cb4b5-2b96-579d-ae15-5de01f510a4a | note | Responsibility: Site Engineer
| checkpoint | 2.4 - Proof Roll
2f7ac211-1969-5356-983c-53ceb410b081 | note | Frequency: After placing material
909a1957-73ff-5651-bef7-276d22785b57 | note | - - - - - - - - -
6725b2c7-9f6b-556c-ad4a-f57ed95f5009 | note | Acceptance Criteria: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
bfd11b81-5db5-5029-bf0a-227e80acb895 | note | - - - - - - - - -
cd39026d-0a0e-5795-a90b-b1960611e83e | note | Reference Documents: VicRoads Specification Cl.304.08(b)(iv) Cl. 173
908a0f1f-6e7b-5549-954a-154b3fc16945 | note | - - - - - - - - -
127f2c4e-c0b3-514c-9f9c-81bee237c562 | note | Inspection / Test Method: Site Inspection
893ca0ef-3f5b-56ce-96cf-bad2cc7d949f | note | - - - - - - - - -
0c9a0d1f-cc18-54c9-878d-025a291cb006 | note | Record of conformity: Signed ITP
1a84cb47-fa2c-5928-a170-a9b86a0c4141 | note | - - - - - - - - -
722fbaa4-cb3e-5df2-9a61-41938b35a3aa | note | HP
f99f382f-bde5-58b4-ab77-039f65e2030b | note | - - - - - - - - -
76735ce6-2f0b-5fb2-af7f-246210e743e0 | note | Responsibility: Site Engineer & Superintendent
| signoff | HOLD POINT AUTHORITY
| section | 3 - Testing and Inspection
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
6370529b-b36d-506d-9653-5f3f915f5944 | note | Frequency: Prior to Testing
b2958d79-5644-516c-bc6c-62fbfd7decf3 | note | - - - - - - - - -
d8b95bd6-60d0-51cb-93c2-b8edeab6f81e | note | Acceptance Criteria: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
cb6af634-f1c0-5439-9ac2-b0db254fa61d | note | - - - - - - - - -
c4393f96-557c-5320-8284-913b043875bc | note | Reference Documents: VicRoads Specification Table 204.161 VicRoads Specification Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111
7c08629d-afa8-5035-a44c-9897cfa701f6 | note | - - - - - - - - -
54757904-703c-5603-a889-c94d285bda76 | note | Inspection / Test Method: Document Review/ Site Inspection
e3a3d8a7-870e-5ed0-b27f-c250821923a0 | note | - - - - - - - - -
01d962e2-6d02-548b-8195-a932658fbd6f | note | Record of conformity: Signed ITP
27f4a0ec-f0f5-5b17-81db-124909d51ba5 | note | - - - - - - - - -
49961fb8-37ad-5307-9271-516c5c4a97bf | note | IP
120a5220-7fab-5a19-b04d-4b464ed3125b | note | - - - - - - - - -
4e92d719-2ca1-524b-8255-18554655afc8 | note | Responsibility: Site Engineer
| checkpoint | 3.2 - Modified Compactive Effort
a6c0fe8a-ba91-5ae5-adc3-6a1207757aad | note | Frequency: As per 3.1
bdcd6862-f0ec-511f-8c75-2e38b3975b67 | note | - - - - - - - - -
32a8a68a-e469-5622-a83e-17ab9f3727d1 | note | Acceptance Criteria: Characteristic Value of Density Ratio for Subbase:- > 98.0% for Scale A and >97.0% for Scale B. For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six.
0d743980-f1f8-504d-bee6-2b64b8d41d43 | note | - - - - - - - - -
1967ea68-7b83-5ddc-9664-9ed99aedec31 | note | Reference Documents: VicRoads Specification Cl. 304.08 (b) (iii) Table 304.081
bae0172e-200f-57c5-bf56-f136431182a2 | note | - - - - - - - - -
c14867ef-43df-52be-8967-0f4d6fd6f91d | note | Inspection / Test Method: Site Inspection
3c5ef7cf-5e4b-59be-a72c-58928f7dff67 | note | - - - - - - - - -
278145e6-b6a0-5b3f-abc2-f559006b6c37 | note | Record of conformity: Test Records
0b7c5031-add6-544d-a54e-50167cf7cafb | note | - - - - - - - - -
f162b18f-d539-5ad5-a9d7-377845be74ae | note | TP
5f0d8cce-77d6-53a2-a8bc-9577edb49c2d | note | - - - - - - - - -
f38c6829-34fa-5898-9d12-11ae8ed0c6b8 | note | Responsibility: Site Engineer
| checkpoint | 3.3 - Permeability Testing
6c82eaf9-3cfd-5b7c-9c7b-430cfa56bb76 | note | Frequency: As per 3.1
3820f209-76df-5998-b2eb-5fb3f8dab27d | note | - - - - - - - - -
9c6540ec-4b61-5121-94ec-4e09df64653d | note | Acceptance Criteria: Class 4 Crushed rock max 5x10^-9 m/sec. Class 3 Crushed rock max 5x10^-7 m/sec Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051
d71be7ce-212f-55f6-9e6a-55729d7833ae | note | - - - - - - - - -
3772cc15-aa7c-5e9b-8ebd-73c1787417a6 | note | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.051
61106585-161d-5d3d-99db-71d26f37141b | note | - - - - - - - - -
3059fcf5-16f6-5e43-bb1b-a65909f5f89e | note | Inspection / Test Method: Site Inspection
ec6e66bf-205c-57b8-a549-ab24b1d9ce5d | note | - - - - - - - - -
f05c8a15-4b19-529f-a277-ac898f930c79 | note | Record of conformity: Test Records from Supplier
c498a16f-96e5-58b1-82c9-2a8c44e9c92f | note | - - - - - - - - -
714ab1c5-fb56-5a1a-83a0-3625b0ea2379 | note | TP
3118d2fb-fc2b-5439-8748-ac05618a37dc | note | - - - - - - - - -
c353710f-ea44-5cf7-bddd-d9f157187b75 | note | Responsibility: Site Engineer
| checkpoint | 3.4 - Post-compaction Plasticity Index
c859a818-b139-572e-932f-b084c02fe965 | note | Frequency: After compaction
9a291c0a-cc5f-51b9-bfb3-23e2aacac614 | note | - - - - - - - - -
466e3895-576d-5611-92ca-ee6126372736 | note | Acceptance Criteria: Post-compaction Plasticity Index must comply with the requirement of table 3040.053. Class 3: 0 < PI < 10.
a1b5e19c-7e08-583d-b3b6-1e8f31e1b86a | note | - - - - - - - - -
b9872f3e-fa31-504e-9e6a-b9b970ab584b | note | Reference Documents: Project Specification Cl.3040.05(a) Table 3040.053
675c3278-28e8-5b38-b3ed-e93cc9acf0fa | note | - - - - - - - - -
4e00828a-8f3c-5a38-ba54-ce6c9e550a56 | note | Inspection / Test Method: Site Inspection
af38b70e-835b-5fca-a4b4-bd3a43dd049b | note | - - - - - - - - -
272fe470-a46f-5873-910d-660b4c9b6184 | note | Record of conformity: Test Records from Supplier
85f1cc34-3272-5381-9687-ebd5c0b79b8c | note | - - - - - - - - -
db6b2f16-eb1c-5831-a209-943ce1169947 | note | TP
5ff0b0d8-10c4-5ef8-8f58-5ea8f39775ae | note | - - - - - - - - -
bde3282a-51f1-517f-bd66-2d727effca0c | note | Responsibility: Site Engineer
| checkpoint | 3.5 - Post- compaction Grading
46a968b1-9e63-5926-bb21-38859894733d | note | Frequency: After compaction
cf943c01-47a0-507f-96eb-dff60e2d5e01 | note | - - - - - - - - -
cd2b3281-b071-5500-bba5-3155d2f3e3ad | note | Acceptance Criteria: The post compaction grading shall comply with the requirements of table 304.101
082d3f41-f08e-52d0-b67e-dd5fd063cd6e | note | - - - - - - - - -
b9eaa437-3546-5c34-8582-73b7efb10b9f | note | Reference Documents: VicRoads Specification Cl. 304.10 Table 304.101
3f70b5c7-1793-5f42-9ed2-9201ff9e455e | note | - - - - - - - - -
ddb3f2e1-f0c9-55a8-8898-ae0e8b7b6c80 | note | Inspection / Test Method: Site Inspection
ff93ceaa-a7b1-5175-90f4-619438fea743 | note | - - - - - - - - -
eceac276-fb32-56bd-b735-b9ec5bb04675 | note | Record of conformity: Test Records from Supplier
1eaf23d2-340e-5d72-8dc8-c814708b1ab2 | note | - - - - - - - - -
0c52a960-af40-5601-9b35-9619592c2f72 | note | TP
96103029-f5ab-5574-8b95-80f39ece84fa | note | - - - - - - - - -
57099d31-1008-5836-9ee5-40f3612b2d49 | note | Responsibility: Site Engineer
| checkpoint | 3.6 - Test Requisition
94a12814-65f6-5f85-bf27-fc2967cca595 | textbox | Test Requested on
b5643e16-4224-5d77-ae46-b4240dd80b6b | textbox | Location
de5b94ee-e995-5c20-bcc9-cda6970fd3d5 | dropdown | Material Type | Type A,Type B,See comments
ea7c54cf-16d8-51cb-a82b-d9a7b74c7ec9 | dropdown | Material Source | Holcim,Boral,See comments
b5781ddb-a10e-56ce-b512-465c967ca6ce | tickbox | Compaction Test (Standard)
36be0681-74be-5e8b-9e7b-b94d63f08560 | tickbox | Compaction Test (Modified)
9ea1746c-5227-5e3b-897c-a4862dadac41 | tickbox | Maximum Particle Test
19ed1d2e-427c-54d4-97af-f82f4e2f3c4e | tickbox | CBR/Swell Test
4cd2cc1a-591e-509b-987b-29bad9c5de79 | tickbox | PI Test
ef86e3c2-989b-5554-87c5-6ce87f752aa3 | tickbox | Permeability Test
2eb994e1-5b80-5152-ad72-f6cbc992d677 | tickbox | Grading
83470543-fe9a-523c-aa7d-f59ec116f1ef | tickbox | Moisture
f12fdd96-1051-5817-80b2-cc5922b2473a | tickbox | See comments
1d313a6d-0618-5a6a-b27b-21820218a078 | textbox | Test Level/ Layer
| signoff | Test Requisition
| checkpoint | 3.7 - Survey Level
ad70f33d-7c3b-52bc-bf27-c40d0d268f5d | note | Frequency: At completion
408fe277-2b75-57f6-b9df-54564fa50fe2 | note | - - - - - - - - -
c81570b0-892c-565e-94f0-7aacfae30b41 | note | Acceptance Criteria: Scale A: Minimum number of measurements per lot: 80 for Upper — Upper Subbase: Mean + 4mm to -8mm wit a maximum Standard Deviation of 8mm — Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm — Base: Mean +- 5 with a maximum Standard Deviation of 8mm
bf2cfa25-79ab-51c8-9a9f-a8a4eee468dc | note | - - - - - - - - -
7b8d9ae9-e8b3-51c0-80a8-4fe5baaebb59 | note | Reference Documents: VicRoads Specification Table 304.061 Table 304.062
f756fe28-edff-5ef2-b8fc-f90ea7f58231 | note | - - - - - - - - -
e1f34062-4882-570f-b520-7ba8f65732ca | note | Inspection / Test Method: Site Inspection
79f910da-cb04-5de7-b6cf-2d13b5d8a3c8 | note | - - - - - - - - -
a473e8b0-50e0-5b3c-8b06-bad0b4124d59 | note | Record of conformity: Test Records
91070437-2af0-576e-b366-4654ff977066 | note | - - - - - - - - -
c5ca17bf-b554-5cbd-b917-776b86562d10 | note | TP
db6e5a01-0e5f-5ba7-8f72-cb93cd3cc243 | note | - - - - - - - - -
73094a2f-7fe3-5f73-9f26-ca7094f1a537 | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
5f349af8-c657-5484-9509-62d42b2260ed | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c1aa4edd-d0c4-52bb-ae04-bed247f439e6 | textbox | Name:
25ddc6ba-86d6-57c3-b4eb-b81d4bcb3e3f | textbox | Position:
fe92a357-f912-503b-964e-6cd4f968b966 | date | Date:
c3d1e3b6-1264-5114-844e-842e6b5a7f1f | date | Work Completed On
| signoff | Add Signature
| checklist | ITP 0010 - Subsoil Drainage | itp | ITP-010-AX-LOT-XXX - Desc | 6f726905-41bb-4a7b-9ee4-dee5210a57e3
| section | 1 - Material & Methodology Approvals
| checkpoint | 1.1 - Subsurface Drainage Pipes
e5927028-9f84-5b56-bae8-5c9c955446fe | note | Frequency: Prior to Commencing Work
c085220e-be9e-50b8-ac82-b42d5c946104 | note | - - - - - - - - -
dabdb380-380d-51d4-8c20-475c956666c2 | note | Acceptance Criteria: Ensure all subsurface drainage pipes ordered are Category 1: perforated plastics Class 1000 and Precast concrete Class 2.
ac6cb323-cf69-5023-86dd-90ce9314a695 | note | All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2.
6060f8df-7149-5df2-a183-65d1ac18346d | note | - - - - - - - - -
2e51b7e3-738d-5f8a-bc45-2886ff6cf4c7 | note | Reference Documents: VicRoads Spec. Cl.702.04
43e19d0f-d8b1-5974-b1ef-556ac53147aa | note | - - - - - - - - -
e91c53e8-9598-5644-ae60-fc44624e0e64 | note | Inspection / Test Method: Document Review
81bda2f4-b20a-536e-ba2f-0618d4916e15 | note | - - - - - - - - -
6c13ac55-9831-5a04-a30c-f8d7f1575240 | note | Record of Conformity: Insert Teambinder Material Approval Number
562e63ad-bd4c-5476-89e9-69217789caa9 | note | - - - - - - - - -
b03b1164-d431-5a3f-b0d0-3462a1f4299f | note | IP
a5104cba-3e49-5e57-8b10-9e32e8de1005 | note | - - - - - - - - -
789cc4c3-0113-5cbd-bf0b-f498363f006d | note | Responsibility: Engineer
38e54a57-6e02-5b94-b4bf-ef7bd4943506 | textbox | Enter Teambinder Material Approval Number:
| checkpoint | 1.2 - Drainage Geotextile
a5a668eb-a8cb-528f-8e62-e97af099711e | note | Frequency: Prior to Commencing Work
c4f27cf4-4796-5709-9084-d6a5b275d234 | note | - - - - - - - - -
ce815aed-438a-507e-925c-6a9547110cf4 | note | Acceptance Criteria: Type 2 drainage (NFC) Geotextile filter to meet requirements of a First Stage filter as per Table 702.061
6226a6b1-9c70-5ccf-92e7-da5a60a9e52a | note | - - - - - - - - -
4a1b7f9e-6b76-597c-825a-e26926f4dde5 | note | Reference Documents: VicRoads Spec. Cl.702.061
e57f25ab-8725-5348-ac8c-099f146fb6fd | note | - - - - - - - - -
b2a59722-27c2-5026-ad91-e02d21833559 | note | Inspection / Test Method: Document Review
51e61c06-dbbe-5c06-a2b5-c2e56de8e339 | note | - - - - - - - - -
14a2856e-6d16-56cc-929c-83d596744121 | note | Record of Conformity: Insert Teambinder Material Approval Number
78666382-8f77-5099-a5e7-fa2e1aa7bccc | note | - - - - - - - - -
7265961d-d6fc-51fe-9890-b6f797baa8b5 | note | IP
a5bd7890-5680-5cca-bd71-f9ecef812d66 | note | - - - - - - - - -
bc148583-d88d-5dd7-b1c1-aa684cd1ec68 | note | Responsibility: Engineer
741afeb6-7756-58e7-9537-9bbf3b6f7dc6 | textbox | Enter Teambinder Material Approval Number:
| checkpoint | 1.3 - SSD Backfill Material
be6fffcc-2eee-5bf6-8ebd-e72413c0f5be | note | Frequency: Prior to Commencing Work
92c3f453-1e94-5e73-b407-e238887f3049 | note | - - - - - - - - -
2528f249-7ed0-52e0-a595-450eba6d5dbc | note | Acceptance Criteria: Type 2 and 3 backfill material types to be reviewed against specification and approved prior to ordering and use.
db693077-e3c9-5949-925b-1581b098ed74 | note | Minimum testing requirements are reflected in line with 702.13.
d1230d0e-03aa-5d38-9036-f5c38d847216 | note | Type 2 NFC Grade B4 Filter Material
4d34856f-7cb1-5232-ae0f-5112a25b59f5 | note | Type 3 Sand Filter Grade A4 to A6 Filter Material.
b40c0d26-cdfe-5693-9dfe-dc51ddb98af5 | note | - - - - - - - - -
228040bd-2fc9-597c-94b8-672a1486c6a8 | note | Reference Documents: Project Spec. Cl.3030.05(a), Table 702.131
4ad7fbe5-9e3f-53df-9e58-93fe6a5c04b5 | note | - - - - - - - - -
bb51456e-4393-508f-baa1-22e7cd6fdfe4 | note | Inspection / Test Method: Document Review
d79430c5-5701-582d-ad88-5f1d63e9a5ef | note | - - - - - - - - -
9a710fe6-5723-5394-b6ef-4475ff697e85 | note | Record of Conformity: Insert Teambinder Material Approval Number
3de3f0b8-3b96-5dce-a8b5-43ce391e467b | note | - - - - - - - - -
68f03b4e-5afe-5654-a960-feb0aa1eb0d2 | note | IP
62a7f994-f013-5c12-8a6c-df91e901b01d | note | - - - - - - - - -
c2bd0711-6b3c-576b-bfe2-db6852d1fb50 | note | Responsibility: Engineer
5785c953-13ee-5427-b7d3-a0227d1638d7 | textbox | Enter Teambinder Material Approval Number:
| checkpoint | 1.4 - Terminals & Pits
aeed6607-6feb-5a88-a7bd-9a0897e53ccf | note | Frequency: Prior to Commencing Work
542685d5-f363-54bc-a967-4ec587dad322 | note | - - - - - - - - -
6ffc81e3-3f5c-5669-80f5-bec7c0feb2de | note | Acceptance Criteria: Terminals and Pits
556b47bb-a811-501c-a46e-9e41975168da | note | Flushout Risers SD 1631 and Type S1 Pits reflect VR SD 1611.
32f1076b-4899-504f-8798-d02af83b5055 | note | - - - - - - - - -
8b6e0939-fcf4-54d4-906f-7ee0ec0e046f | note | Reference Documents: SD 1611 Issue D SD 1631 Issue E
1d6ca93c-9714-515f-962a-696388a0bb79 | note | - - - - - - - - -
8ae1c66a-8df3-519c-a8b4-b94ca1c5981b | note | Inspection / Test Method: Document Review
1631b5df-98d9-54e3-8e25-0184a3952f18 | note | - - - - - - - - -
33b848f5-eae0-550b-b1d1-ba33d4ff4e2d | note | Record of Conformity: Insert Teambinder Material Approval Number
1dc54554-1eca-5033-a8c2-ba9e8b53d132 | note | - - - - - - - - -
eab2341f-126d-518f-8288-2139a66ead4e | note | IP
fed4fcc7-c960-5bfe-92a9-8a3b17b41e4f | note | - - - - - - - - -
ab64beb0-8799-560c-b5d4-4416c1f6dae6 | note | Responsibility: Engineer
90896ea9-af4c-5c46-a65d-dc934854d7e8 | textbox | Enter Teambinder Material Approval Number:
| checkpoint | 1.5 - Compaction Methodology
ac274d92-ed3e-5f35-98b0-2bec7b6982a3 | note | Frequency: Prior to Commencing
9e0bf446-8f1a-52c1-99f5-11f24c3aea6e | note | - - - - - - - - -
f194d4c3-e594-5699-b963-c3100e0de8d6 | note | Acceptance Criteria: Ensure compaction methodology of No Fines Backfill developed and submitted for review prior.
8a8c7dc5-4db0-531d-b1fe-2422363b68bf | note | - - - - - - - - -
4e603d3e-f759-5ec2-8b47-e3af8c1a330f | note | Reference Documents: VicRoads Spec. Cl.702.09(g)
bf10f3e1-e33b-5fd7-88c1-52501c240912 | note | - - - - - - - - -
ffc89554-01d2-5897-82ed-c6b18829bc5b | note | Inspection / Test Method: Document review
12e08467-b78b-5590-a0dd-41491a0c6740 | note | - - - - - - - - -
9955bd27-0c31-5d7c-ae26-4e82216a3bbc | note | Record of Conformity: Insert Teambinder Reference number
20e2f957-b9b1-5d97-964c-9dd0060aec62 | note | - - - - - - - - -
fd4c9a72-596c-53c9-8322-a54ad998bb0a | note | HP
8d12d564-9eac-54ca-b028-5c1885e0d79b | note | - - - - - - - - -
df7d2ca7-d782-5848-b4d6-26f7c024c7f6 | note | Responsibility: Superintendent / Project Engineer
7442ebdd-7c8a-5ba4-bd80-6c607184dcae | textbox | Enter Teambinder Material Approval Number:
| signoff | HOLD POINT
| section | 2 - Preliminary Works
| checkpoint | 2.1 - Check current revision drawings are being used
b71d820d-8b17-5914-a6ee-f399c2284efe | note | Frequency: Prior to Commencing
0d6b34b8-4d55-5437-88a2-dffc73c5934b | note | - - - - - - - - -
8e6c0895-14f8-5e45-a13b-86ac68e29262 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
2bc4a807-226b-521a-8985-592ebc9a13fd | note | - - - - - - - - -
870d384c-596d-5fd2-b6fe-0f5e1c07f985 | note | Reference Documents: Project Drawings / Drawing Register
5e373caf-881f-5b71-b5ef-34904adc9e2f | note | - - - - - - - - -
17171f1c-2522-59d8-ac69-2c355c36739f | note | Inspection / Test Method: Document review
5444389b-3d2a-5493-bc43-c9650367c394 | note | - - - - - - - - -
8de5badf-4fe1-5279-8c10-7a65c52f26dc | note | Record of Conformity: Latest Revision Drawings
3071fe62-33c9-5187-8eb5-8872e4b03235 | note | - - - - - - - - -
50f11d56-fb74-55fc-9f36-d08f5911e9fb | note | AP
52440adf-dcad-5c54-8891-f8276e534ef6 | note | - - - - - - - - -
5e014b18-93d1-5169-a48e-3d677572bca1 | note | Responsibility: Site Engineer / Foreman
| checkpoint | 2.2 - Excavation Permit issued
829a15ae-94f2-5dd6-be1d-5ddd51173b22 | note | Frequency: Prior to Commencing
3cbdf403-ce44-5f31-bead-9fa0a0fafe40 | note | - - - - - - - - -
2cb5cef0-38c6-5158-9d3c-2f77454acbf0 | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed. Ensure DYBD Plans and Drawings relating to the particular area are available, current and where applicable highlights temporary services installed by Contractor
07bd4951-fc6f-568a-bd11-e5d193c61efc | note | - - - - - - - - -
5577ec6c-905f-533d-910f-8c325fd7cf8f | note | Reference Documents: Excavation Permit
bf877fa3-00d2-5345-a309-2a4fd28a23c4 | note | - - - - - - - - -
efd9c995-77ef-5479-8cf2-de0d7e4b068c | note | Inspection / Test Method: Document review
2af6a5b5-5c24-5b61-9199-b7cbf3d140ee | note | - - - - - - - - -
cd145366-1013-52ca-a7f1-cf1a628614bb | note | Record of Conformity: Excavation Permit #
3106066e-2e14-5997-b9fc-3b237afb0590 | note | - - - - - - - - -
df3dfcf4-0602-51f8-8538-101b456a89b4 | note | HP*
2d7eec84-4e67-56af-ab23-757c4e8a4e10 | note | - - - - - - - - -
8eda3bad-6e53-5110-8cb9-8095de837573 | note | Responsibility: Site Engineer
| section | 3 - Subsurface Drainage Works
| checkpoint | 3.1 - Suitability of Materials
b6126539-a608-51e1-84e5-1b4d2a78fa51 | note | Record of Conformity: Signed ITP
b5c291b1-c06c-5891-9a2e-a7ede571e2ba | note | - - - - - - - - -
300c92ea-09e1-5c2e-a7d3-7d90fba5cd48 | note | IP
aac45eb0-ba9f-5495-9315-672b96a17c55 | note | - - - - - - - - -
1fb15237-88c0-5f82-aa08-c25af8f618f9 | note | Responsibility: Site Engineer
| checkpoint | 3.2 - Managing Existing Drainage
39d2fcfd-9a1c-5aef-95ad-a32e6195a902 | note | Frequency: When placing drainage
5d003208-b397-5df5-97b0-7aabcda028bb | note | - - - - - - - - -
2744fc66-3eac-5cd8-9889-883befae38a6 | note | Acceptance Criteria: Ensure removal and disposal of all redundant pre-existing subsurface drainage assets.
77e112e2-8b32-5fc8-95ca-a62f67452bee | note | The area is backfilled with Type A material to subgrade or surface level.
0734f01a-30eb-5c01-83a4-ea1aea98380f | note | Where backfill is required above subgrade level, backfilling must be with pavement material that matches the pavement design for that pavement.
e52dba03-af29-5394-83df-f52577fc168d | note | - - - - - - - - -
11c03cbf-9084-5fbf-963f-0d96d582c217 | note | Reference Documents: Project Spec. Cl.3030.07(c)
7ee11e32-1184-5a84-872c-36e8adc2c15d | note | - - - - - - - - -
02c61df1-5612-5628-94b4-a5e146cf3d0d | note | Inspection / Test Method: Site inspection
8413b798-09db-5da1-ace7-4b46f04a8809 | note | - - - - - - - - -
e0a44964-4ebb-5b09-bf15-c98d6b1e7e43 | note | Record of Conformity: Signed ITP
4234a79c-c955-5f1d-a269-06ea20205409 | note | - - - - - - - - -
bc4090ca-9231-5e70-bc7b-5a4c06355c43 | note | IP
9b97b62f-d085-5cf0-bf99-45c402bd85f9 | note | - - - - - - - - -
07f3476b-408c-5546-ba85-a47b22908dad | note | Responsibility: Site Engineer
| checkpoint | 3.3 - Excavation of Trench
361530b2-c077-5b36-8b09-8b4aadbe1964 | note | Frequency: When placing drainage
7b460664-5e5f-5199-b6b4-1ed70bf2aa09 | note | - - - - - - - - -
bdcd2da8-0928-56c9-841b-57717ce2de38 | note | Acceptance Criteria: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed.
7ea3bbc1-d95a-58f9-a074-b71585b220a4 | note | The top of any subsurface drainage pipe shall be at least 300 mm below the subbase and setup for the subsurface drain type.
9766e83f-8b57-5311-9a6e-8312944027d9 | note | Grade of trench to be not flatter than 1 in 250 gradient.
3234c0b1-c504-5fb6-98a9-041495963951 | note | Base of the trench shall be inspected to verify compliance with the requirements prior to placing bedding in completed excavations.
4c0cd88e-b36d-5178-a9cc-aecbcfd7b4ba | note | - - - - - - - - -
66c64909-2752-51b2-ac8d-022c74d818c1 | note | Reference Documents: VicRoads Spec. Cl.702.08 VicRoads Spec. Cl.702.09(a)(b)
af4ce76c-2338-5e74-baa2-b945b357755f | note | - - - - - - - - -
400dbf1e-f19e-5585-8658-506ed2b1964d | note | Inspection / Test Method: Site inspection
05c49ea7-2394-5dda-b69a-4e648f964e5b | note | - - - - - - - - -
9e5e8112-dc2b-5501-8fd3-39baebf6d42a | note | Record of Conformity: Signed ITP
c5143ae9-66ab-5179-bfd1-eed528507b43 | note | - - - - - - - - -
df204f8f-1143-5070-9fb9-e5a907c166ae | note | HP
9a2449ba-eaf9-50e3-a86e-6bacbafa5b1d | note | - - - - - - - - -
a83165aa-9c35-51f7-9460-08eee3310053 | note | Responsibility: Superintendent / Site Engineer
| signoff | HOLD POINT
| checkpoint | 3.4 - Use of Geotextile
5d3f83c4-a446-5c78-bbc3-671d874302a9 | note | Frequency: When placing drainage
aaf3d033-8448-53f6-b6a4-1c81711e1ba8 | note | - - - - - - - - -
1eca2e27-0a17-5429-b443-41f2c1ab1c0e | note | Acceptance Criteria: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when granular material is placed.
985c29f9-5d2c-5872-9456-e052bab9eafd | note | The appropriate Subsurface Drainage Type 2 (B4 NFC filter) or Type 3 (Grade A4 to A6 filter) has been setup prior to backfill.
24a347e8-f8e7-5779-86b7-b4649bc42b84 | note | - - - - - - - - -
ca02b27f-d81b-5c4c-ae68-3e7e0621ac2c | note | Reference Documents: VicRoads Spec. Cl.702.08
50e4f9bf-a830-5a2e-8570-969fb5a06248 | note | - - - - - - - - -
33b6178e-83bd-5f23-b2ee-0ed0c77abbf0 | note | Inspection / Test Method: Site inspection
c0cac4fe-a1b6-59d3-a37b-88c8674eb99b | note | - - - - - - - - -
92b6272a-ba02-516f-9271-c9fb1518064d | note | Record of Conformity: Signed ITP
4dc24efe-0b92-5c9e-b556-e1668b2e6466 | note | - - - - - - - - -
dc3b4ffd-9213-5bfc-9a68-5c26d6994d9c | note | IP
0fd5a6d3-958b-5c73-adfe-75c4d9987850 | note | - - - - - - - - -
cc3f33a4-a1d1-5fd5-aa14-56248d6e5463 | note | Responsibility: Site Engineer
| checkpoint | 3.5 - Installation of Subsoil Drainage
9d6764a6-ddbe-546c-accb-c417fced5b35 | note | Frequency: When placing drainage
ae905300-466e-5e80-a9c3-0e0e11f3e6e2 | note | - - - - - - - - -
4c45b69e-e4dc-50e6-9608-afd77dfa717d | note | Acceptance Criteria: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level.
2a768a6e-4047-53b3-8bd1-35620a55fd88 | note | Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe.
25618bbd-2dac-5143-b038-6276e72b0129 | note | Flushout Risers, S1 Type Pits and Outlets are appropriate positioned to reflect the subsurface drainage design.
be750bae-1bbc-54be-821d-1be0b8775a22 | note | - - - - - - - - -
68895621-df04-5711-82ce-c9e6a179226f | note | Reference Documents: VicRoads Spec. Cl.702.09(d)
3be95f88-b65c-5aa9-b253-b7da106bd69a | note | - - - - - - - - -
4548c387-1683-5502-8fd9-6389e6d8dc22 | note | Inspection / Test Method: Site inspection
43ae4cf8-ef39-5587-9133-4103a73c28e5 | note | - - - - - - - - -
d2bac44e-2ad2-593c-b700-d69c1871be58 | note | Record of Conformity: Signed ITP
0b66e35c-d0fb-5eae-9071-21a2d70646a5 | note | - - - - - - - - -
53526238-051c-55c4-9e49-3d9a9373ac62 | note | IP
474329c5-d3cf-59a9-bae9-410be22b64f3 | note | - - - - - - - - -
442857e7-b0ac-5792-b15d-d1e60d1d71c3 | note | Responsibility: Site Engineer
| checkpoint | 3.6 - Placing of Granular Filter Material
3047799f-2cfa-51d5-9721-d10204cb6bb7 | note | Frequency: When placing drainage
0579c205-1d1d-5c07-ac4f-69854f944856 | note | - - - - - - - - -
8f61f1cc-0ccb-5dad-a8c2-2da8392abf34 | note | Acceptance Criteria: Filter socks must not be installed on subsurface drains backfilled with no fines concrete (Type 2). (HP)
1536e111-b6f7-5938-b5e4-148c87358b36 | note | Filter material shall be moistened and compacted with minimal disturbance to pipes. The loose thickness of layers shall not exceed 300 mm.
d5b02def-621d-57ce-9af1-fcf91b145a14 | note | For Type 2 (NFC) No-fines concrete shall be placed and compacted within 1 hour of mixing.
c9b8b9da-1c95-5082-a0c5-3e46aeaf3902 | note | - - - - - - - - -
a4bd392b-a5fe-5043-9c0a-a6d7eeedfb75 | note | Reference Documents: VicRoads Spec. Cl.702.09(g) Project Spec. Cl.3030.05(b)
001afff5-7bf2-5d9b-8467-223310a49db3 | note | - - - - - - - - -
4c5b9a1f-4faa-5bc1-8a1d-93ba3da3cdb8 | note | Inspection / Test Method: Document Review
3a0ff6a6-0010-5513-a1c6-8fd8d0904fed | note | - - - - - - - - -
569895cf-36dc-5e88-aff3-d664d850b0de | note | Record of Conformity: Signed ITP
48e86c07-556e-5ded-b167-afa155cba410 | note | - - - - - - - - -
6612fed6-9b20-5152-967d-7fae05cb5f46 | note | IP
9bcbacd8-32af-50a4-a059-4581f4cae81d | note | - - - - - - - - -
147e95d7-eecc-5a73-8483-30338c06af41 | note | Responsibility: Site Engineer / Foreman
| checkpoint | 3.7 - Installation of Subsurface Outlet marker posts (If required)
7f8752cf-5323-5cdd-833f-f2edfbc3d6be | note | Frequency: After drainage is placed
6f5291d2-12c7-5ded-a63c-f90058889dac | note | - - - - - - - - -
25e71990-ade7-579e-8dfb-42c083d75d81 | note | Acceptance Criteria: Marker posts installed at all subsurface outlets, and must be 75 mm diameter x 1500mm treated pine inserted 600mm into the ground.
93b5c240-1afa-54a7-9c44-f59371bc28d1 | note | - - - - - - - - -
d2dc34e3-f3d3-542c-bd48-c0f90708f8d6 | note | Reference Documents: Project Spec. Cl.3030.07(b)
34f8ca42-8fc0-5b6c-bc7a-34a01af03f27 | note | - - - - - - - - -
4760d73f-8d30-5923-9ebc-b1dc0197a088 | note | Inspection / Test Method: Site inspection
4a662806-9f58-55da-8dd2-5a76c982a5e1 | note | - - - - - - - - -
d3cf6fa3-0e18-5b57-a016-3dcf6ea0bf5f | note | Record of Conformity: Signed ITP
93a41b0d-a41a-5f0d-af3e-02ee61bce1f9 | note | - - - - - - - - -
4792a47b-6513-5a27-bded-00ebb2c0edd1 | note | WP
cd9a25b6-4ec3-5f30-9fa9-78309109618c | note | - - - - - - - - -
57b2bdcd-0df0-5ece-971f-d4078108d3fd | note | Responsibility: Site Engineer / Foreman
| checkpoint | 3.8 - Flushing Test
6df60297-0f8a-5a52-b201-d346a2a50121 | note | Frequency: After drainage is placed
a4b3481f-3ce4-52fe-a997-d31ff405b267 | note | - - - - - - - - -
0f359665-83e4-5909-9c19-f1aac39e7a14 | note | Acceptance Criteria: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction.
43b6fc2c-822d-5fe3-855a-078b9f532814 | note | - - - - - - - - -
96b8c2d2-abe6-58be-9af8-ac44a140c5af | note | Reference Documents: VicRoads Spec. Cl.702.09(h)
35613f10-82ba-52f0-8a53-e804a89de832 | note | - - - - - - - - -
0f34a2a5-af4d-5b69-96cd-4fa292cca173 | note | Inspection / Test Method: Site inspection
f6e308aa-c36a-5caa-af6b-4b0433a43e5e | note | - - - - - - - - -
d3b5ab0b-e50a-5445-a18d-b9e04d69ce58 | note | Record of Conformity: Signed ITP/ Record of flushing tests
e0b576c1-8cfa-5e7a-ab21-0d434d3ce5ca | note | - - - - - - - - -
90ec7360-0b6b-5417-ae43-b1c3f3cd16a4 | note | WP
20b4cf05-d472-5cf6-a81c-8479714d70ed | note | - - - - - - - - -
65c793cb-7e87-5227-a203-bdd32b0a0f07 | note | Responsibility: Superintendent / Site Engineer
| checkpoint | 3.9 - Inspection and Completion
2e3b19f6-8fb4-5e4a-baab-166bb53f9701 | note | Frequency: After drainage is placed
f0cc677c-2d39-5cc3-a376-c8c9c815b6c3 | note | - - - - - - - - -
d4673731-ace1-5d8a-8767-9fecf3707e3f | note | Acceptance Criteria: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV),
0793f070-9946-5616-b201-dc726c72e456 | note | Verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
18cec18b-8640-5667-b8a8-4ef99d076521 | note | Placement of asphalt cannot proceed until after this inspection. CCTV is completed, damaged or deformed drainage pipe removed and replaced. Along with waste and defect free condition of lines verified by the Superintendent.
579ce323-744c-5d7e-874a-c4a452172f68 | note | - - - - - - - - -
0b98a40b-2ab8-5181-b211-00c631d70f19 | note | Reference Documents: VicRoads Spec. Cl.702.09(h)
1f4d3a09-ae0d-5b06-a0f0-9461d2f6453e | note | - - - - - - - - -
003d36d0-bdec-53e4-9525-92138f409c2c | note | Inspection / Test Method: Site inspection
3a82bc96-39da-57f6-ba2e-34d4e50d4cab | note | - - - - - - - - -
4fef94e1-a641-5788-9353-0d37c986cae7 | note | Record of Conformity: Signed ITP/ Record of flushing tests
8bbe4d9a-d9f1-5070-9f9a-b1c2cadaed8d | note | - - - - - - - - -
e1548a96-9a44-5596-88a3-b7499ae0f9d9 | note | HP
bbea26e3-230c-5582-b92a-ce81f09c8014 | note | - - - - - - - - -
8bb38d54-b784-541f-854e-7311c37126ee | note | Responsibility: Superintendent / Site Engineer
| signoff | HOLD POINT
| checkpoint | Final Inspection
edf68a01-a11a-54a8-9cce-5abec84361da | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
50fb1311-8c89-5f3f-9a99-bc9f18735a15 | textbox | Print Name:
8db77b64-62b4-5fa9-909a-274a3f979c7c | textbox | Position:
1afde231-2c2b-52d8-9191-975069f07ebe | date | Date:
1938dca1-93fc-5298-b5b5-7114d84e509d | date | Work Completed On
| checklist | ITP 0011 - Cement Treated Crushed Rock | itp | ITP-011-AX-LOT-XXX - Desc | 72a3b4fa-8a3a-474a-9c06-a590a8981aef
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check that current revision drawings are being used
8b302701-2ca8-5dd7-916d-8dc8e1f7757b | note | Frequency - Prior to Commencing
61df6261-e425-57c2-b2f7-9efee030e9a4 | note | - - - - - - - - -
43dda34f-219b-5fcf-a058-15444e8c1697 | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
3f88cca2-982a-5815-a3c8-d7deea88d21f | note | - - - - - - - - -
8958daee-ce3b-58a5-b2a0-040f34328a12 | note | Reference Documents - Project Drawings / Drawing Register
00fa0616-0810-50fc-8a79-27176bf6e967 | note | - - - - - - - - -
448c71e9-9c7b-5e93-a310-272082c95db0 | note | Inspection / Test Method - Document review
1a539965-afbc-5172-b6ec-495241811817 | note | - - - - - - - - -
f59a47fc-2512-52be-b589-858c8aed0bc3 | note | Record of conformity - Latest Revision Drawings
0d6f6262-476f-5ff2-9dec-518235d70639 | note | - - - - - - - - -
968a6841-166e-5f22-b106-9f39af5faa49 | note | AP
1f4a7cc1-fabf-5590-b932-1211587629b0 | note | - - - - - - - - -
fbafdbf1-af2e-56e9-9e08-c777bd768cb8 | note | Responsibility - Site Engineer / Site Foreman
14e14c9c-2ae4-534f-8ae8-479a866ab801 | note | - - - - - - - - -
309975d4-968e-592e-8ce0-f70466eb13c8 | date | Date Completed:
| checkpoint | 1.2 - Submit Mix Design - Cement treated crushed rock (CTCR) mix
792ab7eb-95c2-58a2-9de9-a96471b52340 | note | Frequency - Prior to commencing
8e28473c-33f7-52ba-ac01-f30c6b0e2a82 | note | - - - - - - - - -
87a1ec80-3030-5177-a59e-088881f5095a | note | Acceptance Criteria - Cement treated crushed rock mixes for use on specified works can be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
c35f5258-12e4-5eb9-9064-4fb3c3a7c01e | note | - - - - - - - - -
06e1cac7-029d-5e51-a77d-bce6dc57764d | note | Reference Documents - VicRoads Spec. Cl. 815.05
c33c11ee-6395-5e35-8e20-f5dce07d210f | note | VicRoads Spec. Cl.306.04
4c1bf01e-985d-51ea-8f9f-087aa66a293d | textbox | Team Binder Approval Number:
a87b5915-5da1-5b68-857c-a9fc72e8cdd9 | note | - - - - - - - - -
70d40c12-96cf-5272-9fe6-aeab10920837 | note | Inspection / Test Method - Document Review
616fb92b-e283-5a62-a76f-bc77cf47dfe3 | note | - - - - - - - - -
86e720dd-a482-5939-8f47-97a65c06d7f9 | note | Record of conformity - Issue to TeamBinder: VicRoads registered cement treated crushed rock mix
698354ca-98ae-53e1-8c81-7980511805ad | note | - - - - - - - - -
e47a4e74-ff55-53d7-a66f-7f65136d0c16 | note | HP
2a6fd40d-6763-5fbe-bad3-740b9217b0e4 | note | - - - - - - - - -
aca9ed7a-4591-5002-8ef7-0ea41c2d1c5f | note | Responsibility - Site Engineer & Superintendent
1a13c4f5-1257-5df1-ba47-8e9260e3d7ad | note | - - - - - - - - -
fd63842e-5204-5cdd-82dd-9715dad85ad0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Survey Set-out
26ea724d-7fd7-55b7-b74a-8d5663ab0a8c | note | Frequency - Each Lot
2d3559e1-625f-5dc7-b2d7-1e4ae1ece8da | note | - - - - - - - - -
aa68686d-b826-5d23-8887-665538b5df0a | note | Acceptance Criteria - Survey to set out works in accordance with IFC Drawings
735656e5-1e7c-5a1e-97ac-15c732578f78 | note | - - - - - - - - -
481c866a-e936-52b8-8106-6c6f3ef2393f | note | Reference Documents - IFC Drawings
7afba0df-08b9-578b-9dca-08faa553a01d | note | - - - - - - - - -
658209b3-8e63-5500-8de2-7571f552520d | note | Inspection / Test Method - Measure
8684bf3d-80b9-5294-b5fe-332d9d5f386a | note | Visual
74bbb109-9faf-5222-b25a-abae1dbe612a | note | - - - - - - - - -
b028d00d-64dc-5a2a-b795-80c37ac53d92 | note | Record of conformity - Signed ITP
988176bc-e606-548e-a4be-865799d3c894 | note | - - - - - - - - -
986229d3-4681-5eac-ad57-adf168e91f65 | note | IP
d3b70241-0b48-5f5d-86d7-de9b504b300f | note | - - - - - - - - -
61bd886a-3058-5ec0-855a-905eb9aaf440 | note | Responsibility - Site Engineer
96699829-21c5-59d7-8dd7-9a788e8b91ed | note | - - - - - - - - -
956e8e2b-90a5-5087-b671-2f29ace789fe | date | Date Completed:
| checkpoint | 1.4 - Previous Layer Level Conformance
ad5d86f9-6960-598a-811e-a590b87595eb | note | Frequency - Each Lot
f54957c7-f780-5563-a9d1-ec669a67fbf0 | note | - - - - - - - - -
8e40f4f5-224f-5db7-a3c7-4857844a57e7 | note | Acceptance Criteria - Confirm previous layer (prior to CTCR layer placement) conforms to IFC drawing and specification requirements.
9588e627-e9a8-5785-ae81-034faaa9e7ea | note | - - - - - - - - -
8f01b79d-a0c6-52cb-ae7b-945d10d494ff | note | Check the previous fill level/survey (e.g. fill, foundation . Subgrade, base course etc) to ensure CTCR minimum thickness requirements is achieved.
d62f8953-19cf-5e6e-8534-37fc15a3861d | note | - - - - - - - - -
29e70f2f-f2b3-59e1-a06c-36e3b09fc669 | note | Reference Documents - IFC Drawings
80e6bbba-32c1-5e38-8b00-4cb99dd576d9 | note | - - - - - - - - -
d8aa52f0-4384-5b4e-b9f7-e489c857e2f5 | note | Inspection / Test Method - Document Review
51e8b627-292f-5c2f-a24a-68966671d368 | note | - - - - - - - - -
ed9f3baa-ac09-5ce9-8dd2-9378b400203b | note | Record of conformity - Signed ITP
c780edaa-c43c-58c4-a9c9-e878f11db0f3 | note | - - - - - - - - -
9dcc2edf-ba0c-565a-bfc4-38cf22fdaf96 | note | IP
eb2c15a8-7ad0-501a-bc33-d24d673b444f | note | - - - - - - - - -
d5ef3033-ead9-50f8-a574-4affebf6382b | note | Responsibility - Site Engineer
dca664be-2a21-565c-9615-df6b21aa0682 | note | - - - - - - - - -
0e154c50-dcc9-5430-b0fd-cad7a0d7ba67 | date | Date Completed:
| section | 2 - Placing Fill
| checkpoint | 2.1 - Lot Size
341abbc3-b2da-564d-b2a8-2ddcdabb780b | note | Frequency - Check prior to placing material
9ee77d96-68ac-5206-99b1-b1e3686672d9 | note | - - - - - - - - -
bc135891-eb11-5241-9ed3-ba7656577eec | note | Acceptance Criteria - The maximum size for a single lot shall be considered a single layer of 4000m2
938ba504-1462-5e4b-9b2f-ed3e1be1d4a6 | note | - - - - - - - - -
3a146f76-e5e0-5aa9-b395-931c9815ddbb | note | Reference Documents - VicRoads Specification Cl.306.03(b)
ac694b2f-ac30-55c6-ae88-f376f858f21c | note | - - - - - - - - -
7e611293-e8c2-5970-bfd0-1ec63afc03f5 | note | Inspection / Test Method - Site Inspection
fcec1c30-851e-51fc-ab07-e46648d6804b | note | - - - - - - - - -
daa0d149-54c3-5a6b-a416-872c8435be00 | note | Record of conformity - Signed ITP
9ac5b572-6e67-54b8-a293-586ebe667cbf | note | - - - - - - - - -
4f272c30-7b2c-56e9-a2e8-71ed2cddbd8e | note | IP
00628384-1e25-56b0-aa19-bc2bf1c36e1e | note | - - - - - - - - -
01c75afe-083d-5e7b-bbc2-cbbbb8440276 | note | Responsibility - Site Engineer
67ae0087-6688-5696-ac8c-fb6db7db9a0d | note | - - - - - - - - -
d7eb7b5f-5d5b-5c5f-b8f3-835d7e0c0f11 | date | Date Completed:
| checkpoint | 2.2 - Hold Point - Alternate Binder
12b48bf3-e574-5235-b47b-d66fe8b7dd7b | note | Frequency - Prior to Placing Material
94565670-9968-58fa-9491-4f588cc08dae | note | - - - - - - - - -
388d74d8-e67f-5fa6-869e-ef4e179b990d | note | Acceptance Criteria - If a binder other than those listed in Table 306.091 is proposed for use, laboratory test results must be produced to show that binder satisfies the required working time and strength determined in accordance with the VicRoads Test Method.
75dc228e-e294-5116-b2c4-a841b3ea5b0f | note | - - - - - - - - -
d0cc6a29-a8c9-5e09-97d0-28738095cf22 | note | Reference Documents - VicRoads Specification Cl.306.09(a)
522ce360-c3da-5dd4-b22a-28869afd9dcd | note | Table 306.091
1ab84cdc-7518-5de9-a3f5-da04ab7c81e0 | note | - - - - - - - - -
1c5bce75-2922-5dd4-8cc9-fd60eb699087 | note | Inspection / Test Method - Site Inspection
3051c8c4-09cc-5a69-bcb2-f6ee5e26e2e3 | note | - - - - - - - - -
43035da4-333e-50b2-adf1-09944c043770 | note | Record of conformity - Test Records
880fcdf6-f1f8-5cd7-9a11-fd2d2a37db3e | note | - - - - - - - - -
6bec6ba2-d6fc-54a9-b91a-8451ccdd47ff | note | HP
30c7b843-6ea7-5904-b665-79ca538ac635 | note | - - - - - - - - -
a27e54bf-f3b5-59af-a47c-2a0504af8b39 | note | Responsibility - Site Engineer & Superintendent
ef7a5301-7be1-5bfd-a840-aa18e08cf0a1 | note | - - - - - - - - -
f1b2aaa7-4311-543f-aa30-b32cbc9d2f50 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Transverse Joints
4dcae285-e9fe-5096-a566-71b60278c609 | note | Frequency - Check prior to placing material
dea7d35c-b884-5852-a771-88f506517761 | note | - - - - - - - - -
e0516971-e0b1-558d-9ce9-25ed9e9a290b | note | Acceptance Criteria - Material should be spread to minimize number of joints
920f5e8a-ca55-557c-8a5c-1c802ab5e69a | note | Transverse joints offset from one layer to next by not less than 2 metres
557615b6-66c2-5595-84ca-82dc25232b75 | note | In any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m
3682b9c5-4b68-598e-9269-d1c04dc1d153 | note | - - - - - - - - -
446f8d4c-121f-5130-934c-2ecb7be5ba1b | note | Reference Documents - VicRoads Specification Cl.306.08 (a,b &c)
215cec76-fce6-52f3-a685-683b3ce93282 | note | - - - - - - - - -
e214591d-a20d-5754-9dec-cacc31642054 | note | Inspection / Test Method - Site Inspection
e8c77445-35d6-51cf-b6ad-d1e19b9017cc | note | - - - - - - - - -
920d4c65-d91e-5ec3-be24-fae782cd51cb | note | Record of conformity - Signed ITP
c3810f7a-e8e6-5a54-a2ec-2b2557bf2bbc | note | - - - - - - - - -
f4f4eec8-3e3a-51b3-90b3-082d4d2a241e | note | IP
385e68c9-de27-5aee-988f-15d699df9e8b | note | - - - - - - - - -
b7c43504-f279-5bb8-b379-fb87fb2fb895 | note | Responsibility - Site Engineer
f38b5e01-7ab8-55e4-b508-c3a2835f231f | note | - - - - - - - - -
0f3e02d8-fc72-5ac5-8c51-d5afeb363905 | date | Date Completed:
| checkpoint | 2.4 - Longitudinal Joints
e50e8439-b448-5040-9345-7fb7083c188e | note | Frequency - Check prior to placing material
ea65277f-82c8-55e1-b643-5905c9f0fca8 | note | - - - - - - - - -
619afd3e-bdfe-5708-8cf5-abe448d9ccf2 | note | Acceptance Criteria - Material should be spread to minimize number of joints
39440d24-e71e-5687-b989-9b4d0a7dc187 | note | Longitudinal joints offset from one layer to next by not less than 150mm
122d823b-9379-5eb2-910a-2671f81abb1f | note | Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
0d25827a-e7df-56f9-aa0f-50bb4c7e231e | note | - - - - - - - - -
7b955d03-622f-5925-959e-357fcf280e55 | note | Reference Documents - VicRoads Specification Cl.306.08 (a,d &e)
f7983d2a-51e5-52a1-b267-9bfd156cc396 | note | - - - - - - - - -
3ec40274-19ce-5281-a609-dc7d990126ac | note | Inspection / Test Method - Site Inspection
f9f29bc5-dfa5-5363-82e1-dc51b9ab12a5 | note | - - - - - - - - -
beee696e-9b72-5bc0-8f12-9def331ea47e | note | Record of conformity - Signed ITP
e871c2d8-8da2-53a4-a312-6e7465c1c15b | note | - - - - - - - - -
527ed9cc-603c-536a-84f6-adde1c102098 | note | IP
76a4c4e1-b540-5e46-aab1-f00a929ecd2e | note | - - - - - - - - -
4f8f47b7-a948-5c8f-9f7f-5f447cac1161 | note | Responsibility - Site Engineer
5f3e4732-5e82-555f-b343-3cebc949eab4 | note | - - - - - - - - -
82d86ed1-d4ff-59aa-9e4e-ca22553e99d8 | date | Date Completed:
| checkpoint | 2.5 - Layer Thickness
e5ae58af-5541-5788-8485-7a65838b4490 | note | Frequency - Check prior to placing material
ac76ad92-9d9a-558a-9d53-fbd88fb5bd79 | note | - - - - - - - - -
f46db5e5-eb1b-53b1-9bdf-8a508c34ba7d | note | Acceptance Criteria - Compacted layer thickness should be not less than 100mm and not greater than 180mm.
d9da9f06-d272-599b-84d8-4dfb761dc60c | note | - - - - - - - - -
4a94e7b5-f0cd-573b-8924-9d9138dfa3df | note | Reference Documents - VicRoads Specification Cl.306.11
11f98c44-9e1f-5f3f-ab0f-d00714384414 | note | - - - - - - - - -
88d8934f-1fed-5b0d-91f9-62afba4d3cdd | note | Inspection / Test Method - Site Inspection
b5f3d79d-f588-5564-858d-54f242300784 | note | - - - - - - - - -
9b9c96f3-71c7-508e-89fe-36babf6fe3a3 | note | Record of conformity - Signed ITP
4e981969-83a5-57fe-93cf-ed5496a46f8a | note | - - - - - - - - -
83d537e3-8b56-5d1a-9ab5-89c76f0decf8 | note | IP
3b025eb9-e2ee-51f0-80a1-1411a8855e28 | note | - - - - - - - - -
727c5752-82a5-51e4-ab69-3e807d6d6740 | note | Responsibility - Site Engineer
928894d7-ff64-59d4-88db-048e0a9bc203 | note | - - - - - - - - -
12ccea30-bcb8-56b6-b2d4-1fd621553923 | date | Date Completed:
| checkpoint | 2.6 - Delivery, Placement and Working Time
b9d87ed2-5da8-504c-9a2b-4c8b77adfd37 | note | Frequency - Each Lot
357f247e-28f0-5598-a580-26080fd0a7a2 | note | - - - - - - - - -
435439f6-7100-5445-891f-2312d8e02e74 | note | Acceptance Criteria - Review delivery dockets to ensure all information required as per 306.07 (b) is recorded and meets the specification requirements.
2ad9465b-bfcb-52e7-a18d-36f222393a0a | note | Working Shall Not be more than specified for each binder: Rapid Setting (GP) - 2hrs (Oct-Apr) 3hrs (May-Sept) Medium Setting (GB) - 3hrs (Oct-Apr) 5hrs (May-Sept) Slow Setting (Slag) - 8hrs (Oct-Apr) 12hrs (May-Sept)
5a9b6569-541a-5b65-869b-b6616597f8c3 | note | - - - - - - - - -
10ab176e-ac74-5e05-a193-4ef78921a2be | note | Reference Documents - VicRoads Spec. Cl.306.07
405612f6-3663-5df8-81d9-a369870a7586 | note | VicRoads Spec. Cl.306.09
155cb056-17f1-55b3-82dd-2bd556dfcf26 | note | Table 306.091
800511c4-4e19-50b9-8ebf-aa7b4e4518c2 | note | - - - - - - - - -
512cdc3a-a07c-553f-b082-05098ed8e327 | note | Inspection / Test Method - Site Inspection
d5ca206c-9b76-518b-b2ff-06d9b3bf8743 | note | - - - - - - - - -
7136a15a-2681-5c22-957c-d5c08cdb610e | note | Record of conformity - Signed ITP
ecdd1266-0f1d-5eb1-998c-4c5d39955ef8 | note | - - - - - - - - -
608f739f-6a16-50ce-8f40-7c5ebd7d779a | note | Attach: Delivery Dockets
ed94180c-d565-5129-a322-29496ac50139 | note | - - - - - - - - -
b5d492e5-4517-5a78-8a0e-bca6597d7b26 | note | IP
468768cc-8283-5240-9710-9a9e4fad768b | note | - - - - - - - - -
ab1752a5-a82a-55ef-bd6f-dd4e2265e2dc | note | Responsibility - Site Engineer
43e997b7-180e-5b25-a9be-ed964972b240 | note | - - - - - - - - -
1e085dcf-0ddf-5e63-bcce-8f1931ee7671 | date | Date Completed:
| checkpoint | 2.7 - Water
f0fd1998-84d2-563d-9820-23614c0bb050 | note | Frequency - Each Lot
581f2f6e-5628-5494-903e-dac3d520d4bd | note | - - - - - - - - -
dc053589-c243-53e0-b7b0-18a6cb651731 | note | Acceptance Criteria - Except for the purpose of curing, no water shall be added to the cementitious treated material.
d7237664-b0d7-5b9d-9a87-5c8e0e7b4d4b | note | Water shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
527a77cb-a8b4-5e35-aebe-c5ecec2fee08 | note | - - - - - - - - -
7dfc2da2-36e3-5e36-8292-fd7bb97b5334 | note | Reference Documents - VicRoads Spec. Cl.306.06
0a8d3214-aeff-5e88-a5d4-699f8c843fd4 | note | - - - - - - - - -
cb788fe3-2da8-5f33-a539-dff39729b801 | note | Inspection / Test Method - Site Inspection
c06353dd-7221-57ac-a96b-49332bf64d0b | note | - - - - - - - - -
4e0788fd-4319-5487-807b-5cc26f7920d6 | note | Record of conformity - Signed ITP
bc289088-aa54-5190-a30e-c40b01e5e058 | note | - - - - - - - - -
5baffb1d-f445-57e9-98ae-85257a0cd2d2 | note | IP
156ffb30-20b7-5acf-a2e1-ff2eabb80139 | note | - - - - - - - - -
8edcb614-c15b-5405-8e26-c89308e3975d | note | Responsibility - Site Engineer
b01e541e-a6d6-5812-8aaa-a1d94fdf8011 | note | - - - - - - - - -
dc0316b1-7f3e-55a3-8a96-dd596b5fe290 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale
23d33378-8747-5cb7-a7f0-a320a28dbe0a | note | Frequency - Prior to Testing
3b9db9e7-cf9b-5d8c-8f0f-b9b1a5045ae6 | note | - - - - - - - - -
eec9ad79-973b-55e1-b732-ea5fc93c6b94 | note | Acceptance Criteria - Compaction Scale Required is Scale A.
28a4b6c8-ba88-5c2d-9e10-3ce8465565f5 | note | - - - - - - - - -
6b256164-9f44-5485-bd37-d3ee924b3d27 | note | Reference Documents - Project Specification Table 3040.064
43a8febf-c79b-5dc2-89f0-fc5128dff7a5 | note | - - - - - - - - -
4746e68f-4de2-5e3c-8078-ddbc33d12f88 | note | Inspection / Test Method - Document review
e46d9d40-eeba-535c-b084-8287a977918e | note | - - - - - - - - -
d717033d-4c60-5be0-8b17-c2a51f122bbb | note | Record of conformity - Signed ITP
a7847862-ab6f-538f-8b5e-c3cb61ed5a45 | note | - - - - - - - - -
e8455e35-cb9a-5de9-9ded-efba429db887 | note | IP
a2328fbd-cf87-596b-818d-235ecad28b7a | note | - - - - - - - - -
9d1130a3-cab0-53ce-8bbb-a6964c4a82d6 | note | Responsibility - Site Engineer
71e96480-2cf7-56ff-a811-ea91a97d9145 | note | - - - - - - - - -
265ed30e-e772-5c19-925e-f24215da6727 | date | Date Completed:
| checkpoint | 3.2 - Compaction - Modified Compactive Effort & Moisture content
b047158e-d131-578c-961a-eb506600424f | note | Frequency - Six tests per lot
a358eb14-ed5e-5171-9eab-a2362882063f | note | - - - - - - - - -
4e91358e-5e29-51a0-81df-6a2fe6670480 | note | Acceptance Criteria - Characteristic Value of MDD to be 96% or greater. Moisture content at the time of spreading and compaction, is within +0.5% and -1.0 % from the Modified optimum moisture content.
98bc847f-9e5b-5f3e-8e58-5f454a98e106 | note | - - - - - - - - -
7c2c0b89-871a-5a69-a853-1d25dd920930 | note | Reference Documents - VicRoads Specification Cl.306.09(a)(b)
d8eb48fa-8d4d-5aa4-bdf5-15afd1a19db3 | note | - - - - - - - - -
66f1deee-5797-5fa0-8c6a-8d7fac392af8 | note | Inspection / Test Method - Document review
a0de5e3e-7459-5d7f-a514-d7ceb30c6f64 | note | - - - - - - - - -
37dec858-9c5d-5fde-a335-74398447bce4 | note | Record of conformity - Test Records
e484110a-e6ec-5e92-98ab-ef66af203bfc | note | - - - - - - - - -
cacadad3-7db6-52b3-a632-8466468b3105 | note | IP
77699f76-b589-58db-af15-0ed4dbfcd1b6 | note | - - - - - - - - -
e53cd810-62b0-56a0-b22e-66e61cb8408f | note | Responsibility - Site Engineer
33ca8fc3-8056-53c2-b747-31a2a44f807a | note | - - - - - - - - -
3016ed51-72f6-53eb-96f3-efb1e9293d01 | date | Date Completed:
| checkpoint | 3.3 - Surface Shape
e620c06b-2f9f-59e9-8348-32aeb3276afe | note | Frequency - As required per Lot
0209e21a-5ba2-51c1-ab3e-5c76f190db64 | note | - - - - - - - - -
4f098c62-883b-5b83-8d84-c147a5265222 | note | Acceptance Criteria - No point on the surface of the cementitious subbase layer shall vary by more than 8 mm from a 3 metre straight edge placed in any direction. Water shall not pond on the surface of the cementitious treated subbase
c76724b0-5195-5edd-bc27-53db165c9de4 | note | - - - - - - - - -
76c0bc97-3990-5b65-907d-6bc66dd6bfa6 | note | Reference Documents - VicRoads Specification Cl.306.03(c)
fda8ec90-ad58-538e-bb05-8195011a964d | note | - - - - - - - - -
f416a7e7-b986-595c-b912-8a50c6194b02 | note | Inspection / Test Method - Document review
d0da6c8b-298c-5399-b597-019727f3df54 | note | - - - - - - - - -
10fefe55-ec97-5281-a8bb-da9c185851ab | note | Record of conformity - Straight Edge Verification records
f78d5df8-ef00-52e3-9c88-7cd972b7faaf | note | - - - - - - - - -
af669436-c34f-5751-98db-5aba17155c39 | note | IP
38e9bc20-b82d-57cc-9846-7f157de373a1 | note | - - - - - - - - -
d68f3ea5-c4b1-5eb8-8856-dc9caf27f815 | note | Responsibility - Site Engineer
5059747d-cfbe-5418-937f-a5dedb2cc23e | note | - - - - - - - - -
8a24ca1c-7d16-5708-9de1-5d07bd4c1299 | date | Date Completed:
| checkpoint | 3.4 - Surface Level
4ba229b1-2d23-52c1-8f38-650f41a0ad19 | note | Frequency - Minimum 80 measurements per lot
0cc4df23-e5b1-53a5-9924-7e9691289d77 | note | - - - - - - - - -
aa14b904-c4ed-5029-a99e-5f59c8c4dec4 | note | Acceptance Criteria - Subgrade:
3b87f67d-0fe9-501a-8767-d3af9557aca6 | note | – Mean value of all level readings to range between +5/-15
e0714f45-dc3d-5f91-b4f0-80844a966e30 | note | – Standard deviation of all level readings to be less than or equal to 12 Subbase:
2cf88dbe-a5b2-5b50-9bd2-5edaa5efbef9 | note | – Mean value of all level readings to range between +4/-8
7a21a937-c6fb-51e6-9348-b112e7772d64 | note | – Standard deviation of all level readings to be less than or equal to 8
00e6218a-b9bd-5138-9af9-ab4394eb9e27 | note | - - - - - - - - -
87091ac7-a0e4-5562-81ad-057b1e7114e4 | note | Reference Documents - VicRoads Specification Cl.306.03(b)
302c1af2-579d-5d52-95d3-ca89983bf27e | note | Table 306.032
77456773-a273-5219-ad05-1ddd69076c76 | note | - - - - - - - - -
85fe6336-6a72-5e0f-9922-d490ca30bc3b | note | Inspection / Test Method - Document Review
ea491a3f-f654-53d0-939b-5c9c029274fa | note | - - - - - - - - -
c24aafe1-2325-5b57-bdba-7b7fc5e7ed4e | note | Record of conformity - Survey Report
7ee0721e-99c7-5358-bf58-51a6cf986dad | note | - - - - - - - - -
1327fe19-1feb-5074-8e38-f0de34243318 | note | SCP
b04d04a6-996f-519e-a178-67637b1d195d | note | - - - - - - - - -
6b1e5cf6-6678-5c70-80d8-fe83bb665125 | note | Responsibility - Site Engineer
9d2b2219-a5a7-534c-ab31-48f6fd0bba24 | note | - - - - - - - - -
dace130d-6ba0-525e-883e-f77ecf38fbf6 | date | Date Completed:
| checkpoint | Final Inspection
52675fbb-32c5-501f-b6b7-6a424e1d6d3e | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
f4b4c88a-e455-5563-b2e7-a84f5736aa78 | textbox | Print Name:
d0caf819-8bd0-5428-b2d1-530b1f50fdca | textbox | Position:
d38541ee-eddc-5d1c-bb68-2e8e3fd56d08 | date | Date:
03e27f14-69c8-5478-aba3-863857204d54 | date | Work Completed On
| checklist | ITP 0012 - Kerb and Channel | itp | ITP-012-AX-LOT-XXX - Desc | 077a9954-51c3-4509-bd1e-92dab7d13edb
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check that current revision drawings are being used
03c3c4f4-d4e1-5c29-8ef0-925f9efad60e | note | Frequency: Prior to Commencing
19cb669f-345a-58e1-9799-357b4ce36337 | note | - - - - - - - - -
f69a62fd-e529-5e60-b94e-798d05f53833 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
db884241-f9cd-5017-b4e1-57a6290b1c8f | note | - - - - - - - - -
6e3a1ed5-23ed-58a1-a382-4a546eab3adb | note | Reference Documents: Project Drawings / Drawing Register
c825b2e8-7bf3-5b06-803f-9576c6d65beb | note | - - - - - - - - -
4d0399d7-b590-5d75-9a42-f0c5a7409a64 | note | Inspection / Test Method: Document review
7ea51c3e-5e71-569d-b747-6eeb6bfe57f2 | note | - - - - - - - - -
eed3bd26-7d4f-5b64-add1-26e58fc92285 | note | Record of conformity: Latest Revision Drawings
40903d2a-0149-58a8-860c-ec2322d86e24 | note | - - - - - - - - -
b2207207-aefd-5798-a795-05eec10772f1 | note | AP
88be3834-aedf-514c-9eeb-5a25dd29ff5a | note | - - - - - - - - -
761f938a-8ec3-59d8-a660-4c85502a69c6 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Mix design
8402a322-29a7-5d82-9059-6f0bed4a86fd | note | Frequency: Prior to commencing
69c131fe-c6ec-5ee7-8319-9c753330c2a4 | note | - - - - - - - - -
8a58f279-0fcc-5f11-9bc6-4f7aaa57f1ea | note | Acceptance Criteria: Approved VR mix design to be used. Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3. Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cementâ€“based concrete
2a140213-ef47-5ef2-b4f5-10397a7b9ff6 | note | - - - - - - - - -
7e44499a-3c4a-56fe-a268-9bf72c727267 | note | Reference Documents: SD2001, AS1379, Section 703.05, 703.06, 703.07
79178f8f-f039-5950-a9d7-a2a3dbb0c284 | note | - - - - - - - - -
85a00654-8492-53b6-8aa2-fab50f8e7258 | note | Inspection / Test Method: Document Review
9803f13f-62cd-5bd8-a141-c63f9c7a1106 | note | - - - - - - - - -
acf23adb-7712-56d2-98f0-cc703b32c967 | note | Record of conformity: ITP signed/Mix Design Certificate
766ce301-2ae8-5b9e-b5f3-f01d18dd0da5 | note | - - - - - - - - -
452adfdc-b499-5ca0-9f1b-931b33891670 | note | HP
c59a2826-bfb7-560a-af34-1f48319daa5c | note | - - - - - - - - -
8f7794e5-a1ae-5a58-9649-6f8bd8b89787 | note | Responsibility: Site Engineer & Superintendent
| signoff | HOLD POINT
| checkpoint | 1.3 - Bedding Material
4775c70d-8bfc-5b55-a131-bf7bc25ead3b | note | Frequency: Prior to commencing
9f8e369c-e07c-5d80-ab74-3498a1bc67e3 | note | - - - - - - - - -
a63e8390-71a7-5d2f-a0f4-d2df9efddf61 | note | Acceptance Criteria: Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
68e3f42a-051a-5667-bfe3-60dc937e9496 | note | - - - - - - - - -
f04e0088-6ebb-5045-a239-4ed644bba863 | note | Reference Documents: Section 703.21 IFC Drawings
32b12911-b423-5d72-a7c4-6d0fe8e3cf58 | note | - - - - - - - - -
11e822cb-cee6-5aad-b6e0-250915899735 | note | Inspection / Test Method: Verify
6a6980c8-384c-5592-9e51-a749e7993389 | note | - - - - - - - - -
088441f9-8ad3-5d3d-9974-ff87e431d47d | note | Record of conformity: Material Conformance Certificate
1a34448e-0115-50f1-bf51-9609474f3082 | note | - - - - - - - - -
18333a42-7222-598a-8861-6167358890d5 | note | HP*
d3b80ada-03f5-58e3-ae09-1c4f26a95a83 | note | - - - - - - - - -
f6843afd-7ac7-5ae3-90f1-6be39f506516 | note | Responsibility: Site Engineer
| checkpoint | 1.4 - Curing Compound
79c9f203-98ad-5818-875c-f06c33514318 | note | Frequency: Prior to commencing
5c2553fc-a64c-589f-819b-fe4c4d1952ab | note | - - - - - - - - -
8921b2dd-67d7-5cad-83bb-e53fe8ceee05 | note | Acceptance Criteria: Curing compound shall comply with AS3799
31b71ab9-77fb-523d-8b20-fa2857ffd1ff | note | - - - - - - - - -
45a54779-2b26-5daf-9d60-2d785595aea1 | note | Reference Documents: Section 703.10
319fe73e-f956-581e-9089-a45437a14fed | note | - - - - - - - - -
5926d2da-f316-5c37-a0d3-a3acb0f95283 | note | Inspection / Test Method: Verify
103ec1e8-3927-5324-a724-37376e0db1c1 | note | - - - - - - - - -
dc1e60a5-7270-5892-810a-78a5f1bcc90e | note | Record of conformity: Material Conformance Certificate
8db88d2b-0d33-530f-abf9-71a1098b74c5 | note | - - - - - - - - -
5e5809ec-b868-59c5-8763-713cd3f5fd08 | note | HP*
2ac15609-1b6b-5d20-ba36-b8a446bbf1d8 | note | - - - - - - - - -
30e36550-82a0-529b-b6c6-a0a5d3a4564c | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Temporary drainage provisions
0600bce6-790d-5594-97ed-3c85933f3d55 | note | Frequency: Prior to commencing
66681e01-1050-553f-a602-00031c8a0acd | note | - - - - - - - - -
a2cdc689-fc98-5ff1-921e-5117eacf6a92 | note | Acceptance Criteria: If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place. Need to obtain prior written approval from the relevant waterway authority prior to diversion.
b187ca6e-cb8f-5b4f-857a-342d47a7ec48 | note | - - - - - - - - -
7e6fce1b-b231-52a1-a298-d2d19c22a81b | note | Reference Documents: Section 703.18
7072b56d-3834-5eb5-a15d-d386a65563c4 | note | - - - - - - - - -
44ddafe7-524d-534f-a1d1-6be37eef9f30 | note | Inspection / Test Method: Visual inspection
e2b8e451-71a6-5bd6-b2b0-34ce674dda61 | note | - - - - - - - - -
cd1f74bd-9b64-59ee-88b1-a57c306673f3 | note | Record of conformity: ITP signed
8664d83f-9264-53f4-9292-6f5a939ad91f | note | - - - - - - - - -
4fafd8b5-6411-5a25-adba-c3da85ad844b | note | HP*
f294ba5e-69a9-570b-9d35-48bfc4bdf7ca | note | - - - - - - - - -
b945e4bd-1334-51e6-87ec-0470565dd98d | note | Responsibility: Site Engineer / Site Foreman
| section | 2 - Construction / Installation Activities
| checkpoint | 2.1 - Setting out
821a3170-a6a8-5a6b-b4d5-53649493e1a2 | note | Frequency: Prior to start
1fd94a6a-c059-5d56-b5c7-326ee60e3d81 | note | - - - - - - - - -
bf4cd62a-9ba8-58fa-af3b-132f7c6fb71f | note | Acceptance Criteria: Set out work in accordance with drawing. The superintendent will review and confirm set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
eddf8786-7871-5139-b6eb-af5421903b33 | note | - - - - - - - - -
c4ec2608-2551-5e80-b2e4-31216ce5066e | note | Reference Documents: Section 703.17
c0476831-9053-5b91-aeda-a9712ff75418 | note | - - - - - - - - -
de1c781c-4db2-519c-a89e-68055b0e4b48 | note | Inspection / Test Method: Site Inspection
392fc2b1-2ec8-5b48-81f7-0224905f1dc1 | note | - - - - - - - - -
73dcc3d2-81c9-500d-8225-c94bddf52680 | note | Record of conformity: ITP signed
3fe78624-fbb1-5149-9f54-44b372f67f38 | note | - - - - - - - - -
1d40f2ab-bde0-5794-aadc-cdc4071ebdef | note | HP
88c654ed-086d-5f09-9fa8-2da9b270584f | note | - - - - - - - - -
6da70bdc-1387-5479-8591-c2119738191e | note | Responsibility: Site Engineer & Superintendent
| signoff | HOLD POINT
| checkpoint | 2.2 - Bedding
32f51d7d-ca9c-5dfc-ab22-9bc111f23cea | note | Frequency: Each lot
7364b37f-4305-5e6b-8e77-0a4e889db7d9 | note | - - - - - - - - -
a5fb4d9b-d48c-547f-8725-9e67875ee79e | note | Acceptance Criteria: Bedding to be compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted .
bc5de1ec-3e35-52df-91f7-debca994ec17 | note | - - - - - - - - -
3b8ea6a7-2ac4-54ed-b351-b79c8034eda5 | note | Reference Documents: Section 703.21
72e9b41a-e907-51fa-81f3-fcd19c2a01fa | note | - - - - - - - - -
07fd3614-1b05-56f8-8c2a-2112afa5a306 | note | Inspection / Test Method: Site Inspection
5c7b111a-0ea8-50d3-9749-57835207e7d2 | note | - - - - - - - - -
b53745d7-f489-5877-bf9a-9d41bd48e4ce | note | Record of conformity: ITP signed
5726c0b6-cbc4-5871-bf0f-7ec863332886 | note | - - - - - - - - -
604f5faf-f2b3-561b-b596-c782f52886a2 | note | WP
cb8d0801-a90d-5543-a811-111551b54ea7 | note | - - - - - - - - -
3b73eff6-b946-5c87-beaa-7e2d4586835d | note | Responsibility: Site Engineer & Superintendent
| checkpoint | 2.3 - Formwork
d0bd00e6-2bac-5002-9fc2-b556feaa0902 | note | Frequency: Each lot
2f2305a1-95ae-5f66-a784-a0564478817d | note | - - - - - - - - -
023a91df-5388-5358-a8f8-3c4b5ab07e0f | note | Acceptance Criteria: Joints in formwork shall be constructed such that loss of mortar is prevented. Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
12150cc8-a621-544e-81f7-16e873e35373 | note | - - - - - - - - -
9c6c2094-1aa1-5fdf-a4fe-41eddc8e91e3 | note | Reference Documents: Section 703.12 AS3610
ebeb75b4-57a6-5979-a2e7-cce59c3c8ffe | note | - - - - - - - - -
e0daa7a6-5c67-5f28-8dc5-690f661a286f | note | Inspection / Test Method: Site Inspection
ff931d15-8aac-5e02-9a2a-90b468cea219 | note | - - - - - - - - -
63974bb4-6606-5576-b2ff-f63f47ebf2e8 | note | Record of conformity: ITP signed
4ef25b73-0276-5af7-8426-db37246661e8 | note | - - - - - - - - -
59948fd6-8e5c-5d24-a6d9-ca80e819fc7b | note | WP
333e53cd-8b39-50a6-af3f-179ca2d965d0 | note | - - - - - - - - -
7aef8986-6d4d-5d98-8d12-34746b67e4ed | note | Responsibility: Site Engineer & Superintendent
| checkpoint | 2.4 - Pre Pour Check
5067fef1-782a-5309-8022-7cc5daeeb03e | note | Frequency: Each lot
279fc57d-fffd-5197-be32-a3eb4cbad130 | note | - - - - - - - - -
2b021afd-c980-5967-89f4-89104442fb72 | note | Acceptance Criteria: Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is > 35Â°C or < 5Â°C
9f93d2b3-080a-55d5-9a22-7f7b8dff3022 | note | - - - - - - - - -
7248d0b7-2ffd-5b25-a1d2-ffc793603ce8 | note | Reference Documents: Section 703.09 Section 703.21 Section 610.17a), b) & c)
52c437f5-97e5-5dc4-a492-fde10689e93d | note | - - - - - - - - -
a703bfd7-24b9-5126-b65f-fbfe29018e8d | note | Inspection / Test Method: Site Inspection
5d08a497-feaa-5ef7-a4fe-d542f48a5322 | note | - - - - - - - - -
435d3ba5-7151-5dae-a358-2a011ddf60bf | note | Record of conformity: ITP signed Ambient temperature-----Â°C
0eb5447d-22e3-585b-97bd-dca5a429f345 | note | - - - - - - - - -
9b9ff796-9a78-5684-9f1d-81acd29c20e0 | note | HP*/WP
78883e20-f4c0-54ba-80d5-5da21bd3f3a7 | note | - - - - - - - - -
9babebc4-1980-5084-9a97-f2951320673d | note | Responsibility: Site Engineer/Site superintendent
| checkpoint | 2.5 - Concrete placement
a1a2bc3f-d385-51de-8dee-0486316f380b | note | Frequency: Each lot
9c9a82cc-ff45-5df3-8490-5625afece3e7 | note | - - - - - - - - -
8d485fc2-d95b-51de-b350-b89a149b25d2 | note | Acceptance Criteria: Temperature of concrete to be measured immediately prior to placing and shall not be less than 10Â°C or greater than 32Â°C. Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches. Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints. Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
6ddb3cb3-30e2-5097-ba31-24464ca72efd | note | - - - - - - - - -
2d8daf94-5ebf-56a5-a4ec-62add5307301 | note | Reference Documents: Section 703.08 Section 703.23
b5aca965-4853-58d9-bbc5-55389eb118e3 | note | - - - - - - - - -
954a5e5b-1ee7-5766-b883-224937dbc3b6 | note | Inspection / Test Method: Site Inspection
94c038bd-7161-5a16-a247-c44cdb347cfe | note | - - - - - - - - -
d1dbd245-143e-5019-a21c-7653228da3c2 | note | Record of conformity: ITP signed Concrete Temperature ---Â°C
9fc81721-0984-5ba5-93d7-08c3272b6ff9 | note | - - - - - - - - -
f8e1de68-99f4-5042-adb2-c893d04bd783 | note | IP
a8b1d499-c51a-56ff-b86c-6d00e4903fc0 | note | - - - - - - - - -
a6012995-dbc4-5192-8409-5bd99a0fbbef | note | Responsibility: Site engineer
| checkpoint | 2.6 - Transitions
ff482e61-8ae7-5902-93ac-014454eb25b2 | note | Frequency: Each lot
8153e2ec-b361-5630-9ce3-3e463d856e40 | note | - - - - - - - - -
72b6843e-3974-5ec8-b738-b5f9054edca1 | note | Acceptance Criteria: Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
06f8c096-dda6-5c2b-a225-ede3194325af | note | - - - - - - - - -
ce4dad3a-bc76-595d-bb44-c09c091d3fbf | note | Reference Documents: Section 703.24
f4e2120a-b121-55c3-a714-304e6fdd9c7d | note | - - - - - - - - -
c782e203-b91c-5a3a-9d3a-7c277beb0dbc | note | Inspection / Test Method: Site Inspection
fcec476c-df77-5dfc-a245-578f1fdb0c4d | note | - - - - - - - - -
8857833d-a148-58e1-a686-7adfa9feed98 | note | Record of conformity: ITP Signed
bfed5462-e8b1-5c9e-9133-8a8d83f6ab48 | note | - - - - - - - - -
e20b6887-2c05-5c64-9683-00964bed69d8 | note | IP
68616c8d-ab15-5a6a-a7ae-210eb4130ce5 | note | - - - - - - - - -
a72cd6b1-c9bc-5b52-9481-4624e8805eee | note | Responsibility: Site engineer
| checkpoint | 2.7 - Surface Finish
8f424198-14a0-51de-9a6d-53a46a147545 | note | Frequency: Each lot
e91afee6-07c7-5539-9655-afb1330ad92a | note | - - - - - - - - -
61d5fdbc-5759-5585-af76-db2da4e7a0ff | note | Acceptance Criteria: All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished. Renderings shall be applied within 30 minutes of extrusion. Concrete to have a neat appearance and uniform colour. Class 3 finish required for external surfaces. Class 4 finish required for permanently hidden surfaces.
25669f6d-64c6-5a46-adf1-66f817528aea | note | - - - - - - - - -
18744e27-6b5e-5bb5-bea4-b8b34257c7e4 | note | Reference Documents: Section 703.25
14547fda-c5ab-5663-b891-081927b67379 | note | - - - - - - - - -
8dd59177-931e-57cc-9d25-2ae4bf8ebd6c | note | Inspection / Test Method: Site Inspection
ffa44311-3d6b-5e77-8a98-db51f9a16f98 | note | - - - - - - - - -
5887467a-d670-56d1-a74d-018883a12ac5 | note | Record of conformity: ITP signed
56762e4a-3fdd-5c0a-a356-9d8cbf5a87cd | note | - - - - - - - - -
bc9f39b0-272c-561a-9a9c-691d0c8ed6c1 | note | IP
d460f7af-b488-50f6-927e-f9bc9ed27786 | note | - - - - - - - - -
a980acd9-0edd-5080-9a2b-eb41fc045fa4 | note | Responsibility: Site Engineer/ Site Foreman
| checkpoint | 2.8 - Formwork Stripping
2078b6e4-1685-5488-b93b-ad2dc69bf3e0 | note | Frequency: Each lot
f0aa4512-ce1a-5f92-bb19-eade37a81cdc | note | - - - - - - - - -
f605859d-75f5-599a-9952-6a6253f49b5c | note | Acceptance Criteria: Formwork shall not be stripped before the minimum time of: External faces 2 days Permanently hidden faces 1 day
99fe3bd9-01ee-59ff-899d-76799d2f7dbc | note | - - - - - - - - -
cf918bfe-f4a4-534b-859a-87ae5ed53cbd | note | Reference Documents: Section 703.12 AS3610
d683cbc3-d023-5375-a499-1153068123a3 | note | - - - - - - - - -
8f441eee-bd09-53be-b301-2f11d8c17160 | note | Inspection / Test Method: Site Inspection
c32f3e19-4b3b-5005-9857-a1a7b5d28ad7 | note | - - - - - - - - -
37841320-38f2-5a79-8a77-3dc7e94d518b | note | Record of conformity: ITP signed
72b457ff-ef8c-5abe-8aab-89be9d2f2960 | note | - - - - - - - - -
d8a30341-c698-54bd-847b-026fd95dbf1c | note | IP
89c9f4e5-a610-5487-8511-90b6d5ec3043 | note | - - - - - - - - -
e6751a8c-70fb-5673-9773-cf3690e050cd | note | Responsibility: Site Engineer/ Site Foreman
| checkpoint | 2.9 - Tolerance
13813b6f-1541-59b7-a0c6-8ee38dd7141b | note | Frequency: Each lot
d7d49331-3a1e-5dcf-9e5f-bb2d28fa60f5 | note | - - - - - - - - -
248db10d-3974-5fe6-b372-660084bb95ed | note | Acceptance Criteria: Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15mm for width , for dimension less than 25mm tolerance to be Â±3mm. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm. Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5 mm at any point.
0b3bbb22-977c-593f-a18f-5e600f23e13b | note | - - - - - - - - -
658ee229-d782-5103-aeab-7558268f267a | note | Reference Documents: Section 703.15
ac929c6d-c540-53ba-8f2b-0e3f39570075 | note | - - - - - - - - -
9acbe953-ce2d-5ac9-ab32-03001feb8d2c | note | Inspection / Test Method: Site Inspection
8b257957-6699-5584-8865-6a2065c0ddcf | note | - - - - - - - - -
a10a2008-94a7-531c-a6fd-464ed7f9a65c | note | Record of conformity: ITP signed
28f99d48-0055-58c1-998a-454f5a280a9c | note | - - - - - - - - -
04072674-8aae-5c09-9869-79890bb4c3d8 | note | IP
2b81a988-b268-513b-ad4e-119ecc92aaa7 | note | - - - - - - - - -
dcb7ba29-afd3-5efd-aca1-913f188ba55d | note | Responsibility: SITE Engineer/surveyor
| checkpoint | 2.10 - Curing
5a25d0b9-1358-5689-823f-32ac358228f8 | note | Frequency: Each lot
bf8a54f7-6534-5a6c-816a-932717daf06e | note | - - - - - - - - -
d1d9a21a-a88f-5119-89cb-5325c2824cf0 | note | Acceptance Criteria: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed. Concrete edgings shall be cured for a period of not less than three days after placing the concrete
b67dfed5-e62d-5fe6-9853-d615961c3d95 | note | - - - - - - - - -
7a02e9f6-8851-5d18-8eb7-d90b0473a2f7 | note | Reference Documents: Section 703.10
5c7606bf-7e02-54be-859e-0b854a9ef374 | note | - - - - - - - - -
c4659408-b95c-5b84-b1df-e490701656ba | note | Inspection / Test Method: Site Inspection
8d15ab53-2c80-5d78-889a-17369fce3169 | note | - - - - - - - - -
d98a0d1a-dc08-599e-a1ea-91fb797916ef | note | Record of conformity: ITP signed
b40a1945-c941-57df-bdbc-31560e2b1cbe | note | - - - - - - - - -
90d0b0f4-09c7-529b-b762-77dcb27ccd03 | note | IP
0b7d563a-5a14-5d8c-a8dd-9557a02ca00b | note | - - - - - - - - -
3f86e047-32b1-5df0-94c9-3289ac508ee3 | note | Responsibility: Site Engineer/Site Foreman
| checkpoint | 2.11 - Joints
202662c0-9c95-5f57-ae44-47b19f4e7cfe | note | Frequency: Each joint
20ca555e-0bb5-5f98-9c5e-8b89ff12323e | note | - - - - - - - - -
f9e5485e-0c52-508b-b864-697ea658c84e | note | Acceptance Criteria: Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section). Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
3a74b83d-91ef-5f33-a3be-29427ce1b717 | note | - - - - - - - - -
8df31700-162c-5a04-aea3-c8cc124878ea | note | Reference Documents: Section 703.26
3384d50f-d31b-511e-998d-204bf4f6c3ff | note | - - - - - - - - -
d17ffa11-1074-5ddb-be36-551cbf45bad6 | note | Inspection / Test Method: Site Inspection
b2a1618d-30ff-5170-90c5-ec0a437e39b7 | note | - - - - - - - - -
a42a28f7-4d0c-57be-9222-c5af927ca51a | note | Record of conformity: ITP signed
fea26e42-67e1-546b-a916-4f573adfd5c3 | note | - - - - - - - - -
4362bff5-e9c9-5bfc-995a-2b199a4648fe | note | IP
6e0370b9-d219-50cc-9748-f4db3faaa6a4 | note | - - - - - - - - -
3b8a3bd1-0bac-5957-9115-bbd79c0053cc | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 2.12 - Backfilling
8a2ff20f-0aa5-5192-9004-8348bb7c2c52 | note | Frequency: Each lot
2c5b5e63-5088-5fd4-8d77-814886e6ed4c | note | - - - - - - - - -
132799eb-6ad3-59cb-baa1-d48274d61cdf | note | Acceptance Criteria: No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
1e8117f7-f68e-55ef-9365-e3992f2a00d1 | note | - - - - - - - - -
785f16d2-d984-583c-bf53-39e4e16c23b4 | note | Reference Documents: Vic Road spec 703.29
f19fd8b7-2e1e-5429-a687-b8e8ea59c6cc | note | - - - - - - - - -
c645e88b-8c02-5921-bff2-91330ce3ef39 | note | Inspection / Test Method: Site Inspection
360fa6b8-dae4-5120-a1b3-006fce76a59b | note | - - - - - - - - -
e56412da-84f8-5ee0-a11d-29f5f4b35fc1 | note | Record of conformity: ITP signed
14ea599c-d9d4-53a5-abdb-0636bf3df0db | note | - - - - - - - - -
533d4b70-0df3-5cb0-89e9-eb813be61126 | note | IP
55546ae1-37b3-5bb3-84d6-6ef46ca4b4ca | note | - - - - - - - - -
10a1c14f-971a-5f16-90a0-d9432589eb2a | note | Responsibility: Site Engineer
| checkpoint | 2.13 - Protection of Concrete
e399fc9c-c843-5326-88a1-9b4bb415a482 | note | Frequency: Each lot
ec257f57-d9fb-5657-a27b-98f9b3d6c8d3 | note | - - - - - - - - -
3f436246-8fad-5500-9dee-f5745e22167f | note | Acceptance Criteria: All concrete shall be protected from damage from early loading.
d50c4d25-a980-56d0-b8c5-7d723e63dc25 | note | - - - - - - - - -
088758e1-710b-5806-964b-1e685d068c43 | note | Reference Documents: Section 703.27
8fb9e6cc-f643-547f-ab82-51d366608b2e | note | - - - - - - - - -
b080d957-f95e-5e64-92ac-7e3930d550ee | note | Inspection / Test Method: Site Inspection
130136cc-5bc5-514f-aa2d-31a88299106a | note | - - - - - - - - -
10afe4d0-f085-5cf3-8141-844983b1a22c | note | Record of conformity: ITP signed
ffd4acfe-95dd-5696-8fd6-8f77599dd5b0 | note | - - - - - - - - -
c5bcc2bb-1026-575c-886c-f04fbd09b750 | note | IP
03f6fb18-6e52-5522-aedd-fd24f4fb9508 | note | - - - - - - - - -
891e626a-01b3-5e9f-97b7-d29ecd37f8f8 | note | Responsibility: Site Engineer
| checkpoint | 2.14 - Cracking of Concrete
7f851159-b474-5577-af3f-14dca6c40822 | note | Frequency: Each lot
2a23315a-c366-533c-9d70-1531ca4a7f04 | note | - - - - - - - - -
2ff4c6f3-cfff-551a-b09f-05bf927bca25 | note | Acceptance Criteria: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
31da604a-ce09-535f-8534-3d40d4fdb5ef | note | - - - - - - - - -
f14212c1-7fb3-5385-9dd0-26f31d8dff70 | note | Reference Documents: Section 703.30
4b53271c-f0cb-5625-a8a3-1d038296bc7b | note | - - - - - - - - -
9876ea18-6cb9-5d9e-9dab-393818fb6ffd | note | Inspection / Test Method: Site Inspection
c36f5e43-0e88-5d87-a0e7-3ff7fc8a6e71 | note | - - - - - - - - -
01fb8f8c-49cd-577e-8a4b-ea258f362816 | note | Record of conformity: ITP signed
ae1c51c4-9b7a-5388-8909-48fba5d29a89 | note | - - - - - - - - -
9b80d215-db8e-5bd9-8aef-3746c4d00fff | note | IP
bca573c2-2518-5455-a27b-9c8926ddad17 | note | - - - - - - - - -
3344a68a-458f-5c85-945f-52956e4178a5 | note | Responsibility: Site Engineer
| section | 3 - Post-construction / Post-installation Activities
| checkpoint | 3.1 - Survey Conformance
97792f7e-7a32-577e-adfa-3c7db7ee0e75 | note | Frequency: Completion of each lot
b18ac26a-f660-5f32-8a5e-fc98fbc5d9a0 | note | - - - - - - - - -
f58b823a-17c4-527d-ae3f-4ed8e34ec6f0 | note | Acceptance Criteria: Survey to as built the works and to confirm the works are within the specified tolerances.
849a651b-e7a6-592e-bfe3-03a452369768 | note | - - - - - - - - -
ea51b1f4-c033-5a2c-8651-836cac99b93f | note | Reference Documents: Section 703.15
78df2864-61e9-5fd8-b0b8-30337f204484 | note | - - - - - - - - -
adff243a-fc34-553b-a0cb-e75c04814546 | note | Inspection / Test Method: Document Review
b6569e9a-f246-5303-930e-2a735ddaea5d | note | - - - - - - - - -
6a8c0df2-5278-5f9f-94a0-0b3ef7a5c904 | note | Record of conformity: As-built survey records
2b211048-a3be-55c5-95ad-f6ef9059edfa | note | - - - - - - - - -
9fe5ee4a-28cf-51e0-afcc-cc2d6eaacad1 | note | WP
440cf657-f36e-539b-9d12-00434017869d | note | - - - - - - - - -
3b2e2d6a-3635-55b1-af48-1ad93f853bc9 | note | Responsibility: Project Engineer/ Surveyor
| checkpoint | 3.2 - Non-conformance Report (NCR) Closure
f1afa088-a895-5301-9fa6-33e500cb096d | note | Frequency: Once, prior to closure of this lot / element / Work area
5976a098-a6f7-59d2-84ba-d5e54c5e7c43 | note | - - - - - - - - -
361fbbf4-9f17-5d88-8001-2593a3a8d615 | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
d4a853ac-90f1-51d7-93bd-085479561f33 | note | - - - - - - - - -
84a3f3cc-ba7f-5915-9edf-1bd7f4525a68 | note | Reference Documents: Quality Management Plan
4de77ef8-377d-5bc7-872c-c09dd5fbefe3 | note | - - - - - - - - -
70c6fc18-a3a1-530c-8d5e-1bab1b0ee363 | note | Inspection / Test Method: Document Review
9ad8b6db-27a8-5ec7-ace0-ba4e964b28e3 | note | - - - - - - - - -
2abf77ad-d10a-5a7f-9be4-d0ff72bfafd2 | note | Record of conformity: This ITP
bcac742b-4d21-5a1f-866c-57d4bd11fea4 | note | - - - - - - - - -
c63576df-b27f-5dc6-a372-4ace55e5e4de | note | HP*
91c3f567-1214-534a-95af-46295c64d59e | note | - - - - - - - - -
6bcd2531-cdef-5d98-a727-b4c9ba5d829d | note | Responsibility: SE/PE/SPE
| checkpoint | 3.3 - Red lines
c36c437e-7cb9-56fa-a93f-771bf8a8541f | note | Frequency: Once, prior to closure of this lot
97c93aae-15b7-569d-9964-e8864e5be09e | note | - - - - - - - - -
71eced55-49c9-574e-8b6c-c9a303b70d75 | note | Acceptance Criteria: All RFI's and deviations from drawing to be marked in accordance with CRU red line markup procedure
3a0fadc1-2926-57e8-800f-df8b70019d11 | note | - - - - - - - - -
be9cac88-185c-5f78-9202-de2a035fafaf | note | Reference Documents: Quality Management Plan
d1290bd8-c946-5e3b-80dd-41316ce8a042 | note | - - - - - - - - -
a3a4aa35-6b7b-5a9c-a4b7-39cb9064e51e | note | Inspection / Test Method: Document Review
e8712c2b-34fa-58f2-98ea-3dd65f8ae1e2 | note | - - - - - - - - -
7eea6f4e-64ef-5056-b0ca-96fd3e5d9271 | note | Record of conformity: This ITP
bdb4cd32-8361-5bb4-a02d-26fc75bd3f41 | note | - - - - - - - - -
c5b2ce25-049a-5bb4-ae5e-e2d1505e18b5 | note | HP*
7d4793e9-c6d4-5610-aec4-2382ad103791 | note | - - - - - - - - -
4cf50dce-aeb2-5dba-abe5-56fd1d968f40 | note | Responsibility: SE/PE/SPE
| checkpoint | Final Inspection
87c8807d-6c80-52a8-8e62-b1a56b6ab2d5 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
8e23e8a1-2750-50e7-868c-67764c82b6d5 | textbox | Print Name:
d1b01e5e-40da-5ed1-a948-0e36153e7e65 | textbox | Position:
3e86a484-0225-5683-98ab-a3a4d4785ed8 | date | Date:
fffb949a-eb00-539c-aa62-d668523e1889 | date | Work Completed On
| checklist | ITP 0013 - Structural Concrete | itp | ITP-013-AX-LOT-XXX - Desc | 5210e9b4-9ed2-48fd-a6c7-3f29aa61738c
| section | 1 - Referenced Documentation
| checkpoint | Referenced Documentation
89623fac-2352-584f-afb9-9f9776c72f47 | note | Document Title: ITP-013-AX-LOT-XXX - Description
bd5cd853-32d3-540e-b136-08b44d9cdc55 | note | ITP Description: Structural Concrete
d264adc7-f04e-5cd7-9c76-87ab0597a0a2 | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0013
cd4c73e5-dfa0-5a84-ae39-bd0fc8ee5644 | note | Revision Number: 00
1618d6bb-a46d-58dd-8e27-0b91e7d4c2fe | note | Revision Date: 26/05/2022
a30bbea9-7567-5045-bc4a-934829154791 | note | ITP created by: Omar El-Khub
79768b7e-c72c-5101-81dd-58df05d70e7b | note | ITP approved for use by: Babak Rudd
e2248142-6475-5075-a31c-aa17550561c4 | note | 1.1 VicRoads Section 204 Dec 2015
333776e5-5a74-5711-82a9-934ff69e49a2 | note | 1.2 VicRoads Section 602 Oct 2007
ae12acfb-b06b-56f4-b8c4-01ce54a482b7 | note | 1.3 VicRoads Section 610 Feb 2020
2cde4d40-6d57-5ae9-a426-a821f107e90b | note | 1.4 VicRoads Section 611 Nov 2018
ba859eed-dad0-58ef-ae03-03bdde110d81 | note | 1.5 VicRoads Section 613 Jun 2017
3b296aa5-a780-5699-ba3b-16f50664c8b2 | note | 1.6 VicRoads Section 614 Jun 2017
04959291-11da-593d-b048-7bd62c6365d4 | note | 1.7 AS5100
b4f4d26f-073b-53d7-8282-aeda95477602 | note | 1.8 AS3810
| section | 2 - Preliminaries - Materials
| checkpoint | 2.1 - Concrete mix design
bdddd1c0-04d1-5320-98fa-610b05c04ce7 | note | Frequency - Each Mix, not less than 4 weeks prior to the placement of concrete
1b0eb799-f4fe-5b61-b8da-ff3f7f9f8f08 | note | - - - - - - - - -
6734ba87-2a75-596d-9743-6b1dc88b901c | note | Acceptance Criteria - Ensure all mix designs have been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
5dc6038b-2a6f-5878-b093-1c91a4b134d0 | note | Concrete Mix is Registered with VicRoads.
d2cd535d-f662-510b-ac67-c5bb0495c550 | note | Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
240e8bc2-38bc-5d41-b8f2-2d6e17b38649 | textbox | Teambinder Material Approval number
79727544-072b-55e8-80c1-6848574dae5a | note | - - - - - - - - -
e5a9269d-bd61-57b2-83a1-dde4718e7e1e | note | Reference Documents - VicRoads Spec.
3b2cbc93-fc6b-5d73-a153-0e86b810aa48 | note | Cl.610.07(b)
c0e97616-17d2-59dc-8ea4-5f2a82dbdf30 | note | - - - - - - - - -
b47f9a85-f0b4-5f46-98ef-27f249ac61fe | note | Inspection / Test Method - Document review
d5b534c3-979f-550f-bf7c-627c10c53df3 | note | - - - - - - - - -
4d448263-dd5b-5a9b-bbe3-2aebbe4f5d92 | note | Record of conformity - Approved Mix design
37b55194-8e6d-55d4-9a02-53c1318eb2ce | note | - - - - - - - - -
fe45fcf5-4731-5d5c-8cf7-230bf397049a | note | HP*
41faaa88-c341-52fd-b1d0-1ee37e114d26 | note | - - - - - - - - -
28319535-325a-593e-a7e8-55540b5a50b2 | note | Site Engineer & Superintendent
89e10857-5651-50ee-8333-b0fd8fe38ec0 | note | - - - - - - - - -
c5e04cce-8d97-54ae-987d-d6eb39af0543 | date | Date Completed:
| checkpoint | 2.2 - Reinforcement Certification
8bd4a4b1-7c50-5784-8f6e-f6f83903a6f9 | note | Frequency - Once for each supplier, 14 days of award of contract
9c8c9a9b-a055-50f4-869c-e94824d65bf5 | note | - - - - - - - - -
e37d8e7e-ae69-5323-9dfb-951b01113369 | note | Acceptance Criteria - Ensure the manufacturer and supplier of the steel reinforcement is in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance submitted to superintendent within 14 days of contract award.
b9617e35-b74e-5e79-abd8-2ba1ca3df34e | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g. 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
43373bc6-1680-564a-83c0-c12d0ff1aaa6 | textbox | Teambinder Material Approval number
a120ba6d-5d55-540f-8171-37638ba31784 | note | - - - - - - - - -
c7b0faff-d8cf-5c9a-9561-16531e9af99c | note | Reference Documents - VicRoads Spec.
918eb23b-2d70-5896-bfb9-dce38e18cb9b | note | Cl.611.04
cac5f865-80b1-5dad-87ca-65ca3c973599 | note | Cl.611.05(a)
a6614474-0401-5cb1-98eb-3fa82747070d | note | - - - - - - - - -
066a8b81-8aad-58a7-96aa-7d6ba3e9b854 | note | Inspection / Test Method - Document review
b7465c76-3809-55ad-957b-72f7108cc6ae | note | - - - - - - - - -
589bf065-73ad-5c05-9f16-9a66855215c1 | note | Record of conformity - ACRS Certificate of Approval.
5baebfc9-fc93-59f9-8ee8-3e159399799b | note | - - - - - - - - -
ea4038ae-ecdf-5f04-95c5-b32e8dd6249c | note | IP
ff1937d6-5fd9-5cb9-8d6e-d6c71c69122d | note | - - - - - - - - -
47ae0b7e-f3a1-5def-b09c-c04bdc40ec14 | note | Site Engineer
6aa6b4da-ab13-5b06-b83b-2d8a603dcc26 | note | - - - - - - - - -
29eb3f04-fe14-57e9-ac2c-be293172dd7b | date | Date Completed:
| checkpoint | 2.3 - Bar Chairs/Aspros Certification
7b0a12a6-a858-598f-8e09-06df7d797f14 | note | Frequency - Once for each supplier, 14 days of award of contract
e9e6347d-78f1-5063-8dae-b148ba8b269c | note | - - - - - - - - -
dc85ea67-86e0-5f0f-8e32-2d94f264ecf9 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
a5417b91-d00f-5d62-9306-56517983defd | note | Concrete aspros require annual compressive strength and soluble salt testing is required.
64822bf7-3496-522b-9c81-09dd26aa031c | note | Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
a9d6db6f-26d2-5021-94c0-cca8ca8530a5 | textbox | Teambinder Material Approval number
aa99e370-9333-5b1f-b9ea-52c7acb88a60 | note | - - - - - - - - -
9936cce6-b02d-53d7-9515-3068df1d2da0 | note | Reference Documents - VicRoads Spec.
8af23dc2-1831-560a-b9f8-2563e8c5fd18 | note | Cl.610.26 (a)
4792d705-9505-5fd1-af42-afdf26a6b90d | note | - - - - - - - - -
d6d0e096-45b0-5a8d-82cb-c37a4352d0f9 | note | Inspection / Test Method - Document review
ccb1e637-372b-5be5-a6cf-fc2b5bc57eef | note | - - - - - - - - -
982cd336-836e-5aa4-bcda-f31c8c29e93c | note | Record of conformity - Approved bar chairs and aspros
e00b4e52-02cf-5678-b01d-943371e081eb | note | - - - - - - - - -
86ea65f2-054c-5041-8f69-ca6cac9216b9 | note | IP
29f9e0de-6814-568f-b0af-d65a06b4c6d3 | note | - - - - - - - - -
7a65ffca-2d87-5164-93d1-bea6c9377336 | note | Site Engineer
d21f2d35-2762-58dc-b56b-3c7ae3d2f4a0 | note | - - - - - - - - -
4e14ae58-b118-50e0-9574-ddac49bbfcd3 | date | Date Completed:
| checkpoint | 2.4 - Evaporative Retardant
2b333001-3741-5c09-ae28-da5e185f14ed | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
d0f82760-6dbf-54c3-85c3-b1a70e1b39ba | note | - - - - - - - - -
d04a8071-0f69-5944-9315-66b06286207b | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
26b24b13-4c82-5eb7-a378-118539245eb6 | textbox | Teambinder Material Approval number
2d0711c3-4683-578a-be1c-9fc4caefe2ce | note | - - - - - - - - -
d03f1cd4-a48d-5f24-a29f-5f79c44f2137 | note | Reference Documents - VicRoads Spec.
0a8a69c8-da68-5c02-bf01-3ed457ecf4aa | note | Cl.610.17 (f)
c12f81d0-b7f9-54de-bbdf-caa57f4583b1 | note | - - - - - - - - -
335efe3b-e7d8-5b17-ba51-cec3f83b8cd7 | note | Inspection / Test Method - Document review
a8f02089-5a1f-506e-83fc-150bdcbfeeb6 | note | - - - - - - - - -
bd028518-d76d-5da0-999d-48917137609a | note | Record of conformity - Approved evaporative retardant
98e92e86-02e9-59b3-96e5-6f651b8dd841 | note | - - - - - - - - -
9003d1a0-921c-5d85-98cb-d823cff710f4 | note | IP
08d11c3f-6600-5a12-95ce-1ee18a6a94a2 | note | - - - - - - - - -
63764da9-cd16-5285-aa7a-f81f478a398f | note | Site Engineer
f530a7f6-c335-5ff7-a98f-ba8c19f1bd24 | note | - - - - - - - - -
cdf4cf59-a0d9-5e04-98e3-a0867d8450ae | date | Date Completed:
| checkpoint | 2.5 - Curing Compound
578bb188-9ddc-56af-8b00-447a116e5ab2 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
6c88e5ba-05ce-5399-888a-29a45135c77f | note | - - - - - - - - -
001e18c2-4667-500d-b93d-225896243a24 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
165ff0fc-21e1-54e9-aa2c-f96828dcd764 | note | Teambinder Material Approval number
224d808a-874b-553d-8a01-0144fb5a1a33 | note | - - - - - - - - -
a7073eb5-29f3-507c-833a-7f6541bc008f | note | Reference Documents - VicRoads Spec.
725c8049-b683-5c6c-849d-2a6a619a63a0 | note | Cl.610.23 (b)
e6603590-55a4-592a-a917-9a917b339f17 | note | - - - - - - - - -
0df9dfbc-90cf-5b13-bb90-6df8d3c357d7 | note | Inspection / Test Method - Document review
d2f83d51-9d32-584d-9a8d-b526bce4ba58 | note | - - - - - - - - -
7aea7b42-6f27-55f1-99a7-e553fa0ed5a5 | note | Record of conformity - Approved curing compound
1fcfe800-d69e-5520-9ff7-0d812da181d2 | note | - - - - - - - - -
dd2375e6-6bf0-5a82-b6c9-eec2e327f176 | note | IP
6406cdfa-3271-529f-ae8b-6b52054435ba | note | - - - - - - - - -
4956b14a-2417-5d11-a7aa-3f0d5aa3a3d5 | note | Site Engineer
90074ac5-165c-53cb-a034-60c7f3982657 | note | - - - - - - - - -
954b72c8-713f-59f6-bff1-6ee934bacdab | date | Date Completed:
| section | 3 - Preliminary Works
| checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
580eefbf-8fcc-56f9-bd66-3e2728f4cba4 | note | Frequency - Once, 4 weeks prior to placement of concrete
d3eda1aa-ed99-544b-aff8-2a81607f5aa7 | note | - - - - - - - - -
155efd30-99fe-5ae4-b968-471cfd2bf847 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to MRPV
dd128741-3a7b-551d-a5b0-7547d4d0b8c3 | textbox | Teambinder Approval number
3045daeb-77dd-52af-9996-7b6398068063 | note | - - - - - - - - -
6127e61e-7288-5f4a-8fb2-7241725f9183 | note | Reference Documents - VicRoads Spec.
ec45de6e-667b-527e-b733-e63f91786c8a | note | Cl.610.18 (a) (i)
2890f71a-95cc-5533-9863-0c17ed1292ce | note | - - - - - - - - -
84e32433-fea1-5c7a-bbbe-93428709aa70 | note | Inspection / Test Method - Document review
1c293e9b-462f-5592-a5ba-98ab769b48f0 | note | - - - - - - - - -
dc7da628-ee4c-5f53-b8c9-d28f56720772 | note | Record of conformity - Approved WMS
547a134f-57b8-5674-b478-03e988df4d19 | note | - - - - - - - - -
38676e63-e2e0-5513-8d57-93f9a94dad9a | note | HP*
114076af-9b29-5807-8477-4ad799cddf19 | note | - - - - - - - - -
a691ff01-d1dd-5e30-ad75-7cee09d9a4c2 | note | Site Engineer & Superintendent
1b4c5593-521f-57e5-889a-101a925eee7b | note | - - - - - - - - -
7dfc82cc-e343-566a-bee1-0dbdb466d60d | date | Date Completed:
| checkpoint | 3.2 - Concrete Sampling and Testing Procedure
a81f0ef0-04b9-5a0b-972a-4beaa0b4e3f3 | note | Frequency - Once, 4 weeks prior to placement of concrete
53cf9409-40fe-5ecf-a0dc-b967f91923b8 | note | - - - - - - - - -
2197aec5-a9ee-5d01-8f99-aaf520909120 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to MRPV
fd4d6dab-f7da-5a00-a685-07031b854f5a | textbox | Teambinder Approval number
6ac8beee-52e9-576a-b98a-3ef223da89ae | note | - - - - - - - - -
3d6472c4-631a-5832-b855-89872d0ea1dd | note | Reference Documents - VicRoads Spec.
8c643103-7ee8-542d-ab76-d30e09649d78 | note | Cl.610.18 (a) (v)
fd1f78e5-951f-5384-b651-744d21127c01 | note | - - - - - - - - -
8c0f1219-a5e8-5a4e-8750-89f51da53e37 | note | Inspection / Test Method - Document review
57a70ea4-2eb5-5f2b-b50a-ecf0b032cea3 | note | - - - - - - - - -
2ae0913a-5a6a-5fb1-abdc-ccb5f94e5edc | note | Record of conformity - Approved procedure
02a8f195-6789-55f9-8a66-782dc2d6f89f | note | - - - - - - - - -
027f09a7-87e7-5fa9-b89b-917c2452239a | note | HP*
ddbdde63-ac3a-53c8-a724-b8f9bccda75e | note | - - - - - - - - -
d27e7624-9721-5e97-b86d-70ca9fe742a8 | note | Site Engineer & Superintendent
61c925e6-2c35-5e1d-9d12-f0ec339a61ff | note | - - - - - - - - -
e4aaa093-1be7-5339-8520-f2c8b31535fc | date | Date Completed:
| checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
cc6aa1ec-50ef-5e57-a597-ae834256ed7e | note | Frequency - Once, 4 weeks prior to placement of concrete
c5111e0a-e5b9-5f21-90d4-042bbcea604a | note | - - - - - - - - -
812c3c99-72b0-5442-bc94-b0aa9b528388 | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
f64b841a-06bc-5d95-9153-903a6da9494f | note | Minutes of this meeting to be submitted to MRPV
9ed79b7f-6fb8-51ff-9c1c-defaa3c07704 | textbox | Teambinder Approval number
31bb8b6a-254d-506e-9354-f1c909899440 | note | - - - - - - - - -
ef6960da-b453-5820-a4e7-61ce76f577f2 | note | Reference Documents - VicRoads Spec.
a549c17d-adb7-538c-82bf-befa0488b57b | note | Cl.610.18 (a) (iv)
a2da8356-8c06-57d1-a17b-d1afd33d85b9 | note | - - - - - - - - -
bad75990-d3dc-5c93-ad53-656b7d70cfe8 | note | Inspection / Test Method - Document review
d7b4f012-1536-528d-a152-8772640c3f26 | note | - - - - - - - - -
7fee968d-7fb6-5266-9306-50c6e0daa9d5 | note | Record of conformity - Approved quality requirements
925df293-01f2-5c78-8f59-6823dee6eb24 | note | - - - - - - - - -
7a3cbbcb-735a-53cf-a622-637440e41420 | note | HP*
0b333291-4adb-5dc3-9d21-fcad311ad621 | note | - - - - - - - - -
a3047fdd-21cd-5e1f-8026-62cc89106887 | note | Site Engineer & Superintendent
dda2f45a-7f4a-55d3-bcc2-9199ae59cde6 | note | - - - - - - - - -
5151f65d-97f7-505f-b9d6-97e28a4555c0 | date | Date Completed:
| checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
c6fff41e-8e33-5c03-b51f-f99208b4d929 | note | Frequency - Once, 2 weeks prior to placement of concrete
a9bd0569-e90e-573e-a9cf-ecec3ecfca28 | note | - - - - - - - - -
f862084a-5740-5f17-8985-c81518790d38 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to MRPV.
9dfe52ec-9654-525f-a759-06d8312cf839 | textbox | Teambinder Approval number
24caaf03-f966-5448-be2e-f42fb4508b56 | note | - - - - - - - - -
c8a63774-13b2-53e9-977e-18dd93831358 | note | Reference Documents - VicRoads Spec.
b3aad2d0-e951-5406-9190-4db16bd921ce | note | Cl.610.17
d0e62156-b273-5302-b9c4-948dbbf38942 | note | - - - - - - - - -
7a95345d-6b4d-55b4-9de4-4298ac589970 | note | Inspection / Test Method - Document review
f4ef9787-441b-5e42-954c-baa02d58e4d4 | note | - - - - - - - - -
64ee376f-10a7-5270-a355-40e107c8b08f | note | Record of conformity - Approved procedure
ddd770e2-79e5-503d-85a3-3bca502cfedf | note | - - - - - - - - -
ec65c4c3-966a-5a45-a92b-96459d266bd2 | note | HP*
6bbce2cb-7b1e-5693-b73b-29357112e91f | note | - - - - - - - - -
b9ddf85a-8737-5085-8634-51b8694b5d97 | note | Site Engineer & Superintendent
a04b2ae4-3d41-58bd-9a8c-8f3bfbfe98a4 | note | - - - - - - - - -
9ea62ae7-0ab9-5ad8-941d-00cbe26a3b34 | date | Date Completed:
| checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
7320de7d-a0ff-558a-8a61-0c85d49450b7 | note | Frequency - Once, 4 weeks prior to placement of concrete
2fb0924b-ec06-5c8b-a936-af2f1be47e89 | note | - - - - - - - - -
62568e40-bd99-5fbd-a1a7-88f929f0befb | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to MRPV.
a20c5415-9270-515a-bbc4-af338c667bf8 | textbox | Teambinder Approval number
831d0519-7262-5cbc-ae04-9d813144e783 | note | - - - - - - - - -
9a1425ef-bd75-535c-9207-bb5de0e017cc | note | Reference Documents - VicRoads Spec.
5776e96c-f427-5f4e-9a95-db98d5b14933 | note | Cl.610.23 (a)
2aa46c9b-aa17-5a99-a0a5-4154954c7d83 | note | - - - - - - - - -
e5418a7b-6a1e-57e9-bc24-7add66857534 | note | Inspection / Test Method - Document review
68bf71af-fba2-5cfc-9f78-6800fd3f3072 | note | - - - - - - - - -
1d8364e0-05b2-59c2-9acc-f0ef8c82f31a | note | Record of conformity - Approved methodology
83e34364-095d-5554-b46f-2624b36dda65 | note | - - - - - - - - -
0ed9d9a7-2967-5134-8ef1-30f7f5eda478 | note | HP*
5c55d4fb-a7e0-5ad0-9161-7ae3e6e17975 | note | - - - - - - - - -
f3c2efb9-15f2-5e0c-b7fc-329ffafdca02 | note | Site Engineer & Superintendent
04699796-7a70-5b88-ba7b-560c02503925 | note | - - - - - - - - -
727eaa89-3d3b-5dac-b1cf-de5d41bd3dfb | date | Date Completed:
| checkpoint | 3.6 - Concrete Drilling Procedure
c170dbd0-2b2b-56e8-99a2-6f092ade7052 | note | Frequency - Where applicable, once, 2 days prior to drilling
c01f3791-ea19-586f-a35f-21fa9c83935c | note | - - - - - - - - -
7dd96940-d52b-59c0-a693-78cf4fe1fa5f | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
05e94e1d-1d78-5c52-8bb2-47528af9419d | note | The planned locations and drilling procedure shall be submitted for review to MRPV.
edb59cfc-a4d3-5d90-a4c6-904586f33024 | textbox | Teambinder Approval number
a5f22a3d-8964-59e2-861e-b801a5a42b0d | note | - - - - - - - - -
27d7ca9e-3708-5f7d-a569-3663f8fc25c1 | note | Reference Documents - VicRoads Spec.
13ef3c6d-642d-53a5-b93b-e8f8265a4bd6 | note | Cl.610.46
0ff6aa55-240f-52c6-951d-99ab9304156a | note | - - - - - - - - -
13cee391-2b43-5ac0-8651-b735364868fe | note | Inspection / Test Method - Document review
3f22e7f9-c15f-5d8c-9d61-3e8df1736cb9 | note | - - - - - - - - -
051e3750-798a-5510-9987-b6b3c490ced5 | note | Record of conformity - Approved drilling location and procedure
07337dce-f134-571e-b8ac-b0a05dddb0ab | note | - - - - - - - - -
335de048-088f-560e-b024-c779095b53a3 | note | HP*
1d5fc1be-bd69-552d-af9c-f352416eb7db | note | - - - - - - - - -
517f909b-0771-59ae-8d3a-f3def4ed4750 | note | Site Engineer & Superintendent
b2af37d1-dd1b-517e-8727-a418c28e50dd | note | - - - - - - - - -
030da16f-7353-56ae-bd53-ea1aa53c09cc | date | Date Completed:
| section | 4 - Pre-construction activities
| checkpoint | 4.1 - Check that IFC drawings are being used
a4e918f7-d06d-5e5e-8f43-46e701b37a6c | note | Frequency - Prior to Commencing
9c664970-cd70-50ab-8838-6f1c99759380 | note | - - - - - - - - -
bfb770c4-acdc-5b8d-ba92-4a10f7cb812e | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision on TeamBinder is used
9cb242c3-89cd-5fda-b71d-89ed3bef1c1a | note | - - - - - - - - -
0628e825-b414-5dfe-93dc-9295ad9f7c29 | note | Reference Documents - Project Drawings / Drawing Register
d14bb513-f82a-54f2-a139-8604b6bea677 | note | - - - - - - - - -
d94aeae3-c161-5587-89f7-60bbdac8697d | note | Inspection / Test Method - Document review
897f8c35-02a1-5d8e-a49d-475f17c63203 | note | - - - - - - - - -
90684c4c-8912-5714-bbf7-413dd65967bc | note | Record of conformity - Latest Revision Drawings
b46d8666-6c36-5380-97ce-1aa87e62203c | note | - - - - - - - - -
d1b575eb-9d7a-51a6-8d82-803abc02a971 | note | HP*
dbf8e540-db62-5f61-a8d9-b7a7f1d4d8fb | note | - - - - - - - - -
705afea5-cbfa-5070-812e-37c9c3c48da9 | note | Site Engineer / Site Foreman
825d4b2a-286a-5f56-addd-d4f7dce239d1 | note | - - - - - - - - -
337857d8-9e49-53e8-afe4-a9d54718bc40 | date | Date Completed:
| checkpoint | 4.2 - Survey set out works
f8308a8b-065f-52be-95b3-e1066017235d | note | Frequency - Prior to Work Commencement
686732a3-0ada-55ee-97c4-33e28b444aa8 | note | - - - - - - - - -
1ec040d2-09f8-55b8-ae33-242af14cb22c | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used
1f40102c-bf75-50c3-a59e-6d690fd1b164 | note | - - - - - - - - -
0be53dea-5218-5687-9180-6d954f52a43f | note | Reference Documents - Project Spec.
08618170-ec75-5359-a58a-11df525209f6 | note | Cl.1190.06
539ee084-b086-5536-87de-22ee611c5bf9 | note | - - - - - - - - -
9389ca0a-40d0-59ec-b9c7-8a071b1137f5 | note | Inspection / Test Method - Site inspection
3ab8e29f-d69c-57d7-b832-717f04335c81 | note | - - - - - - - - -
33f99d20-6c46-5d41-bc13-e097323f8c89 | note | Record of conformity - Survey records & pegs on the ground This ITP Signed off
e21592d7-db6b-5dfd-8f89-abe20a77bc04 | note | - - - - - - - - -
046e7a25-47cd-56f0-92d8-16b65b8f2a40 | note | SCP
58b2cbd3-aa2c-5064-873b-c207ae5ff5c5 | note | - - - - - - - - -
d014e0fe-186b-5f9c-b433-12fb761a561c | note | Site Engineer, Foreman & Surveyor
9fc896af-4e64-5753-930e-98ecc4466a6c | note | - - - - - - - - -
fac13b1c-1a8d-54d4-8e08-0bfa23f05324 | date | Date Completed:
| checkpoint | 4.3 - Excavation Permit issued
63ab4952-d479-5bab-a12f-b651c45eb57e | note | Frequency - Prior to Commencing Work
de1b2de6-2a4d-5bef-aa53-fd9e248ac9fe | note | - - - - - - - - -
ca10850e-06f4-5f50-a3c9-f5cf741049e5 | note | Acceptance Criteria - Current Excavation Permit signed and specific for the area where works will be executed.
157b622e-c101-510f-8584-67b8cd0647cb | note | - - - - - - - - -
65a82547-c022-562a-979f-afe2774f090b | note | Reference Documents - Excavation Permit
49d1e995-05c9-5d43-92d8-1c24b62cab9a | note | - - - - - - - - -
fb6f51ae-a704-5284-9415-d3a9de9cee18 | note | Inspection / Test Method - Document review & Site inspection
89d5aee8-94a7-59a3-92f6-d1704519692d | note | - - - - - - - - -
9fc561be-8d49-51c3-a277-b9bff25b2417 | note | Record of conformity - Excavation Permit #
1ffaee08-77e6-54ca-86f7-1f5c42d2290d | note | - - - - - - - - -
81598f8a-f652-5550-8387-e718217450d6 | note | HP*
26543cde-5695-53bb-ad05-8e545b69ef5e | note | - - - - - - - - -
75a13ed8-a6e3-5b94-9bc8-79ac3d98ca0b | note | Site Engineer
9250e1bd-1e36-514d-a699-96846022b327 | note | - - - - - - - - -
9d126739-5ddc-5af6-a49e-fcac3ac1c0e2 | date | Date Completed:
| checkpoint | 4.4 - Excavation Inspection
16820701-9187-5595-9fbb-a4d5d5b94982 | note | Frequency - Where applicable, prior to placing blinding concrete
7475c93e-b095-527f-94d6-804bae5f4cc1 | note | - - - - - - - - -
d5a3731a-d602-5e17-9d3b-78e547c1b617 | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
6e4cc57e-fb7e-5c4d-8c28-bb7516b1204f | note | - - - - - - - - -
482fdd17-79f1-5413-b350-f6a8abd0f3b9 | note | Reference Documents - VicRoads Spec.
b808c31e-f34c-5edf-a245-1f1a6f72f8cb | note | Cl.602.03
9238229c-4f17-5c5d-b4a5-7f4a4505d44b | note | - - - - - - - - -
4a853c5b-ad4e-5b1e-a3da-96a91ee04f45 | note | Inspection / Test Method - Site inspection
b5fbfd01-dc73-5b35-a5c7-b9a100e6ad8a | note | - - - - - - - - -
f2da07af-5fce-5d1c-9014-121a92190d83 | note | Record of conformity - Superintendent approval
9a84a95c-dc2e-5afa-bb28-f2142b4cbbde | note | - - - - - - - - -
72ceb703-0197-5e9a-976e-b01a1ed51775 | note | HP
74758826-b397-577e-a250-1e1010aaa36f | note | - - - - - - - - -
80f30877-d7d7-5e33-943f-d0f9b51da68b | note | Site Engineer/ Project Engineer
fed206cb-aee6-51ab-9a4c-d334fc63ad2a | note | - - - - - - - - -
7563e782-226f-5e03-9cad-c129aadb2735 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 5 - Construction Activities - Formwork
| checkpoint | 5.1 - Formwork Design and Construction
de8b2349-5a48-55a5-a0e2-3470a48cd159 | note | Frequency - Each Pour/ Type of element
7245fe07-8967-593f-83c9-230f66c2b2f7 | note | - - - - - - - - -
6693c949-0d19-53e5-9d8e-d9b5ecb51317 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete. Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish. Formwork shall not be placed where steel & fixtures cannot be inspected.
c1c4f766-c51a-5881-abe5-cbbae2a3558c | note | - - - - - - - - -
35bca3c1-965b-5f41-8a5a-63c0c42eff79 | note | Reference Documents - VicRoads Spec.
1e05fcca-14e3-59af-bebf-59029cad4318 | note | Cl.614.04
ccaad7b5-33d5-5dc6-b8eb-023a252181ff | note | CI.614.05
923e04fe-8146-5165-9de2-87edfcba394f | note | Cl.614.06
ec2151c3-8a34-5fb2-a98b-b3d407608183 | note | Table 614.041
8cfa0fdb-921f-5b82-ae40-39c718e3f2ef | note | - - - - - - - - -
72204971-6d17-512c-abdf-e5ce01448c4f | note | Inspection / Test Method - Document review & Site inspection
2cac9808-d516-55d7-a6c8-e57b4f3079ef | note | - - - - - - - - -
baf57184-18a9-561b-b746-30ec07bbd771 | note | Record of conformity - Proof Engineering Certificate approved This ITP signed
c91d3ccc-08b8-5dbd-b417-4f9bcddc67a9 | note | - - - - - - - - -
098923b1-a466-5f57-bb83-47f36b24afb8 | note | IP
d5fe01c8-92f8-56e1-b2bd-7b62999c9bdf | note | - - - - - - - - -
33afe687-1c52-5acb-959b-f7eb935ee8f1 | note | Site Engineer & Superintendent
014b5b2e-e6b2-55f9-ba22-1aee8c9be85a | note | - - - - - - - - -
2ce87a24-43a0-5afd-b7d5-4a554fb5dd9c | date | Date Completed:
| checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
1c835e0b-7990-5aed-9ce5-2895fe6f6d6e | note | Frequency - Each element (where greater than 2m)
f2b0a438-465c-5959-aed5-cb2cee183d50 | note | - - - - - - - - -
15612313-178e-5339-812d-95615d700dfb | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
7a253919-8904-5640-b080-93120adeee19 | note | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights greater than 2.0 metres
c612ec6d-8788-5d3a-86e9-6d9369996ddb | note | All other concrete members
144f9896-cca4-57e2-b1e2-751049c36d7f | note | Any member for which self-compacting concrete is proposed.
f077ab5f-3b9c-5933-8f82-6f69d0931aba | note | Attach: Attachment A
b1858a02-8769-5de8-a543-9b9df3ac674c | note | Attach: Attachment B
a55aa7d9-d7e3-5b17-93f6-115ece945f03 | note | - - - - - - - - -
48640f16-5c0b-5492-a53c-bed767eec0b6 | note | Reference Documents - VicRoads Spec.
165cebf8-d016-5c10-990c-4f16f32bd663 | note | Cl.614.08
5d5900f2-402c-5bb2-8ca0-9f852c744c92 | note | - - - - - - - - -
59f9506c-a011-5e92-ab92-b96418483add | note | Inspection / Test Method - Document Review
9b459d2c-8a4a-5f1c-a26e-dfa053c867f9 | note | Visual
18b9212e-b5e0-5e82-a012-666215ea000c | note | Measure
af1e7910-400e-569c-abd7-613eb3e30fd6 | note | - - - - - - - - -
b3e49004-b924-562e-a96e-b26ad1925eda | note | Record of conformity - ConQA Hold Point Release
79ca55d9-35e5-59f8-b4ed-7d68cd53a593 | note | - - - - - - - - -
ce4ffe9a-a640-5be7-9c76-b9daed67f55c | note | HP
ec493549-dade-533a-a5c6-81ad58efd78e | note | - - - - - - - - -
65ae3709-6480-5289-8cf7-de61e1decfb9 | note | Temporary Works Designer
8733a741-e19d-53ad-b0ee-37289fac4ba6 | note | Proof Engineer
62056314-d70f-56b0-8181-5f4016790788 | note | SE/PE/SPE
078e6cbf-720e-5b5d-829a-036ad9f6db7d | note | - - - - - - - - -
9c0053c4-adad-5f82-a617-261daca3ffaf | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
37f45d6e-0cb9-5c19-9794-af8e4895e8f6 | note | Frequency - Each element (where 2m or less)
0da62d80-bfa4-55ba-bc77-4a792ad622d9 | note | - - - - - - - - -
2d8ba990-22e8-5d6d-b815-d770507cbe22 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
ac849c8d-9bba-5d0a-a000-5e6c48bc6434 | note | Abutments, pile caps, footings, solid piers, pier columns and walls, with heights less than or equal to 2.0 metres
56e65ba2-cc23-5c09-b1c1-9d4068cbb183 | note | Attach: Attachment C
c0eca90e-071a-54a0-819b-5fc1b296fb82 | note | - - - - - - - - -
8cc90153-6805-5133-aab9-d71a91945255 | note | Reference Documents - VicRoads Spec.
10872467-a87b-52f0-af1d-b8446e2f163f | note | Cl.614.08
b337ddf4-56df-5b73-a406-3df21875458e | note | - - - - - - - - -
5af1ead2-6b47-5af1-b218-3dfe36a62003 | note | Inspection / Test Method - Document Review
1eef8fe1-4619-5a16-a577-2057db19b84d | note | Visual
8b408184-ceee-55d1-ab65-1dc6bd034711 | note | Measure
b1d2f72d-10b7-5975-b822-8bb2b1b22a6a | note | - - - - - - - - -
32c22e6a-7c68-5e76-9ac5-73c94c3b2072 | note | Record of conformity - ConQA Hold Point Release
8aab6aa2-29f3-5105-aa91-df2d908b03ee | note | - - - - - - - - -
49a3dfbf-f97b-53bf-9114-6e0083ab2a14 | note | HP
21fc367c-4200-5a33-8df8-82027df17053 | note | - - - - - - - - -
73e2cac9-76d6-5bf3-bcae-82e275f2c84f | note | PE/SPE
8de0144f-267d-5b7b-9ab8-71aa5664f9e4 | note | - - - - - - - - -
6a7d3cbe-2de7-525c-882a-de545d909b5c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Reinforcement Placement
13622271-d35f-5b3b-a20c-a1b97f1c948b | note | Frequency - Each Structure
9db130e4-dfff-55b0-985a-ca3d63404fe0 | note | - - - - - - - - -
4b55c103-4926-5f16-818d-d4bae2885466 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
ff542fe9-c0bc-5885-977e-ec69d732329a | note | Projecting reinforcement is the correct length and location.
a5787fff-e663-5581-b395-012d81dc0e09 | note | Splice lengths achieve the minimum length and are in contact for this length.
c990ebf9-2a54-5f96-a59f-ce1af093e4f6 | note | The reinforcement surface condition is free from dirt, debris and damage.
2999b34e-0d5f-5629-9275-63a90b341501 | note | The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
24e48b3d-8391-5764-8e5b-30a4b657fdaa | note | Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
4929d0a5-5e63-5586-996a-bfc1204614de | note | - - - - - - - - -
018f9dea-bc3e-52c6-adcc-3df5f4ac6eef | note | Reference Documents - VicRoads Spec 611.06
b372576c-21b3-582e-aa68-93af3787fff9 | note | 611.09
a55add28-25d6-5293-a8ea-a84f4fd8861e | note | 611.1
ad5d1516-4864-57a0-9790-764660a9722a | note | 611.11
e62b751f-4195-5778-ab2c-7f7b4d1dd497 | note | 611.12
379f14ae-2b00-5287-9a6d-d09c93197a51 | note | - - - - - - - - -
2c036648-f091-5886-a71f-176adce8eb94 | note | Inspection / Test Method - Measure
c4371cd8-b964-5580-9d98-736613026002 | note | Visual
62687777-8750-5d5b-b638-d3a4f379610d | note | - - - - - - - - -
40d91109-42bb-51c4-8600-bf448b3e9abc | note | Record of conformity - This ITP Signed
dfd45470-1b91-531c-8bf4-95c7a573f900 | note | - - - - - - - - -
c1e98e5b-b72b-517a-b83a-4bddc5c790a6 | note | IP
66e1806f-3059-5150-bd07-5beb140c2931 | note | - - - - - - - - -
02b65d5b-c428-5167-87f9-25282326c445 | note | Foreman
2d7ded18-ff2b-5854-b4e6-d86fe70d220c | note | SE/PE/SPE
7f507766-e64e-5210-8fbb-446fda4fd5bc | note | - - - - - - - - -
d99b39dd-c41a-5bc1-a37b-898f75213f9e | date | Date Completed:
| checkpoint | 5.5 - Pre-pour Survey
5082440e-1bba-599d-a974-bdc5d128c488 | note | Frequency - Prior to concrete pour
4e503492-1423-5d19-ae2a-190ec88de66a | note | - - - - - - - - -
a20b9af2-3d37-5dbe-aa9a-c905e222a87c | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
10348038-1b6c-5025-b078-10a8b7578cae | note | Erected formwork within the tolerance as Cl.610.36.
6e22de4f-b398-55c3-8ca6-e6b481411997 | note | - - - - - - - - -
4823f90a-1ce8-5bf6-97f0-b934b3d8eb27 | note | Reference Documents - VicRoads Spec.
7180070f-f79f-5c71-860c-000227fbad6a | note | Cl.610.47
a5bfb4d6-940f-59d7-8c55-6e86de929d8e | note | Table.610.471
eeb5d2cb-d881-5e5b-80bf-21478ab0c1ad | note | Table.610.472
1ac444fd-cad1-5547-99dc-ef59d4e2c914 | note | Table.610.473
3b2a01d5-8ac3-5a9d-8547-fe8e6a906b83 | note | Table.610.474
0ec95f6e-0bef-541f-be8b-2bbb3134a63f | note | - - - - - - - - -
19b72f72-79cd-5568-a3c2-4d088c81ea08 | note | Inspection / Test Method - Site Inspection
697f138b-15c4-5a03-b149-befaf804e199 | note | - - - - - - - - -
6d2aa0fe-c096-5cb1-8bdf-55f001537676 | note | Record of conformity - This ITP signed/
ad00e745-8b28-5ebd-a5fe-6f59ad3b5a13 | note | - - - - - - - - -
78fd21fb-ab9b-5c5d-a9ca-758fdba3b7c5 | note | SCP
309a34d1-11a8-527d-baa0-9fbcae5fe184 | note | - - - - - - - - -
f68cfef2-8a03-53f4-ba31-95d54dafb350 | note | Site Engineer/ Surveyor/Foreman
4ce88276-75b5-54bd-afbe-5b14d77e621d | note | - - - - - - - - -
079e332c-8f15-51d4-89a9-62e340e573e4 | date | Date Completed:
| section | 6 - Construction Activities - Concrete Pour
| checkpoint | 6.1 - Construction Joint Preparation
f95c3e6d-814f-58e8-8dcc-9dc5103a63f2 | note | Frequency - Each concrete pour, prior placing concrete (As required)
84f569b3-f553-51dd-9bb2-043080108b9e | note | - - - - - - - - -
7b84c89b-6b20-5f46-99df-a2032b822d18 | note | Acceptance Criteria - Construction joint preparation in accordance with CL.610.20
5429dbbb-04eb-5021-8bee-0ffbe6850d8d | note | Existing concrete to be roughened by removing all laitance and sufficient mortar to expose the coarse aggregate to a depth of 3mm.
ee5bf04b-ea6c-54f1-9fb4-7d00e0807fbe | note | All surfaces should be cleaned, moistened with water with any excess removed immediately prior to placing concrete.
3be5d218-c6a2-5730-87c5-1a149db5ecec | note | Joints shall be at the locations specified on the drawings
98d1b2d3-7504-533d-a525-7fa2d3fc996f | note | - - - - - - - - -
eb6a2852-302b-50bf-8544-554c6ae99793 | note | Reference Documents - VicRoads Spec.
d5e2c59a-0e35-5895-8cb8-49401cdd28f9 | note | Cl.610.20
31a19e1d-888e-5ea0-a9c4-8a0f38745aaa | note | - - - - - - - - -
571e283a-1c9b-533a-96d8-52fd2cfdab1e | note | Inspection / Test Method - Site Inspection
d8bc79c4-7259-5a83-ae2b-641271c5e560 | note | - - - - - - - - -
a3e1bb91-b063-55bd-b065-76c54ef88744 | note | Record of conformity - This ITP signed
b8e7b2cb-6608-54a7-8331-b748712bd9db | note | - - - - - - - - -
363c65f5-7bb4-5381-8d38-cffd7b3bed1f | note | IP
8ad361b9-e8c7-5a30-a192-b35e5c3e5038 | note | - - - - - - - - -
86ce359b-5510-54ba-9ca8-d7becb166ad1 | note | Site Engineer
33cd7675-7581-5b11-9c68-09332374cbdf | note | - - - - - - - - -
98615745-4618-5544-9515-3ef1e05264fb | date | Date Completed:
| checkpoint | 6.2 - Cast-in Items
bd113c6c-f19a-5847-8393-cd4e3883cf2e | note | Frequency - Where applicable, each element
ef4be792-3ce6-5b87-b9f8-c787eece413a | note | - - - - - - - - -
a2f5ce0e-8bbc-5176-b000-3e9d2d46445a | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
ea934a71-2862-56e0-801a-951a1de298e2 | note | Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
c9f61f42-37e2-540b-827c-817b9b8f909e | note | Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
2e932635-defd-5a76-b10a-b1eb00dc93f8 | note | Grout tubes shall be fastened at regular intervals to prevent kinking.
c9dbdd0e-11db-52b9-ade1-2478f46762ea | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
d46b1728-3529-5e21-81b5-2af8da596f0a | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
4da3f253-4040-555d-84b7-184d4d277d46 | note | ii. Running dimensions of a group of the above = ±6mm
87e43e8f-8f0a-5ae6-a8aa-19432a9104b4 | note | iii. Ducts and conduit location = ±12mm
347314c3-55f8-52bc-84e0-d6d62fb150e7 | note | iv. Diameter of ducts and conduits = ±3mm
76171174-9154-54ec-b582-36a651018a8e | note | - - - - - - - - -
d0a6f415-64ae-5ac1-90f8-c9ee09cd3f00 | note | Reference Documents - VicRoads spec.
2134f6a2-826b-5757-98c8-8c4753a7520c | note | Cl.610.47 (a)
b4a64745-f876-5424-b6f2-0dc37c1f0f89 | note | AS3180.1 Table 3.3.6.2
5eee4fe3-e7bf-5b98-9b04-a9b5951bb801 | note | - - - - - - - - -
4f65e776-9524-53b4-b1d2-9ab29c308dc7 | note | Inspection / Test Method - Site inspection
34e4618a-fa2a-5977-8960-087cefeec2d8 | note | - - - - - - - - -
3e575971-36c2-5c56-acdd-81d714a4df92 | note | Record of conformity - This ITP signed
081d0af5-c9d6-56a4-a232-0b25cada53e7 | note | - - - - - - - - -
249af44a-bb37-5909-91f0-519e750f4d7d | note | IP
2235aeb6-6011-53a7-9c35-3568e9581f7b | note | - - - - - - - - -
e1d5423b-ebf3-55c2-a753-0c1a0d0283ff | note | Site Engineer/ Foreman
fda02dba-3ee1-5289-8dd0-09011f61391c | note | - - - - - - - - -
1ec1d90a-aa87-5d9e-9d73-aefbe57f3a6b | date | Date Completed:
| checkpoint | 6.3 - Pre-pour Inspection
e4c5daba-6c64-53f8-a3ea-989ae246c6dd | note | Frequency - Each element
46bd3627-9861-5462-924c-5faf49f86a29 | note | - - - - - - - - -
63b78312-9bcb-5dcc-a437-0df297ec2b64 | note | Acceptance Criteria - Evidence that the forms, reinforcement and cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority.
1e67ee0c-e620-5593-b2d4-4ee0d514cd4d | note | All foreign material has been completely removed from the forms.
e3fc342d-2d16-5e3e-ab27-04a3693a4510 | note | - - - - - - - - -
765bf5d6-afc7-5520-aada-8e3c6c303269 | note | Reference Documents - IFC Drawings VicRoads Spec. 610.18 (a) (ii) & (iii)
7b1af325-d0a2-5435-94ec-170717ce228a | note | - - - - - - - - -
9e81db6f-bcfd-5fc9-9503-f4fe16037baa | note | Inspection / Test Method - Measure, Visual
492c2b99-f285-5e02-8eeb-5dec3a52f5d6 | note | - - - - - - - - -
17d9871c-6424-56c1-944c-a5052171f9b3 | note | Record of conformity - ConQA Hold Point Release
40653d21-3f35-59dc-a21d-ebe165814257 | note | - - - - - - - - -
9680d985-ea47-5e18-a5fc-3538c431eb2d | note | HP
2932ed12-9aa3-5b11-aac6-d3987609ac6a | note | - - - - - - - - -
9d32c6a6-b35b-57bb-bd02-4143b1da347c | note | Superintendent
c51e8c49-2aad-5134-8a98-00d37b1e9258 | note | - - - - - - - - -
9f270120-a76f-595e-a84f-de786bda7310 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 6.4 - Weather Conditions & Evaporation Limits
4395c50d-2373-5535-835c-a9c971e45b9a | note | Frequency - Prior to concrete pour
8769543a-db2b-5697-9108-772b9fc9a5da | note | - - - - - - - - -
8b5ce5e9-18c5-5abd-9c29-5aeb45472f25 | note | Acceptance Criteria - Unless otherwise approved by the superintendent, the following conditions must be satisfied when placing concrete:
2f4c09aa-12f1-559b-9b16-cfeed9888b15 | note | a) The temperature of concrete, measured immediately prior to placing, shall not be less than 10⁰ C or greater than 32⁰ C
d1055979-2584-5f54-be76-7ba46e9c606b | note | b) Concrete shall not be placed if the air temperature is greater than 35⁰ C or less than 5⁰ C.
2a37a212-b182-5dd3-b6f4-4d96aeb60d60 | note | c) Concrete shall not be placed during rain or when rain appears imminent. Freshly placed concrete shall be protected from the rain
a590df53-7218-50a4-856e-519de31784e7 | note | d) Rate of evaporation < 0.50 kg/m2/hr. If not, additional controls initiated as per 610.17. Refer to concrete pour record
b8b69b12-f096-5aaf-a32d-8f8cefcb2a84 | note | - - - - - - - - -
d1608b33-8836-54cf-a506-4610e651e9fe | note | Reference Documents - VicRoads Spec. CI.610.17
96b61fd4-a40e-534e-9561-852e386f710b | note | - - - - - - - - -
bf073f8f-5a35-5aea-aad7-7d3eb97c681d | note | Inspection / Test Method - Visual Inspection
d43be27e-0990-5aea-9808-7ffa4cd5e612 | note | Concrete Pour Record
b5f4924e-d4ec-53e0-a836-fdf1cbbddf76 | note | - - - - - - - - -
a1ee14d3-8cb3-5f15-859a-6593c495d0d5 | note | Record of conformity - This ITP signed
2b682d54-9c20-53f1-8151-fdbd7ad4beb4 | note | Concrete Pour Record
ed9f2689-89de-5178-b21c-ff3726dce4ca | note | Concrete Dockets
0a7c28da-48dd-5faa-b2a4-3c075a41a67e | note | - - - - - - - - -
fcdfdb38-6d50-5857-872b-d75a2db42391 | note | IP
a56303e1-b198-5d5e-be38-8d1e2fc0a22e | note | - - - - - - - - -
bd8c9f58-2e1c-5c2b-84c4-1795e93a98d5 | note | Site Engineer/ Foreman
d8f28c5c-9697-5ff0-ae4f-8e94a247d156 | note | - - - - - - - - -
f51b78f8-f2fe-5def-a182-3b2fa09bed9c | date | Date Completed:
| checkpoint | 6.5 - Concrete Testing - Sampling Frequency
23e2ac60-7abc-54f7-a582-f01ee1ed9da9 | note | Frequency - Each concrete pour
96294161-0f18-5bc0-9c14-349441071092 | note | - - - - - - - - -
590fee72-385a-55d8-869d-a2c0cf9de3ac | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
99af02ba-336e-5e2b-b2f2-91bf616a495a | note | 0m³ to 10m³ = 1 sample
f965ba00-0af4-5caf-befe-5cf6885c7979 | note | 10m³ to 25m³ = 2 samples
ba350131-cc82-5088-b58b-fc1c9189c7a1 | note | 25m³ to 50m³ = 3 samples
45f38f4a-2725-54b8-800d-974c2c57d916 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
1ffc74d9-5451-559a-8f13-6f611a7afbb2 | note | For each additional 50m³ and additional sample shall be taken.
0b20bccd-38dd-59b6-b1dd-468404e9498f | note | Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
dd5d76de-c0c1-58ea-bddc-592f48e7c8cc | note | Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
477d1c39-a1f8-5080-bca3-e3f2a6129e8b | note | Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
670f2b55-ae99-5124-876b-342a1dfdd2a1 | note | Record: Required information on the Concrete Pour Record.
30d54d81-9abc-5e97-af76-558879ce9026 | note | - - - - - - - - -
ac80a8cc-1732-538c-90f9-ad33f2d951f4 | note | Reference Documents - VicRoads Spec.
10537dcf-cd2e-55e6-ac12-a29bd33f717d | note | Cl.610.16 (b)
422d4d94-b718-5fd1-b6f6-6860ef2a42f7 | note | - - - - - - - - -
70224d02-0a09-5099-884c-9113e913f77e | note | Inspection / Test Method - Testing
5c756a4d-c541-5831-983e-e7c8e7c79cc2 | note | Concrete Pour Record
25531554-275b-5911-bfc6-e48e54213c16 | note | - - - - - - - - -
ca7b742e-3c82-5dae-b7eb-ae6a794e2407 | note | Record of conformity - This ITP signed
d002ad5b-11fb-5c98-b9ce-e284a6dfc765 | note | Concrete Pour Record
8dcde46c-28bd-546e-8b09-9d158d1c1415 | note | - - - - - - - - -
bdc1381a-b7d0-5385-aae8-bac8b60b8641 | note | IP
baa63091-6100-5006-b06c-e72b2435126d | note | - - - - - - - - -
1a46caf4-e6d7-5e81-afe7-1537fc1eae5b | note | Site Engineer
09d4cb5f-979d-5acb-943f-1e8c773f38be | note | - - - - - - - - -
ae153745-ed89-5ca5-8d37-9a4b9f40faf8 | date | Date Completed:
| checkpoint | 6.6 - Concrete Testing - Slump
17bc6982-e8ca-5b71-a922-b7088cd5a40f | note | Frequency - Each concrete pour
75e1d0b2-30fa-5811-a632-89ebd041410c | note | - - - - - - - - -
436e4fef-6659-593e-9b73-5e39393fb73e | note | Acceptance Criteria - Slump testing tolerances =
01863b05-6992-5ae0-9701-86d073037709 | note | <60mm = ±10mm
543eee74-4c47-59fe-a32d-ba0718810b4a | note | ≥60mm to ≤80mm = ±15mm
f47ca848-3eb5-57b9-95cd-8a5d0bd86047 | note | >80mm to ≤110mm = ±20mm
ea011e01-6947-555a-ae18-8fb1345be5e5 | note | >110mm to ≤150mm = ±30mm
b068d068-af72-57df-81ac-e7f99ada5c66 | note | >150mm = ±40mm
9a61628e-b5ff-5c8a-8688-77660ac4822a | note | Record: Required information on the Concrete Pour Record.
de3a2322-a3cb-5de0-9023-6ecacedc213b | note | - - - - - - - - -
6c74a8b8-7e8e-57cd-938d-ced9ced9834b | note | Reference Documents - VicRoads Spec.
6a241fd5-10df-56b9-9b6d-c3f79aa14c5f | note | Cl.610.16 (c)
ba0f56b7-5bbc-5ac5-8666-9d1eb1892337 | note | - - - - - - - - -
c109bc39-ae0a-5f44-8daf-fd1fae36ba34 | note | Inspection / Test Method - Testing
9eeb85d0-0f51-595f-bfcb-82efff84d59f | note | - - - - - - - - -
22351d7e-9b7d-573b-a198-bd82e3a0f3ac | note | Record of conformity - Concrete Pour Record
0ecd2b86-0811-5025-9471-223a838ec4ee | note | - - - - - - - - -
e1869f48-bd76-533c-8bb0-9682fcdec825 | note | IP
4a55b05e-312c-5732-84e5-476e9fe78b29 | note | - - - - - - - - -
f7b83522-068f-5cfd-93ba-713647c6ddf4 | note | Site Engineer
c29fe606-9a8b-5154-9a10-e7d759a787be | note | - - - - - - - - -
089897dd-8950-5c42-bc44-9e4dbe34ec81 | date | Date Completed:
| checkpoint | 6.7 - Concrete Testing - Spread, Passability & Viscosity
ed24d33e-dd5c-5a5a-b61f-bf2749611088 | note | Frequency - Each concrete pour
31451af1-87fa-5007-82b8-ab3347923c4b | note | - - - - - - - - -
786f9f0d-3456-500c-86ea-d552056fb55a | note | Acceptance Criteria - Spread range = 550mm to 750mm
9acb76af-fd71-5071-b58c-995c90f30d00 | note | T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
9823b658-356c-5c4e-83cc-8826aee55e1c | note | Passability = ≤10mm (aggregate height differential)
d9d0209c-a30d-55eb-9116-40497194e83f | note | Record: Required information on the Concrete Pour Record.
c86cf111-7042-52fc-8961-ebf6e5e3bade | note | - - - - - - - - -
8325528a-cd8d-534b-ba10-cbe4ffa63dc7 | note | Reference Documents - VicRoads Spec.
7b71e5af-ebfa-5d5d-9fea-ff2844ed6b97 | note | Cl.610.13 (b)
c50a022f-bbb5-587c-ab85-f5ed04f9a38a | note | - - - - - - - - -
7a31b8de-7991-5541-85d1-f3ef75afb28e | note | Inspection / Test Method - Testing
55bf6b76-fe27-510f-848d-6e97afa0d0ec | note | - - - - - - - - -
fc4f3304-af6f-5058-abf1-55ca602ecca9 | note | Record of conformity - Concrete Pour Record
ae0d4a39-d086-5812-bb56-a098725cad8a | note | - - - - - - - - -
1e151278-f7a5-52ed-97f3-8f1b8deee3c5 | note | IP
69834ffe-55d2-5aac-a9df-172eae884ddc | note | - - - - - - - - -
7c74d305-b396-55a5-9294-0bf16a7769ac | note | Site Engineer
eb1a9e86-e3d7-55b0-9c0e-19f0c2420e79 | note | - - - - - - - - -
3d3c8074-4807-56a0-b448-124f2b27a74b | date | Date Completed:
| checkpoint | 6.8 - Concrete Testing - Compressive Strength Cylinders
e42e1038-e6c6-50b4-b683-9a09e6ca94b3 | note | Frequency - Each concrete pour
a9732278-e37c-5c85-ae32-5fb0fbc47337 | note | - - - - - - - - -
7c29e9e3-4754-5610-ae70-f97015387179 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
3f52ed4b-4415-5b97-84b7-be4809009ef5 | note | Record: Required information on the Concrete Pour Record.
e697f146-b6cc-57f9-8f34-ee80bce29f3d | note | - - - - - - - - -
3052ee21-fdc4-5ee2-9048-7b0b5b6bb65f | note | Reference Documents - Site Sampling and Testing Procedure
ea5aa890-a8a6-5fe6-bb15-33322bb0e169 | note | - - - - - - - - -
8b8fa7ca-b5fb-538e-9064-64267cd2d544 | note | Inspection / Test Method - Testing
94bf2ad5-8c4f-5ada-a9cf-81697e95821c | note | - - - - - - - - -
75f0eeb3-4853-538b-a1f2-ddaa18217cad | note | Record of conformity - Concrete Pour Record
04c05506-0679-5628-9c82-4c9bd5a921d1 | note | - - - - - - - - -
a4b5289c-2b5b-51fa-b1ce-5584dafedaf1 | note | IP
cd02c8b4-26b7-5d4b-862f-2ad6a7d1fe3f | note | - - - - - - - - -
9d28391b-97d3-59e4-96da-3eef6ede79f3 | note | Site Engineer
59715180-b51e-5e62-a3b6-f814670f7c3d | note | - - - - - - - - -
9104352e-e9c2-5e99-9b12-61a1b59677f1 | date | Date Completed:
| checkpoint | 6.9 - Supply & Discharge Rates
a9d8d6f7-ed21-5bee-b590-6d1e87820d00 | note | Frequency - Prior to concrete pour (each load)
597f392a-0112-5101-9ecc-193ffb53bdfd | note | - - - - - - - - -
92587a17-c28d-5a17-a977-813c889332c1 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
0d2f9500-0d11-53ba-ad3c-365fb0ba705c | note | No water is to be added once discharge commences.
808ff992-0ae3-5779-b7ac-2a97b8519339 | note | Maximum time between batching trucks is 25 minutes.
9f36e329-05ba-51e1-a93e-26b0854ec47b | note | Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
46baf563-0540-5fad-bd5d-d6ed1a342bed | note | Concrete that stiffens or is showing signs of stiffening shall not be used.
0a9e29c4-af72-54c7-adf2-e58108cba6e2 | note | Concrete is not dropped freely from a height exceeding 2m.
da54305d-3572-5342-807d-1084e2edb912 | note | Concrete is not moved horizontally by use of vibrators.
aae4698a-e94c-599b-9b1a-ada187edcc99 | note | Record: Required information on the Concrete Pour Record.
5839f3c8-2ba4-5cee-ae2e-200b784aebaa | note | - - - - - - - - -
eab4d53f-df52-54c3-996b-0f06ed767c20 | note | Reference Documents - VicRoads Spec.
4ddfcec2-39cd-5be1-8272-3dd1e3b4e7d1 | note | Cl.610.13 (a) & (e )
7e01b616-14e7-5dc2-8028-962d0ac7cdba | note | - - - - - - - - -
4ebbb7cf-d7f4-5519-a1e7-82355e595359 | note | Inspection / Test Method - Visual Inspection
3ac64e5f-5ab5-56d1-aaf6-c9134b7517aa | note | - - - - - - - - -
9bccb663-7f7b-5b0e-b5c0-f4cc7d90009e | note | Record of conformity - Concrete Pour Record
99e3a0b5-36d7-5a52-9d62-7316fac26008 | note | - - - - - - - - -
f40e031b-86cb-5047-ae75-4b13ef3a3440 | note | IP
db22a5b4-5e0a-5844-b2f3-c333f86dd335 | note | - - - - - - - - -
7a1e9cdc-cfe4-5ae6-8315-93472798408a | note | Site Engineer/ Foreman
ec9abdeb-f239-5d5d-95c9-978889e4d551 | note | - - - - - - - - -
06eb812d-d886-5157-a62c-13ed8ea95c2e | date | Date Completed:
| checkpoint | 6.10 - Surface Finishes
3506248f-fe92-58e9-8f65-8d3dc8d260fe | note | Frequency - Each element
8af6cf61-9ac6-5aca-aceb-bdb7dd8fb007 | note | - - - - - - - - -
aff3c0fb-cbef-5b5d-911c-1821cff7bf18 | note | Acceptance Criteria - Surface finish as per IFC drawings.
06b9262d-4ca6-59ce-9f81-b2a70a72cc2b | note | Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
9b7a062b-5ad7-55f7-b7a7-00d38d6db849 | note | Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
b75d1dd8-cb5c-5c43-bb43-7ed222a250d7 | note | - - - - - - - - -
8205bf6a-8e4f-5b2c-be15-60cf46c14133 | note | Reference Documents - VicRoads Spec.
acababb6-901f-5a85-a0d3-048f242eb42f | note | Cl.610.31
adb68a9c-4f5b-50f3-88be-e64cf2fa0d92 | note | Cl.610.20
c732e0bf-e282-516f-806a-1db3f169b043 | note | - - - - - - - - -
ec359d27-47c6-57cc-ab6d-4b06c42e60dc | note | Inspection / Test Method - Site Inspection
f6b417bf-2e9e-5cf9-8319-e79e7115b7d4 | note | - - - - - - - - -
cc519b9b-cb26-5125-96c4-4b2bc4166862 | note | Record of conformity - This ITP signed
8a8ecc86-6a47-5494-83e5-4630a773c772 | note | - - - - - - - - -
b4375cc2-ca0c-5801-ae5a-b664206340e4 | note | IP
b0dda4c7-ac97-525f-88aa-2d42b4caa0a9 | note | - - - - - - - - -
f60643b9-43de-5666-aac1-a83c0a31f3e2 | note | Site Engineer
c09dc73f-7079-5621-907a-75149cb23684 | note | - - - - - - - - -
7096ffc9-c606-5b56-ba7d-91b905406dfb | date | Date Completed:
| section | 7 - Post-pour Details and Inspection
| checkpoint | 7.1 - Thermal Differential Monitoring
bf4adc40-ee9d-546b-9be4-e8328b50d93a | note | Frequency - Each concrete pour
5dd53bca-33de-530e-874b-0a875639dcbb | note | - - - - - - - - -
aef938d0-fd01-578a-adc8-9e5f0442e063 | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
dfd511ba-006f-5bab-a474-f4cd3a0cbd77 | note | Only applicable if the element has:
4a977315-b35b-5dee-8594-c092807579d2 | note | i. the smallest sectional dimension exceeding 500mm
c55acd4c-45f4-56b9-8a9b-0fddd4fb3b7b | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
0977fe47-52ed-5136-830c-fa4aa88c7af3 | note | Attach: Thermal Monitoring Report
485016a6-7d69-5bff-a0f2-5c3717c74045 | note | - - - - - - - - -
a95ef7e0-5d1c-52fb-a669-b231e2a31867 | note | Reference Documents - VicRoads Spec.
f6ac7b5b-1038-5219-808f-84c0627403cb | note | Cl.610.22
e1cff250-dddd-53d8-a05b-3e3641577089 | note | - - - - - - - - -
55a5d35e-4168-52a8-bf5e-8aab5d189f51 | note | Inspection / Test Method - Site Inspection
a5153b67-df78-5fbf-8ab2-4902fbcec27e | note | - - - - - - - - -
37732175-af6b-5c58-a273-1404a28395ef | note | Record of conformity - Temperature data acquired and proposed control measures to reduce differential temperature submitted to Superintendent for review (if applicable)
470dd152-f2f3-556f-9eff-e1c7107c830b | note | - - - - - - - - -
2add5f80-8014-51ca-b919-5a257e965742 | note | IP
f728b0fa-f639-523e-ad38-58b9fd162a17 | note | - - - - - - - - -
c2d536b4-6750-54eb-91e6-0b833ef035f7 | note | Site Engineer
583ab676-2d0a-5b4c-b750-a34c3f86ae1d | note | Subcontractor
88582e9f-62a8-5b4e-bf75-c4d42fb74d65 | note | - - - - - - - - -
30cc8270-f17f-5a63-8f22-603d1e71172b | date | Date Completed:
| checkpoint | 7.2 - Early Age Compressive Strength Test Results - Removal of Formwork
550d13f7-6f4c-578b-9010-7d90e29a6660 | note | Frequency - Each concrete pour
d9a21102-7532-5b86-b9c9-7ccb4dee3fe4 | note | - - - - - - - - -
e11654fb-8a95-5abc-bb54-36c85c6e985f | note | Acceptance Criteria - Where IFC drawings do not nominate minimum strength development for removal of formwork, refer to Table 610.251.
1a9cd49c-2e91-5df2-94df-22d3e6bb5e2c | note | Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
52a9ee83-57fe-55c6-b1c3-3a6b9cc50ac6 | note | - - - - - - - - -
ef779fb7-7b8a-5fbc-a69b-2fedcbb0c493 | note | Reference Documents - VicRoads Spec.
b8b6a6a5-7950-5d11-95f3-76f83dd0454d | note | Cl.610.25 (b)
fab0c0aa-bc6b-5dd1-8bce-93b2da23624a | note | Table 610.251
9dae9326-d605-52b4-8749-a53413db88a7 | note | - - - - - - - - -
0470886d-1b93-5bff-a5ae-50950b612b60 | note | Inspection / Test Method - Site Inspection
a8755566-bc7f-5be7-bea9-406c136d40f4 | note | - - - - - - - - -
3011e4a1-436b-57f2-9005-901ebf63d9ec | note | Record of conformity - This ITP signed
0f16b086-1d39-5d48-beb8-3542597e9d19 | note | - - - - - - - - -
b1b8a641-f0a1-5c7c-87a9-18124a752dac | note | IP
831885d8-8625-5eb7-b8ee-ffadb8ca2eab | note | - - - - - - - - -
721f10f4-214c-57cb-8335-ed05f44d5da2 | note | Site Engineer
f66e31dc-e926-50eb-afa6-3232308b5661 | note | - - - - - - - - -
ace3e948-e448-516c-9075-36af2a4cb012 | date | Date Completed:
| checkpoint | 7.3 - Surface Inspection - Cracks
8b19ffeb-56cd-5338-94fa-efacf9615b60 | note | Frequency - Each element
31e303d8-c016-5601-a4bf-28f0e6be0126 | note | - - - - - - - - -
c47d2cdb-8484-505b-b8a6-7ec64ed5dac8 | note | Acceptance Criteria - Repair procedure submitted to the Superintendent. Repair undertaken in accordance with VicRoads Section 687.
f52cf40e-283c-5361-bf16-2257ef1a374e | note | Cracks investigated and if greater than specified in the table 610.241, an NCR raised. Notwithstanding the requirements of this clause the acceptable crack width at the concrete surface of precast pre-stressed concrete elements shall not exceed 0.1 mm.
44e84268-6c47-5528-a64b-d9ee8dd50bdf | note | - - - - - - - - -
1dad1242-7ff3-56ee-b9d4-a87e82023653 | note | Reference Documents - VicRoads Spec.
de269ff9-9cdb-589a-b8dd-b291e488c40c | note | Cl.610.24 (a)
739372e9-e3b8-5212-ad29-d6c3cbeb9f22 | note | Table 610.241
4bad8a30-13b2-5e4e-b001-a1f140808cf6 | note | Section 687
7375589d-99fc-5c7f-987c-98e70c9690af | note | - - - - - - - - -
9ec36065-9253-52f4-b938-7299e496c86c | note | Inspection / Test Method - Site Inspection
cf8a572a-529e-58ac-b7cb-e335fb35e770 | note | - - - - - - - - -
29b1fa07-f4ab-53a1-9793-0e7295b5cddd | note | Record of conformity - Superintendent approval (if applicable)
cb0c2985-77e8-5d26-a457-8aa91d5f1ee0 | note | - - - - - - - - -
45aa75ee-bcc1-5d84-8d38-edacd6d4ad25 | note | IP
8779dbcb-ec35-53a2-9f2c-10892805d6d3 | note | - - - - - - - - -
d834afa7-2cb4-5bbc-89eb-d7eca8becb9f | note | Site Engineer
c1757a54-6527-5f18-ac35-ecde4f496270 | note | - - - - - - - - -
0cb0fc97-f2cd-5b7a-a693-6295cc135fb7 | date | Date Completed:
| checkpoint | 7.4 - Early Age Compressive Strength Test Results - Placement of Fill Against Concrete
05e8467e-cc55-53d9-9d9a-8c1411301d4a | note | Frequency - Each Pour
adf76685-19ca-5151-a073-52c18ae51aa6 | note | - - - - - - - - -
18ec7bc5-542f-57c4-96b4-474d85b58e1c | note | Acceptance Criteria - No fill is to be placed against concrete within 14 days of casting in accordance with the requirements of Clause 204.11 of Section 204. Proposed placement prior to 14 days from casting shall comply with the early application of loading requirements of Clause 610.16(l) or maturity testing requirements of Clause 610.16(m).
4f9f385f-99a8-52bc-8037-d8cde69a0fd1 | note | No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
7c3eee0c-bd08-5e19-87d8-23b6e4ea9a9a | note | - - - - - - - - -
6d861def-54c3-5fa8-a6e3-68b4bf4707a8 | note | Reference Documents - VicRoads Spec.
7327894c-78e3-5854-ae18-db0067c92d75 | note | CI.610.35 Cl.204.11(b)
380908f7-8b9e-5b04-a816-6454b0a50bc3 | note | Table 204.111
43323513-042e-55e4-ba85-34fc975f3bbc | note | Cl.610.16(m)
8f777645-fc2a-5cef-9f8c-a58b257dc853 | note | - - - - - - - - -
b20b0bfb-2c96-5f77-b57b-20d7f890fadf | note | Inspection / Test Method - Site Inspection
4320569c-0be9-56c6-8935-fb7b9abe9b00 | note | - - - - - - - - -
fe36c6c1-f879-5080-966d-9b606b08b0f1 | note | Record of conformity - Holdpoint released
cde89cf6-4b8b-520a-83eb-3120065cb9de | note | This ITP signed
cdc03bb0-d8d0-5dc4-8b99-8f8d05a76a91 | note | - - - - - - - - -
8c740334-4d24-528d-b132-a9c24eed00a2 | note | HP
f6a5b8a1-c157-5186-b78c-bc2d094917d1 | note | - - - - - - - - -
95e9f4ec-a972-5d45-aad0-214a3e3a0df1 | note | Site Engineer/ Superintendent
32433ba9-7745-58ac-b44e-fd46c50c8ce2 | note | - - - - - - - - -
368b0067-28b4-5232-b460-1b4281cbdaa5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 7.5 - Compressive Strength Result
091b3542-7aeb-5fa8-ab95-13896a3f312b | note | Frequency - Each Specimen
4aef4043-a441-56ff-a5b8-bc044eaaec3d | note | - - - - - - - - -
0f703a7d-082e-5c9f-8bd9-da32f1fbe8ff | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
408b0f62-c71c-5d5a-9cff-11dc0136e87c | note | 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
7bfe0a31-003c-5953-bffc-9ca702b2b5ad | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
b511ebb5-398c-58d1-ab7b-e8d3ffc0c0c6 | note | Attach: Compressive Strength Test Results
137bfe06-644b-54ef-af49-4c680759dc42 | note | - - - - - - - - -
c5e1782e-8f6a-5e80-94e6-c225b6264bb7 | note | Reference Documents - VicRoads Spec.
4cd15974-e1b2-5719-928f-d171e6dd4d54 | note | CI.610.16 (g)
f4b9f28c-d6da-5e75-a53b-5b947f9d386d | note | Table 610.051
e18fd85c-ee77-5ea6-8e9e-8bca994d9b87 | note | - - - - - - - - -
a7041fe3-9a2d-5116-b5a0-bf2eb6ee5b3e | note | Inspection / Test Method - Document Review
34b9df76-4169-52ed-a25a-33fa03298d1a | note | - - - - - - - - -
3cd44d1b-2177-5431-b3ed-a335639cc6ef | note | Record of conformity - Concrete Test Result
c24c8daa-aeeb-5a06-87f3-6ecafc476897 | note | - - - - - - - - -
c89e7b14-2cde-52f1-aee9-2a9dfda44366 | note | IP
1d15060d-e9c4-558a-9374-9193152eaac8 | note | - - - - - - - - -
0b4b4a5e-5f15-593a-9e4f-370eb8e6cb17 | note | Site Engineer
77048b92-d7dd-5487-8b8e-dad19a9fbcf0 | note | - - - - - - - - -
52c24b55-b47d-5953-b084-35708d72e89e | date | Date Completed:
| checkpoint | 7.6 - Post Pour Concrete Cover
2f9c17b9-f57d-5dbb-ad09-0f8ec8bce9b3 | note | Frequency - Every 25m2 or part thereof.
d2706217-17dd-5baf-8f4c-cc549a88cf3c | note | - - - - - - - - -
116fb05f-7dbb-5c50-b0d0-eeee6312ec75 | note | Acceptance Criteria - Concrete cover meter check one 3m² test area for every 25m² exterior surface area.
5d967384-11fd-52a0-8ceb-0e601f6491e1 | note | Minimum 10 no. measurements recorded in each area.
ce9dc8fe-b40d-5787-a5a7-f4c3785ee2ff | note | Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
267c5377-93e8-59a2-bcd1-fa14d3e41818 | note | Attach: cover meter Check Record
223af025-0c73-5884-a390-0baf9a517a92 | note | - - - - - - - - -
029f0c24-b461-5165-8855-bdc1ee7ae03d | note | Reference Documents - VicRoads Spec.
04695e04-1efe-5032-aac0-713e727b3a9f | note | Cl.610.34
9b2c4d10-5b68-5f46-a72f-caf46563b009 | note | IFC drawings
d664dcce-a9a6-5ae4-9786-876a85ae1fb5 | note | - - - - - - - - -
cc61a95a-3e21-5384-a37a-8a584c00cb3c | note | Inspection / Test Method - Site Inspection
aed8ac81-61e7-5ef7-97ca-ae448edb49ae | note | - - - - - - - - -
ac52a894-0df4-5cd7-9567-b39aee3057f1 | note | Record of conformity - This ITP signed
0b03745f-1655-5a52-a2ed-807e0796afc4 | note | - - - - - - - - -
e076b4c3-4351-582a-a188-414c345fff94 | note | IP
fdc2c65e-373c-54c8-9d7d-fdaa5ea84c90 | note | - - - - - - - - -
730360d3-6a8e-5dbf-876a-d1218f1d7d16 | note | Site Engineer
8cdee55e-09b3-5c20-8ae2-1f118d7bba1c | note | - - - - - - - - -
1035f859-ef1c-547d-aacf-9a41684f999b | date | Date Completed:
| checkpoint | 7.7 - Prepare As Built Drawings
754cddd5-7f74-5f4c-8631-3b1351338785 | note | Frequency - Prior to lot closure
59756483-8340-5b8c-a4a3-9dda4e9d3076 | note | - - - - - - - - -
838cd123-0f08-5ed7-a006-2a4cce353400 | note | Acceptance Criteria - As-built survey completed and drawings (IFC Mark up Drawings) prepared for the lot and copy of the drawings kept in the files
d162f7f2-552a-538c-a883-0122bbd6457b | note | The tolerances listed in Tables 610.471, 610.472, 610.473 and 610.474 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
e5502f25-dc74-5793-825b-3b6f5c8eb495 | note | - - - - - - - - -
0c064b3a-130c-5388-b783-ae1253ad22e3 | note | Reference Documents - IFC Project Drawings
dc1381d3-326e-5332-bccf-c622ccedcb0c | note | - - - - - - - - -
a7f45682-f7cc-5146-9cd7-8e1d365f11e0 | note | Inspection / Test Method - Site Inspection
6224a788-a7d5-5137-a0a5-d28b0827c9f3 | note | - - - - - - - - -
2727bdd0-9a0a-5b70-aa8e-54bd0877d113 | note | Record of conformity - As-built survey and drawings
f091be53-73ca-541d-934c-55301baf8c76 | note | This ITP signed
176490cd-501d-54fc-b05b-1b7127033a0f | note | - - - - - - - - -
8ca55e82-d101-5eac-8b91-344dab5780bf | note | IP
b7541bfa-1ba5-5099-9548-49a67ec9faec | note | - - - - - - - - -
4c8480cc-7167-51f3-833a-5326d99f1752 | note | Site Engineer
e807e36f-caec-5658-ae44-d611525f459c | note | - - - - - - - - -
a83caec9-9ac0-51fd-a96a-a27df660fb1d | date | Date Completed:
| checkpoint | Final Inspection
7a51e3c2-f3d9-5cd1-82bf-32152e04bfc8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e5ce45a9-2f40-5b3a-b2cc-e1f0761c7c92 | textbox | Print Name:
5039fc7f-3faa-558d-9d1b-67c8fdd3690d | textbox | Position:
986500c3-f682-5d9f-a052-35ddeca2db33 | date | Date:
04576471-f75f-504c-96e7-f9132bba3fb8 | date | Work Completed On
| checklist | ITP 0015 - Structural Grout (Pedestals, Bearings, Base-plates & Pockets) | itp | ITP-015-AX-LOT-XXX - Desc | 207a7c00-f02c-48e6-a023-e8b8074b7dd5
| section | 1 - Preliminaries - Materials
| checkpoint | 1.1 - Product Selection
96a8db7e-a9b1-5449-a208-682005d79168 | note | Frequency: Once, for each product, prior to placement of product
1d1ee971-2fb3-56e6-a5e5-1231cf5123c8 | note | - - - - - - - - -
f5556270-a9e0-5ae8-a209-e996158df961 | note | Acceptance Criteria: Product to be selected based on the following criteria:
33277c81-21c4-529a-b867-6557337634c1 | note | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout OR a single component low shrinkage mortar
bc845ed2-df37-5a0b-8ba0-8cf20c215ae1 | note | ii. have the required strength at 28 days as noted on the IFC drawings.
171c204c-be5d-5f1b-869f-6e8b14decbd6 | note | iii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings.
48c340dd-180d-5468-b623-9f5c1aca0f89 | note | Note: Pedestals 200mm or greater shall be constructed from concrete - use the Structural Concrete ITP instead
bb93c581-2766-5096-9d49-97c9ea624072 | textbox | Enter: Teambinder Material Approval number
ea7f6a2e-f25a-5067-abc4-2c4c6c710dff | note | - - - - - - - - -
307d1e60-d6ad-5b6d-9c96-2d03bb39c130 | note | Reference Documents: IFC Drawings 610.28, 610.33
e8f0f788-b333-53ae-b860-02a642b7cae3 | note | - - - - - - - - -
c85d4eed-c667-5571-801f-9731a48d334c | note | Inspection / Test Method: Document Review
34e486f0-6dc9-5975-99dc-4c021977e51e | note | - - - - - - - - -
b2cff1ad-b261-5da0-b012-dd4e0253a055 | note | Record of Conformity: This ITP
9fbf4a19-490c-56eb-a205-3a6725bf5cf3 | note | - - - - - - - - -
463acfa1-71b9-5c97-95be-dea72adf8b04 | note | AP
ef3e09a6-2473-5e62-a0f9-c16155b09842 | note | - - - - - - - - -
def7dfe7-38f7-51e6-96d9-144a662c50f5 | note | Responsibility: Superintendent
| checkpoint | 1.2 - Curing Compound
ce213761-b024-53ca-a93a-e87b90e85295 | note | Frequency: Once, for each product, prior to placement of product
f8fcc1d4-36dd-5477-9fc0-8832076691f4 | note | - - - - - - - - -
c8de2979-eefa-55f8-8b43-83dc485175e2 | note | Acceptance Criteria: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
95f05a9c-b090-51d1-8a09-a1fc10dc3fed | note | Note: This may be the same product used for the concrete curing
f42c7cf6-46e0-535b-8b81-4d446ca4296f | textbox | Enter: Teambinder Material Approval number
d99e23f1-5784-5932-a9e0-f4f3582bc843 | note | - - - - - - - - -
e5579792-77ed-5b1a-b2dd-b98d901fc5d1 | note | Reference Documents: 610.23 (d)
7f0add1f-c004-5dfd-a153-f889abb9cf1b | note | - - - - - - - - -
42a1a9e6-04b5-52af-b168-342ff5aac380 | note | Inspection / Test Method: Document Review
f95f60f4-9a74-5063-a66f-125e9cad05cf | note | - - - - - - - - -
0c70af3d-788b-53fc-b388-cbb7ecd01b11 | note | Record of Conformity: This ITP
67c3e403-0c7f-58c6-9813-bfa7172c50e8 | note | - - - - - - - - -
175c7ebf-0ee0-589d-b1c0-da8cf06fdb69 | note | AP
8962b859-83ae-55ad-9b6e-9193a0293d32 | note | - - - - - - - - -
d70c67df-01d3-51d7-9d68-61fe02c91c7f | note | Responsibility: Superintendent
| section | 2 - Preliminaries - Procedures & Documentation
| checkpoint | 2.1 - Curing Methodology (for Concrete, Grout and Mortar)
9408c48b-0c59-58e5-921c-a34fe9951bab | note | Frequency: Once, 4 weeks prior to placement of product
32e4c7d7-47d3-5a78-a6b5-a6f8a424477b | note | - - - - - - - - -
f2d67743-6ade-5d30-93cf-193295610812 | note | Acceptance Criteria: Curing methodology/procedure to be submitted for review to the Nominated Authority.
5b1ab5f3-41b5-55d8-bb2a-d003bda207b9 | note | Note: This may be the same document used for the concrete curing.
c2d4fac6-31b7-512c-9292-3572f468356c | textbox | Enter: Teambinder Correspondence Approval number
98789ab3-dd6c-56a6-9e29-727bb12b6dfc | note | - - - - - - - - -
fdd19a9f-0d17-5f0c-b0fb-26449ee0b549 | note | Reference Documents: 610.23 (a)
470608c6-b0b1-5fbd-8291-b2ab9886f82f | note | - - - - - - - - -
6a097766-d871-54f8-b2bc-5b8cac2abf6d | note | Inspection / Test Method: Document Review
eb25ad97-c2c7-5969-ad7d-07b8a5ebac6c | note | - - - - - - - - -
82c41bf6-b920-57bf-b722-c6c83bc9f7f1 | note | Record of Conformity: ConQA Hold Point Release
ee298e7b-750e-537f-989b-e148cbf4bf4b | note | - - - - - - - - -
bd2e0e24-0ca1-5375-9fa3-9989b887e6b7 | note | HP
00fd64f0-de70-5099-a92e-5636bc3dad60 | note | - - - - - - - - -
c4d9d95e-f7d4-5eae-b93e-089e781175a0 | note | Responsibility: Superintendent
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Pre-construction Activities
| checkpoint | 3.1 - IFC Drawings
8fa4f507-79d3-5ce9-ab35-d471122c3fbb | note | Frequency: Prior to starting Works and at regular intervals
c53298ab-1707-5259-8129-72bf8b81db8a | note | - - - - - - - - -
3673ce84-1a7d-582f-bd17-4747cbe08deb | note | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
4121c005-4aa6-5a7c-85c5-369a9d441f0b | note | - - - - - - - - -
d54e5912-23fe-5456-a0e0-001ccef14d53 | note | Reference Documents: FH Quality Management Plan
81df0fe4-0c13-5e0d-936b-6552abdc0fa3 | note | - - - - - - - - -
4e903f05-46b9-5057-9a3e-8511b808c362 | note | Inspection / Test Method: Document Review
0912681b-556d-50c0-af38-b9abcb7639b3 | note | - - - - - - - - -
3dcbaa96-5296-5475-904e-0f8b7866a949 | note | Record of Conformity: This ITP
621544b2-1884-5dd2-8021-cd423060dc1c | note | - - - - - - - - -
c93edfd7-c40c-58dd-a954-028751dc51bf | note | HP*
a5fa3195-d3d1-5274-ba20-6f23c70206e2 | note | - - - - - - - - -
4a3b7f40-d2cb-5964-974e-2bb987f8a6fb | note | Responsibility: All
| checkpoint | 3.2 - Survey Set-out
cc5bea48-ed33-5591-b191-bbc6096eabbe | note | Frequency: Each element
05b2ef95-a6d3-5540-86dd-880ac9449cde | note | - - - - - - - - -
a63d0a0b-8fa3-59e3-a22e-ab892e751ce1 | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.472 as applicable to the element.
345c10e4-627b-588d-ab6b-e578a11b3093 | note | - - - - - - - - -
9c6be423-a1df-5a0a-b985-3722a1affb08 | note | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
c8e5d3f2-0069-581c-bc64-d48e2817bccc | note | - - - - - - - - -
d26e3ac3-d60c-5d9a-86ff-f0fd9cc116a8 | note | Inspection / Test Method: Measure, Visual
5930283f-b0ed-551c-b20b-9d7c5a621f06 | note | - - - - - - - - -
d00f2ea1-0ed3-5abe-ad3b-4cc0b1af54e7 | note | Record of Conformity: This ITP
52ede7b8-ec8a-5ddc-abbf-4406f725d76d | note | - - - - - - - - -
d1be0c47-d93d-5722-9f6a-9c6f423d3b29 | note | SCP
2263e638-38c1-5a72-84ca-20afd208ebc9 | note | - - - - - - - - -
212f5d93-b8d7-5803-b490-608ff56698ac | note | Responsibility: Surveyor, SE/PE/SPE
| checkpoint | 3.3 - Construction Joint
66ba4577-cc84-5203-afa1-9a1457b7b505 | note | Frequency: Each element
fd4def8b-9e1a-5347-8ac5-7ffa413be882 | note | - - - - - - - - -
1420be8d-40bf-561e-b81b-d0a83ac37fc6 | note | Acceptance Criteria: Where required, the concrete substrate is to be roughened / scabbled in accordance with the drawings and or Product TDS.
66916310-514b-57d0-a90b-83b06e4855f1 | note | Pedestals shall be rebated to 20mm minimum below top of the crosshead / abutment.
6ad803cb-9782-55e3-874e-165002b4222e | note | Where required, any reinforcement shall be adjusted to suit the depth of the pedestal and nominated cover.
92a4d353-4634-5019-8e00-6bc1248c6e73 | note | Concrete substrate surface saturated with water for several hours in accordance with the selected product TDS prior to pouring product.
e9c695ce-6211-56c5-a5ac-3113fd0ec451 | note | - - - - - - - - -
48c1275d-d96d-5d5b-af6b-4654336ecb55 | note | Reference Documents: IFC Drawings, Product TDS 610.20 BTN 024 Note 4
c51381a6-2764-5a9f-8e17-056968870625 | note | - - - - - - - - -
7d9b6a40-1a3a-5f25-afba-9f362e319d23 | note | Inspection / Test Method: Measure, Visual
f48966e9-7897-50d4-b8e2-15c0d3b87b43 | note | - - - - - - - - -
336b2506-1dcc-583e-95dd-aba57993f1c3 | note | Record of Conformity: This ITP
0c81e753-90c5-5539-bbdd-922bd8a38719 | note | - - - - - - - - -
0055041d-4a73-5521-a150-6b44dac3379b | note | IP
bd5f43e3-4386-57a6-b4b7-c2e38dffb90c | note | - - - - - - - - -
a6a234d8-dd9a-584a-b5fc-79b8dc0dad4d | note | Responsibility: SE/PE/SPE
| section | 4 - Construction Activities
| checkpoint | 4.1 - Formwork Construction & Placement
f8cadb90-fa39-50a0-bda1-e72e38d751de | note | Frequency: Each element
aa0fccd9-cdf4-5f04-9172-95b09de9a8f6 | note | - - - - - - - - -
2fd68635-149a-527b-b544-07f32d8626a3 | note | Acceptance Criteria: Dimensions in plan as per drawings to achieve the desired grout profile.
1a3bf5ae-60d9-5728-b670-7dfc96437cef | note | Formwork rigid, sufficiently braced to support the pressure of the product and sealed to prevent leaks.
459b691b-ca08-5a2d-bb12-8c29009dc00f | note | Where applicable, any cast in componentry (ferrules, conduit etc.) secure.
0a87c0fd-d6ec-5d33-b1f3-3c941794132d | note | - - - - - - - - -
06e32726-3867-50fe-9815-71280647652d | note | Reference Documents: IFC Drawings
2c3d27b6-7814-5185-9381-f9fa59bd93f8 | note | - - - - - - - - -
0c41ccd5-b6c2-5d0d-bad2-a6d854063511 | note | Inspection / Test Method: Measure, Visual
2f3eb685-2be4-5632-96bd-d73a42d21871 | note | - - - - - - - - -
98cec6a2-65e0-5956-a73a-bd1dd699715a | note | Record of Conformity: This ITP
9a0001a5-a02b-5298-871b-d00c6d401aae | note | - - - - - - - - -
aa9c7eee-cab9-5671-babb-bdc35b0f83bd | note | IP
a74683f8-c0e0-573a-8272-0a60ed70df3f | note | - - - - - - - - -
e9c6ac08-6a4b-50a1-a7ba-209dba15bcc0 | note | Responsibility: SE/PE/SPE
| checkpoint | 4.2 - Pre-pour Inspection
3e56031f-aa37-5309-8105-442ac634dae6 | note | Frequency: Each element
20571963-8eb0-52c5-b202-2be59ce6a07c | note | - - - - - - - - -
6fc53705-b0db-55e9-b7b1-4b81177fa6bf | note | Acceptance Criteria: Concrete substrate surface moisture condition as per the Product's TDS, with no ponding of water.
3c14f78e-01f4-5e3b-9317-01501e9f8832 | note | Formwork location and RLs comply.
7c72790d-382e-57b9-92c8-8abcad7da0bc | note | Where applicable, any reinforcement is clean and has the required cover.
746d59b0-2ae2-5d68-9f82-0fed14c22ef4 | note | - - - - - - - - -
ea41c7d6-2d72-5c15-9527-ecf16baed542 | note | Reference Documents: IFC Drawings, Product TDS 610.20
93c52d92-5563-52cb-92ff-a0db520ff57f | note | - - - - - - - - -
a2ec8553-c7d1-5f95-a68c-81bca6736061 | note | Inspection / Test Method: Measure, Visual
bc083cf4-3e49-5a70-a395-13bbd695bd2f | note | - - - - - - - - -
510b25ed-0609-5ec1-bf4f-1a3b0dcb2729 | note | Record of Conformity: This ITP
f0471237-1716-5cc3-a18b-bee739deb544 | note | - - - - - - - - -
61c92bba-56de-5963-8043-9f7c7681b67d | note | IP
e49862ee-4992-549f-90b2-41a6ebbf0d03 | note | - - - - - - - - -
549c4fb7-ca6a-5d90-9c34-e170aaa5e7f1 | note | Responsibility: SE/PE/SPE
| checkpoint | 4.3 - Weather Conditions
f53bd107-a65e-5231-9ec8-0d4e85e9a3c1 | note | Frequency: Each element
18990355-abd1-5550-8922-5bcd9ad88f44 | note | - - - - - - - - -
27d7f645-e56e-56c6-adbf-b198808a061b | note | Acceptance Criteria: All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
ae07df73-d5ad-5874-8ff2-5b59bb46ef83 | note | The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
fa286591-360e-5215-ac24-64cb672b1c37 | note | Record: Required information on the Grout Pour Record.
082e482c-d75e-5b41-ba67-57880f8601fa | note | - - - - - - - - -
fe2ee8eb-d403-591e-8580-7aae4e2ddd08 | note | Reference Documents: 610.17, 610.17 (a) & (e) Table 610.171
8ae50c65-f70d-5edf-b933-fc5f908da584 | note | - - - - - - - - -
25129b16-d29e-585b-9ba0-d899fbc83ec5 | note | Inspection / Test Method: Measure, Visual
a1fe6d5d-c084-5fa3-bbe8-807fa7bddbaa | note | - - - - - - - - -
25f85d97-9009-5f1a-9cf0-5bf23a7fb355 | note | Record of Conformity: This ITP
b7c5fe68-37a1-5d28-a45d-6361066a6e8f | note | - - - - - - - - -
d77fef3e-1e60-531d-9dda-5019ad463a63 | note | IP
287d2abe-d58a-5467-a35f-2fdbbdfc9a25 | note | - - - - - - - - -
de094134-b7e1-5ffc-b7ad-574a03eedced | note | Responsibility: Foreman, SE/PE/SPE
| checkpoint | 4.4 - Mixing Product
aa6c85e3-ee3f-535f-91b3-eefe6042644f | note | Frequency: Each batch
29f7f6c2-2bd3-5c8f-8eb6-06bfb1dadbca | note | - - - - - - - - -
b8206124-6ba2-52c1-918f-1392ca153aa5 | note | Acceptance Criteria: Size of mixer should match the application.
d1568823-58e5-56c9-b992-9694acbae1df | note | Only whole bags to be mixed with potable water.
418c0f33-d1df-5020-a4fa-d9b629a17112 | note | Volume of water matches the required amount for flowable consistency and accurately measured.
c74832d4-fc75-5dbc-863b-cb18cbf58185 | note | Product poured into the mixer slowly.
488bd572-6cbd-5963-99a2-47897a24ad41 | note | Mixing time as per TDS so that a smooth, even consistency is obtained.
a90a207d-be81-51e3-81bc-82eb6e52f7a7 | note | Enter: Required information on the Grout Pour Record.
cc05c78f-bffa-5524-b174-a5027e7c4f5c | note | - - - - - - - - -
0c5177b7-d773-59d1-9018-5a177e9bb28b | note | Reference Documents: Product TDS 610.28
0a7aefaf-0acd-5d9a-95b5-5717f2d70292 | note | - - - - - - - - -
aab3ee36-c743-5bbd-895a-524aac245dfe | note | Inspection / Test Method: Measure, Visual
56b7edf1-956a-5300-8f08-6682fcab717a | note | - - - - - - - - -
66b7eb89-356c-5895-b7e9-5a30a89c840c | note | Record of Conformity: This ITP
5dae6d46-a8eb-5cb5-8ed9-8b34969678e4 | note | - - - - - - - - -
48e498b0-1d6c-5d20-933a-141609eee6c5 | note | IP
8ac1d01f-21c2-56ac-b778-e3165b190287 | note | - - - - - - - - -
cf92efab-c191-5b8a-986d-5460ce73fa0c | note | Responsibility: SE/PE/SPE
| checkpoint | 4.5 - Product Testing - Compressive Strength Cubes
4c0f60c0-b0be-5a41-b0f5-9a5cd9121f6e | note | Frequency: Each element
f84669fc-eec5-5ab1-85e3-48991bef3d62 | note | - - - - - - - - -
747fa074-c97b-537f-831c-fd546b4dea85 | note | Acceptance Criteria: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
594fd0a8-ef40-5a5e-8eb7-80152fe95b1f | note | Testing is be in accordance with the following frequencies:
2daa7c93-676a-54b8-ba4a-c1d93eec4dcd | note | First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
6549e62d-67a9-52db-a84d-363f964d002f | note | Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
68ff6541-9e74-528e-a7e3-ecb693ddf52a | note | Enter: Required information on the Grout Pour Record.
6a077721-88dd-5549-9e8d-4c9586d6af45 | note | - - - - - - - - -
ebcf4191-a92d-5637-8248-2223afa525ea | note | Reference Documents: 610.28, 610.33
6380dfaf-6340-5956-9467-961ea7a6db9c | note | - - - - - - - - -
86808098-df39-5d44-9d72-96823e737858 | note | Inspection / Test Method: Test
78b5ec90-575e-5ebc-b414-652469f2f8dc | note | - - - - - - - - -
a06ccb25-0a96-5e19-b743-2c18a77a3903 | note | Record of Conformity: This ITP
b7c921c1-b68b-5465-b73c-9cf3f424573b | note | - - - - - - - - -
34abd21f-4648-5e60-b884-3102a7e4e5c4 | note | IP
9559e8b4-d576-59a0-b82f-0bfa6aa09df6 | note | - - - - - - - - -
5fcfe6d3-5d02-5898-88f8-87237b1d0f15 | note | Responsibility: Tester, Sub-contractor, SE/PE/SPE
| checkpoint | 4.6 - Placement & Compaction
415e796d-e32e-5bcb-85f3-ddd2fcf9fde0 | note | Frequency: Each element
5125887b-dbcd-5eaf-b8b6-0bcdca10d3b4 | note | - - - - - - - - -
ca2bb08e-4072-521a-869b-e6583f9535ac | note | Acceptance Criteria: All batches are traceable.
1c8cff4d-8ac5-5ae2-9688-45b210e73875 | note | Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
acf6caea-c295-5b24-9190-e6e34159f3ca | note | Product should flow to all areas and self consolidate.
a17e4575-b5e2-5e76-be60-6cdf4891bbbc | note | Product that stiffens or is showing signs of stiffening shall not be used.
2e65fb4a-c27f-5363-99ba-c9a7509ee913 | note | Enter: Required information on the Grout Pour Record
0f8ff846-635c-590b-94c2-d473e1459582 | note | - - - - - - - - -
dcc68ade-69ca-5ddf-a1e9-e34028944ed2 | note | Reference Documents: Product TDS
b2a447f5-1302-5c2d-b733-38641a85c382 | note | - - - - - - - - -
09643902-136e-50b0-bedf-9b9710c7594f | note | Inspection / Test Method: Visual
1dea3499-0033-54aa-a8c4-51a3d77d6f1e | note | - - - - - - - - -
e84a71d8-d452-525d-b232-7319155b0770 | note | Record of Conformity: This ITP
e964ce07-0385-5cb6-91d3-27245cfbe178 | note | - - - - - - - - -
ea03971b-6c6a-5bdf-a2fd-7ca0e1badbfa | note | IP
abda90f9-c6d0-594c-9ac0-3d381c2338be | note | - - - - - - - - -
2e98874a-af7e-5a12-b370-7df8fb4926cb | note | Responsibility: Foreman, SE/PE/SPE
| checkpoint | 4.7 - Surface Finishes
3dca5697-cbaf-5d4a-a874-6c51f2f3b2bb | note | Frequency: Each element
c97b4a3c-91b4-55f2-a2a5-800b4e4ee61a | note | - - - - - - - - -
6b34bb36-d313-528a-8bc9-d2c73115c6d5 | note | Acceptance Criteria: Surface to match the IFC drawings.
671c17b2-c50f-5729-8062-ba6b03ccf1c4 | note | Where not shown:
ab0a9037-89a9-5ce1-9a63-3655dd62ee1b | note | Pedestals:
bafcff9e-d3f8-5360-a848-6ea4031d7762 | note | Surface to be finished flat with a surface roughness of an amplitude of approximately 0.5mm - 1.5mm, likened to 40 grit sandpaper.
8f6e5b50-379c-56e5-9ac4-0cad8a35fa6c | note | Bearings, base-plates and pockets:
8dd71918-5a06-5780-a914-ff1dca5bdb19 | note | Surface to match the the surrounding surfaces using a smooth trowel finish where exposed.
f8e8517d-b23a-59a9-a62e-3f0ca0b4959a | note | - - - - - - - - -
a75e8e56-ded6-5846-8935-b6e6e4d4c691 | note | Reference Documents: 610.28
60fe69ee-80ae-551c-baa0-b3a159c4b31f | note | - - - - - - - - -
9584907f-3ae2-5c7d-8f4c-4a2e4bf4a8a6 | note | Inspection / Test Method: Visual
b4712f42-5730-55ef-8914-4079784dcf61 | note | - - - - - - - - -
01be13c9-084d-581c-885a-ad0bda61e3e0 | note | Record of Conformity: This ITP
4e25f484-94e8-56df-a5b9-e9e8e25b639e | note | - - - - - - - - -
36c8c8c4-06d2-57af-b5f1-7bc09236da61 | note | IP
d9b9ad9f-d8ef-5910-9e3a-fd9051a37a63 | note | - - - - - - - - -
da168fe5-2335-507b-82f8-bc6e899f6761 | note | Responsibility: Foreman, SE/PE/SPE
| checkpoint | 4.8 - Curing
aedb6d39-9c31-5928-87f9-cbd10e966a82 | note | Frequency: Each element
bb4dcbad-ecf5-5ef9-a22a-0cac8d98d751 | note | - - - - - - - - -
34620ff7-4804-54a0-840b-a17deec160a7 | note | Acceptance Criteria: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
faead20a-0be2-5d5e-86b8-9db32b08ee24 | note | Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
638b5d70-c927-579b-9717-1244d3439dd9 | note | - - - - - - - - -
c96b68c7-9e96-51d4-ac61-eeb6f05dab6f | note | Reference Documents: Curing Methodology 610.23 Table 610.231
aeab0905-a7f1-52a8-96ad-558417cba41d | note | - - - - - - - - -
46d2240a-5093-5142-8dbe-a1c586cd9298 | note | Inspection / Test Method: Visual
ca63ed8d-87c0-5f1f-8e32-de31fb4a184b | note | - - - - - - - - -
69f75438-5a10-5018-b012-89130908a1f6 | note | Record of Conformity: This ITP
e31f6940-bfeb-534f-9547-06d19eaf2d15 | note | - - - - - - - - -
209d8fd4-b418-5343-af15-978ccdd4b1e3 | note | IP
9c1ab900-7210-5b80-a35e-49cc117cf5ef | note | - - - - - - - - -
02e00457-a118-5ab1-837d-fde303dbc88c | note | Responsibility: Foreman, SE/PE/SPE
| section | 5 - Post-construction Activities
| checkpoint | 5.1 - Compressive Strength Test Results
e8eafaba-8c45-5f54-817f-dd843cd4e71e | note | Frequency: Each cube
87a8e040-5133-5808-a1f7-9ba80e285225 | note | - - - - - - - - -
3b5c52d8-a4c8-569e-81a0-7ba0748f7f83 | note | Acceptance Criteria: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
656b523f-4d50-5184-bd15-c0556fa3f01e | note | 28 day compressive strength per sample comply with the design strength.
dd35e463-8321-583c-85d1-93caeea05dc1 | note | Attach: Compressive Strength Test Results
a2d0f152-8e2e-514d-936c-67386cc1e857 | note | - - - - - - - - -
b385398e-9330-5102-aa5c-2244e8d6bd28 | note | Reference Documents: IFC Drawings, Product TDS 610.28, 610.33
6717a42f-7a75-5af8-bfc5-8c102ef3bbd5 | note | - - - - - - - - -
ee716392-da84-5629-b822-a2a297e0237e | note | Inspection / Test Method: Document Review
566475fd-adce-5723-8b71-35babf826884 | note | - - - - - - - - -
1b126051-4380-52ec-81cf-443f7b464024 | note | Record of Conformity: This ITP
20aeb793-2f8c-5561-b898-b25d3b47053c | note | - - - - - - - - -
a6877787-8958-5512-9fb9-c23965bf7398 | note | TP
d644b832-5856-5fe7-8341-d073e8c5499e | note | - - - - - - - - -
e55b69fe-05a1-59b6-82a5-4d944cac2c05 | note | Responsibility: SE/PE/SPE
| checkpoint | 5.2 - As-built Survey
c254772a-5f17-5fb2-917a-702059acf0fc | note | Frequency: Each element
7fb1427d-9e71-50bf-8ed2-a2769ba9e84b | note | - - - - - - - - -
393bf89a-c88b-5869-8b23-f10d2c789506 | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances below:
617d5422-0e55-511e-b6d6-607ab0108e7f | note | Reduced level ±2.5mm
2b936f5f-dd59-5513-bcf5-2629074413ad | note | Variation from grade across the width of individual pedestals shall not exceed 1 in 200
0b4554c9-9400-54c2-a087-d1e70f20ed9c | note | Deviation from flat surface ±1mm
79d1498c-47be-50fb-90fb-ca478c64297b | note | Attach: Survey As-builts / Survey Report
104adeef-b1a0-56e1-9482-81e3ef6c9561 | note | - - - - - - - - -
e2c7fd4f-fcbf-5d3b-a78c-381f50499b76 | note | Reference Documents: IFC Drawings 610.47 (a) Table 610.472
212b6ec1-4b1f-5157-87c7-d627845fe7c7 | note | - - - - - - - - -
3f4d9721-1cdc-5ffc-82ad-6624c2c04a52 | note | Inspection / Test Method: Document Review
6b2794a6-b395-5bf5-bcf3-2c04a27a7e29 | note | - - - - - - - - -
fb050edd-6968-5723-9488-a7ce1a5dc55d | note | Record of Conformity: This ITP
023882ba-4d99-55fc-a19d-e435c0020d76 | note | - - - - - - - - -
4e0d7c7e-f0c9-5027-9e4f-cca13ebe535a | note | SCP
fa9292cc-de26-5387-ae03-e9f1f359d22c | note | - - - - - - - - -
8b3a2bca-ef3a-5724-8018-e76284189e34 | note | Responsibility: Surveyor, PE/SE/SPE
| checkpoint | 5.3 - Non-conformance Report (NCR) Closure
4333a2f0-6dcf-53fd-a89c-29bd5203b2e2 | note | Frequency: Once, prior to closure of this lot / element / Work area
06de9df4-a380-58c2-889f-5f89001e17b6 | note | - - - - - - - - -
0a2dfd73-a3a1-584a-ac74-01c9e137abe6 | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
f0376ff8-11d8-5ab9-90a3-a60a99a7b383 | note | - - - - - - - - -
531e15e8-17a2-53e1-9c82-00d2267f9a89 | note | Reference Documents: FH Quality Management Plan
6ad508df-a604-5e7b-aced-554ee92c4acf | note | - - - - - - - - -
4b347384-425a-52d3-905f-509ba64bc14a | note | Inspection / Test Method: Document Review
be43b404-4db1-5098-9878-e04fbc251ed2 | note | - - - - - - - - -
28e6dd18-356c-5e60-af9d-29385933b700 | note | Record of Conformity: This ITP
fae66785-2a87-5c80-84aa-7d0824b3d98e | note | - - - - - - - - -
25a19040-85b6-5f23-aa82-7e4c9374ef1d | note | HP*
fc6a91c6-9e10-5d5d-9b55-bb14f8d6b460 | note | - - - - - - - - -
089c5a6e-6670-5930-a4ce-a67eb1ea2694 | note | Responsibility: PE/SE/SPE
| checkpoint | Final Inspection
4a100126-b016-580c-b085-9a54fde1061a | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fb3e7cb5-feb9-5a02-ac6f-ddcb25f7dabc | textbox | Print Name:
d6b35da7-c0fe-5465-9118-c15828dd35f2 | textbox | Position:
6f87a7d7-aac4-5658-ac6b-a1ea6add2d95 | date | Date:
155fc95b-79dc-5ee3-8f2c-2ed4ba79d181 | date | Work Completed On
| checklist | ITP 0016 - Bored Pile Construction | itp | ITP-016-AX-LOT-XXX - Desc | 9108e340-54fc-4ea0-9d05-aae48b003723
| section | 1 - Preliminary Works / Design and Submissions
| checkpoint | 1.1 - Induction
dc69fe4f-2927-5eed-8d51-7ec415f5396e | note | Frequency: Prior to Commencing
546ef0ee-6a87-54d8-8742-4aca166ce964 | note | - - - - - - - - -
f1b61500-e339-5670-8388-0510a63352ba | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
4435852c-7dec-5a6f-ac3f-18889684eeeb | note | - - - - - - - - -
eab03875-3513-5a7c-81c1-656eed51c2bc | note | Reference Documents: Site Induction Register
12f8a4e0-60db-5407-8f81-adfd0ac8f389 | note | - - - - - - - - -
464774b7-3728-562f-ad52-915de1efd59e | note | Inspection / Test Method: Document review
85c2150d-fca4-55a5-8625-9bb0ba429993 | note | - - - - - - - - -
4db4a3e1-1c02-5fd5-9c19-0357445148bd | note | Record of conformity: Site induction signed.
2eaa54a8-5f8a-51b1-a01c-cd5a3442ca8d | note | - - - - - - - - -
36e7ceef-a7d9-5f3d-89ad-bac3901f5bfb | note | HP*
70d992d5-ee26-53fd-ba6c-ccfb8ee3f3f2 | note | - - - - - - - - -
91f92f57-ccfb-5520-9441-ea938a91a9a5 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Work pack briefing
e2bf3668-0eaa-568e-a04c-215beebcd696 | note | Frequency: Prior to Commencing
709efc91-f573-55de-a2e1-ccbd954cb089 | note | - - - - - - - - -
dd6c3a0f-3bb5-5c24-91e0-45f04cb3ab58 | note | Acceptance Criteria: All personnel on site have been briefed on the relevant work park relating to scope of works.
ec8ce36e-5d9c-5239-b0fd-aa668220f2b8 | note | - - - - - - - - -
8c67c823-8dc2-505d-a881-1533175fa5ee | note | Reference Documents: WP
4079b96b-335a-5fd6-a651-4558958056bb | note | - - - - - - - - -
86bbf4b0-f967-57d1-a07f-c468364fbadc | note | Inspection / Test Method: Document Review
5d45ea71-3c56-53ad-b9bb-6519406b14db | note | - - - - - - - - -
d8b2d85c-1f9f-58e8-963b-48e9b699893c | note | Record of conformity: Work pack signed.
fa4cda53-42d2-54e3-8711-20b588c3f056 | note | - - - - - - - - -
0e788b57-7a34-53c8-a59c-494bb5c2a0a1 | note | HP*
bd002e1e-4027-5218-bc01-7201e187a205 | note | - - - - - - - - -
d133ddd8-d685-52cb-b006-cab96c9a165a | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
0d17df8a-f571-5bb1-8a70-204e5b6eb807 | note | Frequency: Prior to commencing
471e360f-9c59-5fad-bdf3-d34b9c06c114 | note | - - - - - - - - -
8f053ab6-297d-5362-8811-1e8f07912690 | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
a20c401c-8a10-5e8b-b2ff-e15a1e0252e9 | note | - - - - - - - - -
abb51c34-4bb0-58c6-9f5d-57e8c24ca803 | note | Reference Documents: Health and Safety Co-Ordination Plan
bf4f083e-2e7c-5142-85cb-c34813ee0f41 | note | - - - - - - - - -
bef0debc-5e3d-5889-a0b9-ae83255c2b21 | note | Inspection / Test Method: Document Review
a1c8baf4-9b50-566f-b2f7-390583387585 | note | - - - - - - - - -
07d300fb-0032-5d29-b684-295c4066008d | note | Record of conformity: SWMS(s) signed
2328a072-45d6-5230-a798-631dbe7c061f | note | - - - - - - - - -
eed284e8-b365-529d-8b7b-1b93c4a50d46 | note | HP*
b8d91945-eeda-5d44-b775-64ea3287f315 | note | - - - - - - - - -
970f27ac-5043-503b-94c0-beff2bd85743 | note | Responsibility: Site Engineer
| checkpoint | 1.4 - Check that current revision drawings are being used
0ede8ae8-41c2-54ac-abe4-8cf8a7441566 | note | Frequency: Prior to Commencing
f74e9451-f60c-5716-8356-81b28e494e94 | note | - - - - - - - - -
6ae35365-7dcd-534c-bb49-773f8bad3476 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
91d605c0-93ff-5770-acb1-2e6204b302cf | note | - - - - - - - - -
95a584de-85aa-509c-a260-f600249878ea | note | Reference Documents: Project Drawings / Drawing Register
65caa2cf-13f9-55fc-a8a2-f89a765f25b6 | note | - - - - - - - - -
d7290a81-77e0-556a-a305-447dbef70482 | note | Inspection / Test Method: Document review
adf4a7be-9fe9-51f0-a5e8-4e4e0c5b438c | note | - - - - - - - - -
438d63b1-d219-5ba9-a15f-ddb1fd3be3e9 | note | Record of conformity: This ITP Signed
2430e25d-8cf0-518a-a8be-6bad145fe9b2 | note | - - - - - - - - -
215091e0-7eac-566c-b191-da795c695819 | note | HP*
a85f8c5d-e456-5c95-8c03-5b3081469d56 | note | - - - - - - - - -
0a33f83f-f63d-513f-9950-9c416f647194 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.5 - Confirm understanding of current Environment Management Plan (CEMP) related to the work area and that all prescribed environmental controls are in place
3565156c-2b01-58b5-811e-bfd40cf348fb | note | Frequency: Prior to Commencing
d246b354-638d-5930-8e53-4fd6065a4447 | note | - - - - - - - - -
54e96d51-e68a-5361-81f7-83b23dedc0c5 | note | Acceptance Criteria: All personnel on site have been inducted and briefed on the requirements of the CEMP. All environmental measures including sediment and erosion control to be implemented as per current CEMP.
081a5490-6950-5267-a3db-d684a4268add | note | - - - - - - - - -
6c3249dd-e41b-5bb0-9f98-02ab572e8fad | note | Reference Documents: CEMP
37c2cd52-dc35-5609-8511-659b61d106d8 | note | - - - - - - - - -
fd64fa9c-698c-528a-89b4-287d18ba2e9e | note | Inspection / Test Method: Document review & Site inspection
2b520bae-7c22-5675-9ba3-8b2df072af29 | note | - - - - - - - - -
ae921873-9a52-5d22-bb6f-ebc173c30382 | note | Record of conformity: This ITP Signed
78d1a428-9c11-52f5-a9e0-e82b71c713f4 | note | - - - - - - - - -
322ec191-f0eb-51b5-9d49-e48e1d2ea3f9 | note | IP
14bbe912-4f0b-59dd-a009-d297819e18ed | note | - - - - - - - - -
c93ca0e0-f102-5e37-a938-472a78979e42 | note | Responsibility: Site Engineer
| checkpoint | 1.6 - Excavation Permit issued
1cad79ab-e91a-5649-bf8b-4cd06dd7d5a2 | note | Frequency: Prior to Commencing Work
805fa348-940e-591e-ad20-1f6930bd3016 | note | - - - - - - - - -
e2966e24-8e32-5039-bf8b-1d7b427307a6 | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
c8ba18fe-97ea-5f50-91a9-9eb9f21ebcea | note | - - - - - - - - -
ffe87a8d-1cc1-5158-9481-a53a31128a85 | note | Reference Documents: Excavation Permit
5256c8c5-27db-56a6-9d4f-aaa958073ea1 | note | - - - - - - - - -
ca59627e-d940-586a-96fb-714db73b0ef7 | note | Inspection / Test Method: Document review & Site inspection
fa9f194a-b37c-562b-90fd-70d84c7ef7fe | note | - - - - - - - - -
4105a8de-a570-5b90-811a-c65237af6438 | note | Record of conformity: Excavation Permit #
49b55e7b-9e11-5e21-9014-9267007c5a17 | note | - - - - - - - - -
52ad18d4-5669-544a-a8e7-e236fe110974 | note | HP*
91ffc05c-0ab5-5880-92d8-74e247bfaf22 | note | - - - - - - - - -
0118ac5f-79b5-51cb-b9a2-7d3b9f2500d2 | note | Responsibility: Site Engineer
| checkpoint | 1.7 - Traffic Management (When required)
c2315c35-c18e-511f-b9f7-e16be94d3145 | note | Frequency: Prior to Commencing Work
cb6cde1e-46a8-53fa-881e-fceda9a8295b | note | - - - - - - - - -
45d91b6d-97e2-5733-a77a-48356e7fe343 | note | Acceptance Criteria: Approved WTMP and MOA
b8986edb-9aa4-5326-89cd-3ad316192350 | note | - - - - - - - - -
01607292-3013-5d97-a44e-59d67cde8edd | note | Reference Documents: WTMP
4a726a54-91be-59ec-8f5f-7025f5a6d7c3 | note | - - - - - - - - -
c7b2e3b3-f824-5a0c-b24d-b56d6ed5bef1 | note | Inspection / Test Method: Document review & Site inspection
18805fbb-cb5a-5fbf-bde3-a8332d92010b | note | - - - - - - - - -
d29d69c1-d178-5fc1-92fa-a7fbafe693fb | note | Record of conformity: Superintendents Correspondence
69269e86-cedc-50bf-87f4-38c2732029ce | note | - - - - - - - - -
056dbe9b-8b46-5051-936c-8908d0e9aff3 | note | AP
38b68378-500d-5ba3-b1ee-c7454c6bfa18 | note | - - - - - - - - -
87dcee6d-1683-5680-980a-9112a3d53ca1 | note | Responsibility: Site Engineer
| checkpoint | 1.8 - Mix design
5db029b9-90a7-55b1-a51d-891959eff701 | note | Frequency: No less than 4 weeks prior to commencement of activity
ce8460d1-96df-5ac6-9ba6-5a9fca5e7ebd | note | - - - - - - - - -
c6040e21-b134-5a0a-b4fa-62054c3dd902 | note | Acceptance Criteria: The concrete mix design details shall be submitted for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
081730bc-cdec-550a-83de-4a8355b6d652 | note | Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
47314ce1-3b1b-5520-881a-1f2a685d49b9 | note | - - - - - - - - -
ed853613-680e-5656-a58d-49414db82d46 | note | Reference Documents: VicRoads Spec. Cl.610.07(b)
7e808f0b-ec4b-5384-b9ff-47e3edd49b81 | note | - - - - - - - - -
e1d6df09-ad4f-58a5-beb4-9969b40ce83d | note | Inspection / Test Method: Document review
75967714-4e69-5d2d-8755-593e711d56ec | note | - - - - - - - - -
ce5b445d-1be6-5fbb-82ba-e95b6b142386 | note | Record of conformity: Approved Mix Design
97f3afd8-c8fb-5d71-b70c-e8bac66af460 | note | Allocated registration number on the Register of VicRoads approved concrete mixes.
036d8780-4bae-5f3a-9ab3-09781b7b381a | note | - - - - - - - - -
509adcc5-020c-5ec5-bd6d-f31b3a9a419a | note | HP
9166c39a-bd9b-59b0-896f-6de848f0a079 | note | - - - - - - - - -
0f765674-b610-575d-a5f0-235a1bda3089 | note | Responsibility: Project Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.9 - Steel Reinforcement
8760f045-22d1-51b7-b37a-7918d243452c | note | Frequency: Prior to commencing works and no more than 14 days after contract award
d50d0ecb-6a10-50b3-824b-fc3653d9b588 | note | - - - - - - - - -
5caac51b-ffce-54bc-ba62-d57d53f3f0de | note | Acceptance Criteria: Steel reinforcement shall comply with the requirements of Section 611. Unless otherwise shown on drawings, bars shall be grade 500N. Allowances should be made when preparing the steel reinforcement schedule to achieve the specified tolerances on member dimensions, concrete cover and location of steel reinforcement
2b83a8a7-e66d-5a5d-a14a-310157dfcd1e | note | Manufacturer of steel reinforcement materials must be in possession of a current certificate of approval, issued by the Australian Certification Authority for Reinforcing Steel (ACRS). Evidence of compliance with this clause shall be submitted to the superintendent within 14 days of award of the contract.
e9c3ef22-74a7-5ebb-a279-d80ed321a50d | note | - - - - - - - - -
8b737217-1580-5cdc-b7aa-ecff1562a411 | note | Reference Documents: VicRoads Spec.
ed129e50-de4b-5560-90d8-db3e4624652b | note | Cl.611.03(a)
cb32f037-c6d1-540e-97f2-33e73f8bc339 | note | Cl.611.04
bc2a973c-9c74-5e97-b69a-28efc47a03d7 | note | Cl611.05(a)
4cf3e100-858a-5a34-b25d-1afef9dd8b1f | note | - - - - - - - - -
a572644b-51ad-5c39-b6d6-35e310fce6c5 | note | Inspection / Test Method: Document Review
f100962a-c1be-540b-8fe2-66da61097ee4 | note | - - - - - - - - -
bc3eedf4-1a9b-5f0c-ad72-e2294754a9c7 | note | Record of conformity: Submitted Product Details
db42bf53-e325-55ea-b252-0e2f3687815f | note | - - - - - - - - -
c3daefeb-a9cd-530d-802a-62c6f6d35949 | note | HP*
d0da58fa-7b44-5298-8197-11eccc44940c | note | - - - - - - - - -
d2c4e37a-04fd-559c-9c5c-e3ce23fcc0e7 | note | Responsibility: Project Engineer
| checkpoint | 1.10 - Quality Procedure for pile construction
37900ba0-6733-526b-8063-32b495a71fb5 | note | Frequency: No less than 4 weeks prior to commencement of activity
9f3bc1bc-349d-55cb-93e9-67b69aaf0fef | note | - - - - - - - - -
61c0c34c-9319-59d5-9b90-9c84a9017365 | note | Acceptance Criteria: A quality procedure for the construction of the piles shall be submitted to the Superintendent not less than 4 weeks prior to the commencement of the piling works. Piling works shall not take place until the quality procedure has been reviewed and approved by the Superintendent.
e1fd79df-61cb-5ead-8296-0789981158c1 | note | Reinforcement and/or concrete shall not be placed until the proposed method of removing mud, loose rock or similar materials, and the method of placement of concrete under water has been reviewed by the Superintendent.
d1c9bb0a-95f1-5acf-9d68-38ece63a8be9 | note | The Contractor shall submit the procedure for placing concrete in bored piles, under water and in dry bores, for review by the Superintendent at least four weeks prior to concreting.
25162713-fab6-541a-9fcb-8a2e939610f4 | note | Concrete shall not be placed in bored piles, under water or in a dry bore until the proposed method of placement of concrete has been approved by the Superintendent.
60996b58-aa90-5f84-a4b8-3ef8082838fd | note | - - - - - - - - -
0eecb4e4-73e6-5869-8815-a8901e224b71 | note | Reference Documents: VicRoads Spec.
8b5ba7a5-7ca9-5221-8cf8-fdecd2db413c | note | Cl.606.03(a)
a495e896-c927-5ced-a633-f4c6102fdaad | note | Cl.606.06(a)
56fedf67-d6b7-5a95-8060-7d42093ca7a3 | note | Cl.610.18(c)
d4ad183f-321e-50c2-a455-edb15d4996b6 | note | - - - - - - - - -
4ac9ed43-adbf-5e2e-9818-f043126a7021 | note | Inspection / Test Method: Document review
c166fa39-686c-589c-ac1f-f36f993c2add | note | - - - - - - - - -
da27afa4-738d-5a16-b046-3867d70bd2de | note | Record of conformity: Approval of Quality Procedure for piles construction
87764a5c-03f3-5360-9e19-3835e8d486a0 | note | Procedure for placing concrete reviewed
454c0299-1cc2-5fb0-bc0b-c74c4cea6757 | note | - - - - - - - - -
97056944-6329-5258-bcb3-79b4a6864413 | note | HP
61a78550-bcd0-5d5a-a18b-09159f18f25c | note | - - - - - - - - -
9a08f5cf-acfc-52f3-bd1a-c302f1f8e7aa | note | Responsibility: Project Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Boring
| checkpoint | 2.1 - Survey set-out
1db36842-bbb3-52b9-aebf-596819d6c4ba | note | Frequency: Prior to Commencing
561f1fec-d63c-5ea1-8353-0718c6f161e6 | note | - - - - - - - - -
297c1af8-49c3-5093-a6db-a4e00056a155 | note | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
22dc564d-223c-5524-bff4-a281c21b7a24 | note | - - - - - - - - -
7fc2ee7c-4b98-5630-bfba-db682ce14249 | note | Reference Documents: Project Spec. Cl.1190.06
b7482430-4235-504b-b8d6-fe5c22e4c6e1 | note | Latest IFC Drawings
ef11b993-0904-594c-b33a-f0bec25b8fe0 | note | - - - - - - - - -
eb20934f-0bd4-5713-ac6d-e7f2a48ca045 | note | Inspection / Test Method: Site Inspection
e46ab6fc-881d-5a1c-82d2-ba9da906bf1a | note | - - - - - - - - -
948d9211-c5a4-5851-be2a-f055dd44d47c | note | Record of conformity: This ITP Signed, Survey Records
44b40d6b-4c51-51bb-b59b-3de8701c6c52 | note | - - - - - - - - -
6d25bc8a-4243-5cbf-9fbe-4fd669d07c02 | note | SCP
b19f6c5b-18d9-5202-be9e-4d3137c79940 | note | - - - - - - - - -
360396a4-45bd-549c-b2b4-0acbada73083 | note | Responsibility: Site Engineer & Surveyor
| checkpoint | 2.2 - Protection of Adjacent Piles
ad2b878a-c8cb-5892-9850-4070c8f80a6c | note | Frequency: Prior to Commencing
b51a96c1-e25f-5dcf-93f3-8e225e86bdd9 | note | - - - - - - - - -
21ede96c-49ab-58f8-94d7-fbd095f2550d | note | Acceptance Criteria: No pile shall be commenced within 2.5m clear distance of a newly cast pile until the concrete in the pile has attained a strength of 15MPa
a367bfe2-b23b-562f-88ea-d835336d5ceb | note | - - - - - - - - -
58568ba9-856f-56d2-8093-ef629f734feb | note | Reference Documents: VicRoads Spec. Cl.606.04
26cda1ef-c36c-5a45-88ef-879ec7a143ef | note | - - - - - - - - -
30bdc91f-0291-5199-8126-1ec6d2de5a21 | note | Inspection / Test Method: Visual Inspection
c51c45be-53a0-539a-92a3-430f3819d003 | note | - - - - - - - - -
44c6eb2c-32a9-5e57-8d75-209559bebbb7 | note | Record of conformity: This ITP Signed, Bored Pile Checklist
3f49e86a-c697-5f70-b283-245be59b184a | note | - - - - - - - - -
f0b06174-5229-5698-94fb-cfcabfc0da80 | note | IP
97ac4019-3f7c-52f9-9142-a6115c562b33 | note | - - - - - - - - -
2fe0a2e4-31a4-5d9a-8a07-28a9da34de4e | note | Responsibility: Site Engineer
| checkpoint | 2.3 - Excavation levels
1427bcf4-a3e8-55a9-9ccc-c0450050055a | note | Frequency: Each pile
b77095f1-bb23-5b14-979c-d7f1f12eb932 | note | - - - - - - - - -
badb2844-513c-5547-93d0-46acff5ecd15 | note | Acceptance Criteria: Check the toe levels conform to the drawing.
1a73db28-b9aa-5593-8758-8faa4997846f | note | - - - - - - - - -
c01ad651-0700-544d-9ea2-81c6d5148e44 | note | Reference Documents: Latest IFC Drawings
0f47431a-d33a-5ecf-bd81-296275e4f25f | note | - - - - - - - - -
67f44378-500e-536e-b670-66340d4a15f7 | note | Inspection / Test Method: Document review
a8f2139e-8740-5ec6-add8-04c5b40ed96f | note | - - - - - - - - -
0a8d6d3d-d9df-59cf-9d03-edd2f23d1445 | note | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
b6565bd5-5261-5e17-aac8-0a80344c2e03 | note | - - - - - - - - -
add65dda-0edb-51bb-a9a0-128f09fa76eb | note | IP
11e6dc20-a937-5753-80d4-1ab7374d0883 | note | - - - - - - - - -
d151b7db-539d-56e6-bb56-980308677057 | note | Responsibility: Site Engineer
| checkpoint | 2.4 - Inspection of Pile Excavation
ef06541f-c89c-5e2e-9058-fa64a76fbe37 | note | Frequency: Each Pile, a minimum of 48 hrs notice given to the Superintendent for arrangement of the inspection of the pile excavation
4c00fb4c-af34-5d97-8d4e-9d786fcdced1 | note | - - - - - - - - -
bbb75e95-6d19-59ff-bd0a-38ab2d0b3dff | note | Acceptance Criteria: The temporary casing (where used) shall not be removed, nor shall reinforcement and/or concrete be placed until the pile walls and base have been inspected by the Superintendent and that the inspection has confirmed that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
a13a6798-f9cc-5013-9711-911d0461f8d7 | note | - - - - - - - - -
32ff3fc2-0e01-5324-b555-fd8e009d0269 | note | Reference Documents: VicRoads Spec. Cl.606.05
cf35167b-a27b-5b4a-92d4-b6d7923d7c8a | note | - - - - - - - - -
ccadedbd-005f-5a2b-a2ec-81586a1b5e97 | note | Inspection / Test Method: Site Inspection
faae29fd-4ef6-5470-861c-cc49bf0a8de2 | note | - - - - - - - - -
ffb1a42d-9db7-5461-95f4-8c2da595590c | note | Record of conformity: Pile walls and base inspected by Superintendent, This ITP signed off
c353748b-027b-5ecd-9193-789f0eb657de | note | - - - - - - - - -
4757d796-adf2-5fdb-a413-a0f04283cdab | note | HP
2a695df7-df6d-5978-89e6-402cd368d0de | note | - - - - - - - - -
12f1e87a-17f2-5da1-ab3e-7439ad6310fb | note | Responsibility: Site Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Check reinforcement cages
ff8ac8fe-aa09-51a0-a39e-e99794441153 | note | Frequency: Each pile
7ed39972-f216-55ab-b754-3a57da584468 | note | - - - - - - - - -
2e732604-e0f7-535c-8d66-fc0ff08c6fa1 | note | Acceptance Criteria: Steel Reinforcement shall be securely held during placing and compacting of concrete. Steel reinforcements shall be made of concrete blocks of a strength similar to the structure, strong enough to withstand the imposed loads without movement of the steel reinforcement. No other materials to be used as supports.
29b21273-08b7-5b07-822f-eb546563c488 | note | Spacers and supports for bored pile steel reinforcement shall be placed at intervals of no more than 2 m along the full length of the steel reinforcement cage to ensure that the specified concrete cover to the steel reinforcement is maintained.
27c15f21-f271-51d0-a26e-199790b2f0a9 | note | Reinforcement as per drawings and specification.
b4095342-a73b-59ce-8b52-338ff7348953 | note | - - - - - - - - -
7d1f9fa7-fe47-5c37-b5bc-392757cec9d1 | note | Reference Documents: VicRoads Spec.
58341619-e143-595f-bcb7-088f5ea8a29b | note | Cl.606.06(a)
08969adc-ed36-5b02-9b88-ed311a36a777 | note | Cl.611.03(a)
05626b6a-36ee-591d-9775-5732e6c21df3 | note | Cl.611.04
5883311c-b580-59e9-ab95-bcdde058d994 | note | Cl.611.10
65bc8271-fab1-57d5-abbf-5f3df13fedfc | note | Project Specification
257e00f1-7c29-5138-91a3-cfe617366d99 | note | - - - - - - - - -
131b7bad-beb1-50e8-9951-8a825f0f7b86 | note | Inspection / Test Method: Site Inspection
56db9ee1-7394-5394-a621-0c9c5b12d47c | note | - - - - - - - - -
3b2c186c-fa25-5a23-aa51-29fbcef2c316 | note | Record of conformity: Bored Pile Checklist CRU-FH-CL-0006
1f909e03-d4f7-521f-84d3-a322bd18da0e | note | - - - - - - - - -
e852542a-d4d3-551f-9359-47bb34573c00 | note | IP
00241a2c-795b-553a-9891-453f27d17c60 | note | - - - - - - - - -
ba06da14-3926-584f-970f-288efad5a80a | note | Responsibility: Site Engineer
| checkpoint | 2.6 - Pre – pour checklist
fb03d168-2f7b-57ac-a92a-e708ef478a64 | note | Frequency: Each pile
9a0d71e5-83f6-5222-ae00-930e28159e59 | note | - - - - - - - - -
7033f7bd-e240-5ada-8f3d-88961fe58d8b | note | Acceptance Criteria: Bored Pile Checklist completed and signed.
1e17b4f1-d0ba-5b55-8a3a-b16c5c59f072 | note | - - - - - - - - -
243add8b-d467-5927-9e29-29f976ba1164 | note | Reference Documents: Work Pack
c3b7ac3c-5f11-5931-a462-2422d9024c26 | note | - - - - - - - - -
f4b367e0-57ee-54ad-b29b-7ae550a4b835 | note | Inspection / Test Method: Site Inspection
9a8cdcf4-0066-5bf9-be34-7a8e8124d2fe | note | - - - - - - - - -
d68beebd-3901-5587-bac1-c3a4a30257ef | note | Record of conformity: Bored Pile Checklist CRG-FH-CL-0006
848559a5-062d-55da-91d4-9ef9c6bd0609 | note | - - - - - - - - -
152998f5-22d6-57f3-8fff-778efb209c4e | note | HP*
9357f3d9-f5be-56f7-911d-9deec9c57c69 | note | - - - - - - - - -
1e6b5755-6fe2-5f1c-9430-0892b56bcc56 | note | Responsibility: Site Engineer
| section | 3 - Placing and Finishing Concrete
| checkpoint | 3.1 - Carry out sampling of concrete
2640fc8d-ad46-5ef4-b9a2-805a3607c7f0 | note | Frequency: As per table 610.161
d8899796-4d05-5bd9-8662-099bb48010bd | note | - - - - - - - - -
3764827a-d37f-53d3-84e5-35bcff2bf404 | note | Acceptance Criteria: Slump flow: 550-800mm spread
a2cc4788-c9e2-55f2-b6d4-2c01f31afa66 | note | T500 time: Achieve a spread of 500 mm within 1 to 5 seconds
a98e051f-7637-5982-8c45-71520f3e922c | note | Passing ability ≤ 10 mm.
be033ebf-79e9-5926-aee0-a965b0be13dd | note | Observations as per Table 610.131 of VicRoads Spec.
ecb60699-cff4-5959-a7c3-2608e046efd9 | note | – Three cylinders taken from the same sample used to test. 1 cylinder crushed at 7 days. 2 cylinders crushed at 28 days
00e77687-db2c-549b-b718-e435f8ad3ccf | note | – Number of samples taken shall be as per Table 610.161
b45dd9c2-5956-56a4-9b13-d4743a5daf60 | note | - - - - - - - - -
7cd4f508-0136-5627-aaef-47b1a1a21bd4 | note | Reference Documents: VicRoads Spec.
65e70041-db43-53c3-bfd8-90f680dd9453 | note | Cl.610.13(b)
0511e752-325c-5b1b-8a44-6c8b0af76a17 | note | Cl.610.16(b)
c3755d10-3e94-5ecf-ab0e-b68978363771 | note | Cl.610.16(n)
1f239f5a-cd48-51ac-9275-727a306c3e3a | note | Table 610.131
aa27702a-b2ae-50e0-a1da-8531fd4006ce | note | Table 610.161
311af692-3241-5dd1-861a-4a0ea19c7f05 | note | - - - - - - - - -
5eddfd14-e30b-57a7-ae3b-7372651d3e52 | note | Inspection / Test Method: Site Inspection, Site Sampling
aed563df-f070-5c8a-8ab3-249c6edf168b | note | - - - - - - - - -
eb261bd8-fc63-54ec-aaf3-0a1b726865e6 | note | Record of conformity: Concrete Pour Record CRG-FH-CL-0003 and Bored Pile Checklist CRG-FH-CL-0006 completed
e48fe400-c5de-5d0c-b5bd-37a7a2f1cfe7 | note | - - - - - - - - -
311913b6-7908-5049-abc1-3a7114553bc6 | note | IP
83fe8081-761e-5af2-ae74-81a794f5d628 | note | - - - - - - - - -
43889e52-4f08-54bb-8ec9-8cdbcfba85bb | note | Responsibility: Site Engineer
| checkpoint | 3.2 - Place Concrete
77fc28f5-9241-5ade-ab57-04597bfa93c8 | note | Frequency: Each Concrete pour
9eb8204c-870b-5fdb-9666-1d45f6b57c6d | note | - - - - - - - - -
43367c1c-0430-5cbf-9503-c4ef0b4ec365 | note | Acceptance Criteria: Piles shall be concreted within 24 hours of completion of the pile excavation.
47482bb5-0449-5bf7-a4ce-8de934cf1c0d | note | Discharge time between truckloads for the same cast to be <45 mins.
d5d7e730-81f0-50e7-a5e6-1a5ef9189e5b | note | All concrete to be placed within 60 minutes from batch or as specified in the approved VR mix.
b6d0cc60-8a6e-58fc-9e7b-ee5c73eefdc7 | note | Each batch (truckload) of concrete delivered to site shall be visually inspected to ensure consistency of concrete supply, and the estimated slump shall be recorded on the identification certificate for the batch.
5058f583-0fd2-57d6-9d05-b82829d127e6 | note | Piles places in the dry shall be constructed to a minimum of 300mm above pile cut-off level to allow breaking back of contaminated concrete at the top of the pile.
a72e7a27-9a3c-540d-98a0-b08fae3a0b19 | note | - - - - - - - - -
ff010d12-0a29-50d2-9cb5-57fe754d3efe | note | Reference Documents: VicRoads Spec.
95168c98-fdc6-5a57-a114-8192b4d502ac | note | Cl.610.16(b)
b624940d-5378-5e2a-a2fa-966327e56149 | note | Cl.610.16(c)
0c6f866f-0e20-5b93-b5ba-a1690dc0c3fb | note | Cl.610.13(f)
e501454e-7d42-524e-948b-da56210241c4 | note | CL.606.06(a)
7a2bb556-7e7a-5454-83a4-c367449938c6 | note | - - - - - - - - -
12dbb0e5-a7ab-5b5c-ae75-c8e6808ff72c | note | Inspection / Test Method: Site Inspection
926b0303-194f-5a65-bc7b-1fec1efa4d83 | note | - - - - - - - - -
76ff800c-4d98-597b-8d8f-c86b52806f52 | note | Record of conformity: Concrete Pour Record, Bored Pile Checklist, Concrete dockets
51ec21f7-0115-5df5-a278-1d3a8ab5b4b0 | note | - - - - - - - - -
1db71b52-8568-5f93-af68-591c813e4669 | note | IP
c5bfe90e-ab58-58e4-b533-808fcbff8b22 | note | - - - - - - - - -
058e23e7-13d0-5180-a949-2228d552906e | note | Responsibility: Site Engineer
| section | 4 - Testing Requirements
| checkpoint | 4.1 - Pile Testing
90afd58c-2796-5dac-9128-6a02c59d76d2 | note | Frequency: Representative Sample determined in consultation with the Superintendent.
26407198-f350-5b30-8e57-de0ff0dd530c | note | - - - - - - - - -
0916b162-96d6-5142-a1ed-1657f9044cb7 | note | Acceptance Criteria: Unless dispensation is granted, a representative sample of piles shall be tested by a consultant prequalified to VicRoads as per the requirements of Section 606.07 including:
9819a897-4ef2-530b-a213-6aa688966cef | note | (A) Integrity Testing - First 6 piles constructed, then 1 in 3 remaining.
87061f52-ce26-52f0-8a63-7273412986fb | note | (B) Static Load Testing
a5022319-1f37-552f-9705-c389bf10e831 | note | (C) Dynamic Load Testing - 1 in 10 Piles with a pile depth within 2m.
52a887d7-4907-5cb8-8160-528d86629db7 | note | Results including raw data are to be provided to the superintendent per the timeframes requested but no less than 48 hours after collection of results.
b3df06f3-6c74-51a2-a208-1adb808312b3 | note | - - - - - - - - -
f6f4db33-03ad-575d-84d3-02cd0f423588 | note | Reference Documents: Project Spec. Cl.3050.07
987c56cc-e359-5293-96e4-fc1b6639a1a4 | note | VicRoads Spec. Cl.606.07
06b7ba9e-a03c-5573-ba49-218d00238df4 | note | - - - - - - - - -
13260bef-63d2-5e9c-8ce6-c4f4b271a88f | note | Inspection / Test Method: Test report
8defc519-e8e7-5516-a81e-7b768e75bfe8 | note | - - - - - - - - -
d71aec36-c383-5b4c-9ee2-ee9ea5bb3662 | note | Record of conformity: Test reports provided to Superintendent, This ITP signed off
a2b12f86-88de-527e-9d19-b3bc7f467c7c | note | - - - - - - - - -
35dd8d3d-c0de-58f0-aaf8-3c45f0be1e1d | note | HP
4747dd63-8c11-58f7-9bb5-47d3bf7d0495 | note | - - - - - - - - -
59fffdb8-baf2-5814-beac-47d82f1cfb09 | note | Responsibility: Site Engineer / Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Concrete Test Results
f9bb735c-bad8-5c47-9a68-b1d0a81421c5 | note | Frequency: Each sample
ef0a6bd1-b951-5070-9d43-d23e81ee6ae0 | note | - - - - - - - - -
a90aa11d-9193-565c-b7b5-ef8961f67807 | note | Acceptance Criteria: Minimum 7 day strength (26MPa) achieved as per table 610.051
997f5f98-d548-50d8-bacf-12acd2bcebea | note | Minimum 28 strength (40MPa) achieved
d833dcd7-59f1-58ff-9a58-ac9b3e8c5cef | note | Strength average of tested cylinders
a88a7b02-90a5-5cb2-a0bc-40ba7f43f87a | note | - - - - - - - - -
e47dad48-81ea-5a63-952d-ab2f2cce00eb | note | Reference Documents: VicRoads Spec. Cl.610.05
93e9e68b-2a80-5672-80b2-a8e17a868ec9 | note | Table 610.051
79ce608e-c6d8-5b91-8881-2c9017ce017b | note | - - - - - - - - -
84d1b5e5-aa81-50f6-88e0-9f3e8759ab5c | note | Inspection / Test Method: Test report
026aba0d-79f2-5118-9557-27bc55409c92 | note | - - - - - - - - -
502044a7-43ba-5f62-8aae-021610141924 | note | Record of conformity: Compressive Strength (MPa) Test report, This ITP signed off
795608bb-6114-5b2b-ab9c-1d2ba9253498 | note | - - - - - - - - -
032ecffb-7933-51a7-917c-f82272e43070 | note | TP
e1d9a134-8253-5553-8e93-7ff9b2dead39 | note | - - - - - - - - -
4a5d2424-a073-5f9c-95b8-1201fecd869e | note | Responsibility: Site Engineer
| checkpoint | 4.3 - Tolerance Check & As Built survey
b38a540e-7fd8-5717-9124-3cc71dcf10a9 | note | Frequency: Each pile
a26a08a0-6eb2-5158-92a7-51153a24f360 | note | - - - - - - - - -
4f232d64-f5b9-5448-b1de-a73e8acb6e68 | note | Acceptance Criteria: Check Tolerances & Survey Pile positions:
fb0f564d-62b3-5b89-a70d-81b5cadbcc43 | note | (a) pile head shall finish within 75 mm of the specified plan position;
1ca6c4a3-3f81-5d25-8c12-8b1a8a8bf188 | note | (b) variation from the vertical or the specified batter/rake shall not be more than 1 in 100;
e1c9024f-67c7-58b2-a418-0a0ab00ec70e | note | (c) where piling excavation has developed a curve or out of verticality, the offset from the theoretical straight pile line shall not exceed 150 mm over a length of 15 metres or proportionally for greater or shorter lengths.
0a947ec8-285c-5484-b32d-f5cb1a60645f | note | Mark all details correctly on as-builts
269a4553-36c4-57a0-afd2-933b6b51cf5b | note | Pile head position & verticality
1f3f8ac2-c4b5-55c9-8f4b-7137d0375fad | note | - - - - - - - - -
49233f8a-96bd-5449-80e4-bd087f8bd99b | note | Reference Documents: VicRoads Spec. Cl.606.08
5b6394c3-972d-5997-81b0-afec95a17647 | note | - - - - - - - - -
81d8e4de-ce47-5ef4-a127-767ed9d452c9 | note | Inspection / Test Method: Site Inspection/ Document review
5752dcfe-d0cd-5f69-9c96-3380037eb99a | note | - - - - - - - - -
8220fd79-bac2-55bc-8140-60875f268d82 | note | Record of conformity: Survey report
76f37e8d-82e0-56f4-96c4-51a57d8fb011 | note | - - - - - - - - -
471b52a6-b692-51cf-93a1-6945e880622c | note | SCP
2718d159-4051-5f6c-a2c6-0e5cf1522d57 | note | - - - - - - - - -
c3f332ae-0bc5-5499-849e-cece8e36239f | note | Responsibility: Site Engineer & Surveyor
| checkpoint | Final Inspection
e50d0a3b-6add-5660-8ae9-4102d62653e3 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9d21d895-fb67-5207-b007-29b80aa302c7 | textbox | Print Name:
50281eba-042b-5735-aa61-49db8ae03025 | textbox | Position:
4e5118f5-cfde-5f72-aa9a-e5a58b82b817 | date | Date:
20df2447-f5e0-593c-8dbe-28c6f98b617e | date | Work Completed On
| checklist | ITP 0017 - Underground Stormwater Drainage | itp | ITP-017-AX-LOT-XXX - Desc | abec4b66-3279-45e0-813f-2db6d5a923a0
| section | 1 - Preliminary Works (FH Internal)
| checkpoint | 1.1 - Work pack briefing
e92d9a3d-d737-5fbd-bd16-740439e7421f | note | Frequency: Prior to Commencing Work
39dce24c-4fb9-54bc-85d6-89d9d217510b | note | - - - - - - - - -
9739a878-9623-5f39-80b7-256487320f5b | note | Acceptance Criteria: All personnel on site have been briefed on the relevant work park to scope of works. (includes subcontractors as/if rerquired)
41c0d26e-4fc2-52b0-827e-31dad0a986f2 | textbox | ○ Work Pack (WP)
55a2dc37-9ed0-53a9-8af4-cc1c028a23ff | note | - - - - - - - - -
6a0acfca-16e0-51e7-875f-86344dd27e03 | note | Reference Documents: WP
b5b7300d-5952-5b36-9a77-8e2bda53ba28 | note | - - - - - - - - -
fa4fff0f-3be3-5de3-b7f3-16b4de24af1e | note | Inspection / Test Method: Verify
d3ffcf41-7e0a-518d-ac32-06266b1a594d | note | - - - - - - - - -
776bfa7b-c5e0-597f-9ef7-417b07f0e2d3 | note | Record of Conformity: Work pack signed.
542e5ac4-4709-5119-b287-c99b551b2f11 | note | - - - - - - - - -
00dfa1a8-2dbe-5cbf-b62d-7a398278bfe1 | note | HP*
15abce60-78cd-54eb-8556-8262cc772400 | note | - - - - - - - - -
0af03560-868e-566e-b5b8-1166ad2520c8 | note | Responsibility: Project Engineer
| checkpoint | 1.2 - Lot Map
85607a2b-42af-5a0e-b058-19263f49507b | note | Frequency: each/line
b3c6f781-b520-58c5-b5f3-edd4f758af43 | note | - - - - - - - - -
ab53f05e-f731-53cf-8ee8-d42e7f4c136f | note | Acceptance Criteria: Lot is assigend and recorded on lot map
d1026796-4545-5199-9447-6fbfe9f72305 | note | - - - - - - - - -
73745cdb-716e-5790-b612-59a49110b744 | note | IP
847ef0b7-8136-5340-a8eb-6eb5f3d6f05d | note | - - - - - - - - -
f7cbd301-cb9f-5170-9fce-e223b91762a2 | note | Responsibility: Project Engineer
| checkpoint | 1.2 - Check that current revision drawings are being used
91b24158-fbdc-5f12-add8-dd011f7a63c0 | note | Frequency: Prior to Commencing Work
1850d66b-64c6-57fa-a783-e8a7d276aed3 | note | - - - - - - - - -
83f08611-aada-5c0f-8177-10cdd284c0ee | note | Acceptance Criteria: Issued For Construction (IFC) and latest available design revision in use (RFI).
005cc43a-eab9-5084-abfd-efc11ef04165 | textbox | ○ Design Drawings
46e05298-6f29-56ba-be5d-b19cfd6ace65 | textbox | ○ RFI Approval Number
fb269202-b3e7-54f0-9839-abebb1c80ad7 | note | - - - - - - - - -
96282a61-3435-56fa-b7cb-31a94c12e13f | note | Reference Documents: IFC Project Drawings/ Drawing Register
828969b2-3ecc-5006-be66-e0ff0e5d12b0 | note | - - - - - - - - -
72a1cce9-50ea-5346-8343-4b6e89ebe289 | note | Inspection / Test Method: Verify
4cceb143-d260-535e-9854-c0d2169f4477 | note | - - - - - - - - -
ee0ae487-e4f6-5886-8108-5f9351470be1 | note | Record of Conformity: Latest revision IFC drawings
60129d88-f401-582b-a547-7e19591f5fd4 | note | - - - - - - - - -
257a22c8-9f69-56df-968b-c4f5c1222081 | note | HP*
26830958-336f-5571-b38f-19b8d735b737 | note | - - - - - - - - -
18db4e1a-088d-576b-af8e-d0c09a188113 | note | Responsibility: Project Engineer
| checkpoint | 1.3 - Ground Penetration Permit (GPP) issued by GPP Coordinator
64c4c2f1-d838-55a6-a1e5-f9b66849d20d | note | Frequency: Prior to Commencing Work
ac58e9f1-b38c-581e-9323-8ca02bddb461 | note | - - - - - - - - -
d3912ade-2c25-5647-941b-0f45edb408bc | note | Acceptance Criteria: Current GPP signed and specific to the area where works will be executed. Including walk through of the work area with the site team and GPP Coordinator prior to works.
888338c2-4198-5104-ba68-143386788a63 | textbox | ○ GPP No
13213aff-b293-55e6-8f42-8c477caf079b | note | - - - - - - - - -
65ba7a56-dd7b-515f-ba1b-4665af658191 | note | Reference Documents: Excavation Permit
8fc63558-353e-56dd-9279-5a95ffd98026 | note | - - - - - - - - -
ac27ea49-0bd5-576b-8d73-6b438e868823 | note | Inspection / Test Method: Verify
643b22f3-8592-534c-a7b6-990d3f32af05 | note | - - - - - - - - -
d82f8522-be63-501d-9e7f-a2b91453ec7c | note | Record of Conformity: Excavation Permit
6f99a2cc-1981-5a45-88ea-f1c13f1173e6 | note | - - - - - - - - -
2173149f-245d-535f-ae8d-de2068469281 | note | HP*
9d9f7376-f934-5481-9ca7-a3e896fc3623 | note | - - - - - - - - -
57d57f19-2724-5e06-9533-d1e7d1a5847f | note | Responsibility: Project Engineer / GPP Coordinator
| checkpoint | 1.4 - Extension/ Modification of exissting drainage pits
2ac4be1d-b520-5785-84f1-2e939ee01f62 | note | Frequency: Prior to Commencing Work
f0caa20d-4744-5d11-bb23-e968d35d57b1 | note | - - - - - - - - -
1ebbfd47-71d3-5c05-9db4-e4d39fb9da4a | note | Acceptance Criteria: If there are any modification required to an existing drainage pit this will require the use of Structural Patch ITP.
2c5ef338-aa2b-5b10-b92a-9edee7a8e4b9 | note | - - - - - - - - -
c23895e0-080b-5f7a-9cff-3ab32ea43ccc | note | Reference Documents: 1145-C200-FUL-QAC-ITP-0082
81497fe0-1d3e-5ce8-82f4-a4552f8667e9 | note | - - - - - - - - -
cfd5b5b8-ecec-5b2f-9325-815b26dcef92 | note | Inspection / Test Method: Document review
03db7468-e043-5729-b767-ae296334c889 | note | - - - - - - - - -
1cc77469-64b0-59ad-ae42-5c38f9b9a005 | note | Record of Conformity: Teambinder Approval, Proof Engineering certificate
c2058219-301f-5813-bd80-cb10e2daf11c | note | - - - - - - - - -
c43bfdb5-f94d-5f5e-85bf-b549b7e7668d | note | HP*
bb648a43-b632-5eaa-a862-7debf714f349 | note | - - - - - - - - -
e7d7c6a7-54bc-5a5c-92a6-6bd82c695a70 | note | Responsibility: Project Engineer
| section | 2 - Stormwater Drainage Material Supply & Approvals
| checkpoint | 2.1 - Drainage Pipes (RCP)
22766316-a1be-5885-979d-45bafabf097b | note | Frequency: Each Line
b54308d9-e20c-539c-bf9e-41b0416b4bb0 | note | - - - - - - - - -
f372daaf-e779-5993-b668-d9069b67432f | note | Acceptance Criteria:
6e45ba54-42b5-562a-9f1f-c0933975998e | radio | Pipe Supply & Box Culverts | CRG XX – Dia XX to XX - RCPA,CRG - XXX - Culverts - XXX,Other
ae0bd16d-e2fa-56ca-8a8c-8a3eae69ea69 | textbox | Other:
fac613e5-d08f-5ea0-b850-56b8b1c783bc | note | Documentation as per 701.05 is available in Teambinder Material Approval form
ebf8b2eb-263e-5f9c-9426-ed551c212581 | note | - - - - - - - - -
092e4e07-2d01-5cfe-80c2-ad8c7d44f554 | note | Reference Documents: 701.04, 701.05
e1b50692-28c0-5273-ae26-726fde286518 | note | - - - - - - - - -
34c02cc0-2896-59e4-bd81-4f46169a5bf8 | note | Inspection / Test Method: Verify
33e8cd24-23b0-57ce-97ac-d9434c54960d | note | - - - - - - - - -
7c7210ce-4baf-53f0-8961-87db4ee47021 | note | Record of Conformity: This ITP
c52aaf31-a183-5d9d-936e-b729606bd3e3 | note | - - - - - - - - -
0d82c38e-8a54-5070-8c7c-88538b11838c | note | IP
210d810a-52c6-57ae-9948-dc9b0e74d3fd | note | - - - - - - - - -
e2b2b8e8-56c4-5312-aab0-decfc9a03a88 | note | Responsibility: SE
| checkpoint | 2.11 - Drainage Pipes (StormPro)
6636fa73-f3af-5c87-864a-d3febb693c55 | note | Frequency: Each Line
2a145988-8cbe-5a49-ac87-29e0f75dd726 | note | - - - - - - - - -
d6d8d709-7700-5ddd-9387-cac5113e46d1 | note | Acceptance Criteria:
3b3d2ff3-a663-5fb1-b864-a4f5258477c8 | radio | Pipe Supply | CRG XX – Dia XX to XX - Supplier Convic,Other
5c198d32-b422-5da2-8fcb-315d4ce9d07e | textbox | Other:
a4544659-0383-5248-a0e8-d6706f3b981d | note | Documentation as per 701.05 is available in Teambinder Material Approval form
d8f8bb33-825c-5fc2-b03b-1b506e1364e8 | note | - - - - - - - - -
746dc524-b537-590a-9ac3-0429fabf3597 | note | Reference Documents: 701.04, 701.05
f6ed58aa-c6ec-5452-9923-55c17c1fe09d | note | - - - - - - - - -
8b292cfa-280e-5adf-989d-f0be6b7201cd | note | Inspection / Test Method: Verify
763ba814-9e4e-5a1f-9757-ec0cf9e1c4b9 | note | - - - - - - - - -
13b313e4-fa1d-547c-a233-cda3203046cb | note | Record of Conformity: This ITP
7e7ad66b-5368-5b50-8ec3-cc7afd48831d | note | - - - - - - - - -
1a1bed6e-f0e1-5adc-a29e-32151c622a55 | note | IP
cf44ff47-6a93-566b-98c2-7ed3a978bcfd | note | - - - - - - - - -
256ce6cb-de2c-5b86-8728-9983f3b49cbb | note | Responsibility: SE
| checkpoint | 2.12 - Drainage Pits
e19be3b8-ae54-5b8e-9837-0c116580754d | note | Frequency: Each Pit
5e6d811c-6cdb-5737-994d-54c676eba84b | note | - - - - - - - - -
ddfdee31-f5af-5f75-a0c9-6930a68b85dc | note | Acceptance Criteria:
4c522a25-3457-5b0f-8ca4-24aee166dcfb | radio | Pit Supply | CRG XX – Dia XX to XX - AUSPITS/CUBIS,Other
19782b71-04b3-5cd8-8867-a3ff9f37a4c0 | textbox | Other:
45905e61-c68a-5de9-8d33-cdeea3efeea2 | note | Documentation as per 701.05 is available in Teambinder Material Approval form
96058c52-c5cd-5117-b355-6cb39c6fceeb | note | - - - - - - - - -
99c506f2-a8e8-536a-86cc-3cd47867be30 | note | Reference Documents: 705.07
8518de3a-917b-5b51-bf93-6d2317a590fb | note | - - - - - - - - -
1d4c3696-984b-55d8-b5b7-4b92bbb849c4 | note | Inspection / Test Method: Verify
4bd13b4b-c77c-5b20-982e-8fa00681a547 | note | - - - - - - - - -
7727591c-443f-5a3c-84c6-f8b881cabcfd | note | Record of Conformity: This ITP
e5ae0845-7992-54d7-86a7-e8bed2f33b20 | note | - - - - - - - - -
c4900e5d-585b-52b3-9634-58daadd34ac3 | note | IP
3ae9cbae-3083-5dff-a0f8-413acad2b83c | note | - - - - - - - - -
304e7d5a-386e-522d-9052-db371321adfa | note | Responsibility: PE
| checkpoint | 2.2 - Drainage Bedding Material Supply Source / Approval Project Wide
d7b8f0fe-ca46-54c4-a917-3f20bfb4f44b | note | Frequency: Each Source Material
fbab3b21-0376-56e7-bb06-e6e7e464f206 | note | - - - - - - - - -
434c63c6-bd99-5aec-8bee-2ba2c1fc3ce6 | note | Acceptance Criteria:
57a99c2c-c342-5ae8-a3ba-419e77e9d1c7 | radio | Bedding & Haunch Material | CRG XX – 20mm CL 3 wet mix FCR/CC – Holcim,CRG - XXX - 20 Screenings - XX Supplier,Other
e11b3697-1ab9-5594-bdf0-093ec4474066 | textbox | Other:
ebbfe5b7-fbb5-5ac6-ba5c-8e79aa3452f8 | note | Material Approved via Teambinder Material Approval Form.
de4c555e-8917-55cd-a654-e7a9169bcf44 | note | - - - - - - - - -
16250bde-ba4b-5aef-af3e-7ff3a26c7929 | note | Reference Documents: Table 701.091, Table 701.092
ce95e05c-5ee5-57a9-ac79-76da13922ea4 | note | - - - - - - - - -
e61fc681-5b3c-556b-ae91-2b2d0c91e48f | note | Inspection / Test Method: Verify
60ccb4e6-3e9b-52e2-ae9b-bd03f3509177 | note | - - - - - - - - -
7e86c833-d493-538c-a908-d4347641bdc3 | note | Record of Conformity: This ITP
31646755-481d-5a0c-8764-bfc9efe82736 | note | - - - - - - - - -
3e73a08f-fbdd-570c-81c9-15c678614f6f | note | IP
869f3726-cee7-5a58-89f6-c50d03afb3d0 | note | - - - - - - - - -
1b359225-72ea-5c94-b355-3c78ce8f6fa8 | note | Responsibility: SE
| checkpoint | 2.21 - Drainage Bedding Material Supply Source Testing
bfbd84f4-7379-508c-8ad2-41bf0776d07b | note | Frequency: Each Source Material/ 1 Test per 1000 tonnes
ec0c78df-f9d6-5c98-9ab2-3d6be3f3ddc9 | note | - - - - - - - - -
5a16df30-a230-574b-a954-42b1962d6e2f | note | Acceptance Criteria: Bedding Materials comply with Table 701.091 and 701.092.
d6c8c507-d87b-5b56-a2f7-772c0f4fc780 | note | RFI-0067 approves the use of Holcim 20mm CL3.
0e7c6f47-572b-5a2e-858d-2fa9b1dc2d76 | note | 100% passing 19mm.
2e1c20b3-214e-551a-bfb7-59b94a1a0a7b | note | 5%-40% passing 0.075mm.
625f8ee2-77a4-535a-82e2-582687548cee | note | PI <= 20.
dd8884e7-d708-5853-984b-b49d72c772fe | note | - - - - - - - - -
23627a00-5ac2-5892-89b6-fc3d8574db33 | note | Reference Documents: Table 701.091, Table 701.092, Cl. 701.29, Table 701.291 1145-FUL-RFI-0067
5ee6fd00-dc90-5e36-8aa5-eaf237d1acf7 | note | - - - - - - - - -
d47684ee-1f21-5543-8deb-e7a47cca8760 | note | Inspection / Test Method: Test Grading and Plasticity Index
9107009f-346b-5051-9906-4c25f3497ddb | note | - - - - - - - - -
0ad3e150-695c-57b4-a8bb-114d93f23d43 | note | Record of Conformity: Test Records From Supplier
ad355300-e919-529a-8e17-b2d6c27678b0 | note | - - - - - - - - -
421a02ca-4764-5e74-97f3-fc66af7ddd2f | note | TP
54486911-e841-5146-b950-4cd6620adb0c | note | - - - - - - - - -
5206631e-9e4e-5cf7-99ca-e7bba15501ad | note | Responsibility: PE
| checkpoint | 2.3 - Drainage Backfill Material
5a3b3969-0c5a-557c-b122-09d96dd847ce | note | Frequency: Each Source Material
3e1a52d3-b4d0-5984-b947-2868e2562565 | note | - - - - - - - - -
394bc114-7e0f-528f-b4ce-ad7cbdaf042f | note | Acceptance Criteria:
334f84c7-1382-5a92-bf3f-b7515920b353 | radio | Select Backfill; | CRG XX – 20mm CL3 wet mix CC – Holcim,CRG - XXX - Type A - Supply XX,Other
b279beb3-ea8f-579d-a028-a8d6192478cb | textbox | Other:
b7fe6f83-e12c-58b6-94c4-b6ff45f970a0 | note | Material Approved via Teambinder Material Approval Form.
874b2342-1336-53a4-88ef-c97c6f6ed0bc | note | - - - - - - - - -
8c1c872c-315e-56ed-8039-94416081c0c8 | note | Reference Documents: Table PS3020.051
cd60a27e-44be-5b62-b269-50ffcaeb9842 | note | - - - - - - - - -
518e5600-e81a-5f1a-9241-28dd1e4cdb42 | note | Inspection / Test Method: Verify
831c7a85-35c2-5377-88e9-64607b15041f | note | - - - - - - - - -
6c874eed-65d0-56f4-abca-6aaa7cc18b1b | note | Record of Conformity: This ITP
12dafda4-1171-50ad-bf00-ce949a03db5b | note | - - - - - - - - -
327e2395-2359-5eda-aa2e-c4808f1c7cdf | note | IP
a4aa4d2e-091a-5616-9d3f-b3fed311c9d5 | note | - - - - - - - - -
0675074c-b7fa-55c6-8d31-a7fb21b1879c | note | Responsibility: SE
| checkpoint | 2.31 - Backfill Material Testing
ab9f0905-ec45-58b8-b328-a618c8484c08 | note | Frequency: Each Source Material/ 1 Test per 1000 tonnes
21e4a4bd-d26f-5a3d-9f36-8b2f1f8c9de0 | note | - - - - - - - - -
ee906c93-0223-5c20-96a2-e37dd40bdb03 | note | Acceptance Criteria: Selected Material "Backfill" material tested at to ensure materials comply with the following:
5ce58758-e7aa-520b-8fc7-afd0602a086b | note | Grading & Plasticity Index- One per 1000 tonnes or part thereof
afdcf36e-5d30-5fd2-a149-5a2fc7e7fc46 | note | - - - - - - - - -
7bed55c8-f577-54b5-bdb4-d76c802ea346 | note | Reference Documents: Table 701.091, Table 701.092, Cl. 701.29, Table 701.291
de4f56b4-bcd6-51a6-a498-5c3015d4044d | note | - - - - - - - - -
c8af990f-3e9f-5458-b847-08b0a28053fb | note | Inspection / Test Method: Test Grading and Plasticity Index
788a6829-1b76-5148-8160-a32fe0229f19 | note | - - - - - - - - -
62f0149f-ea68-5237-bb87-255c6b3c9f09 | note | Record of Conformity: Test Records From Supplier
3c22a333-b092-5c6d-a0f3-83ddaaf0fb79 | note | - - - - - - - - -
2485c54e-003a-546f-9015-5afd2d856917 | note | TP
181228ab-f728-5c69-869b-8fed641152ae | note | - - - - - - - - -
a64a1696-eac7-5c2c-8ab9-bb17dfdbfeb2 | note | Responsibility: SE
| checkpoint | 2.4 - Material Inspection (Upon Delivery)
cea7a9a1-9f28-517c-bd99-3cf99e57f711 | note | Frequency: Each Delivery
391d0c35-5383-538d-be5f-c228f302b47c | note | - - - - - - - - -
bf9ca013-3461-5e0d-87ad-3a7a3cca2e64 | note | Acceptance Criteria: Material inspection to be raised on ConQA for all precast pits, pipes and culverts.
04daeba2-6576-57eb-aacd-a02bafd22a47 | note | Any existing or new pipes or box culverts that have cracks wider than 0.2mm or are otherwise damaged prior to laying and backfilling must be rejected and removed from the Construction Areas.
d60121a4-279c-5528-819b-5665b9ea0476 | note | - - - - - - - - -
6dce8ded-c02d-513b-9554-67b42ddfea24 | note | Reference Documents: ConQA Order Acceptance Form
a5beb80a-a5d8-5e5c-9f23-576f9b0060bf | note | - - - - - - - - -
ed40d36f-96ce-5b4a-91ed-72afa5dc6479 | note | Inspection / Test Method: Verify
7120b918-c610-5238-9cb9-dbe779cc4f76 | note | - - - - - - - - -
47edbba0-46b3-565b-bcce-223d539d85e6 | note | Record of Conformity: Insert ConQA Material Inspection Reference
05a40846-50f6-537f-a176-768f8abd053f | note | - - - - - - - - -
e492d00b-2456-5564-9d63-0db9d0966303 | note | IP
60b1a632-5809-5662-9472-dde04377d259 | note | - - - - - - - - -
3ac4e2ea-493a-5d99-b8b4-79c26d29a473 | note | Responsibility: SE
| checkpoint | 2.5 - Pit Access covers
4455b449-7d37-5ee9-9c48-5abcb540e8e9 | note | Frequency: Each
6eb47158-b158-5296-83ff-3e7f34218ec0 | note | - - - - - - - - -
e94f4faa-43c0-56af-8ca5-ffe63da90a45 | note | Acceptance Criteria:
89cc9ec6-eb62-55de-b3c8-d8b1cf9b417e | radio | Pit Access Cover (s) | CRG XX – Type D - XX Supplier,CRG - XXX - Type E - Supply XX,CRG - XXX - Type XX - Supply XX,Other
f72f1fd6-0b8c-5328-92ce-062bb591a061 | textbox | Other:
69292b6f-bc0f-5471-87ea-c1e7f5f8ceae | note | Material Approved via Teambinder Material Approval Form.
2e03b94e-1624-5840-a260-4a7ed20c9e6e | note | - - - - - - - - -
613b8538-91d4-570a-bbca-cf1923b2dcb4 | note | Reference Documents: 705.04(b)
9f17d753-bf72-5ee8-bf98-ab5d12bffc10 | note | - - - - - - - - -
ffd811cc-6acf-5142-b9d9-216479341680 | note | Inspection / Test Method: Verify
1ba4cb92-9965-5cea-b241-92eff19e95f5 | note | - - - - - - - - -
8fb32b8d-4832-5b03-a1a6-e03d2a0561a6 | note | Record of Conformity: This ITP
f301debb-c641-5459-9965-0cf94f7d9f97 | note | - - - - - - - - -
607ac1f4-693b-5c33-af34-5c026a8d86e4 | note | IP
3eab2a76-b091-55ec-94b2-90f05b407e25 | note | - - - - - - - - -
6ebb8904-2e0d-5f96-96b1-05bf993fd072 | note | Responsibility: SE
| section | 3 - Installation of Drainage Pipes and Pits
| checkpoint | 3.1 - Drainage Pipes & Pits
a8acbdec-d91a-5185-936a-7efc88df2f0c | note | Frequency: Each Line
028258d9-cda2-5eb9-97e7-7ec94460c63d | note | - - - - - - - - -
c1529e36-bbb0-5eb6-a208-f81c86737e2b | note | Acceptance Criteria: Final Check for for any damages / cracks prior to installation
1a675817-fe7e-5f9b-9e78-947f03d958b2 | note | Any existing or new pipes or box culverts that have cracks wider than 0.2mm or are otherwise damaged prior to laying and backfilling must be rejected and removed from the Construction Areas.
880ca6e4-5d53-51fc-bf0c-6aa859403085 | note | - - - - - - - - -
7a17ba8e-b3c9-580c-b47b-4f35e1f8ff59 | note | Reference Documents: 701.31
3ae53932-aec7-59b6-82d4-4c80e4ab7b5e | note | - - - - - - - - -
0737e733-df1e-549d-b2af-3b91e34c0e1f | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
a4b5b497-f22a-5fe3-8321-1a5710918ab6 | note | - - - - - - - - -
594a789a-bcb0-5728-9b12-e38999c67070 | note | Record of Conformity: This ITP
105c81f4-c226-57ff-a38c-136ce5b7bbdc | note | - - - - - - - - -
d0d50934-3345-5def-84c4-b92513058657 | note | IP
fb5eba59-5349-54f8-878f-17984d6a5ede | note | - - - - - - - - -
33ba49f8-48d9-5f26-8b59-1af58384d795 | note | Responsibility: Foreman/ Subcontractor
| checkpoint | 3.2 - Survey Set Out / Position of pipe/culvert/pits
f45ef929-b226-52bf-a7b9-70ca429b6b52 | note | Frequency: Each Line
55a13f08-e9b4-56d3-bcd5-ae9097ed303a | note | - - - - - - - - -
a9a61edb-3f5a-5c90-b313-ea11e42fc4d4 | note | Acceptance Criteria: Prior to commencement of excavation for the culverts and stormwater drainage, confirm the set out position & levels with the,
c4abc12d-b064-5c01-bb83-9b1d1c0ac75b | note | ○ Superintendent
62b34db4-a5b1-5394-adba-066342220566 | note | ○ Area Foreman/ Supervisor
5ba80b95-d6d2-5bda-8c42-dd523b217a94 | note | ○ Subcontractor
8c55e6fa-6fd5-5c25-8817-90158b874007 | note | - - - - - - - - -
5a8e1193-f5b4-5498-969f-479291d97b4e | note | Reference Documents: VicRoads Spec. Cl. 701.10 IFC Drawing
ab68c7fd-5741-50b0-8297-2b1a0b32e53e | note | - - - - - - - - -
e5fff2bf-9098-5e71-ac16-d9b8f5a96615 | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
4c22562b-6431-5b30-b48a-d9024488a917 | note | - - - - - - - - -
de7b831f-ab66-569f-a8ae-f00247bfa2eb | note | Record of Conformity: This ITP
3ea2eb11-ce44-53e0-9f2f-b0f8c84ad76e | note | - - - - - - - - -
9033b811-8e08-5c59-8bbe-84022618f9fc | note | HP
a980624b-99b1-52f1-91a5-4d1510006887 | note | - - - - - - - - -
8faa97ab-5e86-57d1-be6a-069f25cf3b60 | note | Responsibility: Engineer / Foreman / Subcontractor / Surveyor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Excavation
94de2eb4-02a1-50a7-b364-c255a7b8cbf6 | note | Frequency: Each Line & Pit
a368e8df-ce0f-5005-abc0-b2135e4f84ae | note | - - - - - - - - -
45c3db0d-f137-5c15-8cb6-433bd07a1183 | note | Acceptance Criteria: Ensure trench* is excavated to prepare culvert foundation and specified depth of bedding. (*minium from trench wall or shoring as applicable)
ab9f9cc2-42d7-52fb-8bf4-88900653a16f | note | Box culverts:
5c322aea-cb4c-5aad-a0ad-f3f086db9f41 | note | ○ distance between culvert wall and trench wall is between 0.5 - 1.0 x the overall height of the culvert.
137771d9-603b-5416-8f03-0ad87ecace6e | note | Pipe culverts:
c8d1a714-e38e-53da-84ae-83e7c4e50147 | note | ○ the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is greater than >300mm, less than <600mmm.
6ceb3459-fe65-5e34-83c8-8906020eeed1 | note | Pits:
e004f708-e529-588f-96aa-f03115060604 | note | ○ Clearance from external faces of the pit to each face of the excavation to be not less than 400mm
075e8279-17a8-5d83-9cf9-01bfdc1bbe78 | note | Pipes:
6eb524f2-a085-5e50-b295-28a36b17eef1 | note | – – – – – – – – – – – – – – – – – – – – –
303f8a7c-4645-54f3-b72e-be3f14270807 | note | Pipe Type ¦¦ Nominal Pipe Diameter or Width (mm) ¦¦ Horizontal Clearance to Wall of Trench (Min. mm / Max. mm)
cf63a968-4186-5105-b2fe-79f5d4106969 | note | – – – – – – – – – – – – – – – – – – – – –
dfdf21d5-2430-596f-b5ea-a50500322370 | note | Corrugated Metal Culvert ¦¦ All ¦¦ 300 / 1,000
9bf34e0d-7f61-5aa1-8bb7-56bdc0dcf2a0 | note | Other ¦¦ All ¦¦ 300 / 600
ece43790-48de-5a2e-a988-6fa27d9dc2e5 | note | – – – – – – – – – – – – – – – – – – – – –
cbffb572-68bb-58ec-b847-151f0606a6f6 | note | - - - - - - - - -
7299b05f-2e74-57e0-a002-45067e5d54a4 | note | Reference Documents: VicRoads Spec. Cl. 701.15 Table 701.151 Cl. 705.05(b)
f99ea476-5a70-5564-9d21-2453a7e1d4e6 | note | - - - - - - - - -
e3251429-cb1b-5138-a602-79eaaf7bce8b | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
c78de97c-ece8-59ed-9d08-d7ed2272f042 | note | - - - - - - - - -
04fdde95-b987-59c9-bb36-52af5bf9b72a | note | Record of Conformity: This ITP
c0c4fde6-e84f-59b5-bea2-b78bb7763f42 | note | - - - - - - - - -
9d50907d-0657-5c0d-800e-6908cedbe8e7 | note | IP
39c1a879-22b2-5a34-8cba-db18ed2352f0 | note | - - - - - - - - -
15ef12c5-0941-53ed-a599-e8f2b99c4624 | note | Responsibility: Foreman
| checkpoint | 3.3 - Bedding
8ef4e12f-af74-5223-8dcc-4b1d4fff8d31 | note | Frequency: Each trench
d12615ff-862c-5719-b856-0dafdf1ebbd3 | note | - - - - - - - - -
87e215b4-0bca-50df-ad92-eea0423db808 | note | Acceptance Criteria: Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be:
f120ce07-2676-53bc-8641-cb3d787a1845 | note | ○ minimum 100mm for pipes of D< 1500mm
9b9045fd-3a3b-5cee-831e-a08158af0303 | note | 'D' is the nominal pipe diameter or culvert width.
5d3cd34a-3013-5bc7-85b5-585f7f5a8e6f | note | If bedding is being applied on rock subgrade the mimimum thickness shall be 150mm in all instances.
83ee5251-ab78-50ed-bec4-47c916392121 | note | The required bedding depth shall be excavated and placed to accommodate the joint collar.
aab6b5f0-763d-5082-97b1-bd4752a59575 | note | Bedding and backfill materials shall be placed and compacted to refusal using hand held mechanical equipment in layers not exceeding 150 mm loose thickness.
2bec9645-aabb-5abd-9376-5b052ec7317b | note | Once culvert sections are in position, an additional layer of bedding material is placed to a height equal to 30% of the nominal pipe diameter or culvert height.
c8371cd3-92d8-5fbc-b256-cc7e288e1b75 | note | - - - - - - - - -
d2e19300-bcd0-50c2-a361-2ea9664d4c6b | note | Reference Documents: VicRoads Spec. Cl. 701.16 Cl. 701.20(a)
a488adb0-1b5d-5d01-8421-da4981f63618 | note | - - - - - - - - -
1c6eefab-e5ac-5cf5-ae6d-a6fc177c800e | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
5ce07cdb-9f2a-5cba-a41e-819c8e844c71 | note | - - - - - - - - -
e1809b8d-0f81-5a11-a307-40f17655484c | note | Record of Conformity: Test Report / This ITP
e03e08c8-c5be-5f83-9cab-ba8b12e97198 | note | - - - - - - - - -
d6a18004-04b0-5480-a4c7-acdd6545aa63 | note | IP
eb5f2d22-4014-5a37-8009-f69408b77b45 | note | - - - - - - - - -
24edf58c-669f-5385-8184-205a1edaaa10 | note | Responsibility: Foreman
| checkpoint | 3.4 - Laying - Circular Pipe
29776e93-68b2-5e47-9147-2d6d625739b5 | note | Frequency: Each culvert
53cebda3-41d5-5c18-b088-10286ede4c6d | note | - - - - - - - - -
cdd44e6f-05dc-558b-9080-2a72a904826e | note | Acceptance Criteria: Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered.
76acfa18-2942-5feb-9489-4efbc556e96d | note | (Laying from downstream).
4e2f545e-c015-512e-9cdb-d8ae2b682673 | note | The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
9883674a-8f72-5a96-92f4-eb4ebc5da40b | note | The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
8cacde7e-0755-55a9-8c53-ff198a1703e4 | note | - - - - - - - - -
c219bb60-0a6d-5173-832c-fd7c306a6be6 | note | Reference Documents: VicRoads Spec. Cl. 701.17(b), Table 701.171
afffd0b2-32e6-53ab-8609-105f0e5124f4 | note | - - - - - - - - -
c81f28da-fbc3-5ded-aeda-dc7ad8e4324e | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
7aa05297-eab8-50c3-b938-742070eaf962 | note | - - - - - - - - -
9fc582e4-e3e0-56a6-964e-97516db04dcb | note | Record of Conformity: ITP signed
c2e3f42d-61e9-5f53-9232-b59dc261b63c | note | - - - - - - - - -
7766c2b6-b0f8-5caa-998b-154418b4224d | note | IP
955c0481-c7ca-522b-9cdb-5e5305f9c35e | note | - - - - - - - - -
779fadc5-c05f-51e7-93da-9f80bfc3e7b8 | note | Responsibility: Foreman
| checkpoint | 3.5 - Laying - Box Culverts
c75368de-7a09-5cc6-94c1-c06303382303 | note | Frequency: Each culvert
5ab22836-7fe2-5d7a-bc8b-59d0b012a6de | note | - - - - - - - - -
d80148bb-d55e-5a6f-aa6d-75adb19edc1c | note | Acceptance Criteria: Consecutive sections of box culverts are firmly placed butted together. The top section matched to the bottom section and no lips over adjoining bottom sections.
844ee077-a543-58cd-b0e0-cd3bc4bc0864 | note | Contact areas between the top and bottom sections are mortared.
bbba5a4e-9044-5195-9837-9cf9affa187d | note | Multi‑row box culverts laid with sections in each row in contact with the sections in the adjacent rows.
2c2eb31a-cc78-5ebd-a658-63176cc10161 | note | - - - - - - - - -
669db92c-b7b9-50af-a326-7969ed0388f6 | note | Reference Documents: VicRoads Spec. Cl. 701.17(c)
b6f4842e-5c3d-5920-b2a6-b7a173359393 | note | - - - - - - - - -
83b433de-e897-5870-b01b-45ca7405ac54 | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
4f8467f1-e0ec-55f2-b622-276ef19067a1 | note | - - - - - - - - -
ba7a1483-b3fb-5199-8a3d-9e90abfd113e | note | Record of Conformity: ITP signed
132a9a7f-1377-5443-89d7-32a8700710b5 | note | - - - - - - - - -
12078924-a3a0-5bbe-b428-110d3a95cae4 | note | IP
aa6b6b76-a295-5cb5-9097-99fce129df6c | note | - - - - - - - - -
4c8d101b-4d1d-5f1e-be60-97f358145b11 | note | Responsibility: Foreman
| checkpoint | 3.6 - Laying - Cutting of RCP/Culverts (If applicable)
3310da2b-097c-5d6b-918c-65d188eae420 | note | Frequency: Each culvert
8b44f322-9828-5689-ba93-0d0238ae97de | note | - - - - - - - - -
bd751828-cb21-5c16-9ba5-22a4b0f58704 | note | Acceptance Criteria: When cutting culvert section to length or to create a penetration, cuts to be done by machine to achieve a clean vertical face.
e7730e43-b063-5e8c-ab72-9607d9d262f4 | note | Any exposed reinforcement shall be coated with Megapoxy P1 treatment to prevent corrosion.
47541a59-e0b9-5037-a412-9d54e25dbedf | note | - - - - - - - - -
7016e250-bcc3-505a-a8d8-2aadd7e51115 | note | Reference Documents: VicRoads Spec. Cl. 701.17(d) 1145-FUL-AP-0100
f9fad512-0210-5e22-b8da-b686adfe239d | note | - - - - - - - - -
e04bbff8-1428-5698-a871-1036ba4171c9 | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
a3bdd97e-4012-5963-9670-29df3046d94e | note | - - - - - - - - -
ae9bf656-1ae3-5173-819d-3558928b6b5e | note | Record of Conformity: ITP signed
2e520272-baa1-56a5-8f64-aea99519bec7 | note | - - - - - - - - -
b432964d-6972-56ef-b7f4-27ed80c3e461 | note | IP
eb72df47-16dc-5423-9afd-e2af0d736594 | note | - - - - - - - - -
1ba08407-bdca-5858-bfa9-536646560a4a | note | Responsibility: Foreman
| checkpoint | 3.7 - Jointing Circular Pipe
28d3d5d6-0bba-5561-b8eb-837fc035cc92 | note | Frequency: Each culvert
36730c7b-32a4-58c3-ad6a-db92fcc79150 | note | - - - - - - - - -
4f23707a-19eb-553c-8e35-5b18a4005443 | note | Acceptance Criteria: Rubber Ring Joints (RRJs) jointed with rubber rings which have been kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately.
3b2c200a-1e10-5073-a5c9-21b85ae4140b | note | RRJs assembled and prepared in accordance with the manufacturer’s recommendations.
d5a3ce19-a11f-5310-9566-64e2de747f8a | note | - - - - - - - - -
6d0be368-576a-58e3-bd55-123d3e3e957a | note | Reference Documents: VicRoads Spec. Cl. 701.18
54eaee0f-2d1b-53c8-893c-98bf3505439c | note | - - - - - - - - -
6dbbb011-4867-50b2-9176-64a2eab63763 | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
cec1b258-584e-5bfc-8721-0713bc3b4552 | note | - - - - - - - - -
8ee14a8a-06fe-5423-81c3-733a098f6074 | note | Record of Conformity: Manufacturer’s recommendations, ITP signed
90e7173b-1ebe-57bd-8faa-3c75c95a3c2b | note | - - - - - - - - -
56e15e89-aea5-5d9c-8362-b49695f07fe2 | note | IP
b7f81f10-c7e9-553b-a666-1911b50d76b7 | note | - - - - - - - - -
7ffdee9a-fcec-5d8e-9359-7d15bd0989cb | note | Responsibility: Foreman
| checkpoint | 3.8 - Survey
9def31a5-0d5d-512d-8987-bd29bb37e5a0 | note | Frequency: Each Lot
399a56d6-7e60-508b-8ed8-ac8f747ddbe3 | note | - - - - - - - - -
d9e5210d-e232-5fd5-950e-f7bc4c5bd131 | note | Acceptance Criteria: At the completion of each drainage run and before commencement of the next line, the location of each run of underground drainage shall be verified by a surveyor prior to backfilling the culverts. This shall be recorded progressively on the Contractor’s as constructed drawings.
089975d3-7d89-54ba-8a3f-8480a92f635e | note | Tolerances that apply:
4c27bcab-c662-5f20-97db-036314106b2a | note | (a) offset of entry pits required to match lines of kerbs or barriers +/-20mm
c7d86272-2b7b-58c5-9833-cd159f37911c | note | (b) plan location of pits other than offsets to kerb lines or barriers +/-100mm
19ba16a4-eaf2-5542-bff3-cb7733a4deb0 | note | (c) Invert leve of pipes at pits +/-50mm whilst maintaining required drainage grade.
d9665201-af72-5af2-be3d-8f164318a7e0 | note | (d) Departure from design grade of pipe runs +/-10mm in 10m (+/-0.1%) provided minimum grade is not less than 1:250 (0.4%).
6f23d0af-d908-516e-961c-544613a2aded | note | - - - - - - - - -
f43c9c9f-6412-571a-94fd-ccf84f5503e7 | note | Reference Documents: VicRoads Spec. Cl.701.10
0c291b1e-c754-5d44-a89c-318e9e7a3243 | note | - - - - - - - - -
f0250aef-1a03-5298-8186-e86075d12979 | note | Inspection / Test Method: Survey, Daily drainage checklist
cfddd503-9395-5015-bcd8-351c6996c7b9 | note | - - - - - - - - -
51109c7a-4c0b-5b4a-9e0f-307b2707ac6f | note | Record of Conformity: Survey Report
97106368-fc24-549a-ac8c-b2cb8e26ec0c | note | - - - - - - - - -
680538f8-80f1-5aad-879c-a27d0e8df535 | note | HP*/ SCP
3a2a09d6-e51a-5ee6-85c7-da7dfecaebe3 | note | - - - - - - - - -
87ff56f6-a6ae-5638-84d4-828817ca3b52 | note | Responsibility: SE
| checkpoint | 3.9 - Backfilling
a79176de-0d8c-5be0-ba1d-35ff6145aea7 | note | Frequency: Each culvert
445f5671-e273-5b02-b4ea-31ec2163a23e | note | - - - - - - - - -
708c502b-7c77-5b07-8988-a93a409fd3c0 | note | Acceptance Criteria: Excavations for drainage pits and pipes must be backfilled with (min)Type A material or approved subtitutes and, where applicable, pavement material above subgrade level
1e4ab082-a3c1-5446-aa34-20f74a290abe | note | Backfill types HS2 & H2
dac706c7-16a6-5bfd-a7ff-862bab6ccc8d | note | Culvert Under Area to be Paved:
34f1e6e0-6d08-5b0a-a462-941f5af5a5ad | note | ○ If the pipe haunch zone is within or above the pavement subgrade, the trench above bedding is to be backfilled with 10mPa lean mix concrete to min 150mm above the pipe and above that level with appropriate pavement material.
131720fd-61d6-5d3c-a938-b5fb516ff022 | note | Culvert Under Area not to be Paved:
c5e40c48-1e58-5ee3-b8cb-5c3f71a6554d | note | ○ The trench is backfilled with Type A selected backfill material to a level 300mm above the top of the culvert and with ordinary backfill material above that level.
6ac83587-4c92-5bca-a85b-6bebb0352709 | note | - - - - - - - - -
70a43a21-115a-5bab-94b6-682659bfd598 | note | Reference Documents: PS3030.06(K)(iii) VicRoads Spec. Cl. 701.19(a) 1145-C201-ACM-CVP-DRG-2122
ee0ac1fa-38c4-5c01-a295-5a44fd939dda | note | - - - - - - - - -
75e1d114-3edd-58ec-a5ea-a6a806d5bcd0 | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
78503440-b6e5-5b56-bcc9-3d02bdf46979 | note | - - - - - - - - -
5d649235-04b3-5eb5-9f4d-ba2c8cc041a4 | note | Record of Conformity: ITP signed
0bfa164d-10c9-50ac-9315-362d607df902 | note | - - - - - - - - -
dfe110c3-3b4a-5667-85b9-2edb1744922e | note | IP
b62e54ca-3c57-5466-8605-17d9e95267eb | note | - - - - - - - - -
845ba440-b5bc-59c9-9b2f-2b16cd2ebf2a | note | Responsibility: Foreman
| checkpoint | 3.10 - Backfilling with cement stabilised sand (If required)
8f7b43f2-bdfa-5b8d-a97c-11384628e4de | note | Frequency: Each drainage line
4e4fdc06-abc5-5b3a-a0cc-fc5eb416a959 | note | - - - - - - - - -
5c873d9a-8860-5c48-9a79-4b92d7c99a5c | note | Acceptance Criteria: Subject to superintendent approval, underground stormwater drains may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand.
55abfd47-63d8-5296-8148-f6918e8bfe1e | note | Mixture to have a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
f0d1e3b6-540b-5db2-9fb4-4faa50af9692 | note | - - - - - - - - -
8a704760-747e-5935-8eb1-2632c0d1902d | note | Reference Documents: VicRoads Spec. Cl. 701.19(c)
a1a03338-ae72-59c6-8086-e83027197f4b | note | - - - - - - - - -
23a7a8a4-0c93-5ba7-8737-8285a115a171 | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
3eada3f2-1e11-59fa-b881-c09990829c6e | note | - - - - - - - - -
b18c7af1-ffb8-586a-8e10-3c590dbb5b84 | note | Record of Conformity: Superintendents Correspondence, ITP signed
94dbe31c-19bb-57e2-b66b-c9c37d9d192b | note | - - - - - - - - -
d1455fd3-866a-58e6-8546-cd6823e06196 | note | AP/ *HP
15aada7e-0afb-512d-8b7b-3dcbde6fdc99 | note | - - - - - - - - -
d09fda49-122e-5df8-9e4a-fbafab9e4030 | note | Responsibility: Engineer / Superintendent
| section | 4 - Testing and Inspection
| checkpoint | 4.1 - Bedding Compaction Requirements
9ee2a89c-f3eb-5db8-9937-a6d0be968c2d | note | Frequency: 3 test per lot.
3dbdd9f6-4eb2-50d7-a7aa-6d7fe3ed9cb2 | note | (1 lot consists of one layer of bedding for a culvert length between pits or endwalls)
8a3bd790-7a80-511f-aaa1-97e2b855eb16 | note | Min. 20% of all lots for each culvert shall be tested.
9e118bba-ad56-5a5e-9f41-c884a2aa35fc | note | - - - - - - - - -
5beaeeb3-2ae0-5344-a6f8-41c453d00c39 | note | Acceptance Criteria: Bedding assessed for compaction and /or moisture in lots.
96250516-10ea-5cba-9cc3-a31f1f7a91d8 | note | Bedding compacted to refusal using handheld mechanical equipment.
aa53abe5-a50a-5039-9442-da65fbec4b4e | note | Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
c0dfa639-3ce6-596f-9662-c9f29a6e509d | note | - - - - - - - - -
a2411991-dd64-549e-b4fb-8fdc8cf2c492 | note | Reference Documents: VicRoads Spec.Cl. 701.20 (a)
89119578-1458-5be3-90c9-c4967e3884f8 | note | - - - - - - - - -
f93d3c67-71db-56c1-8da5-cfc8be8bf41a | note | Inspection / Test Method: Visual Inspection, Daily drainage checklist
6bda32d5-d223-5a59-ac84-e486091dc660 | note | - - - - - - - - -
f4ac0245-ec6a-5046-b4c9-12cbc7d8b663 | note | Record of Conformity: Compaction and moisture Test Records, ITP signed
92737ec6-c7f4-55a7-be17-0ecc29e67763 | note | - - - - - - - - -
686880fb-b1f5-5485-bdca-77b88c246993 | note | TP
cf73a3b4-4667-505c-9c61-1358c3a92214 | note | - - - - - - - - -
2a52f713-f569-5018-9b33-656aea6b2253 | note | Responsibility: Engineer
| checkpoint | 4.2 - Backfill Compaction and Moisture requirements
36148099-df8b-5d9c-bba1-08cc85ad2181 | note | Frequency: 3 test per lot.
c103f49c-cf96-5e8e-9344-7b9bb2f56174 | note | (1 lot consists of one layer of bedding for a culvert length between pits or endwalls)
10fb66cd-f844-5ecc-afb2-9e36b54ef55e | note | - - - - - - - - -
f4d52b59-dacb-5b3a-9105-30ca64a25c9d | note | Acceptance Criteria: Backfill as per the approved and selected material :
eef52e53-0a79-54d1-a803-9340738160d6 | note | Bedding/Backfill assessed for compaction and or moisture in lots.
1673022e-bc5e-5244-960a-4474c54d48ac | note | If backfill has a swell greater to or equal to 2.5% it must have characteristic moisture content not less than 92% between completion of rolling and the placement of the overlying layer
2c9e6087-4212-5d77-ace4-d5e86827ab8e | note | ○ compacted to a mean value of density ratio of not less than 97%.
78f395fd-1107-5935-b385-e5e7cd8cc000 | note | Min. 20% of all lots for each culvert shall be tested (1 test every 750mm).
5e466ff0-8d47-588a-8af6-e0d7a262ded9 | note | - - - - - - - - -
22a6f86f-d0e1-5094-9164-619a3fdc5f62 | note | Reference Documents: VicRoads Spec. 701.20 (b)
2cb6ec2b-a8ed-5dc6-ae30-dbdad4ea033e | note | - - - - - - - - -
36bdd09d-4200-5417-b883-654e48483784 | note | Inspection / Test Method: Site Inspection
1fa5abef-2420-55f5-b289-0cc75a45e272 | note | - - - - - - - - -
897911e0-71bd-5924-b777-0f8488749c7c | note | Record of Conformity: Compaction and moisture Test Records, ITP signed
d4cf18a0-06cb-54be-95b5-39e9d5f3c33e | note | - - - - - - - - -
e4316447-a934-591a-8e00-e3644059c7eb | note | TP
209ea601-7793-5279-8feb-c12e54a6c76f | note | - - - - - - - - -
a5364d71-664a-5885-ad71-b541bc26e0f7 | note | Responsibility: Engineer
| checkpoint | 4.3 - Flushing System
dd9634cf-70cb-558a-91c6-7d338e023f85 | note | Frequency: Each culvert
4b455957-d207-5ff0-bf80-598e6886558e | note | - - - - - - - - -
9c2a37ce-cac8-536f-bd24-1caae9442952 | note | Acceptance Criteria: Each culvert flushed clean from end to end on completion and maintained in proper working order.
cae25a3d-3ebf-5355-844a-5a86a91eec43 | note | - - - - - - - - -
354e2ac3-ec46-5412-b006-72466fdb824e | note | Reference Documents: VicRoads Spec. Cl. 701.28
e559d7a1-a60c-5a9c-bc0c-07b79af8896a | note | - - - - - - - - -
062bee77-ecc9-5314-aab0-2db2f0a13b0b | note | Inspection / Test Method: Site Inspection
4977577a-5bb2-5e0d-ac7c-2f562302a044 | note | - - - - - - - - -
903cf725-4460-530c-97cc-6a790b39cc3a | note | Record of Conformity: ITP signed
dcd6e9e0-cfc9-59cf-a5be-26e730335a2f | note | - - - - - - - - -
2007bcbd-1e52-5bb8-961f-1d1932173411 | note | IP
1ef49b35-5967-5f69-b88a-6f5e41ce6434 | note | - - - - - - - - -
9316dc76-5570-596d-a9c6-5270622e953a | note | Responsibility: SE
| checkpoint | 4.4 - Inspection of drainage lines
861af292-7ddb-5c17-bf4f-832ed94e2f4d | note | Frequency: Each culvert prior to construction of pavement layers
cbdde34f-cb41-5d25-b462-c5cee32938b2 | note | - - - - - - - - -
55daf26a-e6ad-5534-a655-0abaae3d2bea | note | Acceptance Criteria: All drainage lines inspected with CCTV cameras, after completion of earthworks to subgrade level and prior to construction of pavement layers.
0c1d7f87-ecbe-584f-9baa-0fb32e6eae60 | note | Inspections shall be conducted by an independent testing organisation using CCTV to 0.1mm accuracy and reporting in accordance with WSA 05-2013 (Conduit Inspection Reporting Code of Australia), to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects
2bcfa05c-d689-51b3-845b-3af3ff392463 | note | Reports provided to the Superintendent, with a copy of the CCTV and a summary of the loation of any defects detected.
bfe60ec3-7ecb-51b5-9ab1-29e89ecacbc5 | note | It is good practise to ensure that each culvert is flushed clean from end to end (i.e., Pit to Pit-including pit) on completion and maintained in proper working order prior to CCTV inspection.
717603e1-945e-5980-9a64-dc3bec66f521 | note | Any section of damaged pipe or box culvert which does not comply with Cl 701.31 is to be removed and where approved by the Superintendent, defects are to be reapired using approved procedures
614ea54e-3297-566f-9ffe-d9c0b292c5db | note | - - - - - - - - -
791dd23c-ddec-59a5-b1d5-cd4e41a27667 | note | Reference Documents: Project Spec. Cl.3030.06 (k), VicRoads Spec. Cl. 701.30 and 701.31, AS/NZS 2566.2 Table 5.6
6f18e841-3531-5c0c-a639-08cc6a1cf72c | note | - - - - - - - - -
cc894041-b182-5929-93f1-047a0b9d6de7 | note | Inspection / Test Method: Site Inspection
b3f3dfd0-d516-5ed2-8151-ad56f04edb5e | note | - - - - - - - - -
752eef06-34f8-5cbf-8df4-4100cbea5414 | note | Record of Conformity: Inspection Organisation, Inspection report, ITP signed
fa0faf4a-eefa-5a56-8489-a913e9bc40b6 | note | - - - - - - - - -
1b28d492-a011-514e-ae6b-30211ba64ab1 | note | HP
d7fae9b4-3c2d-5b9e-9706-2249a2d6e597 | note | - - - - - - - - -
585936b4-cd4f-5785-ac22-c04c4af7695b | note | Responsibility: Engineer / Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.5 - Repairs to Steel reinforced concrete pipes
48167bd3-ace5-5229-b8ce-05c33ace306f | note | Frequency: Each culvert
11bc4c24-a994-5e77-b928-58bbf2e854d3 | note | - - - - - - - - -
3f907d36-7611-5ee0-b225-6332797ff326 | note | Acceptance Criteria: Submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
bd9375f6-3ed6-5588-a259-b0af3221ae9d | note | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures. All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
105ac6f0-b746-58df-949f-4d19a2f09857 | note | - - - - - - - - -
41c433e8-3007-5e4e-b73e-8666f5ce35de | note | Reference Documents: VicRoads Spec. Cl. 701.31
14fb23fc-a179-5a25-94f0-dfd591d7695d | note | - - - - - - - - -
af19db28-47da-518a-8f29-2d9e44fa3721 | note | Inspection / Test Method: Site Inspection
feae7603-fea9-5004-b58d-7fbf5c0ff514 | note | - - - - - - - - -
5546184e-7e44-5352-8c53-0793238a916f | note | Record of Conformity: ITP signed
8f76d0ba-0768-5993-a1bc-387c2ed4ece0 | note | - - - - - - - - -
0a775130-397c-536a-9b85-1e0b20b6b155 | note | HP
d0ea86e3-2dd4-51ab-9cb4-5237c669602d | note | - - - - - - - - -
7d044ffb-8711-5a47-9045-8b45eadf8189 | note | Responsibility: Engineer
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.6 - Flushing System
9c05749c-327d-5ea3-ba3d-c8aef4840f55 | note | Frequency: Each culvert
a33db21f-e3c3-5886-ba2a-b06db808e6b6 | note | - - - - - - - - -
8c6fe6c5-066c-5436-8143-2473a199dcbd | note | Acceptance Criteria: Each culvert flushed clean from end to end on completion and maintained in proper working order.
a9fd6999-9444-5f0c-bbcf-d454f71ed818 | note | - - - - - - - - -
1ee3c813-958e-50fa-8af1-abbb176f5e14 | note | Reference Documents: VicRoads Spec. Cl. 701.28
01a8e2fe-f4cd-5e5d-9da2-cd2147d973db | note | - - - - - - - - -
48cf8cbd-3185-54bf-86b1-e721b0a595fa | note | Inspection / Test Method: Site Inspection
0bf74926-f864-57f3-903c-e2fa6d891f58 | note | - - - - - - - - -
36e83c36-1771-5902-bd5e-9210555b10a1 | note | Record of Conformity: ITP signed
4ae8acf0-2f7e-52ef-842a-25fa68fff70b | note | - - - - - - - - -
a12ac862-48e6-587e-b68c-f3cb77fd9c62 | note | IP
9464de87-eb14-555c-9d99-e604aa23bf35 | note | - - - - - - - - -
f97a431d-66c0-5f8d-9912-fbdd6df7b819 | note | Responsibility: Engineer
| section | 5 - Close Out (TBC)
| checkpoint | 5.1 - Lot Map
1bbf56bd-a56f-5e2a-a340-7966fb1f3a01 | note | Frequency: each/line
47c23104-c208-5782-b5cd-e476e0f52670 | note | - - - - - - - - -
9e94b0a5-49c1-57cc-8a2c-78d1e04d1d8e | note | Acceptance Criteria: Lot is assigend and recorded on lot map
3d5790ad-a99c-5356-8042-ea7e7071b1a9 | note | - - - - - - - - -
d1370bda-d7d3-59bc-964c-bb9fd0a4c0ba | note | IP
c42e9032-8888-5f1d-91db-9aa298ba4997 | note | - - - - - - - - -
db7e293a-625e-5ed3-8db8-ffa920cabe6f | note | Responsibility: Project Engineer
| checkpoint | 5.2 - As build/ Redline
5fbb9599-1d1b-546d-b5e3-6b32cf904c8a | note | Frequency: each/line
c6da021f-c26b-5d26-bcd8-cb29930ea938 | note | - - - - - - - - -
721d2ac1-d4c0-524a-b32b-ca2c697b869b | note | Acceptance Criteria: Changes to the design related to the lot have been recorded and transferred to the asbuild/ red line mark up
a564e5e0-8f4e-5521-996f-3ac9d5daa0a2 | note | - - - - - - - - -
0a6cc8e5-12f6-551e-9541-9405f8d9721c | note | IP
a3496649-c2a0-5b29-b24f-2b97183444b2 | note | - - - - - - - - -
58da5776-422a-56d2-ae25-7c0c7de3fd3f | note | Responsibility: Senior Project Engineer
| checkpoint | Final Inspection
de5634cd-b4ab-5a8a-ac1d-641b3b3724fd | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
51a2a5f4-225f-554d-a05b-ca2d09ad25a0 | textbox | Print Name:
405923ec-6195-53be-914f-9bc4a3754bb0 | textbox | Position:
87d7335e-126b-5293-aaf4-316586342b1e | date | Date:
390310bb-76ce-56a4-ac2d-c1ee7a1db610 | date | Work Completed On
| checklist | ITP 0018 - Protective and-or Decorative Concrete Coatings | itp | ITP-018-A2-LOT-XXX - Desc | 96e5a419-a605-4670-b894-849e9a3e20f1
| section | 1 - Preliminaries
| checkpoint | 1.1 - Anti-graffiti System Selection
16c52a7c-24fd-5a22-8524-1b5d825af939 | note | Frequency: Once, for each coating system, 14 days prior to application
037c1a1b-9018-5b7d-a94c-7dd3d95fe3b1 | note | - - - - - - - - -
71da1494-550c-5034-8187-8d1be543e4cf | note | Acceptance Criteria:
99c54263-c2cc-5383-9d82-4be4e199d453 | note | i. be either a film-forming or a penetrant system
43a7c22e-47a8-54b1-829d-6aaaa79e478b | note | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
bd3af846-6542-5861-a8a1-3dba3001a00e | note | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
07a419ae-a86f-58ae-93b4-5f31f6127b71 | note | iv. be non-yellowing, colour-fast and not subject to fading or discolouration
9b5534a4-2ae7-57dc-a9a1-9afce7f68aa8 | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
378b2ca3-4917-551d-a51a-1480eca9f14d | note | vi. application thicknesses (film-forming):
0c7d4de8-270f-5916-b6f0-45ffbc79621f | note | WFT total = 175µm min. OR
3e6d16cf-491b-5aec-ae23-cd9200d4359f | note | WTF per coat = 88µm min.
7b06ced8-faa9-57a8-b28b-1cc77c046e0c | note | DFT total = 100µm min.
7fc47c83-ec8b-5bf0-bfc2-3bd9d03a671d | note | vii. adhesion to substrate (film-forming):
584156a6-cfce-52ae-987c-ca07d60c47e6 | note | 0.75MPa min.
f950f28a-6299-5f3b-b7c2-7f08a9c8ab4e | note | viii. application rate (penetrants)
967dc229-7c2c-59fc-835c-eb06535df822 | note | as per the minimum thickness on the manufacturer's TDS
60eafd54-752c-5b33-b858-0782d1704ea2 | note | - - - - - - - - -
a9aebe60-ffd6-5242-a32a-5a83e76b976f | note | Reference Documents: IFC Drawings, Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & €
14e7a3ed-cdb2-5db2-af48-a1b321fe151f | note | - - - - - - - - -
8f33f851-d8bf-57e8-b08b-c939209b857f | note | Inspection / Test Method: Document Review
771a6b60-a10d-5960-96d8-f64531bff578 | note | - - - - - - - - -
87b07d23-c5a4-53e0-be1d-8306e0bd127f | note | Record of Conformity: ConQA Hold Point Release
c9c782a2-0679-5b96-b63b-0630de069b99 | note | - - - - - - - - -
e8f5274f-5c59-5b06-9c1c-31a64574388f | note | HP
1ebbe877-6277-5a84-ada1-50af91de3079 | note | - - - - - - - - -
fae6f58e-b6f9-5647-8165-09257d3a7339 | note | Responsibility: Nominated Authority
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Decorative & Anti-carbonation System Selection
e33b7a7a-7eef-5d3f-971b-f2019b86dbc5 | note | Frequency: Once, for each coating system, 21 days prior to application
89ddeb5c-f3aa-5252-9c0d-fd6945404ec1 | note | - - - - - - - - -
24d1db10-bedf-5389-84a8-6706ccead8a3 | note | Acceptance Criteria: The system shall be selected based on the following criteria:
63aaed51-a973-5158-9e9e-ef90fc22d4c8 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
cd775355-c08f-5faf-8127-ab92dbc1ad26 | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
bb253852-9712-5e77-94f3-48d8c45b02d4 | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
cc657b32-5b73-52ea-8d15-ce4712c237ad | note | iv. be non-yellowing, colour-fast and not subject to fading or discolouration
9bf8c715-afd6-55bd-9ce7-9c81f70903ee | note | v. be guaranteed to last for 10 years of outdoor exposure
85b18d54-7ebd-5a1e-a309-7045b25d60bd | note | vi. application thicknesses:
caa5a5ad-e521-54de-b0ee-0b8b1e41843f | note | WFT per coat = enough to achieve the total DFT
21f30681-111f-5aba-b240-afa0a74f090f | note | DFT total = 150µm min.
8ddbc317-48fd-5240-9bc0-131b53b4d8ca | note | vii. adhesion to substrate:
cbe2fd21-e9cf-5c9c-a975-42207143bb79 | note | 0.75MPa min.
a213d0a3-6840-51e3-bfaa-b864e7e070e0 | note | viii. able to bridge cracks up to 0.3mm wide
c16c6d1f-438e-58a4-a128-0f5e74c53d08 | note | ix. able to be re-coated within 24 hours
84938fd1-0978-516d-b467-fd0aed4d5314 | note | x. have a minimum pot life of 1 hour
356c0efa-16f7-5719-89b8-6da5d11c9aa5 | note | xi. compatibility to an alkaline surface
af056457-9538-5fbf-9f88-3635fd528a42 | note | xii. equivalent air thickness >150m
b68afc51-a7aa-5241-8d7d-e3a5dd960624 | note | xiii. equivalent concrete thickness >450mm
885cbd8d-ce1a-5add-a9af-de4cf4084bff | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
d3b2598a-3c62-572a-9a72-9c8703e209cd | note | xv. Water vapour equivalent air layer <4m
be07e437-4061-5b9f-974b-5e63ffe94522 | note | - - - - - - - - -
bcf8b2ac-ba23-59f8-9953-94a9a151cea1 | note | Reference Documents: IFC Drawings Coating System TDS, Surface Cleaner TDS, 686.04, 686.05 (a) & (b) Table 686.051
fdc396a5-b7da-58df-87f4-cc2e0cd2c692 | note | - - - - - - - - -
1c6f2614-4400-575e-95ad-c28657a2441f | note | Inspection / Test Method: Document Review
07468e74-659d-54e5-8a4e-a4072fb78c93 | note | - - - - - - - - -
ccf4ece0-4c33-5c2f-b4f7-f49b33dde6cc | note | Record of Conformity: ConQA Hold Point Release
a26c6ed1-3bf5-588a-bddd-e7d3dedf60bc | note | - - - - - - - - -
f4980806-2fde-51ff-9f13-6a304462c35b | note | HP
2159cdba-aad2-5a5e-bcbf-8cfc6fd7151b | note | - - - - - - - - -
68dc206a-4ab1-5d8b-9b59-2053e4e4607a | note | Responsibility: Nominated Authority
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Decorative, Anti-carbonation & Anti-graffiti System Selection
b93f5c44-ed2e-5702-9c80-e10ec83b5f9c | note | Frequency: Once, for each coating system, 21 days prior to application
0b3ff611-9b76-5d82-964d-6c9a34747be3 | note | - - - - - - - - -
175a8d08-f81f-56da-97e0-c8fa5ab50c1d | note | Acceptance Criteria: The system shall be selected based on the following criteria:
66316b2f-7946-5d42-892e-3975bc7ff2a1 | note | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
9437f3f6-b57b-5e85-b007-c24192ff48c1 | note | ii. be water or acrylic based, solvent-free with all coats compatible with each other
7502a5da-0e9c-55ad-b964-b484d66b5370 | note | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
665093d0-a9fd-5ce6-9125-f230e4aef130 | note | iv. be non-yellowing, colour-fast and not subject to fading or discolouration
7fe3812d-6f28-522a-874e-17655f1ae33e | note | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
e25961f6-1fcc-5cd4-bdfb-081b17fcadbd | note | vi. application thicknesses:
92fba9c5-3432-5183-a8a4-34ef9e987f0a | note | WFT per coat = enough to achieve the total DFT
0fe23412-0de2-5f0f-97a5-c980c551da89 | note | DFT total = 150µm min.
8a1f3404-f415-551f-bf39-d883a2a11440 | note | vii. adhesion to substrate:
125fdf9f-2642-5f0b-854f-2d7a1dbbcfdf | note | 0.75MPa min.
775c1176-c147-5e84-ad70-3110d8fdc712 | note | viii. able to bridge cracks up to 0.3mm wide
5031d22d-7068-5521-a7de-a15a2c89bfad | note | ix. able to be re-coated within 24 hours
c37f18cd-7343-51a1-9184-39d1e24caabe | note | x. have a minimum pot life of 1 hour
2b9b738d-5144-5e19-a88e-472bd5bf7d1a | note | xi. compatibility to an alkaline surface
b544f35d-d92f-57cc-a5cf-653e2ee8d48d | note | xii. equivalent air thickness >150m
8f8c3060-8fb5-5ac0-9366-b3de37a0db2a | note | xiii. equivalent concrete thickness >450mm
33bc9f4c-e5c3-572f-a3b7-4e2b413d35ab | note | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
d25bf636-1174-591b-9b5d-965aa764a7d8 | note | xv. Water vapour equivalent air layer <4m
7c551462-c6ad-531f-a49f-64b0993ad6ab | note | - - - - - - - - -
6d779510-0c59-5ff5-9a0b-73ee5fcfb251 | note | Reference Documents: IFC Drawings Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051
31d8ca2d-be09-5df5-a48c-689d8217c336 | note | - - - - - - - - -
ee5ddc8d-e616-5bef-8260-5cddaa8e4176 | note | Inspection / Test Method: Document Review
727545c1-cc42-593f-9b53-08663ab8da77 | note | - - - - - - - - -
f06f375f-e105-58a3-9865-64054330963e | note | Record of Conformity: ConQA Hold Point Release
51ba458e-f8a2-5387-ba7a-10f0e030bc76 | note | - - - - - - - - -
20eb0f69-203e-5eeb-896d-2ac124e03d73 | note | HP
945f8933-49e7-5b50-8e5f-4411a5cda8ec | note | - - - - - - - - -
87eff3fa-87b9-55c5-b161-1ea64b5949e5 | note | Responsibility: Nominated Authority
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Atmospheric & Splash Zone (Dual Protective) System Selection
9fdaa50d-5731-5160-9089-f696614ddb63 | note | Frequency: Once, for each coating system, 21 days prior to application
b7915ab9-73f0-515c-83e2-d5b7c2c731a7 | note | - - - - - - - - -
019232be-69d2-5fe5-a1ac-844bd25248b4 | note | Acceptance Criteria: The system shall be selected based on the following criteria:
b0a768fc-248d-5566-b2e9-c2000bf01ae1 | note | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
cf2688fc-66ba-58e2-843f-4b329f725f1b | note | ii. all coats to be compatible with each other
b1e8478a-493b-53de-a7ea-69340608a5df | note | Penetrants:
50736ace-02bf-5d16-af9a-fdf1d0efcdec | note | iii. active ingredients:
c130e8af-d405-5b32-950c-7ceee60d0f42 | note | Silane = at least 95%
78b09522-521f-5ac2-a5a9-76b366314920 | note | Solid silane & silane cream = at least 80%
251dd510-e9ec-52ae-adcc-89c0fb3c182d | note | Silane-siloxane & siloxane = product shall only be used if approved by the Superintendent
889f3f07-cfd4-5228-a2e5-913e59ed724e | note | iv. application rates:
75556d2e-2a2f-5ea1-b2d4-1b7fbd63d572 | note | Silane = 2 applications of 0.3L/m² min.
53311f69-c694-5156-973a-18c930781f41 | note | Solid silane & silane cream = 1 application of 0.4L/m² min.
9731b30f-62ab-5c2d-a6c5-85cbebf0603a | note | Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
45d6fca8-f587-5549-94ef-e4300365ca0a | note | Film-forming coat:
690c806e-0b56-5e1b-8b46-9e68501964da | note | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
cf849e50-2568-5d35-b23e-4078b38e5f31 | note | vi. to be water or acrylic based, solvent-free
7fb3131e-2243-51cf-9c9d-43eaa7fe4f53 | note | vii. to be non-yellowing, colour-fast and not subject to fading or discolouration
275a3938-b518-5979-9981-de8de956a9b4 | note | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
bdb3a986-d5f0-5ff8-8c9e-c1cc5b3b774d | note | ix. application thicknesses:
373f7c01-53c4-5cde-9db4-7ae81bcc0492 | note | WFT per coat = enough to achieve the total DFT
15b15941-0deb-506a-89f0-37c7732feda2 | note | DFT total = 200µm min.
a7589892-8398-5d45-81c1-9b0d4eb53413 | note | x. adhesion to substrate:
c50ef0a9-d4b6-586a-a232-2d58ca02148b | note | 0.75MPa min.
501c0106-b804-503c-8c2e-95f18757ef28 | note | xi. able to bridge cracks up to 0.3mm wide
61f930ab-700b-570f-b5fc-997b2197e365 | note | xii. able to be re-coated within 24 hours
3e3f46c3-feab-51c1-a79f-3915250567d8 | note | xiii. have a minimum pot life of 1 hour
84ff18eb-82c3-51c3-89f6-c830dc141468 | note | xiv. compatibility to an alkaline surface
0e0df18d-b1c3-5673-b08d-1e247f144077 | note | xv. equivalent air thickness >150m
04ef6fea-5611-57b3-bd7d-cd696630a53b | note | xvi. equivalent concrete thickness >450mm
25e06b80-21b3-5fc3-8340-03f908d2feb4 | note | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
92e9515c-4af7-568a-a187-916224d1a51f | note | xviii. Water vapour equivalent air layer <4m
70359fb7-c96a-5084-858f-3d5057b6e805 | note | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
1efd3f3a-94ec-5d1d-939c-a53f99cc4c2d | note | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
ad400f24-89d9-53c8-8991-8f2534665a46 | note | - - - - - - - - -
a9df61cb-dc88-551e-8bd8-e17b6f041af9 | note | Reference Documents: IFC Drawings Coating System TDS, Surface Cleaner TDS 685.04, 685.06 (a) & (b), 686.04, 686.05 (a) & (b) Table 686.051, 686.05 (c) (i) & (iii)
0b02368e-0516-5cb8-8c47-42f92a3d87ee | note | - - - - - - - - -
21b7a0f0-d796-5682-8a9f-92564d05c006 | note | Inspection / Test Method: Document Review
120d5652-399c-5c29-9f44-cb18d63ee7dc | note | - - - - - - - - -
a84dd4db-eb33-5ddc-b8db-cab2ae0c635f | note | Record of Conformity: ConQA Hold Point Release
f7cbf710-a28d-503c-9fff-9c561882edf1 | note | - - - - - - - - -
28479d96-8633-5bb2-95e8-a3d15a94bb45 | note | HP
0b4f1cb1-9742-5472-94e3-3de7b6a663cc | note | - - - - - - - - -
c9eaa1ec-b503-501f-9eab-88adf80bc5da | note | Responsibility: Nominated Authority
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Work Procedures
8d2a479a-43e7-5e2a-b5c7-9f0c0de134b7 | note | Frequency: Once, for each coating system, 21 days prior to application
ebe28e84-f520-5759-b4a7-5e76d3e85ee3 | note | - - - - - - - - -
a1829c00-9a21-5c2e-92e9-ccde4386b744 | note | Acceptance Criteria: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
4493aba4-badb-5477-b1f2-18bd87c952e1 | note | - - - - - - - - -
65b69eb2-7fd9-5ea9-8389-7fdf67dba892 | note | Reference Documents: 685.05, 686.04
95419911-532f-56d5-a1e8-add5b44246a2 | note | - - - - - - - - -
f88c2cd7-b03f-56f9-b138-1c1c6c74eb6e | note | Inspection / Test Method: Document Review
432ba4ef-b84c-5a57-afd7-79c8c3aa9405 | note | - - - - - - - - -
7464746d-b56f-5f28-b089-912dc57641b2 | note | Record of Conformity: ConQA Hold Point Release
34c66ba5-5214-5db2-b420-cdcfcb63bbea | note | - - - - - - - - -
64439a6e-aede-588f-b5da-6df2e26b8525 | note | HP
c1351492-c377-5d5b-99fa-21b2a88a76a2 | note | - - - - - - - - -
027476b5-4e3c-56e4-9d6e-58d59665a99c | note | Responsibility: Nominated Authority
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Coating Personnel & Equipment
aa6c032c-7c84-5844-8285-d0c5c21f80a2 | note | Frequency: Once, prior to application.
5042fef1-3591-5e70-93fb-da08dd90c647 | note | - - - - - - - - -
be03c9d8-87e7-50af-a98d-2724eb9f895f | note | Acceptance Criteria: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques. Application personnel require 2 years minimum experience. The supervisor shall remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
128c19d9-3d15-5253-b7fd-44f140b95d77 | note | - - - - - - - - -
dd4f8c1f-953d-5d0f-ba32-cbb1aabeb382 | note | Reference Documents: Coating System TDS, Surface Cleaner TDS 685.16, 686.19
69d68ccb-7982-552c-af1c-07bf78c07192 | note | - - - - - - - - -
dce59183-1fdd-5f3b-985c-c233f6ccc13b | note | Inspection / Test Method: Document Review
e155b1e8-73f5-5be8-a41e-efe9ba4a13b7 | note | - - - - - - - - -
1d4c2f9e-b047-53bc-94b9-16853b149a35 | note | Record of Conformity: This ITP
9e731a19-1736-5ea3-af8a-03cb3e2f0ee6 | note | - - - - - - - - -
676966e3-e775-53ce-aece-8a902a03d828 | note | IP
b411c457-b330-5881-8afb-cb0cab6da262 | note | - - - - - - - - -
659f3037-ca80-5f8d-b0e1-bf97a3893acc | note | Responsibility: SE/PE/SPE
| checkpoint | 1.7 - Protection of Adjacent Works & Property
ad4a4f7b-75ee-5316-ab57-a4f7a874e3b6 | note | Frequency: Where applicable, 2 days prior to application.
fbb5375a-d5c3-59f3-8d52-99985a349be4 | note | - - - - - - - - -
d59e3389-36b9-5ad6-8fe5-2e38f0ae6e3a | note | Acceptance Criteria: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
088c7737-6b02-5d6e-b751-95163fb4b60d | note | - - - - - - - - -
1b15659c-c81f-535b-b539-226b8505d410 | note | Reference Documents: 685.17, 686.10
347af568-0895-5a45-8bb7-f600c713425f | note | - - - - - - - - -
cc5582a3-0b26-577e-9361-6118ef21a98c | note | Inspection / Test Method: Visual, Document Review
bfebf8ce-76f4-57da-8b5c-c4e2e75879ef | note | - - - - - - - - -
b34748ed-1161-5ccc-a3e3-39125ba60af1 | note | Record of Conformity: ConQA Hold Point Release
fdfdbd30-1df7-56f3-96f8-67530c7e4d3f | note | - - - - - - - - -
0c819197-cf6b-5cca-9869-b807a61c6467 | note | HP
a718f278-ff7c-59a3-9d1c-f20fbac4983e | note | - - - - - - - - -
8e48d616-3b06-50ae-bf1f-a5de08e0ac6c | note | Responsibility: Nominated Authority
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.8 - Minimum Concrete Curing Period
83315b4e-e9c0-5e1f-aee9-677e7b912fa0 | note | Frequency: Once, prior to application.
66ba8ec6-34fa-5af8-a9d7-9c568880ffe2 | note | - - - - - - - - -
002bd2f6-bacb-588c-8c1a-93f655c821ad | note | Acceptance Criteria: Concrete shall not be coated until the minimum concrete curing times have elapsed:
7d67b6d5-9e09-5dc9-a87a-9988e01a40a0 | note | ○ Standard cured concrete = 28 days, or 14 days with moisture content less than 10%,.
ed66ccbf-b415-58e9-8358-244570e7b688 | note | ○ Accelerated cured concrete = 14 days
e77a034f-8f48-5b64-9594-e7fec146f350 | note | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
d33cde45-d8e5-5641-9e63-8fc1266df239 | note | - - - - - - - - -
3ccae7ba-b812-5073-91dc-3b987793217d | note | Reference Documents: 685.08, 686.16
68ce556b-ebe3-59b3-837d-ee3067ea362e | note | - - - - - - - - -
f9be7e29-8637-59b8-80d1-ff373c44e37b | note | Inspection / Test Method: Visual, Document Review
eb8448db-e35c-5d8b-94aa-da0dc31b1374 | note | - - - - - - - - -
8732b488-51fe-5fce-a228-264f217f9208 | note | Record of Conformity: This ITP
dea0f12f-69ab-504f-92af-37fd36e2b29b | note | - - - - - - - - -
ccf203be-f1fe-5b65-afad-e56aed250706 | note | IP
22405c53-ee54-5bfc-a075-eaf4daeca533 | note | - - - - - - - - -
11a95422-bb67-50ac-bf3c-f4b609749cbd | note | Responsibility: SE/PE/SPE
| checkpoint | 1.9 - Trial Application (or Past Performance) Inspection
1c8a79b3-bd40-517f-ac87-0ad4effc441d | note | Frequency: Once, for each coating system, 7 days prior to full coating application
85f85b1d-4d95-56d1-8fd2-0c37186be2cb | note | - - - - - - - - -
23ece502-5f25-5ea3-bd51-61de3a2c1c1c | note | Acceptance Criteria: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate. Alternatively & subject to approval, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
20c914c4-a63a-5e97-b28d-34995df3d329 | note | ○ Attach: Inspection Photographs
c46c8ea1-c017-5531-ac7f-363a04514dd2 | note | - - - - - - - - -
1c1539c2-7425-52a6-8931-9f4f1a1a0f55 | note | Reference Documents: 685.11, 686.13
2f095323-cb7d-51f4-bd9a-9a8061630a23 | note | - - - - - - - - -
97856f63-aa19-58f3-8503-27115e7eec60 | note | Inspection / Test Method: Document Review
3e09415f-c4e1-53d6-84c4-335acb8694d9 | note | - - - - - - - - -
e191d68c-2a19-5276-98d0-521757d27079 | note | Record of Conformity: ConQA Hold Point Release
f99c41b9-2255-5903-824b-14237e1d48d7 | note | - - - - - - - - -
b553a1d9-7619-5422-8dd6-d2cbc402491c | note | HP
8f7dafa4-08d6-5368-9729-00c9a3d7d299 | note | - - - - - - - - -
e8101e4b-7445-544e-8568-d202f455199e | note | Responsibility: Nominated Authority
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Pre-application activities
| checkpoint | 2.1 - Material Records
7a28fb3c-b786-52a3-9320-6589ee7aa9c7 | note | Frequency: Prior to application
ed1a8071-b941-58d0-a899-1deed6b74af5 | note | - - - - - - - - -
69b5b844-cc0e-56a5-af12-6b2a6d695cb2 | note | Acceptance Criteria: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
a8358ac5-7eb5-5804-90b3-4913a1fe76e8 | note | ○ the manufacturer's name & address
9423626c-ed89-58ce-b070-c9c33134ec6a | note | ○ product reference
38dce0b0-9068-5aad-8de9-13938430c016 | note | ○ batch number
58d1e344-4839-561f-9344-a87d2b444281 | note | ○ quantity manufactured in the batch
787f6344-9787-50d7-b550-354226a5b093 | note | ○ date of manufacture
4209a022-0990-5863-af45-2ef011b12edb | note | – Product beyond the manufacturer's shelf life shall not be used.
81d1dc89-cbaa-54d9-b67c-0ff7f9c836ab | note | – Each product shall be traced to final location.
e0ee40e9-808d-51e8-91b1-8ee1c6100f86 | note | - - - - - - - - -
4488eea0-b8fa-5a6c-9337-8e1ec63135ec | note | Reference Documents: Coating System TDS, Surface Cleaner TDS 685.10, 686.12
59e53f7e-8ba8-50c2-8100-5e614922ba0f | note | - - - - - - - - -
75fea1cb-e6b0-58f5-886f-1ac428a95737 | note | Inspection / Test Method: Visual
36a40ae0-27f9-5dae-b0a3-e520aac89d28 | note | - - - - - - - - -
31e78730-b0df-5de7-85d4-a03f0a685a4c | note | Record of Conformity: This ITP
cb80798e-6fde-593a-a842-7496d09830c6 | note | - - - - - - - - -
0d9a7bae-a74a-5d79-a748-f66d0d22fba7 | note | IP
066ce5c4-ce07-547d-8dca-78aecaba7ffe | note | - - - - - - - - -
3c82c6f0-44bf-55de-8709-9f16081699aa | note | Responsibility: SE/PE/SPE
| checkpoint | 2.2 - Weather Conditions
ff34e4c5-6f07-5521-85c5-3b4bf1367430 | note | Frequency: Prior to application and every 4 hours per shift
df306eae-3446-5e0b-ac12-5ada6b63ebaa | note | - - - - - - - - -
c70c1136-64c9-5fca-9778-3b2217eb234f | note | Acceptance Criteria: Coating systems shall not be applied under any of the following conditions:
45018a3b-c0d9-5526-8bfa-67ccc72a96ed | note | i. windy conditions where spray/splatter may be generated
58f408ef-36b3-5bf0-9678-4e387df17b8d | note | ii. when wind-borne debris is likely to contaminate the uncured surface
56202451-8c6c-505f-b1e6-c3798d8a2f1b | note | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
f0a8fb94-bc88-5b04-a030-40fde666d5de | note | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
6f0c0d09-496a-57c3-bb26-f091dc080def | note | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
859f11d9-32ea-5dbf-94a0-a1e24771aa91 | note | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
8e3ba0d9-81a1-551b-a4d0-58e12cb813f6 | note | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
8b365d98-0e5f-5dc9-8150-05d6988bfcaa | note | – Weather conditions are to be recorded.
0ec8ef37-5f81-5116-bbed-58f57b818421 | note | - - - - - - - - -
3770ecbd-5e35-5dea-b7fa-19e2f9518fda | note | Reference Documents: Coating System TDS, Surface Cleaner TDS 685.09, 685.12 (a), 686.11, 686.14 (a) (iii)
1e05ad5d-6819-5c40-a943-f660f850cfad | note | - - - - - - - - -
ed6d7e6a-a0d4-5bd4-a8eb-6c6f7196455b | note | Inspection / Test Method: Visual, Measure
f5eb2c81-2d8a-59b7-8c87-779fa56edaef | note | - - - - - - - - -
1e17e4ec-8de4-54cc-a42b-046bb6189a89 | note | Record of Conformity: This ITP
1910717a-2c58-524d-833c-c8a3be69329f | note | - - - - - - - - -
285fee0e-b2cd-571d-a20d-7b7e1d1f1b77 | note | IP
cbd17af0-52a3-5945-aaff-45a32810103d | note | - - - - - - - - -
b64f5ec3-35fd-507d-b446-376ac6a45f83 | note | Responsibility: SE/PE/SPE
| checkpoint | 2.3 - Surface Preparation
39c965d0-cb92-5cd3-93af-c4f2c82a68e7 | note | Frequency: Once, prior to application.
c735bc9a-7b60-5b9f-8029-a99199517590 | note | - - - - - - - - -
f0fee166-d92a-5519-ab71-e70d55b49956 | note | Acceptance Criteria: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
c4d56d9a-0f20-53bd-8e77-17d84713cb8c | note | - - - - - - - - -
281c6f1f-63f0-50c1-864b-dbee803311b1 | note | Reference Documents: Surface Cleaner TDS, Coating System TDS 685.05, 686.06
df9f40b9-cb08-5578-b91d-a5142c0815cf | note | - - - - - - - - -
142ec087-d8b5-5644-a844-e4d3e4775996 | note | Inspection / Test Method: Visual
9e261e6f-ca5a-5338-a63b-93c32220a7fd | note | - - - - - - - - -
b6682b43-f3f4-56e3-9b45-10e12a2c8fa8 | note | Record of Conformity: This ITP
cbc844d7-db18-55a3-a2a3-caa3a116a478 | note | - - - - - - - - -
a564bc76-8790-55c1-a748-2a0f952da182 | note | IP
88c3498d-583f-5f68-851d-48a14b3aceb1 | note | - - - - - - - - -
194b7a69-6aa3-5052-b38c-b8716d2985e5 | note | Responsibility: SE/PE/SPE
| checkpoint | 2.4 - Surface Moisture Testing
25f524f2-d8bd-57dd-8f9d-6baefda3e635 | note | Frequency: Immediately prior to application, test 1m2
64504f18-5936-5586-8751-62482e6f7ea3 | note | - - - - - - - - -
b249ca31-d57e-5269-a4d0-b9a029dc4a3b | note | Acceptance Criteria: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
bab117fe-8ab4-5c03-9416-3f2804ed7a14 | note | - - - - - - - - -
213b2f93-9d1a-5655-99ba-0a26c26ae1a5 | note | Reference Documents: 685.12 (a), 686.14 (a) (iii)
91cbb5e3-bc73-5ad0-adeb-0d9222c41b05 | note | - - - - - - - - -
c43f7552-b25e-5d65-b617-238ad3cecbb1 | note | Inspection / Test Method: Test
002cae3f-6f2b-5b06-a3fb-622679c3e590 | note | - - - - - - - - -
c1b6e8a8-8d49-5377-8161-52894df33e5b | note | Record of Conformity: This ITP
b0833b20-1358-53f4-b172-3f6be234efef | note | - - - - - - - - -
a3fcae73-9d8c-5be2-9d88-c558076b2fb0 | note | IP
f271d1f8-949b-5df3-aa24-2bf3c779be6c | note | - - - - - - - - -
f6b16c2b-3ef0-5fc6-bf2a-16623b884148 | note | Responsibility: SE/PE/SPE
| section | 3 - Application activities
| checkpoint | 3.1 - Method of Application
ffc2333b-86e6-5b23-a07e-05c666c510cc | note | Frequency: Each coat
6f5bd19a-559d-5e98-9daf-5f93cc7e7901 | note | - - - - - - - - -
8e47ce8c-8bfa-591f-ab37-954908eef58f | note | Acceptance Criteria: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
6a27eef8-5fb8-5665-8ab5-89741f9ea46b | note | ○ Attach: Coating Application Record
4ef51b15-f820-58c7-bc10-6a238feed303 | note | - - - - - - - - -
a9d168d8-b147-5196-9c98-52065861cce1 | note | Reference Documents: Coating System TDS 685.07, 686.07, 686.09
d9cbe669-a991-5bea-bce9-1a582e638147 | note | - - - - - - - - -
ff3c77cb-1765-556f-a035-771bdab9d3f9 | note | Inspection / Test Method: Visual, Measure
c18b8c0d-be3b-52bb-b36e-f2f3e1d24584 | note | - - - - - - - - -
791712bb-a96c-5ddb-a863-4d0962b003cd | note | Record of Conformity: This ITP
158cf1c6-4793-5b0f-a36f-e80e9e998d7e | note | - - - - - - - - -
8b1d007b-26ac-5a67-9b49-4a71269092d5 | note | IP
ac59d460-4097-59b3-b3e8-9d1d499dc516 | note | - - - - - - - - -
570a6de7-ff21-5b4a-8233-0e1d71cd175b | note | Responsibility: SE/PE/SPE
| checkpoint | 3.2 - Wet Film Thickness (WFT) Testing
c27d6e6d-963a-5f67-884d-464bf832fb89 | note | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
4a1bcde8-86f3-5e2e-8cad-0e0a212c069e | note | - - - - - - - - -
53b14a80-0c25-5944-9971-83d4e5651106 | note | Acceptance Criteria: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
3ab2b9db-89ed-578f-86f6-6477a449f841 | note | ○ Attach: WFT Test Results
1704e195-5045-51b9-bca7-09d1c7f48bdc | note | - - - - - - - - -
f24a9121-949d-56e3-a5d2-156eeb0d0814 | note | Reference Documents: Coating System TDS 685.12 (b) (ii), 686.14 (b) (ii)
9d631bb9-a69e-5e2e-8054-50456e9bdefa | note | - - - - - - - - -
2c566a50-b170-5829-a79d-48d28c9c5c79 | note | Inspection / Test Method: Test
57807a75-f899-5db6-91f6-fce5c30974ce | note | - - - - - - - - -
4f8c7993-9cf9-5771-971e-8d762ce7d00f | note | Record of Conformity: This ITP
3fbc45e7-ae3d-5632-a2cf-5bceced62988 | note | - - - - - - - - -
6df60aa8-31a9-5973-8fa1-516ee970d0da | note | IP
ef347eb4-be9f-594d-9114-6621379b865b | note | - - - - - - - - -
407a6b9e-1203-5a66-886d-75e17202ece9 | note | Responsibility: SE/PE/SPE
| checkpoint | 3.3 - Inspection & Defect Identification
3241dd79-5ece-5a7a-b3aa-dada2ff62201 | note | Frequency: After each coat
5c147f7d-fa2e-5d7a-a007-b2bc0c12dc65 | note | - - - - - - - - -
28b601b7-b24c-5f27-93d1-39143f74427e | note | Acceptance Criteria: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
05feb961-29a5-5b74-8655-0722a3f2b682 | note | - - - - - - - - -
4a626995-eb4a-5940-a04b-861445e7ddbe | note | Reference Documents: 685.07, 685.13 (d), 686.07, 686.15
e7b335b6-0dd3-5318-bf2f-a27596cbaef0 | note | - - - - - - - - -
534f277a-d696-50be-8c2e-14a25226368b | note | Inspection / Test Method: Visual
e39c61d3-22b1-5806-8346-35056c640ed2 | note | - - - - - - - - -
4e825e03-fe24-5fa1-8426-012e88ff7bac | note | Record of Conformity: This ITP
43f6dcb9-323a-5328-9741-d292321f0812 | note | - - - - - - - - -
33f83d79-e4b3-5445-8056-83ddd1a6359d | note | IP
e27afb15-4086-5ff7-8ede-ddcef9f0ed73 | note | - - - - - - - - -
273a2190-3da7-5765-90c6-1e1c8bdd0f9b | note | Responsibility: SE/PE/SPE
| checkpoint | 3.4 - Drying and Curing
d5f83ed9-e9f7-5060-8630-2ee34831bb25 | note | Frequency: After each coat
9cba14e1-f605-5ada-9dc0-96a4464a6e4e | note | - - - - - - - - -
0070d1a7-b007-5e51-a363-344aa85c8ddb | note | Acceptance Criteria: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
42c1519f-ec34-573b-8c85-689800bcbc0d | note | - - - - - - - - -
d2b05ba1-d6b5-50d4-8487-cfb611727c92 | note | Reference Documents: Coating System TDS 685.17, 686.09, 686.10
6af540a1-d51f-5001-8932-cddcba6a211c | note | - - - - - - - - -
b50fc414-f12a-52ac-8e0e-09148baebe1d | note | Inspection / Test Method: Visual
c9a9e0f2-4541-5117-a1c7-c57bf12d316d | note | - - - - - - - - -
d148f3e0-d3f9-51ac-8a72-4847adf91aba | note | Record of Conformity: This ITP
27303a27-6c38-5664-9b5a-b2572ee98232 | note | - - - - - - - - -
e78acbde-29b7-5c03-9488-ca2e2b81000b | note | IP
bcddb11b-d938-5f9a-b1bf-ba7e3937956b | note | - - - - - - - - -
984a84a8-5c5a-59a5-97c8-4c52a9d5951b | note | Responsibility: SE/PE/SPE
| section | 4 - Post application activities
| checkpoint | 4.1 - Clean-up & Waste Disposal
cd1dc02b-1b23-52f3-881c-d3412838c77f | note | Frequency: At completion of Works
8d4a7e56-d86d-5d26-bec9-0ffa814d04b5 | note | - - - - - - - - -
c5d928f9-f1cf-5d82-a4c7-d57e60d13a18 | note | Acceptance Criteria: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
a4f06407-c425-58b1-a626-04958d3866c2 | note | - - - - - - - - -
a865299c-aa37-5f6d-8b5c-cfbbb4d9e16a | note | Reference Documents: 685.09 (c), 686.10
3e5db4de-3964-5e40-8e20-c89202f37436 | note | - - - - - - - - -
6f41068e-a67e-5324-ab49-09a6cba7e259 | note | Inspection / Test Method: Visual
e8dfc26a-4937-5d50-a9fd-cb1d449f2f7b | note | - - - - - - - - -
e519d9e2-416f-52a3-9322-c7b1a56bea2a | note | Record of Conformity: This ITP
c2c52d0b-9d00-5f86-a731-4f5fad88a371 | note | - - - - - - - - -
f843d87c-e775-5701-9cd0-e353af41c068 | note | IP
b680fd3d-489c-540c-9ed8-8dd69fea65b6 | note | - - - - - - - - -
8a6ce9c8-7986-503f-a288-ab7490e91bdd | note | Responsibility: SE/PE/SPE
| checkpoint | 4.2 - Dry Film Thickness (DFT) Testing
42f32e24-c091-54b4-bb8d-13f5d40c6f7a | note | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
dd7e342c-b69f-534c-b824-8c14c013cf5a | note | - - - - - - - - -
f7855a94-6db6-509a-9120-fd822c4bab3b | note | Acceptance Criteria: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
7d87277e-8c8b-502e-a73d-ae805a57e7c1 | note | i. Anti-graffiti system = 100µm
d48265d8-2be3-5e8c-a683-b8092bd4d170 | note | Ii. Decorative & anti-carbonation = 150µm
a95e897a-86f0-5b29-a6f3-8b3136f9ded2 | note | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
60cf1f9a-5660-5b3f-870b-36356f9e0080 | note | iv. Atmospheric & splash zone (dual protective) = 200µm
abaa706a-7a91-595b-96a3-c568c5007fa2 | note | – No more than 15% of the readings shall be less than 90% of the required thickness.
438911d8-187e-585e-a675-2f6746792bcf | note | Attach: DFT Test Results
70015095-f92b-5d6a-9328-8eb37dc806b9 | note | - - - - - - - - -
75a410c0-6513-5c25-a17e-d2693c2e23db | note | Reference Documents: 685.12 (b) (iii), 686.14 (b) (iii)
5201d389-3eba-5437-9124-bd0428dad541 | note | - - - - - - - - -
7978c3b6-fb85-5751-b959-6e84f6e44531 | note | Inspection / Test Method: Test
68b5f614-162e-5561-a373-d51cc7467006 | note | - - - - - - - - -
2e3965e2-dcf0-5c3b-8f6f-9436a8aafb03 | note | Record of Conformity: This ITP
1056386c-9d16-5213-b446-4fb5ab186feb | note | - - - - - - - - -
f48b6c43-7b2a-5da9-8e9e-8900d7479ce9 | note | IP
58917d13-bc05-5c53-a347-55c04f1fa0c7 | note | - - - - - - - - -
ca35f801-d7f8-547b-9718-91ac1637ebe8 | note | Responsibility: SE/PE/SPE
| checkpoint | 4.3 - Adhesion Bond Strength Testing
b8f68649-7743-5b1d-83d0-e05087e7c0f8 | note | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
3c489945-9f05-5699-88d2-48bc3c368754 | note | - - - - - - - - -
5647bb79-c085-5784-8c88-7ba632d2be8c | note | Acceptance Criteria: A minimum of 14 days after application, the bond-strengths between:
1fe31dec-4d48-51d1-9758-e2569db0a811 | note | i. the coating system to the substrate, and
b79cf716-3ece-5537-a322-cba672596fbb | note | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
abe391ed-31c9-5021-a5d4-cdd03cb16cbb | note | ○ The subsequent results shall be greater than 0.75MPa.
538503e0-aca8-5557-96d1-a3400f3cf3f3 | note | ○ Attach: Adhesive Bond Strength Testing Results
428a0874-1e64-551d-bf2d-f07be79bc226 | note | - - - - - - - - -
688273c5-704e-505b-8f95-fc4e3276ef87 | note | Reference Documents: 685.12 (b) (i), 686.14 (b) (i)
fd627bd6-6e82-5b73-b62e-2a3cc01a2bb8 | note | - - - - - - - - -
ea158fbe-f0d6-54a3-8a41-4c60fbefd53f | note | Inspection / Test Method: Test
2e96e505-aeb2-5f0d-a183-4286de9a43db | note | - - - - - - - - -
5bcdfa4f-0b33-5ba1-8c85-3a98b22b3e20 | note | Record of Conformity: This ITP
91696174-d6ec-5c39-9961-857f02273761 | note | - - - - - - - - -
6cdabb1a-c108-54be-9208-a2ad5a1026be | note | IP
0d8fd1c9-d988-5e8a-ae1a-a6d79d30be18 | note | - - - - - - - - -
6bda0058-d2c5-50d9-a316-b94755d7a172 | note | Responsibility: SE/PE/SPE
| checkpoint | 4.4 - Penetration Depth Testing
1de9ff62-5723-53e2-8780-30619912a6ea | note | Frequency: Where applicable, 3 no. tests over 1m² every 50m², or part thereof
c43a463c-a3f3-5fa5-b7e5-8202133a3624 | note | - - - - - - - - -
24c5007e-fdba-5a6e-8207-519f62a0e470 | note | Acceptance Criteria: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
03da8aa3-d86c-545c-8668-c6c54ce96b80 | note | The subsequent results shall be:
2e4e744a-d750-5470-802f-0d786a9a3883 | note | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
ffdb1231-15c9-5817-9826-0931a9c5039d | note | ii. Silane, Solid Silane or Silane Cream = 5mm min.
7d943afa-4841-5aba-80a0-96d6f01c96af | note | iii. Silane-Siloxane or Siloxane = 3mm min.
5efb5b35-5b9b-5766-a445-6400c5affb65 | note | ○ Attach: Penetration Depth Testing Results
dbcba6cb-854b-50c9-a653-96c1baabc542 | note | - - - - - - - - -
3f3218b2-8133-581a-946c-e1f1fc8f3842 | note | Reference Documents: 685.12 (b) (v), 686.14 (b) (v)
1247f42c-22db-5e69-9f5a-0b6e95b3fd10 | note | - - - - - - - - -
e967f39e-d134-55de-8113-e3be78a54a4a | note | Inspection / Test Method: Test
472bdcae-4142-557c-9cc6-dfe35674bee8 | note | - - - - - - - - -
6f538278-2022-5e08-943f-0b4f934672ca | note | Record of Conformity: This ITP
d9228982-5c0b-5b96-93b7-076a3062fed2 | note | - - - - - - - - -
297186a4-b78e-5c16-8c65-1155bf3d6def | note | IP
8249acba-4fac-59c1-85fc-c1961dbe67b5 | note | - - - - - - - - -
b5392f95-f861-5a04-91f9-62e85dea029f | note | Responsibility: SE/PE/SPE
| checkpoint | 4.5 - Non-conforming Coatings
689bdc84-b02c-516a-af06-9b383b225e74 | note | Frequency: Where required
ff07c6dc-c52d-5162-8284-90ed0eb2c70b | note | - - - - - - - - -
ca03a0fc-e993-556d-8afb-27718d24acfb | note | Acceptance Criteria: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
45e54359-4d5c-521b-a366-af2fa8bdb98e | note | - - - - - - - - -
c68f595c-3895-53f3-94c7-06979a18a754 | note | Reference Documents: 685.14, 686.17
db96f43c-2088-5cdf-ace7-049756383446 | note | - - - - - - - - -
ab30bfe0-c721-57c0-b4ec-8af683f2681e | note | Inspection / Test Method: Visual
fa5e9e48-0264-5d7f-a41a-fb1f88836056 | note | - - - - - - - - -
a35135c3-9efc-5763-b5dd-faf67c91b749 | note | Record of Conformity: This ITP
c7faaffc-d288-5202-a939-93cf44eefbfb | note | - - - - - - - - -
d8a3414a-2b30-5457-aa6d-9a40628342f7 | note | IP
d2942f31-544f-5b59-9ab6-bc1b2e02130f | note | - - - - - - - - -
2379564b-187b-54cf-a7c8-3301672966dd | note | Responsibility: SE/PE/SPE
| checkpoint | 4.6 - Coating Application Guarantee
06cf0871-73cc-5f91-a5b4-f25cd338f32a | note | Frequency: At completion of Works
f31d3c14-8d2a-589d-9e0d-083be1d19a18 | note | - - - - - - - - -
0bfcc0f7-d117-5b85-9f80-a58be9b0d703 | note | Acceptance Criteria: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
a64b54a4-632d-5666-a653-5811eddec100 | note | ○ Attach: Coating Application Guarantee
955173e8-46ee-533f-9ddb-bf7c330fd062 | note | - - - - - - - - -
b440d1b1-f919-597b-9fa8-9181b9ae2c53 | note | Reference Documents: 685.06 (b), 686.05 (a)
660e8cf5-f144-51e2-8857-39ad198f07ab | note | - - - - - - - - -
b787e41e-f487-589e-98ad-096e58b20060 | note | Inspection / Test Method: Document Review
fdc70332-1357-56fa-a9ac-5fe1e6f3d443 | note | - - - - - - - - -
7a6136cf-b707-566a-8c7e-9553ff2a1a8c | note | Record of Conformity: This ITP
462ddce5-202a-5893-b762-3d55416690bd | note | - - - - - - - - -
19f8b473-3b08-51b8-9253-247774e6bea9 | note | SP
629c3f9d-bd86-5370-820c-25507f7899ef | note | - - - - - - - - -
b672f632-8c81-5505-8117-f77e1fb98c5c | note | Responsibility: SE/PE/SPE
| checkpoint | 4.7 - Repair to Damaged Coating
cef5594d-79ce-56bc-8441-3d8a8905d79c | note | Frequency: Where required
a1fde467-97aa-5e2d-a5eb-5ab6895d3677 | note | - - - - - - - - -
1b412d07-ea7a-5031-a3f5-02f76e0e93af | note | Acceptance Criteria: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
73a739d4-0909-5602-96d3-e3cd502ceb35 | note | - - - - - - - - -
3621a038-54ed-566b-8f38-e96fd2e0c645 | note | Reference Documents: 686.17
21f7fa26-95f0-5942-bb52-b18453fcdf51 | note | - - - - - - - - -
2dd2b9ad-b4ff-574e-8507-0f4ea77a7031 | note | Inspection / Test Method: Visual
f06a6e42-6e0d-5971-b102-c3e0a1fd14a7 | note | - - - - - - - - -
247c8b30-1aff-53e9-8f15-99865a2cd50b | note | Record of Conformity: This ITP
7f25b652-092f-591e-ab43-f397fe81aa84 | note | - - - - - - - - -
f779f75f-f649-5e42-83ae-71040aaf4b5d | note | IP
49e2c819-28ef-5c84-b27b-5d8074020ed5 | note | - - - - - - - - -
42916219-8e0a-5726-a99f-7dfc2fe76366 | note | Responsibility: SE/PE/SPE
| checkpoint | 4.8 - Non-conformance Report (NCR) Closure
ba137d9e-3a80-5620-b624-9643057803cc | note | Frequency: Once, prior to closure of this lot / element / Work area
8d2ff112-2d34-5fdf-8a4a-815efc456ee0 | note | - - - - - - - - -
ba899ca8-582a-5e9f-907e-9b15faeea790 | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
9b911556-914e-549d-beab-0311d33ff705 | note | - - - - - - - - -
e46601c2-4bd2-5ee4-833f-2fceb6e51579 | note | Reference Documents: Fulton Hogan Quality Management Plan
3f37d7fc-b361-5125-96da-6252fd0e43dd | note | - - - - - - - - -
74fe35d4-fc2a-58df-b3ea-ebec88e74119 | note | Inspection / Test Method: Document Review
3d699c84-7fe0-5c18-9b1e-566e48702426 | note | - - - - - - - - -
c7c34c82-4a8d-5ef7-b89b-2cf67d8f014f | note | Record of Conformity: This ITP
ee770c26-57d1-5734-8108-46795f586647 | note | - - - - - - - - -
d88c5edd-b5f9-5512-b3fa-500037d0c198 | note | HP*
2a21abd3-cf41-5867-92af-05023c57d1d5 | note | - - - - - - - - -
a37c773c-0e13-5ac5-9481-551c72a74da2 | note | Responsibility: SE/PE/SPE
| checkpoint | Final Inspection
bbe72ef9-c4e2-5c22-8bc3-a7b114b50fff | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bb67c996-082c-5c24-9fcc-a6eff3a51fee | textbox | Print Name:
2af4b828-2519-5abe-a2f2-201aef644b25 | textbox | Position:
0f1c4d43-a9d4-5a44-a511-de86c16dd998 | date | Date:
b51148a0-8505-5f35-9dc8-715231919b9b | date | Work Completed On
| checklist | ITP 0019 - Bonded Anchors (100 Year Design Life) | itp | ITP-019-AX-LOT-XXX - Desc | 96d5cae8-80f3-4e56-bbff-27486cd7b9ed
| section | 1 - Preliminaries - Materials
| checkpoint | 1.1 - Bonded Anchor System - Chemical Adhesive
15a9aad1-ca83-550f-8a99-21c471aaa304 | note | Reference:
d5c978f1-2fce-50ed-a717-4ba734f90929 | note | IFC Drawings
39dc5aa0-984f-5d4c-8ab2-73b03cdab2f2 | note | 680.05 (a)
5c236bf4-522e-5bd1-beb3-3dc22685cf39 | note | 680.05 (b) (i - vi)
a40c51ea-8d9d-524c-b76b-de6f50436cb4 | note | - - - - - - - - -
f95f4ecd-fef9-55a0-8ca9-875ea5809c3c | note | Acceptance Criteria: Bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
f9e7514d-8ffc-528e-a050-4ea6ad78252d | note | i. ATIC SPEC 38
5dc482e8-efee-5b54-8631-f0a7ed0dce43 | note | ii. EOTA EAD 330499-00 or 01-0601
85f06b00-9354-5c44-add1-24868846c601 | note | iii. ICC-ES (USA)
c1d24e1f-ca62-5e8b-97f1-4b2410648f6c | textbox | Enter: Teambinder Material Approval number
247fee49-049b-5a40-b0d4-844885338f85 | note | - - - - - - - - -
5ec3e5f1-b36a-5dfd-be98-4c48c48618e4 | note | Method: Document Review
37f16b14-43fc-5690-91b2-796fb694d2fa | note | - - - - - - - - -
f3853078-ee9f-5d3c-a815-141c294de5c8 | note | Frequency: Once, per product, prior to commencement of Works
177edbd7-095d-5e5c-8808-10b8c2fe62b4 | note | - - - - - - - - -
7d78364a-33e7-5642-a2d3-f2822ccda054 | note | WP
0e339dd2-57cd-57f5-aecb-35a655c2194d | note | - - - - - - - - -
8976378a-0d19-5d43-9d2a-e9a6909f37d1 | note | Responsibility: Superintendent
4f11d789-03ca-517f-a0a7-ac035693b0dd | note | - - - - - - - - -
84c52551-c002-5c26-b036-e956365c13b3 | note | Verifying Documents: This ITP
| checkpoint | 1.2 - Bonded Anchor System - Reinforcement
a0e39e65-2f61-576b-8b68-fa9475684f89 | note | Reference:
668b5b4f-0610-50d5-a170-4e6e765c2d58 | note | IFC Drawings
d87bf53f-10f6-5ed7-b02a-97dafed533ba | note | 680.05 (c)
409dc763-aa04-57c7-899d-349247a560c8 | note | 611.05 (a)
3ca87752-63e9-57c6-beb7-50cf8810dc74 | note | - - - - - - - - -
b6cfece5-0524-50e3-afda-27924a5a7a14 | note | Acceptance Criteria: Where applicable, current ACRS certification for materials and for bar processing.
624da397-4196-52b1-9404-cd80636cab3f | note | Anchor bars need to remain uncoated (black) for durability purposes in fatigue loading.
8d11828d-9efe-5f7f-9364-85c575c214f8 | note | Note: Galvanised steel dowels are only to be used where maximum design life is 25 years and only permanently dry conditions.
b190cfe8-cd83-55aa-95ad-1180c0e52f25 | note | Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
0be77aae-d0f9-5a80-adc8-9dfd41e60986 | textbox | Enter: Teambinder Material Approval number
51c35943-f833-56fd-9cbc-e81148bf8349 | note | - - - - - - - - -
1d70ef98-ae05-56f2-8877-809f55ce58fa | note | Method: Document Review
2a5550e0-009a-5afe-960e-9906c2ee966f | note | - - - - - - - - -
82cb5d4b-4b06-5f8c-aea3-69b07c87f3d7 | note | Frequency: Where applicable, once for each supplier, 14 days of award of contract
e49f593e-8cbb-5503-a513-9fee933cbc77 | note | - - - - - - - - -
b1ff93a3-8435-5a1e-93bd-c2f26b37e671 | note | WP
7af4bdbc-d961-5b30-9c95-bb7c10f995f4 | note | - - - - - - - - -
9d89462f-91bf-5306-9f45-32ee2383c992 | note | Responsibility: Superintendent
f5c4d4dd-0da0-5719-9046-dc437cea0124 | note | - - - - - - - - -
1cac9095-9659-54a8-bc2b-3f637add921d | note | Verifying Documents: This ITP
| checkpoint | 1.3 - Bonded Anchor System - Stainless Steel Anchors
f44a65d6-2092-5058-ac54-5f50f4e0db95 | note | Reference:
c2e9115f-6b27-5d28-ba0a-7add360e211f | note | IFC Drawings
df1abac5-6f20-530e-b950-37b79ca6024b | note | 680.05 (c)
084773b0-6d3c-5366-8957-ef827b1bfd1b | note | - - - - - - - - -
70cc9e74-4502-5943-853b-fa4846864313 | note | Acceptance Criteria: Where applicable, stainless steel grades 1.4401, 1.4404, 1.4362 and 1.4571 (marking A4) may not be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
95b2393e-b1a9-54d5-a5af-33bc1f01e3f2 | note | Stainless steel grades 1.4529 (marking C) may be used in conditions where the component is either permanently inundated in seawater or in the splash zone.
06bb2c48-5d52-589b-857c-d0ee96f0fac3 | textbox | Enter: Teambinder Material Approval number
ea83591e-30ac-5b42-aace-44a7d50b9981 | note | - - - - - - - - -
66834259-0722-597d-9e3b-f9b82ca2724e | note | Method: Document Review
a5243000-1491-5994-827c-09a6a5620292 | note | - - - - - - - - -
859070a1-5651-5480-9e50-25dd561c0b7b | note | Frequency: Where applicable, once, prior to commencement of Works
72cee8cc-71b9-53aa-a98b-b94fe082a32f | note | - - - - - - - - -
33c18899-55cf-53cf-8cf0-a65b035a78db | note | WP
f2da37dc-d9cc-5af2-91d1-b9616a50c16a | note | - - - - - - - - -
c2256abb-bd74-5bc2-8c01-9e1ee81ec8cf | note | Responsibility: Superintendent
b9a2d177-901e-5288-80af-b4afe1ca4415 | note | - - - - - - - - -
40a360af-d065-568b-a87e-3436e520f5d7 | note | Verifying Documents: This ITP
| checkpoint | 1.4 - Bonded Anchor System - Proprietary Threaded Anchor Rods & Metallic Bolts
643f8ea3-949c-57db-9441-d6451166b6fe | note | Reference:
fb2d82e1-3389-52e2-b6eb-3c89244bc655 | note | IFC Drawings
cd20fd44-bd10-58d1-852b-0c671e4c1fa8 | note | 680.05 (c)
4490e959-a2ea-58ff-a6fe-ff67d1d81ee1 | note | - - - - - - - - -
178d7bf8-1157-5953-b794-fd7afcad2d5d | note | Acceptance Criteria: Where applicable, bonded anchor systems shall be certified in accordance with a third party materials accreditation scheme shown below:
599e013c-8967-5b6b-9a32-15a6126a66d6 | note | i. ATIC SPEC 38
30d9e442-ad17-576f-9283-60154799b9ef | note | ii. EOTA EAD 330499-00 or 01-0601
476e114f-2d7d-5612-aecc-5fb3a0d326b4 | note | iii. ICC-ES (USA)
feccaa44-a699-5a36-90af-d4c3b7588d44 | textbox | Enter: Teambinder Material Approval Number
b74b9900-1fb2-5d12-b9cc-49dfd48d180a | note | - - - - - - - - -
d6882b20-f2bd-581e-ad67-334077f52ff5 | note | Method: Document Review
549420f4-92d1-5581-b1f9-d00a212985ff | note | - - - - - - - - -
ea3f58c3-390d-5277-b0d8-974f572e4059 | note | Frequency: Where applicable, once, prior to commencement of Works
bf762007-5b57-59eb-9608-833e607a5255 | note | - - - - - - - - -
24f5f63b-fdf1-5789-a64e-f2bd8004af62 | note | WP
c4957df9-45cb-59c4-87ec-cb79fbbfed1e | note | - - - - - - - - -
7d0953e1-dd33-57c7-843c-a5f9163d4f3b | note | Responsibility: Superintendent
4a4f8af7-8e8b-5de8-8535-2cd7022d0265 | note | - - - - - - - - -
ba291e7a-9301-5041-88b4-f3efe4db0a71 | note | Verifying Documents: This ITP
| checkpoint | 1.5 - Ultimate Load Testing (for Alternate Product or Changes to Existing Product)
b91ca245-113c-5ae7-b3c5-a79172e3ac65 | note | Reference:
5295a848-5d64-5de7-832b-4d225be2f6cc | note | 680.05 (a)
303bbb4b-508e-57aa-a8dd-40a1f522ec41 | note | 680.09 (b)
d89a0702-bb72-5167-a383-5e82b3b79739 | note | - - - - - - - - -
f82572fd-5437-5229-b45a-e1a809b319e1 | note | Acceptance Criteria: Where applicable, if an alternative system is proposed, where a bonded anchor system falls outside the scope of certification or where directed by the Superintendent, Ultimate Load Testing shall be performed to validate the bonded anchor system meets or exceeds the intended durability and load capacities.
af2159fb-ca20-5281-85f0-960f7c65d2cf | note | A sample of 5 no. anchors per combination of adhesive type, anchor orientation, type, grade, diameter and concrete grade shall be installed in accordance with the manufacturer's installation instructions, load tested and results reported by a third-party accredited testing authority.
e653d50e-cf54-58ac-966e-53d544e92ccb | note | Refer to section 5.2 if the Ultimate Load Test fails.
c7829ac7-ca8e-5f3a-9909-3a05901a86a0 | note | Results of the Ultimate Load Testing to be submitted to the Superintendent.
4b23c3aa-e25a-5303-83fd-add7155f099f | textbox | Enter: Teambinder Approval number
19515afb-f47d-51e5-989f-a8bf7a97ba66 | note | - - - - - - - - -
da9087b8-99d5-56a8-a6c3-edfba888b6e8 | note | Frequency: Where applicable, 2 weeks prior to installation of anchors
6fcb0c96-8932-5b8b-abe6-fe197c7e4296 | note | - - - - - - - - -
9250b576-50ec-52f7-b6a7-cad2d6bf947c | note | HP
a6df646c-a7bd-565b-828c-16f7add3c98f | note | - - - - - - - - -
4e1e8f3a-60bf-524b-90b6-368c0b34cfbb | note | Responsibility: Superintendent
577e06cc-ecc0-5555-920f-9eb3c149b2c0 | note | - - - - - - - - -
42be4e31-2d8c-5fbc-8eb0-adb9966d1c23 | note | Verifying Documents: ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Preliminaries - Documentation & Procedures
| checkpoint | 2.1 - Design of Bonded Anchors Subject to Tensile Forces
9a9306ab-a2b3-5107-a43a-ca1b89f63f0a | note | Reference:
2719f9f9-2358-5f15-95b1-2d6ee49351fc | note | 680.04
022ae7b6-08ce-586c-b3a3-863be0009f03 | note | BTN 006, Clause 2.6
fc6098f0-20db-55fc-afa0-b463c3aa4211 | note | - - - - - - - - -
c7ec3fbc-ff58-5fb1-b7a6-9856347e6d18 | note | Acceptance Criteria: If bonded anchors are proposed to be used in full or partial tension, submit full details of the proposal, including a Proof Engineering Certificate of Compliance, for the approval of the Superintendent.
25ce048d-686d-5714-8ea8-6a71c859983f | note | The Design Engineer must be a member of Engineers Australia and have a minimum of 5 years experience in the design and construction of bonded anchors.
f05ea488-8ed1-5e13-b849-90aabc719f72 | note | The Proof Engineer must be independent of the Design Engineer and be pre-qualified to DTP's level PE.
7f22b1ca-368f-5d9d-bf2b-d22373a581f4 | textbox | Enter: Teambinder Approval number
6af128d4-57e8-5de1-aa92-7e7c8a3d57cf | note | or
23781719-2f7e-5528-83b7-837b2ba3c9a7 | note | Attach: PE Certificate of Compliance
c3b1180d-8124-5774-b171-a3ab3be096f5 | note | - - - - - - - - -
70c2da03-bc17-546f-a37f-09fd6763abc7 | note | Method: Document Review
07c27a7f-f3b8-556e-821f-4ebc8798f670 | note | - - - - - - - - -
5665d39c-7cb8-5f75-89df-77c411844ea5 | note | Frequency: Where applicable, 2 weeks prior to installation of anchors
10359d01-6985-5f86-a31f-2423cbd7a978 | note | - - - - - - - - -
4d8188cc-12ee-597d-9d51-5cd1217b762d | note | HP
fd7d6b1c-9ef2-50d6-92f4-7d66f004169e | note | - - - - - - - - -
69fadbd2-30f4-59f8-867a-7c6a9ae26af0 | note | Responsibility: Superintendent
79f7f520-37a4-5263-a884-6d01eae8a1a4 | note | - - - - - - - - -
e284504d-28a2-5cf5-9000-f5e8bcbf099d | note | Verifying Documents: ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Bonded Anchor Work Method Statement
1352dd11-fec3-58ed-9b74-24a8c9887394 | note | Reference:
0e90f3e2-22f8-5c2c-bbb0-bd93ac110bed | note | 680.11
dec586ed-68d2-54bc-b615-de10739c6d42 | note | 680.07
f306bd43-0cdc-5214-9625-7d93db92f81a | note | - - - - - - - - -
5d78e320-db7d-5914-ac7e-d27fe7fcc535 | note | Acceptance Criteria: Bonded anchor WMS, detailing the method for locating reinforcement/tendons/services, equipment to be used, load testing regime and repair of concrete (spalled and cracking) to be submitted for review to the Superintendent.
4dbb7857-8497-5ab9-905d-f93f587cc4fc | textbox | Enter: Teambinder Approval number
ee692758-e701-59c6-b86c-ccd2bb81c58c | note | - - - - - - - - -
9612041e-8924-5e60-9297-f28692cbafab | note | Method: Document Review
6523ce66-c629-5275-b264-ef880b05c027 | note | - - - - - - - - -
1c93b4d4-7ad0-5528-85ce-f53cc4b40497 | note | Frequency: Once, prior to trial installation
e1df0190-db4c-56f5-a82b-e6444ed22fc8 | note | - - - - - - - - -
9756422d-afbd-5810-9bc8-f2c005c71229 | note | HP
d0ea8c4a-c6e2-5501-90d6-ba755fdff318 | note | - - - - - - - - -
388da6d7-c6e1-532f-b977-39a39c988b26 | note | Responsibility: Superintendent
1a2ef470-37ba-58c5-b99d-8c9a6f161f9a | note | - - - - - - - - -
4991d424-a5af-5623-8b8c-ade7bc950789 | note | Verifying Documents: ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Load Testing Work Method Statement
cae8c287-4472-5bc2-8de9-4ca7b3b3dd55 | note | Reference:
834536f7-7f79-563d-841c-62774941265c | note | 680.09 (a)
95a72c91-3c11-539e-94f3-42271cb1378c | note | - - - - - - - - -
6881edc4-7995-5647-a4ca-915d9a3063e3 | note | Acceptance Criteria: Load Testing WMS, detailing the target loads (1.5x or 2x the design loads), load increments, duration for the load to be stained at each increment, testing frequency, measures if fail occurs and equipment to be used.
9c230e2b-922f-5c7c-8551-e345b33b0201 | note | Additional testing equipment requirements:
30f2b958-2488-52b5-b738-8468909bbb81 | note | i. capable of measuring the applied force to an accuracy of ±2%
72eef97b-9923-5a2c-813b-79c8cd56e5e2 | note | ii. capable of measuring the elongation with an accuracy of ±0.02 mm
1981702c-df63-5508-a995-717b528e38f5 | note | iii. have a valid calibration certificate
0be7b1d6-19bf-5095-9b89-e292c35ed7bb | note | The above is to be submitted for review to the Superintendent.
d887dd66-11bc-5a84-9ecb-45d5f1e274da | textbox | Enter: Teambinder Approval number
656ae351-a942-5576-9151-7fa4875d6dcf | note | - - - - - - - - -
7863c653-d4a8-5a47-98e2-77e6f577fc4b | note | Method: Document Review
2e782301-5e5a-53d6-8380-5e181a816da3 | note | - - - - - - - - -
dd756fa8-6fa6-55c2-91ca-2d03b79a69c8 | note | Frequency: Once, 1 week prior to prior testing
00f67536-47b0-5d49-966f-7d2b0d6dfa8b | note | - - - - - - - - -
b1b7e73f-ac4d-548c-ac70-7bc75a2e8d25 | note | HP
832d577a-1b30-5c8a-a027-8125433884ff | note | - - - - - - - - -
0c77849a-4596-5604-b3ad-18b4bbddd915 | note | Responsibility: Superintendent
19c16a65-27c9-523a-a64e-2f8324aac9a6 | note | - - - - - - - - -
1ede3dfe-753f-55b5-9ffc-f0856efb1702 | note | Verifying Documents: ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Competency & Training of Personnel
c71fae87-8f24-5dd0-bd63-9dab41bf9692 | note | Reference:
5a9edf32-cf2a-523d-9744-d3fe38710c20 | note | 680.06
cdf67431-6e89-5021-83ba-47590fa19c70 | note | - - - - - - - - -
cfebe860-5f11-5d67-a993-d396da8219a5 | note | Acceptance Criteria: All bonded anchor installation crews and direct supervisory personnel shall either be:
56ee59ce-e9e1-512e-9cde-2cbb500d44b8 | note | i. listed on the "AEFAC Certified List of Installers"; or
e284dbe1-dcb3-551a-a22b-ffd21726025b | note | ii. trained by the Supplier of the bonded anchor system.
fbba3fab-4241-5c95-91b5-cb74bb618acc | note | Evidence of either is to be submitted to the Superintendent.
15c20bf8-5cdf-5cc2-b87b-3391713bc02f | note | The bonded anchor tester shall be experienced in testing bonded anchors and test reporting.
1e09a0bb-88f2-555e-8356-5411b8a65441 | textbox | Enter: Teambinder Approval number
8fbc0413-e9cd-5e1c-af70-b48893f48145 | note | - - - - - - - - -
616bf190-b1fa-50c2-88b8-01c0a23ed4a2 | note | Method: Document Review
8be1c857-cb44-50b0-a6a0-11bd6ca07eb2 | note | - - - - - - - - -
a6d62b33-ea08-503e-b6d3-71a9d0bc85ed | note | Frequency: Once, prior to commencement of Works
03443a4c-f4ee-5597-8a4a-32bd6b654ca8 | note | - - - - - - - - -
89c81995-2fb9-5e75-9ece-2ec4dbf3e5a7 | note | WP
9ee75881-cb9f-5dcf-b377-a6159cacae9f | note | - - - - - - - - -
39c6738d-e26a-5f86-b92c-387f05a7b0a7 | note | Responsibility: Superintendent
8c58ae86-84a7-5ff3-8f5e-30257d63d3d7 | note | - - - - - - - - -
ead849ba-73c3-5184-9945-a66a1f60e4b1 | note | Verifying Documents: This ITP
| section | 3 - Pre-installation Activities
| checkpoint | 3.1 - Installation Equipment
dc62810b-24fc-571b-806f-348d48e7523a | note | Reference:
72ffe9fb-e0e9-5ade-91c1-a2f040e7009f | note | 680.07
1e889193-69f6-5542-9a4c-dd3f0a4d8f8d | note | Manufacturer's Installation Instructions
01a6fd5e-db89-5910-a58f-c6db1dfb9c70 | note | - - - - - - - - -
c8c4f136-48fe-5087-b54c-c36db3162d77 | note | Acceptance Criteria: Bonded anchors shall be installed using the equipment specified by the bonded anchor system's installation instructions.
739f8dc9-c7e8-5f3f-b95d-c81717263602 | note | This includes drill bits / dustless drill bits, diamond cores, roughening tools, cleaning brushes, mixing nozzles, piston plugs and extensions.
e1b3c439-38ba-51ce-915a-0cc79e35b1e0 | note | - - - - - - - - -
13af680d-dc52-555b-bbb0-d83c4bec96a8 | note | Method: Visual
8e80e566-82ff-5e28-bef3-e914d3641419 | note | - - - - - - - - -
2cef4c63-9d15-5b42-869c-3f76a2fde07e | note | Frequency: Each discrete population
f3127f84-a201-53bf-9a66-5ea996d0d3ce | note | - - - - - - - - -
edab0448-6c3c-5471-8638-8b92e1f0e4d9 | note | IP
| checkpoint | 3.2 - Setting Out
c3354cac-4cbe-518f-b959-b71e0fdd7baa | note | Reference:
7b442203-7537-58bb-a985-71945eac67ac | note | 680.08 (a) & (b)
e19eaa82-f190-56db-873a-080ae9184d24 | note | Manufacturer's Installation Instructions
aaff6399-9ffa-5a3e-8e48-89729e203b63 | note | - - - - - - - - -
75cbe088-7551-58ff-9bd8-185f1b44f9ca | note | Acceptance Criteria: Locations of bonded anchor holes shall be positioned at the design spacings and angles using a calibrated covermeter or ground penetrating radar (GPR) to ensure that no damage occurs to reinforcement, pre-stressing strand, ducting and embedded services.
4a76401b-659a-5cfd-abf3-957a435094d7 | note | Where clashes are detected, adjust the anchor location if able to maintain the maximum and minimum spacings, edge distance and cover requirements.
2bba49af-7020-5a8d-ae6b-a56b1b5b4454 | note | If unable to maintain these parameters, consult the Designer Engineer via the RFI process to provide updated locations.
d6c847c7-30e8-5b5e-a2e1-7847ef6a895c | note | Note: The marked out locations shall be traceable to determine a discrete population of anchors and installed by the same work crew.
3954b0fc-b40d-5d35-80e8-4e227428422a | note | - - - - - - - - -
47fc10b1-e1aa-57e8-ab34-1f9d145b38e3 | note | Method: Measure, Visual
1dc1e81f-5085-5238-996a-71aeda5a1d61 | note | - - - - - - - - -
18615527-c1ad-5ccf-89c3-568db88adb75 | note | Frequency: Each anchor
77688443-1e7f-5fa7-ba54-d44cec243194 | note | - - - - - - - - -
22344a73-9fdd-574d-adf8-365b2c88342d | note | IP
d4944046-8a86-533c-9233-ec48897598d4 | note | - - - - - - - - -
c92cdb8b-9bd8-5137-9077-b7a9e0dce21a | note | Responsibility: Surveyor, SE/PE/SPE
26aed29e-8697-5aaa-9031-9ad948445a89 | note | - - - - - - - - -
4dce37f2-28ea-5456-b9ad-2638b4d0f901 | note | Verifying Documents: This ITP
| section | 4 - Installation Activities
| checkpoint | 4.1 - Hole Drilling/Coring
7db45ba4-8bd1-55c4-805d-4dc1f4d157bf | note | Reference:
aa908d65-4101-5f5a-80b0-095cdaa86dcd | note | 680.08 (a) & (b)
0bd30b9d-e1e5-597a-a2ce-cd9007adba2a | note | Manufacturer's Installation Instructions
63189ad3-6234-5ab3-8f4e-28e89af7fa7c | note | - - - - - - - - -
bcaf3861-f537-515b-8b15-a049798b3b63 | note | Acceptance Criteria: Holes shall be drilled or cored in the orientations, angles (if not perpendicular to the concrete surface) and depths shown on the IFC drawings.
3780d0c5-687b-5d86-ad91-e9bd660011e5 | note | Drill or core diameters shall be those shown in the manufacturer's installation instructions.
0e5986db-b11c-5d75-b370-a1af171a890d | note | Coring may require the internal surface of the hole to be roughened.
2b5ebe84-752d-56a3-97bb-c8484327c291 | note | If reinforcement is encountered during the drilling or coring process, cease drilling immediately and relocate the hole.
bf2b3d03-adba-50d9-a649-42f4b6bab2f0 | note | Refer to section 5.4 for repair of abandoned holes.
04139aa1-5e0c-5e58-a092-041679d8d6ab | note | If reinforcement is damaged, consult the Designer Engineer via the RFI process to provide a clear direction moving forward prior to continuing installation of that discrete population of anchors.
0241d7a4-992f-5273-98b2-2950540a2a64 | note | - - - - - - - - -
4122ce8c-d146-53df-bdfc-49c860ae8017 | note | Method: Measure, Visual
1412cf50-3f2e-5c56-a20a-37725ee5a5b1 | note | - - - - - - - - -
e7aaf7ef-35d4-518c-9b6f-07f475ebb6ef | note | Frequency: Each anchor
7132ea43-ce2f-5fcf-8fdf-97934c55562f | note | - - - - - - - - -
c095b0ae-9f07-5384-8b66-f3d81144c765 | note | IP
d41cd9ef-5fa3-55f3-97fb-9107fbad9c40 | note | - - - - - - - - -
96a2fefe-2f7e-52f5-b6cc-e84b3dbd96d1 | note | Responsibility: SE/PE/SPE
8146de53-366a-55bc-9bea-9f57386438db | note | - - - - - - - - -
649a6985-b3f5-53b2-9323-1d845d4586c1 | note | Verifying Documents: This ITP
| checkpoint | 4.2 - Hole Cleaning
7ac57d50-d368-5ce0-a972-cf6dafba3dd1 | note | Reference:
10be5c13-edcd-5200-85f4-4c87628486d9 | note | 680.08 (a) & (b)
2de45514-e0c2-529d-bc2a-15bc4af17a44 | note | Manufacturer's Installation Instructions
f4c12722-4ecc-530e-b7a6-0dbe6ce0631c | note | - - - - - - - - -
7ebbef77-3f42-5021-a4b7-dd2695258adb | note | Acceptance Criteria: Hole cleaning shall commence as soon as practical following the drilling / coring process to remove debris, dust particles and moisture / free-standing water (where required).
4ce7774c-b3e0-52f2-ad87-cfc10523bd57 | note | The process shall follow the manufacturer's installation instructions which is a repetitive sequence of brush cleaning and air flushing, resulting in no dust detected on a finger-tip when in contact with the internal wall of the hole.
cbdb0834-24a9-5024-a3eb-b22c554d31f3 | note | The minimum hole depth shall be verified before proceeding to the next step.
c1c008fe-cea4-5319-814d-6c9c9374b47b | note | Note: Where hollow-tipped drill bits are used in conjunction with a vacuum drill, cleaning may not be required - consult the manufacturer's installation instructions.
1027e36c-8859-5284-8705-5969df77de30 | note | - - - - - - - - -
28948248-39f7-522e-bd64-0d9024dda1fb | note | Method: Visual
f2d88392-ea8e-5501-8575-26e37f4d1d1c | note | - - - - - - - - -
431aa268-e790-5968-9f2a-17c44092e3bb | note | Frequency: Each anchor
97d1cc80-4939-518a-914b-06488fd1eb99 | note | - - - - - - - - -
d07d677e-dfd1-5b8e-a9ec-48602e5a6cbf | note | IP
39a2e5b5-8a67-5b4b-b53d-44cc208dc513 | note | - - - - - - - - -
8db2ef33-7953-570d-bd72-ff0b7f3a3625 | note | Responsibility: SE/PE/SPE
d81513c4-f47e-5715-8bc2-f92be5d400aa | note | - - - - - - - - -
f53e636d-552e-5659-be98-78c54e186399 | note | Verifying Documents: This ITP
| checkpoint | 4.3 - Substrate Temperature
afc5d251-f750-5211-aabb-8b404f49931e | note | Reference:
986826b5-27c1-507c-b028-18f9310235c8 | note | 680.08 (b)
b3e972a9-b07f-5026-a0eb-e05c540ed4c2 | note | Manufacturer's Installation Instructions
d2e00465-c252-5eb5-9b93-ab1bfb206874 | note | - - - - - - - - -
8cb10dd5-3b21-5d63-9fd4-dcf8d8677c2a | note | Acceptance Criteria: Bonded anchors shall not be installed where the temperature of the concrete is less than -5°C, or greater than 40°C or outside the limits shown on the manufacturer's installation instructions.
d1a929c1-18ce-5e6b-b845-9153e1b4dc60 | note | Record: The substrate temperatures at the time of commencing the discrete population, the corresponding available working and curing times and the temperature at the completion of installation.
8d2155a9-0e1d-5d29-ada0-cde1bebf867d | note | - - - - - - - - -
c289a274-9edd-55aa-ad1c-1884ebfe55b6 | note | Method: Measure, Visual
326d1b46-ef33-50d4-944c-3b18eef8f48d | note | - - - - - - - - -
290fff3b-4053-57cd-8f64-e58b7241bc9d | note | Frequency: Each discrete population
36035df1-a4c8-51ee-a72e-1671e604abb2 | note | - - - - - - - - -
934f76de-8ea1-5653-aa97-d708ecd736e4 | note | IP
f742fab2-ea30-56a0-bfc0-9d8cc6f7a0a7 | note | - - - - - - - - -
fc96b97a-3c8e-54e7-9438-24c8d222f13a | note | Responsibility: SE/PE/SPE
d475000a-bf57-5fae-b51b-024f3d9cdf11 | note | - - - - - - - - -
bf0ffdee-017e-507b-848f-1a6711e4569f | note | Verifying Documents: This ITP
| checkpoint | 4.4 - Anchor Surface Condition
aff1b9b7-3aee-5b52-bdf5-1bfe711e4456 | note | Reference:
6a17849f-a67d-59f1-9c81-7f113046e1cd | note | 680.08 (b)
c478a67e-0930-5509-9f14-ebec9207942d | note | Manufacturer's Installation Instructions
291a54d9-54b3-509b-8cf1-5279c2b9f5e3 | note | - - - - - - - - -
68f29b34-0e5f-5538-a565-90d1563c6cca | note | Acceptance Criteria: Anchors shall be clean, free from debris, oil and other contaminants.
98ee606c-fb6c-5b14-a83f-1149e9a2507c | note | Note: Any substrate coatings may need to be factored into determining the embedment depth
f7034d9b-7e16-5e1c-aa1d-912d96516e63 | note | - - - - - - - - -
ee373815-b645-5611-af52-5602cfc00e26 | note | Method: Visual
e645fbaf-cd79-5eb2-9ba8-cadfc43632a4 | note | - - - - - - - - -
1ad95789-8a02-5e9f-9833-aff0b91f3caf | note | Frequency: Each anchor
4cccf57b-a7e1-51b0-98a7-4e611f499e89 | note | - - - - - - - - -
c19bc63f-9ca4-502b-9d56-ee4e4f2a216a | note | IP
d7fb5278-58f9-53f1-adb6-ec96fea72624 | note | - - - - - - - - -
3ae7eab9-1c2b-5d85-8c39-098e778219df | note | Responsibility: SE/PE/SPE
21e6ce9e-1aeb-58cf-8547-44609c7f2cf7 | note | - - - - - - - - -
dd966bc8-e04f-5689-970b-a5a55039c84e | note | Verifying Documents: This ITP
| checkpoint | 4.5 - Adhesive Injection
c06823e8-50e5-516d-b413-7be4789ca50b | note | Reference:
93a3e54b-7187-5359-b349-58a7f8e05d7e | note | 680.08 (a) & (b)
4fec929e-aac5-5be7-94f4-3acc44ce83af | note | Manufacturer's Installation Instructions
c82a1ea4-5128-5be5-aca1-49e4211b35f1 | note | - - - - - - - - -
ee2ca4d3-e996-5b72-8d1b-5b5731f381ba | note | Acceptance Criteria: Connect the specific adhesive, cartridge gun and required injection equipment (nozzle, tubes, piston plug and valves) for the task and discharge the initial adhesive to waste to ensure that only fully mixed product will be used in the Works.
20edf251-16ff-5b3f-a204-cbe47503ec29 | note | Note: Repeat the "initial discharge to waste" for each new mixing nozzle used and do not modify the nozzles.
96f3520a-f923-5434-bc2d-314b52d25055 | note | Inject the adhesive into the hole, starting from the base working towards the substrate surface at a rate that prevents the creation of air voids, until approximately 2/3 of the hole depth is reached, checked visually prior to the insertion of the anchor.
483c7581-e98e-58d4-b0ce-d4b27450c993 | note | - - - - - - - - -
3005ff3b-9393-58ac-87e2-31d5c5899a84 | note | Method: Measure, Visual
a0d2c2ec-e631-5a25-bb8a-e662715d3be5 | note | - - - - - - - - -
ad15c472-cae9-5e4f-88bb-ee7bc370765f | note | Frequency: Each anchor
7dc1e8d6-24c0-5394-a9f7-08764c89b08f | note | - - - - - - - - -
4185f06c-d629-50b1-a937-4bb1f660b6b5 | note | IP
fe48b1df-ee40-55db-9df5-d9d8259cc9de | note | - - - - - - - - -
40c78205-b3c7-554a-af0f-a00a3b32481d | note | Responsibility: SE/PE/SPE
025352a7-2796-57ce-ab08-e39afb45fb95 | note | - - - - - - - - -
27743f3e-94fe-52ee-9378-27fef3f27076 | note | Verifying Documents: This ITP
| checkpoint | 4.6 - Anchor Insertion
01d9a501-7715-5c2e-889d-eec689bd7320 | note | Reference:
79646a50-422b-5dcc-b962-a35b0000a87e | note | 680.08 (a) & (b)
2f32dd0f-ac7e-570e-bc88-60765242e42e | note | Manufacturer's Installation Instructions
6908d93e-6d9a-597f-82b0-fa44ffd2a3a9 | note | - - - - - - - - -
54a6ce0f-ab90-56d2-b626-2acd0edcd8dd | note | Acceptance Criteria: While the adhesive is within the temperature dependent working time, the anchor shall be inserted and verified to the minimum embedment depth with a singular twisting motion, to ensure that the adhesive completely surrounds the anchor.
7d43b051-3de8-5830-941a-6ebbae7a0855 | note | Where required, the anchor shall be centralised within the hole using temporarily supports to provide a uniform film of adhesive around the anchor and Excessive adhesive shall be cleaned from the substrate surface.
2168d8ec-062c-5443-99fd-2a9f5d230eeb | note | Loss of adhesive during the working time shall be prevented by sealing around the anchor as required.
a8ce5701-c855-5430-a6db-82be963faa49 | note | - - - - - - - - -
7f9e6f0a-9f02-5c1b-875a-c95fcfcf1b4b | note | Method: Measure, Visual
0238f2b7-2475-5765-9415-0b2766faf9d9 | note | - - - - - - - - -
85ebb4dc-81b9-5d98-a581-44ca0a1ccb82 | note | Frequency: Each anchor
300a6144-c0f1-52cb-8d7d-89ee33751947 | note | - - - - - - - - -
91924e78-d069-508d-8f7c-dd5701e95b61 | note | IP
47b58ef8-ee6a-50b4-811d-92ae536caff4 | note | - - - - - - - - -
b6f7a0a1-af4f-558a-b45c-8f1d1f6097b9 | note | Responsibility: SE/PE/SPE
b5bc05ba-8ffa-515c-adc1-caa2b8c4f4e0 | note | - - - - - - - - -
40bbdea4-2cb7-5560-80ae-f17d5ebb1d72 | note | Verifying Documents: This ITP
| checkpoint | 4.7 - Adhesive Curing
634c3610-22b7-55aa-b600-f01127414c39 | note | Reference:
ad25bf61-6003-5fdd-be59-75ecc0b23dac | note | 680.08 (a) & (b)
2ff961ed-6cd8-510c-a125-831912fa0f44 | note | Manufacturer's Installation Instructions
f62722f9-a28e-5ec3-8128-a8ab051bad5d | note | - - - - - - - - -
7a0563ea-d7ff-5404-b5da-6904a192e9d1 | note | Acceptance Criteria: The anchor shall not be disturbed, moved, loaded or torqued during the specified temperature dependent curing period before proceeding to the next step.
828667f5-393d-5882-a90f-3ef7516c609e | note | - - - - - - - - -
a1f32986-431b-5e57-8a96-93907c3985a6 | note | Method: Visual
fdb74d2c-1b02-5747-8884-bac80115ffda | note | - - - - - - - - -
93ccd555-b0f5-5485-956a-08b42a7a5a9c | note | Frequency: Each anchor
f2037af8-ff0c-5c39-87de-17f7d11ba240 | note | - - - - - - - - -
7c52dcbc-f595-59ed-b5bd-cddbedb022b0 | note | IP
e723d4b3-a22b-5e77-9c00-d381f5090d47 | note | - - - - - - - - -
564fd858-565d-5e18-8417-bd4db36b08ab | note | Responsibility: SE/PE/SPE
4661556c-0cc0-5b38-b0d8-4affb18b13ad | note | - - - - - - - - -
7c62fc65-0b53-5d46-882e-b1a513cf50fe | note | Verifying Documents: This ITP
| section | 5 - Post-installation Activities
| checkpoint | 5.1 - Proof Load Testing
ae852b9a-7306-52fe-83e7-0f9b318bdc77 | note | Reference:
24eb75c9-fd64-5a95-8d61-4f24187f10e2 | note | 680.09 (c)
857f5802-9c59-55f6-96fd-8a4458b9687f | note | Load Testing of Bonded Anchors Work Procedure
4abf2a20-dd96-5b2e-9ce8-096d3d565040 | note | Manufacturer's Installation Instructions
1b13ba87-3695-5911-9107-ceac67e1d9ec | note | - - - - - - - - -
228bbabd-4ff3-5fde-8bb8-e33e80a5a21a | note | Acceptance Criteria: After completion of the curing period, bonded anchors shall be subject to proof load testing, as outlined in the approved Work Procedure for Load Testing of Bonded Anchors.
be325302-148b-5b09-b876-c1dc1f805239 | note | All (100%) of anchors subject to tensile loads, a combination of shear and tensile loads or fatigue loads, shall be tested.
6c5023c3-bf4e-51ab-ac68-f5de71b12ae4 | note | All other anchors not subject to tension shall be tested at the greater number of 2.5% of the lot quantity or 5 no. anchors.
171d269e-8403-50cf-82a6-5defe41221c3 | note | Test results shall be equal to or greater than the factored tensile or shear loads and equal to or less than the maximum displacements shown in the Manufacturer's Installation Instructions.
ee707ced-c93d-5953-995e-e5b5a724d9e2 | note | If any anchor fails the proof load or is displaced beyond the limits, the entire discrete population shall be tested for compliance.
cb2c3340-dbb8-53ef-81ff-eccb99430634 | note | Refer to section 5.2 if the entire discrete population fails.
26e74106-b72e-57f0-833b-904ed3ca9fc4 | note | Attach: Proof Load Test Results
56310a96-4e1d-5cfe-8b91-d37b45057c92 | note | - - - - - - - - -
8b5910ba-985d-5dcc-9636-ebfdc249b0e5 | note | Method: Document Review
f644c8e6-7701-5f4d-bda7-82d30358d49a | note | - - - - - - - - -
7554a43b-dd42-54eb-8e30-c168467bf5fc | note | Frequency: Each discrete population
8c513372-9205-5c6c-80a8-c8589e4ac107 | note | - - - - - - - - -
eb95f63b-05a1-5ed4-bcfd-e837bc3c9b3c | note | IP
529bc120-b56f-52dc-9a8d-5901d5cc6cdd | note | - - - - - - - - -
78177e67-beff-5ed5-9fa3-89d540fb4aab | note | Responsibility: SE/PE/SPE
1ec69347-85ef-5633-83dd-62e4ff8d4ec9 | note | - - - - - - - - -
7e7fe24a-7487-574c-a446-08f1ba710cea | note | Verifying Documents: This ITP
| checkpoint | 5.2 - Failure of Load Testing
4e18aced-e95e-5442-b826-c7065abaa531 | note | Reference:
a5ee056a-85f5-5acf-a0c7-526b8213ef13 | note | 680.09 (d)
6a3cddaf-5e0b-5caa-8312-c7bdf66e13d3 | note | Load Testing of Bonded Anchors Work Procedure
ecc4ea6d-8d1d-56ae-96f9-8e3992858569 | note | - - - - - - - - -
e35f1eae-d2c1-509d-8236-9c02c12f3521 | note | Acceptance Criteria: Should an anchor fail an Ultimate Load test, or an entire discrete population fail a Proof Load; rectification proposals must be provided to the Superintendent for assessment prior to any further installation.
25cf5841-6453-551d-bb4c-acc770447e4c | textbox | Enter: Teambinder Approval Number
d9360640-c97d-57dc-9013-02313a2f08ce | note | - - - - - - - - -
bae4a903-5886-5855-8068-c383a19d7a38 | note | Method: Document Review
74218c0f-90d8-5e39-9114-39ee2f4f495e | note | - - - - - - - - -
fe8d6362-e7bd-5b9e-b263-8fb9973b6263 | note | Frequency: Where applicable
169865f7-33aa-523f-bf0a-354cfe851d2a | note | - - - - - - - - -
3e019152-59ed-5f29-8fbd-af39791e26ca | note | HP
d09a11b1-3912-5813-9f74-f30bd2dd98d3 | note | - - - - - - - - -
0998978b-4e14-5173-94eb-81dba0f61af9 | note | Responsibility: Superintendent
a3f981c5-29a1-5073-bfa4-88807af5bea9 | note | - - - - - - - - -
f0c4c530-6839-54eb-9ff2-32b9ee07667f | note | Verifying Documents: ConQA Hold Point Release
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Surface Inspection - Cracks
36944779-b1be-569b-b4e0-07e23138f4d7 | note | Reference:
acfda011-f22c-52ec-b959-bae80e90b2e5 | note | Structural Concrete Crack Repair ITP
d7902db2-1ac1-5a7c-acb2-1523c80e3bd1 | note | - - - - - - - - -
c13de96b-06d7-5815-aba7-e08589b3c92e | note | Acceptance Criteria: No cracks greater than the maximum widths shown below.
c594428b-03fb-5ab7-be23-3936bd0102f8 | note | Exposure classification:
9a474230-3506-5781-8ff4-575fc149ed90 | note | A = 0.2mm
6eb05caf-55ca-5562-ad3a-0414890f79fa | note | B1 = 0.2mm
ec7aebee-ce3f-53c1-8e3c-23a21073563d | note | B2 = 0.15mm
c175eb22-c2ef-5de1-8521-c6ea981ab67a | note | C,U = 0.10mm
78e3a774-81b2-5e1b-bfb8-d21f6d28c1fe | note | If cracking beyond the limits of the exposure classification is observed, follow Structural Concrete Crack Repair ITP (Specification 687), for investigation and repair.
b1674522-4fdb-5b9a-8a46-c9b62ce63469 | note | - - - - - - - - -
4b2d4307-3e4c-5346-8a0c-e11e45568afd | note | Method: Visual, Measure
47c437ed-1b3b-52ba-8c18-1081f39c258a | note | - - - - - - - - -
560100c0-6b2a-5ae5-8a05-6cd1834200a0 | note | Frequency: Where applicable, each lot
eb1f16a5-c0e9-5af2-8ebb-0989d59988c2 | note | - - - - - - - - -
3b1ffee6-4a5f-52b8-92c6-39bea9e50010 | note | IP
b1d394f2-1a72-515c-8c28-58acc0763cd4 | note | - - - - - - - - -
3394a014-9733-5e35-bba7-4aa05bba4781 | note | Responsibility: SE/PE/SPE
52ad78a9-71ea-566e-bd99-b0b486c0d75a | note | - - - - - - - - -
92b3df86-1015-5142-9ea8-61b65c6ae31c | note | Verifying Documents: This ITP
| checkpoint | 5.4 - Surface Inspection - Abandoned Holes & Post-testing Spalling
d08cf1bf-30d1-520b-bd0e-aac846ef4087 | note | Reference:
56ecfa36-0928-5083-af96-2c0fd49f6853 | note | IFC Drawings
9c22fc1e-7cb9-5fe9-b439-7a341f4c21fa | note | Structural Concrete Patch Repair ITP
d96078c5-ec45-52e6-a2bb-a911482992fa | note | 610.31 (a) - (n)
2abfc0cc-48da-5389-8a07-ca0d19e62266 | note | 610.32
3661b159-1d5b-5ff4-bf84-4f7dd3d9e08d | note | - - - - - - - - -
274f108f-712f-5ea8-a09e-3254005f4bcf | note | Acceptance Criteria: Where holes have been abandoned, follow Structural Concrete Patch Repair ITP (Specification 689) for repair.
fd9f0d76-1929-5b81-900d-f3d2639be027 | note | Where spalling around a tested anchor has occurred, preparation of the repair shall follow the Structural Concrete Patch Repair but the repair may allow for the newly cast concrete to create the cover.
eb0deed4-394a-5e01-9f56-e91fc1cbbc12 | note | - - - - - - - - -
0c7f0609-c65b-5dd6-881e-fcd42d2e717b | note | Method: Visual
21a070b1-d3df-57eb-be45-88304f8188a9 | note | - - - - - - - - -
4e79ac71-85b1-5f97-b488-a4d7e5a33498 | note | Frequency: Where applicable, each lot
cd208d73-15d7-561d-a999-f2cc845c2122 | note | - - - - - - - - -
0f767725-6fef-5395-8a28-c32ff23c2582 | note | IP
2d43c01c-3ec9-5612-acf4-acaf0a66b473 | note | - - - - - - - - -
2b5d011e-03a8-5870-8610-a7df39fa7233 | note | Responsibility: SE/PE/SPE
b5f55b2f-e8b4-5d50-adc0-0be96023d234 | note | - - - - - - - - -
b6f32f6d-d30a-5469-9c8d-bd23725b28a4 | note | Verifying Documents: This ITP
| checkpoint | 5.5 - Non-conformance Report (NCR) Closure
e9905fa8-d1ff-5b4a-9fb4-41535eedf200 | note | Reference:
2b6010f8-e1e7-595c-8d17-163789eba61a | note | Project Quality Management Plan
e3e05b82-81a9-575b-b0e6-4963e4e11102 | note | - - - - - - - - -
12baa717-52f6-55f7-b0dd-fc2388846098 | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
cfed423b-186d-58b8-8494-3abe0ab62757 | note | - - - - - - - - -
b05fdf40-8ea3-5280-8abf-1070c2309508 | note | Method: Document Review
114b48af-7c53-522c-94f2-8c8e31ab370d | note | - - - - - - - - -
f0dbd0fe-aa2b-568c-a162-776fce8eb090 | note | Frequency: Once, prior to closure of this lot / element / Work area
7969b1d8-bf7a-5239-bad3-419c1a77efee | note | - - - - - - - - -
bb529f18-b2db-5352-834f-5c6f6effc677 | note | HP*
38d21542-19fa-56d9-be23-f2d5dbb43615 | note | - - - - - - - - -
e25b0f03-5ca7-5533-9262-801f93e06729 | note | Responsibility: SE/PE/SPE
0c252bef-7512-5926-8859-baef9da522c1 | note | - - - - - - - - -
5fc12bc9-c6eb-524c-94a3-109ce5165d8e | note | Verifying Documents: This ITP
| checkpoint | Final Inspection
8e3776a6-1cf9-56fa-8ddc-b622c181ef9d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications
a614a033-37bb-57a2-bf67-7e6f977cbf35 | textbox | Print Name:
ab2b9355-8388-5adf-94b8-e33aa6c7b47e | textbox | Position:
885185f6-1b64-5604-9287-e9513d64dd95 | date | Date:
adcaed43-2f08-521b-84a5-2e908cbab5c2 | date | Work Completed On
| checklist | ITP 0020 - Cycle Railing (Supply & Installation) | itp | ITP-020-A2-LOT-XXX - Desc | 872c98f9-546a-4751-b326-7f4e95fe437b
| section | 1 - Preliminaries - Materials
| checkpoint | 1.1 - Railing Components
1a22bcc8-7593-58f7-9a96-96baba1ff6bb | note | Reference:
1e9af443-173e-5e62-9a46-32088936c148 | note | IFC Drawings
6f5b45d4-76ab-5d9a-9468-48bb82646048 | note | Manufacturer's Drawings & Installation Recommendations
f0d04abb-c054-5329-8f29-c8e0ab9415ed | note | AS5100.2
f64586ff-ee92-51d7-ab0e-ee1581271240 | note | AGRD, Part 6A, Clause 5.5.3
feeabb41-d04a-5236-ac39-98c100e27496 | note | Fulton Hogan Quality Management Plan
aacec2e7-bef0-56c0-a1e4-afeafa522172 | note | - - - - - - - - -
cc9fc3e9-80f8-5171-8df1-a72517fda42a | note | Acceptance Criteria: Where applicable, product to be selected based on the following criteria:
30a1fb6f-2fd4-5731-b755-b372aa217393 | note | Mounted on SUPs and veloways:
3d966994-3c77-560f-9d60-35c410cf95be | note | i. height to rail between 1.2m & 1.4m
da79d5de-19e7-5fb0-9910-c722b0cd325a | note | Mounted on bridges and culverts:
1704d4b0-7643-5652-8447-f3a694e49f58 | note | ii. able to withstand the load conditions
ef5cd89c-5ecb-5f1e-92c3-d12b7a6b90db | note | iii. height to rail 1.4m minimum (on bridges and culverts)
48e383d8-7de8-547f-a680-ece9d4984a25 | note | Details of the nominated proprietary system to be submitted for review to the Superintendent.
e0ed194b-20ed-5341-8c07-27875c4ba2b9 | textbox | Enter: Teambinder Material Approval number
bde71d22-32d2-55d9-a91a-1170a38c65da | note | - - - - - - - - -
a6e7bb40-d39b-5654-befc-befeb8550f4d | note | Method: Document Review
3b08a360-44ad-5e7e-9c62-fb3feaceca0e | note | - - - - - - - - -
f656ebf7-5777-5eae-84b9-27d15257658d | note | Frequency: Each component
d877607a-618f-5974-ae68-601b22ef87f5 | note | - - - - - - - - -
92599e6c-16f9-5db1-9085-811b5e89af6d | note | IP
4887166f-5a40-5398-a1ff-ce9c8de0362c | note | - - - - - - - - -
f1392c90-a5db-5f8c-b87f-862357c154e2 | note | Responsibility: PE/SE/SPE
00bbc396-d0df-5844-b154-8b70a54c2d9f | note | - - - - - - - - -
66adc873-5242-51ef-9d5b-76ef5fb605ff | note | Verifying Documents: This ITP
| checkpoint | 1.2 - Fixing Detail
5b42f5c9-62c9-5005-8fbe-a61e68ee6645 | note | Reference:
9ea90154-b110-512c-a6dd-cac258108a4f | note | IFC Drawings
728cbbd5-8613-5cd5-94b7-e052ef927c46 | note | BTN 006, Clause 2.3
566c6208-e6ea-5287-bdcc-f78ad43f1cf6 | note | BTN 008, Clauses 2.4.3 & 2.4.4
b7c1a454-19a6-515d-9223-078f0a940fb0 | note | Manufacturer's Drawings & Installation Recommendations
d2783141-4701-5ee1-b1d3-465a30296297 | note | - - - - - - - - -
a82ae2e2-a658-59f8-b683-42cc060e821b | note | Acceptance Criteria: Fixing detail to be either positive connection via cast-in ferrules or similar.
b2e34a80-c920-56a9-bc1d-16bd5663d8f8 | note | Bonded anchors are subject to approval from the Superintendent on new structures.
e697ece1-f4c7-5e12-8ece-a9954214c184 | note | Changes to the above shall be accompanied with a PE Certificate.
eaefc0a3-f7ce-53e7-a4e3-2f234c2fb204 | note | Note: Mechanical anchors shall not be used as they will be subject to tensile loads.
334f5a86-5385-5a5f-bb24-994bd59100e5 | textbox | Enter: Teambinder Approval number
c231293f-844b-5d1b-8193-23f99430e6ed | note | or
68e039ad-da7d-5d87-815e-079cb2882f7b | note | Attach: PE Certificate of Compliance
d6da8517-5b99-5917-949a-6f3a40c5c4d3 | note | - - - - - - - - -
0ecc3f47-93dd-5988-b200-62acaecc9876 | note | Method: Document Review
e04c3732-b1e5-59bf-bb17-165cf4d06516 | note | - - - - - - - - -
e286cb25-7bf0-5ebd-bead-b8b4ad30bbb5 | note | Frequency: Each component
c726bf30-7237-5371-bdb5-97d6af233630 | note | - - - - - - - - -
bcd6b4ae-78c2-5e7c-906c-624e92c3bd21 | note | IP
5e3484e1-b32a-576c-ab86-53a3ed01b984 | note | - - - - - - - - -
bf9903ff-4939-50e2-a6b2-bba9eb59e5de | note | Responsibility: PE/SE/SPE
50747bfd-c641-5fd6-8525-68679fdf3b1a | note | - - - - - - - - -
695d65f9-2bdd-5b90-b2ce-360124dfb295 | note | Verifying Documents: This ITP
| checkpoint | 1.3 - Base Plate Bedding (non-structural) Grout or Mortar
f8d02e6b-0aa2-5e7f-87f9-d0ac2549e86c | note | Reference:
fa3f8773-9d33-519c-bf42-5d0648af40cd | note | IFC Drawings
10f1a248-4845-539c-a173-8effd47db232 | note | Manufacturer's Drawings & Installation Recommendations
1b40e280-e254-54e3-8d23-8b72db2a2742 | note | - - - - - - - - -
b37383c1-d822-582d-84b5-bfc093df63d7 | note | Acceptance Criteria: Where applicable, product to be selected based on the following criteria:
151982f2-42f6-5564-84d2-589d289f9dd1 | note | i. have a trowelable consistency
83a7c651-6d19-584f-8e98-6b031b12b3af | note | ii. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
25422ae5-cb0e-56b2-b812-25a09b89e5ca | textbox | Enter: Teambinder Material Approval number
0db4dc98-3e7e-5f92-92a4-e06a44ff3baf | note | - - - - - - - - -
ff85ade7-bbdd-5844-b0a7-07cb8989d6a2 | note | Method: Document Review
9cc072a0-b805-5431-8dde-6b055a382463 | note | - - - - - - - - -
acea3cf4-18f0-547b-9157-e364997227db | note | Frequency: Once, for each product, prior to placement of product
8449a969-4ac3-5ef6-bcbd-5413db5e202b | note | - - - - - - - - -
b568be3d-660c-5dfd-8f9c-60f546c2295e | note | IP
ecaf8ff4-4ea3-54e2-b70a-ca92cd37c05e | note | - - - - - - - - -
7d6f5484-539c-5364-ab77-edb68a43296a | note | Responsibility: Superintendent
2fcfbeda-36ca-5661-aab7-bcfbc39bf79a | note | - - - - - - - - -
f5042597-eb7a-5d5d-9d4a-4571f6bac216 | note | Verifying Documents: This ITP
| section | 2 - Preliminaries - Procedures
| checkpoint | 2.1 - Certification of Installers
4e2f5842-26ba-5cdc-af58-1ed454fb7310 | note | Reference:
060622ee-c4d1-5afe-a457-f10b4a6230f2 | note | BTN 006, Clause 3
6b262396-6bc4-5e26-9a3d-1532de7ba5aa | note | 680.06
4e3ea004-cbf0-5736-9b53-df96a48301f8 | note | - - - - - - - - -
07d8a67d-488e-5662-86de-fa1724f947dd | note | Acceptance Criteria: Where applicable, all bonded anchor installation crews and direct supervisory personnel shall either be:
49f8391c-d9bb-525f-ae9b-e31d6b211f2e | note | i. listed on the "AEFAC Certified List of Installers"; or
8c1dc030-4de7-5263-9d1b-6e35fd0a745d | note | ii. trained by the Supplier of the bonded anchor system.
12b6fe7a-5b9d-55dd-9dac-e9d466ea3aa9 | note | Evidence of either is to be submitted to the Superintendent.
70f8061e-4250-53e6-a6a4-e7d5a32359f5 | textbox | Enter: Teambinder Approval number
41c518c5-28d2-58c3-a1e6-d7393039a321 | note | - - - - - - - - -
f7966d28-fc87-5670-9ecf-e22977482f5b | note | Method: Document Review
d53e6b8b-bc3e-5c7f-b045-aaf4119573c8 | note | - - - - - - - - -
418d964e-b409-574d-b552-224ba47f5e1c | note | Frequency: Where applicable, once, prior to commencement of Works
457f5938-8a8a-52bc-a652-e42d35be5494 | note | - - - - - - - - -
44025972-09f0-5612-ad70-507f5f6f2bb3 | note | WP
70ed0a08-79a2-5543-8ae6-edfeb46c6dd2 | note | - - - - - - - - -
f0ae9fa8-f2fa-5258-afc3-1f7e5551def8 | note | Responsibility: Superintendent
1269bb8a-9716-57ae-b107-9c62c919d925 | note | - - - - - - - - -
6b5d3c9f-78b2-5c8e-9d79-5e01fdc5a94c | note | Verifying Documents: This ITP
| section | 3 - Pre-installation Activities
| checkpoint | 3.1 - IFC Drawings
3235bc57-d787-5dce-af0d-f1a818fa7ac8 | note | Reference:
36d89f5a-7a79-5876-9710-3dda316cf686 | note | Fulton Hogan Quality Management Plan
219b2d82-754b-5c07-b2ae-3dbea15f7551 | note | - - - - - - - - -
05140c45-ab4d-5518-8952-8c742ab44c84 | note | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
be3c740e-1d0a-5a06-95d9-db5eae08daf8 | note | - - - - - - - - -
2c30e7c2-2cc1-50df-8b96-e4fa9994e893 | note | Method: Document Review
ece7b661-0e7f-5f29-8593-55b3ea890e00 | note | - - - - - - - - -
777ad95c-dd9b-52cd-a926-276fb47c3caf | note | Frequency: Prior to starting Works and at regular intervals
7f3302ed-0b65-5f87-9bf0-8a48016b8743 | note | - - - - - - - - -
ada2c18c-0089-584e-9926-b2e75f5053b3 | note | HP*
5d6acbdd-ae58-53e6-ad40-82883c57cf42 | note | - - - - - - - - -
ea525df7-eded-5781-a24d-a0f4400e15a8 | note | Responsibility: All
eab3fd44-4f29-53b1-b1bc-c27eb4ed1ab9 | note | - - - - - - - - -
1bf8f114-7c41-5243-bdb6-eccddbe20cf9 | note | Verifying Documents: This ITP
| checkpoint | 3.2 - Materials Inspection Checklist
8cbf610d-a6ac-53ce-ac94-0c53e2900881 | note | Reference:
d68fdc36-66fd-5c40-8194-1ca187b12833 | note | IFC Drawings
cb273871-f7bd-5704-b59e-46b4d9a60277 | note | Fulton Hogan Quality Management Plan
5a4c0fc6-f7a0-5c4e-ab64-3e4a80c6b8ad | note | - - - - - - - - -
8e4f3f49-162d-50bc-8726-a4e9e7e1ef6c | note | Acceptance Criteria: General inspection of railing components for defects including cracks, handling and storage damage & distortion.
c3a561aa-a746-5fb0-9606-18ad5390ffab | note | Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
2dd67e43-da30-558a-8597-3ed03e8c4e99 | note | Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
3c63e14d-d4d5-598c-84ba-d41b015b2372 | note | Complete: Materials Inspection Checklist in ConQA
c26fa839-5379-59fa-a159-b3e93a1d2ad4 | note | - - - - - - - - -
ee30472c-f16e-5c2d-9629-8277b3e48c83 | note | Method: Measure, Visual
3625babe-bbb4-5ec6-9695-4e0877f77a4a | note | - - - - - - - - -
3f619f54-af6d-5b22-beaa-75c83c8c8f47 | note | Frequency: Each component
742d228d-3eaf-52ae-bf0e-9573f5109a36 | note | - - - - - - - - -
bbf520d6-6cf6-5e30-8844-563b7cd65918 | note | IP
b2dde425-554b-5c01-af55-4e412a842205 | note | - - - - - - - - -
2794478e-f9bd-53d6-bc31-a8605a0d2eee | note | Responsibility: SE/PE/SPE
f4c0f423-7d57-5c9b-bc2e-1819dc99dc97 | note | - - - - - - - - -
9af1ebdf-e045-5460-871e-fa934713c3d9 | note | Verifying Documents: This ITP
| section | 4 - Installation Activities
| checkpoint | 4.1 - Bearing / Mounting Surface Preparation
e4db8f77-9b8c-514b-adc4-1d46496c709b | note | Reference:
5fa054b4-c85a-5cb6-9ef2-46f19f9b1d8b | note | Manufacturer's Drawings & Installation Recommendations
11474153-ba43-52ca-8f31-94cef138d7c0 | note | - - - - - - - - -
e8d8f304-71ca-5783-98d0-d0003cee41e2 | note | Acceptance Criteria: As a minimum, ensure that the bearing surface is clean and free from loose particles and laitance.
adf8ca7e-7c4d-520e-acbf-79e1f084aab5 | note | - - - - - - - - -
91025ec2-d03b-55d4-8652-365d88b959f6 | note | Method: Visual
516c6ed1-c22c-5722-8b5e-5985708120c2 | note | - - - - - - - - -
4aab7e26-6c44-5e45-9d66-700283b88c7e | note | Frequency: Each post location
0ac472eb-6dcf-58ef-934b-ef5dd6933edf | note | - - - - - - - - -
8536309d-d08a-5e2f-a278-aae38dd58e00 | note | IP
18be8e29-f973-582a-9c5e-f67063dd8e09 | note | - - - - - - - - -
58d3cd6f-ff3d-5f9a-8dc2-b4488e6d3cd0 | note | Responsibility: SE/PE/SPE
81a13264-2265-55cc-b2f7-3ab2d1a2a5ff | note | - - - - - - - - -
6caab766-80b5-5864-9cc6-19aa05f74e03 | note | Verifying Documents: This ITP
| checkpoint | 4.2 - Railing Handling
1e6f7cae-9886-568d-97c7-11cab126a298 | note | Reference:
30ffd3ae-03db-58cb-88e3-e59d5d631a15 | note | Manufacturer's Drawings & Installation Recommendations
674b1341-080f-51da-b5f1-0ab680725a24 | note | - - - - - - - - -
37096385-93e4-5aba-8fe4-6e7a1f9d65e4 | note | Acceptance Criteria: The method of handling and erection of the steel railing shall ensure that the components are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
0d6c6680-fefd-55af-bdb3-7df8f9011fa6 | note | Where damage exists, it shall be repaired using an approved repair procedure for both steelwork and coatings.
245af246-e918-554d-9ff1-38b09410abed | note | - - - - - - - - -
cb975082-e69b-5a00-9731-600024604f3a | note | Method: Visual
e5bb852f-0026-5eee-a0e2-d8906c95bd21 | note | - - - - - - - - -
ea20da2c-92a2-5a05-a978-95f2f26594f5 | note | Frequency: Each component
a4d73322-b571-522a-8888-e6656f1a84ce | note | - - - - - - - - -
8a7d5dcd-ef89-5b95-9a51-a4d1ef3e706c | note | IP
f76bbb8c-c0bf-5f32-8ca4-a6000c7c31a2 | note | - - - - - - - - -
4d0567b9-73d3-5803-b8ee-fe017c353f3d | note | Responsibility: SE/PE/SPE
89754330-badf-5b5c-a05f-1129ae51ed7a | note | - - - - - - - - -
b5f46363-3953-5445-b5bb-82a45549102d | note | Verifying Documents: This ITP
| checkpoint | 4.3 - Railing Erection
6ba91cd3-074b-57bc-bef5-859840879ac1 | note | Reference:
e85f6c10-c8c1-521d-aafc-36acef53867f | note | Manufacturer's Drawings & Installation Recommendations
80a6531f-cdcc-587b-9165-81d4d98b3fc6 | note | - - - - - - - - -
8cb14a3f-d71a-5bdb-ba5b-422482eee79a | note | Acceptance Criteria: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown on the IFC drawings or Manufacturer's Drawings and installation recommendations.
75268e20-2d6f-5f00-975c-442771ed76dc | note | Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
3ae19e2c-269c-5f3a-b268-a94c357220a9 | note | Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diameter of the bolts can pass through freely.
0ad1dd12-7f13-50a1-a6b3-36750695cb34 | note | Where a misalignment is found, heating of bolts, hand flame-cutting of holes or (heat) drifting of holes shall not be permitted, only reaming, milling, drilling or machine flame or plasma cut. Internal surface of the hole to remain smooth and free from burrs.
f6c47dc9-971e-59f6-a4aa-7671126ab93e | note | Holes shall not exceed the greater of:
649ccfaa-7869-5b25-b0ed-4bc44df9a3ea | note | 1.25 x bolt dia. OR bolt dia. + 8mm
dc255afb-5614-5dc0-bf83-888974bc821b | note | Slots shall not exceed the greater of:
d13d8162-6b00-59e9-9b67-dcc2b3f91f73 | note | 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
0884e1a6-c606-577f-ac0d-8f56b47fa79c | note | - - - - - - - - -
ad030fd4-6bb4-5d33-ad36-e8772a220d6a | note | Method: Measure, Visual
3ccaa3c1-de50-50be-8dbd-d5a965321aee | note | - - - - - - - - -
d193e7cc-9911-5a8f-9bd2-0ef3dea1b803 | note | Frequency: Each component
00383d22-387a-5c5f-a3ef-4c53feca7ade | note | - - - - - - - - -
1013dc0d-8f79-5bbe-a17e-9028314acb2f | note | IP
70759ae6-6e47-5ace-8723-da5108de0b6a | note | - - - - - - - - -
a66142e9-6963-5f61-8976-20b7ba89d35b | note | Responsibility: SE/PE/SPE
7bff600b-99b1-5e1f-b72d-7a2899a81623 | note | - - - - - - - - -
e1f96d74-24d3-53fe-bcc9-ff1ab27d57c6 | note | Verifying Documents: This ITP
| checkpoint | 4.4 - Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
3af7f941-17a6-56bb-99c1-8999c2bf0de3 | note | Reference:
de5938fd-6ff4-59b0-babb-6bbda086fdd3 | note | IFC Drawings
0cc61a13-f746-5856-8a07-e931991935bd | note | Manufacturer's Drawings & Installation Recommendations
87e16e75-ffe6-5a1e-aad3-29d9e79c3368 | note | - - - - - - - - -
56e96cf6-c83b-5997-9742-6e5d73b1f9dd | note | Acceptance Criteria: Place bolts, washers and nuts as detailed on the drawings.
f863de1b-449a-5f88-9198-3cd654d037ca | note | Washers shall cover the hole or slotted hole completely by 0.5 x bolt diameter.
92051a01-36c6-5ec0-b259-20f637c11058 | note | Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
a4f00aef-d608-5c13-8e4a-30b4ac84c210 | note | Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
3e2879fa-6fda-5aa8-9ac0-4f3676bbb7bb | note | Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
2f94ad82-11fc-5fbf-ab60-ef96f8ce4788 | note | - - - - - - - - -
fc813b19-f972-5e88-9f22-54f27c5c033c | note | Method: Measure, Visual
9144d54b-840a-5f5e-be96-95e9877f1e71 | note | - - - - - - - - -
73e59eea-542f-5a50-b16f-989b96bfe076 | note | Frequency: Where applicable, each bolted connection
789cfa90-507d-56e3-b0f7-b1f84c27232c | note | - - - - - - - - -
a95071b4-cc5e-58e9-982e-e15d98bffe8d | note | IP
b328a092-6f24-546f-9309-f442aa125136 | note | - - - - - - - - -
8eafef44-1dfd-5173-8698-c82792eaeccd | note | Responsibility: SE/PE/SPE
ed5e5b03-975b-5d6b-a96b-3b848886ae7c | note | - - - - - - - - -
b04d1f71-31e2-5345-b410-7f64f824c63d | note | Verifying Documents: This ITP
| section | 5 - Post-installation Activities
| checkpoint | 5.1 - Inspection of Coating
091ab1af-e4fe-5a8e-9997-036e1e987fb0 | note | Reference:
cde0180f-a5b0-58c2-8fcc-0d0e128f916e | note | IFC Drawings
8ca32284-1110-52bf-90cf-398fb159e422 | note | Manufacturer's Drawings & Installation Recommendations
be977175-4ff1-517d-af12-387f4dba9572 | note | - - - - - - - - -
143f4cd8-8f00-5a09-80a0-d76d3203428b | note | Acceptance Criteria: After installation Works are complete, inspect the steel element for damage to the coatings.
36523afa-b802-5d68-956e-5a49ef57bb70 | note | Where damage exists, it shall be repaired using an approved repair procedure.
570a9bf9-3b8e-5efb-aa6c-04ffffbc15d9 | note | - - - - - - - - -
97588797-45a0-5c33-9e58-df3fe12e3854 | note | Method: Visual
85e48353-378c-5ff8-a4dc-1785bb24897d | note | - - - - - - - - -
156e07c1-ac70-58a4-8fc1-3e311601c916 | note | Frequency: Each component
ac739981-738a-539e-8ab5-1f1333422ba5 | note | - - - - - - - - -
bcf75ffa-c8f5-57a8-bc1d-fade4e80763c | note | IP
a1fba726-a2fc-5318-a9d5-117c09a06845 | note | - - - - - - - - -
6543fa16-65bc-5eab-bb8b-1680291f4e08 | note | Responsibility: SE/PE/SPE
6efa2e99-fd7e-5ef8-9214-f1b22aac15a2 | note | - - - - - - - - -
3ef4c8b3-9961-52f4-96e9-e9b9a8edb5b4 | note | Verifying Documents: This ITP
| checkpoint | 5.2 - As-built Survey
c428dd4c-9937-5a2b-a9d9-4ae6102e606f | note | Reference:
7e90afb3-34b6-569e-909b-2823f3f96476 | note | IFC Drawings
880327e8-2a66-50ff-a5cb-5a8c8cfe5721 | note | Manufacturer's Drawings & Installation Recommendations
82d2451b-4836-5630-82c7-283ba1bcbcd9 | note | AS5100.2
b6286136-8a17-52a3-9d19-73e1c35bb456 | note | AGRD, Part 6A, Clause 5.5.3
f1ec3096-3bce-5a3d-86f6-a635dae1f630 | note | Fulton Hogan Quality Management Plan
7dd96e30-a33f-5541-8db4-e200ed8bf9db | note | - - - - - - - - -
de54df54-3e44-5cef-811a-c43165fc9c5c | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
962fe481-3fc6-5769-b2a2-cdc1a8a4814e | note | Mounted on SUPs and veloways:
b983bc75-c31e-501c-9d51-8fdc65c0c92e | note | i. height to rail between 1.2m & 1.4m
968cd7fb-0196-5eb3-9676-6c5fa5a225ff | note | Mounted on bridges and culverts:
99c48fcb-92f0-508f-b689-a6fd8e499aa1 | note | ii. height to rail 1.4m minimum (on bridges and culverts)
6b0deba8-dce5-5a3e-92ae-e4216315ea6e | note | Attach: Survey As-builts / Survey Report
75e746ec-1990-5568-b5b5-f74bc1fa231b | note | - - - - - - - - -
ded32166-e0b9-53e8-9b7e-087d9ae2e2b7 | note | Method: Document Review
aa548bb9-afd8-56a7-a321-b6e557d94739 | note | - - - - - - - - -
be7d1f78-7c0f-551b-a3f6-eec8f091aeb2 | note | Frequency: Each component
fbb6cda3-8a51-5625-95a2-d1a677013b60 | note | - - - - - - - - -
2e5912ab-60a5-5a02-8178-2203527618a6 | note | IP
2902437c-dbbe-5840-be8b-16d2e2039208 | note | - - - - - - - - -
659e2734-0861-5a0f-8ed0-fccee220a3af | note | Responsibility: Surveyor, SE/PE/SPE
1250f8b8-880a-5701-b606-e0aae01587bb | note | - - - - - - - - -
090118d2-5add-5e0c-8217-a738a0e93815 | note | Verifying Documents: This ITP
| checkpoint | 5.3 - Non-conformance Report (NCR) Closure
4ae9d6f2-8382-5401-a018-12a7cc00b2ee | note | Reference:
6e8d7ba4-6b87-5d07-9369-4a5cb9c62c0b | note | Fulton Hogan Quality Management Plan
8df3b89c-66cc-58cc-89d8-1143a64467e4 | note | - - - - - - - - -
f961d9ba-8647-54e4-889b-b2c0c5ff8ee4 | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
a29efc98-c92c-5453-a667-d532236862be | note | - - - - - - - - -
914c2dd3-757b-5f14-9b0b-24a471ab44cf | note | Method: Document Review
61086fd9-95ba-57e6-a662-8fa5f6229f4d | note | - - - - - - - - -
cf40cf38-f345-53a4-8e96-367c0b44c04f | note | Frequency: Once, prior to closure of this lot / element / Work area
58899f90-eb8c-5d71-851c-38ab58dd0342 | note | - - - - - - - - -
9de7e2ea-c65b-52d3-95e1-ee52df6d253a | note | HP*
f5da384e-99a2-5b1c-989f-7c5a6dfa467e | note | - - - - - - - - -
b8804946-c5a9-549e-b0ba-d5adf59b1bb1 | note | Responsibility: SE/PE/SPE
24f85026-767a-55a2-ad3c-65cb6a09ae50 | note | - - - - - - - - -
2c4d4082-b941-585e-8895-a15a80408f28 | note | Verifying Documents: This ITP
| checkpoint | Final Inspection
94ebb300-c87e-58ee-acde-4f130ef0615e | note | On behalf of Fulton Hogan, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
35e64e62-f081-5670-ac8c-bdbafcd72839 | textbox | Print Name:
253d9c3b-c565-5552-80ce-10ccf7ecbd00 | textbox | Position:
e54df967-33b7-5659-8ee2-5dfd5ce8a6ca | date | Date:
d49c81da-1090-5fb2-bed9-6b4f5e5a5080 | date | Work Completed On
| checklist | ITP 0026 - Guardrail Installation | itp | ITP-026-AX-LOT-XXX - Desc | 566c7382-95d1-484c-942e-d6c6de29f556
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Work pack briefing
bcd383ec-725d-5fef-89f9-7b233a21c206 | note | Frequency: Prior to Commencing
d14e8d82-069f-5ca6-8d61-16e966fcc9e6 | note | - - - - - - - - -
362b56d6-4173-516d-83d5-9eec47b67a70 | note | Acceptance Criteria: All personnel on site have been briefed on the relevant work park relating to scope of works.
2962ad50-9403-530e-bb59-f12688a4ad52 | note | - - - - - - - - -
4e94098c-82f3-503d-9983-566b87a58f75 | note | Reference Documents: WP
caf95550-e700-5505-9738-78ad3a7a5bf6 | note | - - - - - - - - -
fab235f1-184a-5754-8189-d7af108291fa | note | Inspection / Test Method: Document Review
3ace1cf7-5a93-5f23-b813-f9dfd6cc73bd | note | - - - - - - - - -
330a3c85-8f21-5e45-aa94-b421b8f82d94 | note | Record of conformity: Work pack signed.
66dac89c-6148-5267-b99b-10ac7724e846 | note | - - - - - - - - -
a1f5034c-a755-5cbd-8b25-a20a26391c2c | note | HP*
debc3640-5943-556a-9abb-49dcbc4a386b | note | - - - - - - - - -
7bce82db-4559-513a-b7ac-9657ddd46c5b | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Check that current revision drawings are being used
82612fc3-dd71-594e-bd03-4c5029315159 | note | Frequency: Prior to Commencing
669a453c-e86e-5c46-b56c-3704c4cbe19e | note | - - - - - - - - -
50abcb5d-5914-50ca-bf8e-8504887c149c | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
c58d0fcf-90c6-571e-a203-5fde322bfa21 | note | - - - - - - - - -
1a603d07-a025-5c79-b925-67bd4ebb614d | note | Reference Documents: Project Drawings / Drawing Register
5204052f-6298-5f36-adc6-ef0796b2128c | note | - - - - - - - - -
c816e42f-898c-5535-b9a3-61087b086941 | note | Inspection / Test Method: Document review
8c505722-17c9-5ad6-b3c0-be7659d907d2 | note | - - - - - - - - -
181724e4-8e62-5641-a924-a06b691428df | note | Record of conformity: Latest Revision Drawings
dc8a1dfb-d880-5164-aba4-f73b59c04668 | note | - - - - - - - - -
32e9b538-f96a-558e-b57c-cc1794e052ce | note | HP*
ddda46f9-e275-5f4f-a263-750d5b69d7d7 | note | - - - - - - - - -
41951338-6314-54f1-a28e-bdf66635acd6 | note | Responsibility: Site Engineer / Site Foreman
| section | 2 - Procurement
| checkpoint | 2.1 - Steel Test Certificates
4a2d8aa4-16aa-59c8-80c8-911a3c42bec6 | note | Frequency: Min 14 days prior to commencing
21c934d0-d6e3-5b1b-a9fe-f6fd72101cdf | note | - - - - - - - - -
e872aea6-5d24-559f-b0aa-9f09bfeb8b4b | note | Acceptance Criteria: Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. All test certificates related to the supply of steel for the works shall be submitted at least 14 days prior commencement of installation.
fd06f89b-b0fc-5307-91d3-cc28eb0fe72c | note | - - - - - - - - -
92921daf-9efb-5ab9-a75b-4438bcadf7b4 | note | Reference Documents: VicRoads Spec. Cl.708.05 (b)
1225c2b2-f329-5894-9838-b3f3ec402dc5 | note | - - - - - - - - -
768872bf-3446-55ea-a954-4da161f2c9b0 | note | Inspection / Test Method: Document review
4cd478a8-faf2-5609-bef3-8ed6f7a94ded | note | - - - - - - - - -
6d0c3728-d452-5c97-8a0e-9288a32bba3c | note | Record of conformity: Data Sheets Material Test Certificates
c735ba5a-0b0b-58f1-b854-9408295eee2e | note | - - - - - - - - -
41e4ed2a-2b15-50dd-8e1b-baf72113e7fa | note | HP
562ea87c-6514-50be-a75d-f46723dee268 | note | - - - - - - - - -
d0eba36e-e1fc-5440-8cc2-19b9ad445d4f | note | Responsibility: Project Engineer/ Superintendent
| signoff | HOLD POINT
| checkpoint | 2.2 - Steel Material Properties & Protection
96996346-101e-505d-8907-8b2fb7041b56 | note | Frequency: Prior to Commencing
dcdd49d1-759f-5c25-a41c-8fc47a2e9936 | note | - - - - - - - - -
72fa97ba-6cda-5fc6-9efa-553d15399f5d | note | Acceptance Criteria: Guard fence steel component shall meet the strength, dimensional tolerances and surface protection as specified in VicRoads Section Cl.708.5.
cb7e99c0-3b60-5480-8503-d259bff37a7f | note | - - - - - - - - -
2a5b953d-560a-5432-aa55-89e4243aa607 | note | Reference Documents: VicRoads Spec. Cl.708.05 (c), (d)
75bd2a20-5ab1-5543-bab7-b937a06dd0b7 | note | - - - - - - - - -
d26eb886-3c44-51eb-b758-740071b82d05 | note | Inspection / Test Method: Document review
31f36cab-84ed-594b-a18d-fa6ec535a228 | note | - - - - - - - - -
a60eccbe-77fc-53ae-a6cf-93919d542892 | note | Record of conformity: Data Sheets, Visual Inspection
de38f3f4-8a2d-51de-89ad-75a163fb48ad | note | - - - - - - - - -
cbc2da1b-2a91-5a36-b215-5ab99ee24b43 | note | IP
2d769534-9193-56d5-a62b-100a58e940a0 | note | - - - - - - - - -
4305beb9-acc2-5def-9b95-c57a3eb104eb | note | Responsibility: Site Engineer
651a3826-a5a2-5be4-826c-7c70a92cdec9 | textbox | Teambinder Approval:
| checkpoint | 2.3 - Identification of guard fence components
71c1d135-722c-59d1-9627-bc80c41544b2 | note | Frequency: Prior to Commencing
63e221f2-a9d9-57b3-a29d-6e26c2a33815 | note | - - - - - - - - -
9f53cf93-fc32-57e8-ac5e-07bc315d65d1 | note | Acceptance Criteria: w-beam sections, both ends of posts and all plastic end treatments to be permanently marked in text not more than 20mm high with: name of manufacturer, batch number or date of manufacture and strength grade and base metal thickness of steel w-beams
9b7d45a8-850c-51bf-8a1f-52b3e836a105 | note | - - - - - - - - -
5fa5f72a-d2e8-575b-87e2-ffe50fa079ff | note | Reference Documents: VicRoads Spec. Cl.708.05(a)
f3a74016-4124-5e4b-b2c3-1778f6045a1d | note | - - - - - - - - -
0436340a-f78b-55d5-a265-dd88fe9dcb83 | note | Inspection / Test Method: Inspection
bda5adb5-12c9-5eba-b76b-8cf2b88b54eb | note | - - - - - - - - -
9a1c2be4-c7ab-594d-b6c3-4c2de73fe443 | note | Record of conformity: Completed Receival & Inspection Checklist (CRU-FH-CL-0001)
32ace884-77b6-5c64-95b2-15e9fc5e53fa | note | - - - - - - - - -
de4fe44a-a65a-5395-ba66-25aadf3e8cdf | note | IP
2117c075-8109-5d1f-b162-f81cbc64fd9b | note | - - - - - - - - -
7d2ba96e-a3d6-5aee-8367-ffe48af9f8d3 | note | Responsibility: Site Engineer
| checkpoint | 2.4 - W-Beam Barrier with non standard requirements or other special measures
67549a3c-74c6-5104-9cf9-6e9b47bafe77 | note | Frequency: Prior to Installation
a488cb08-1fbe-5b91-a958-dd1b6f63e01f | note | - - - - - - - - -
db49c9a1-f781-54e3-b5b2-664b7bbe79d5 | note | Acceptance Criteria: Prior to the installation of any w-beam barrier system where non standard post lengths are required or other special measures (e.g. shallow concrete foundations) are proposed to be used, the Contractor shall provide details of the measures proposed and evidence that the effectiveness of the barrier system will be maintained, for consideration by the Superintendent. Where shallow foundations that require a concrete ground beam are proposed to be constructed, the design shall be proof engineered by a VicRoads pre-qualified consultant.
be2a4e5c-8cd9-56e4-bfe1-9cd7d022c81f | note | - - - - - - - - -
590c82d6-7caf-52eb-b3ea-c049c6844565 | note | Reference Documents: VicRoads Spec. Cl.708.08(a)
5d4762d2-66b4-59a6-b17f-ff69893feddd | note | - - - - - - - - -
3f98b65b-6499-55d5-8bf8-496aaae93ae2 | note | Inspection / Test Method: Document Review
4a8b8f38-0176-5591-b33e-309e3624234e | note | - - - - - - - - -
268fcb1f-a398-50ec-ad12-44262441c9f0 | note | Record of conformity: This signed ITP
10eaf03c-f744-5566-bd9e-6658deb08485 | note | - - - - - - - - -
e8e17d5a-3155-5f88-98cc-a5030530cf43 | note | HP
cc5e67eb-0bfc-54cc-bf9d-8ce89f69dbe3 | note | - - - - - - - - -
31a5c082-48d9-57d6-b347-ba8b4679061b | note | Responsibility: Project Engineer/ Superintendent
| signoff | HOLD POINT
| checkpoint | 2.5 - Concrete mix design (As Applicable)
c78cfd0d-80d3-5a44-b597-fe0246d998a7 | note | Frequency: Prior to Commencing
525d30e1-cd32-57fd-ac3f-1427073a424e | note | - - - - - - - - -
d164f7a6-37f1-5ac3-a579-7953f944a591 | note | Acceptance Criteria: Concrete to comply with the requirements of AS 1379 and VicRoads Section 703, for either: (i) Portland cement-based concrete, N20 strength grade, or (ii) Geopolymer binder-based concrete, 20 MPa strength grade.
bb33bff0-eab3-54d5-8e7b-521867ff22e0 | note | - - - - - - - - -
b8f618bf-34c5-5955-9b71-2b59d1848b1c | note | Reference Documents: VicRoads Spec. Cl.703 Cl.708.05(g) AS1379
ca2b26bd-cb05-5c09-aaee-34cee866b5a3 | note | - - - - - - - - -
dac7a379-ce76-5a7c-9e0c-cc7d837d6941 | note | Inspection / Test Method: Document Review
8a547b3a-a798-57dd-b03a-978288558c90 | note | - - - - - - - - -
bc3c9ade-8cc3-5d57-98ca-dd0dc767d6fa | note | Record of conformity: Mix design approval
c1b55036-dcfa-541f-9242-b1ae548255f1 | note | - - - - - - - - -
0387e5dd-d7e9-5250-8852-2c8ab7fbaf57 | note | IP
3c46cf24-43b8-540b-9756-4f0b2e4bc8c9 | note | - - - - - - - - -
9c2f6a29-d670-5549-b6d2-0f3bf23c3a5b | note | Responsibility: Site Engineer
7a719f8a-bd2d-5f95-83a1-09777c0a763a | textbox | Teambinder Approval:
| section | 3 - Guard Fence Installation
| checkpoint | 3.1 - Approval of location and length
4f2a213f-e552-5974-ab36-e11438eff4e6 | note | Frequency: Prior to Installation
cbad5501-900e-53c0-8b03-145b0b1c51b3 | note | - - - - - - - - -
999715b9-ae82-5dc6-8db5-899a95c357ea | note | Acceptance Criteria: The required location and length of all guard fence shall be confirmed with the Superintendent.
a04bfa85-bc71-5749-91ef-72349797b406 | note | - - - - - - - - -
6b48bb95-8650-51ab-a5fb-febea6a3eeab | note | Reference Documents: VicRoads Spec. Cl.708.08
eb359620-d75f-5f58-8a89-f36b6cffebb2 | note | - - - - - - - - -
eb534451-6070-5e34-bfd4-4e5749d3c64e | note | Inspection / Test Method: Document Review
4744fc3a-31dc-534a-bff7-2f142139f894 | note | - - - - - - - - -
48942932-059e-5beb-a978-fb9b5eac928a | note | Record of conformity: This signed ITP
91f921b2-f702-5614-b0e2-531e303a9082 | note | - - - - - - - - -
b4027443-5f8f-5c1a-a193-dbd943c6cd86 | note | HP
3a095a9f-efe5-54f6-94c4-48e2e81899b0 | note | - - - - - - - - -
d1822bf8-3913-51eb-b837-b4cb747df18a | note | Responsibility: Project Engineer/ Superintendent
| signoff | HOLD POINT
| checkpoint | 3.2 - Survey set-out
3ef3593d-9c50-5c8e-8617-043b077c20e6 | note | Frequency: Prior to Commencing Excavation
52e57c7d-ff9e-589a-bbfb-595e7948e7ac | note | - - - - - - - - -
5ec8f687-1714-563c-a32c-4cdf9650c313 | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
241426fc-bb4e-51e5-ae22-d675a40320b9 | note | - - - - - - - - -
9490da2f-2acb-51ea-8a06-731f8cbf759c | note | Reference Documents: Project Spec. Cl.1190.06 Latest IFC Drawings
80a2d7ba-cc29-5c84-9055-ae5ee8508900 | note | - - - - - - - - -
83ddb3b2-7070-55dd-8308-5385524d08f8 | note | Inspection / Test Method: Testing
e221350a-d764-5481-b464-fff32a36b43a | note | - - - - - - - - -
b1e3045f-547e-5777-a87a-095e542e3ef5 | note | Record of conformity: Survey records & pegs on the ground
59796077-d04d-5b15-9068-95fdfbf40c5d | note | - - - - - - - - -
18468481-cd5a-5643-836d-244b8a10b36c | note | SCP
5d3d0422-06a5-5599-b9d1-0b85b914f60c | note | - - - - - - - - -
80c37412-3da5-559f-8637-a32fdb6fd903 | note | Responsibility: Site Engineer & Surveyor
| checkpoint | 3.3 - Post Installation
52de93e5-205b-58d9-bd1c-2e4ec9f6ce2e | note | Frequency: During construction.
6a2a0dee-1da9-5f8c-ac58-6debcae7687f | note | - - - - - - - - -
df535758-2a45-5730-95dc-0670a5937334 | note | Acceptance Criteria: Posts shall be installed to the depth, line and spacing shown on the drawings. Posts shall be orientated to the direction of traffic as shown on the drawings and must be installed by driving, provided there is no distortion or damage which may reduce effectiveness. If posts cannot be driven, then posts must be installed in holes with the base compacted to the same density of the surrounding soil. Backfill of the post hole shall be with clean, well-graded, non cementitious subbase or base course granular material and compacted to achieve the same density of the surrounding soil
6f5d6032-5f3e-5eb9-80dd-0148c2ab968c | note | - - - - - - - - -
4f469256-ca48-57c3-ba83-44e52fdffeb2 | note | Reference Documents: IFC Drawings VicRoads Spec. Cl.708.08(a)
d727ec8a-bdcd-5011-9968-f8c2d374e561 | note | - - - - - - - - -
d84b7243-0b06-552f-9cd0-e1f4ed40b7bc | note | Inspection / Test Method: Visual Inspection
23e0501d-47b5-5ff6-8118-c62797b316a5 | note | - - - - - - - - -
15f7b76d-9b69-5482-9dee-1144e595f969 | note | Record of conformity: This signed ITP
aa519f30-2dd0-5a43-a71b-f87caa9508e9 | note | - - - - - - - - -
0ab05d75-1bf4-5ee8-a880-ad3678a45c43 | note | IP
2c691c25-e513-5204-86ac-ee5165ba8cbd | note | - - - - - - - - -
771dda74-630f-5fdc-a985-84e3d441d13e | note | Responsibility: Site Engineer
| checkpoint | 3.4 - W-Beams
4a35c716-4ba7-5ee0-b638-dda5da621da5 | note | Frequency: During construction.
227c21f4-430e-5810-a472-da1f805c8a39 | note | - - - - - - - - -
205aa533-8515-55e5-abe5-91ca40400b39 | note | Acceptance Criteria: The w-beam sections shall be lapped so that the exposed ends face away from the near side approaching traffic. The edges of the w-beams section or backing plate adjacent to posts shall be fixed in contact with the post or post blocks and all bolts shall be fully tightened.
30d36714-37e8-5a06-abe7-21d1caa3c31e | note | - - - - - - - - -
08369238-3849-5442-a661-8ec71d24aa4a | note | Reference Documents: VicRoads Spec Cl.708.08(b)
823b251d-6f72-5a4c-bcae-995931001e6b | note | - - - - - - - - -
96b94772-e9ec-58ac-b32c-43462a787bef | note | Inspection / Test Method: Visual Inspection
c8c69bd8-c12e-5111-8e45-752b1c335a73 | note | - - - - - - - - -
b0d3bf7c-0e59-564e-8ecc-8176fd6eb050 | note | Record of conformity: This signed ITP
5197473e-785f-5818-8e5c-0926c65ac515 | note | - - - - - - - - -
702b59f7-bbbf-5f61-acb3-6b85fe061d83 | note | IP
7e9a7c08-e9a5-524f-9db7-21e1cbdefd34 | note | - - - - - - - - -
61f03dba-283b-5884-be9f-d7d8ab46d96e | note | Responsibility: Site Engineer
| checkpoint | 3.5 - Guard Fence Tolerances
4eeb1e79-f65c-5b35-a781-58fa71de0d78 | note | Frequency: During construction.
8de63bc9-1480-50b0-b45d-f530f4367eec | note | - - - - - - - - -
3910c13e-254c-5edb-994a-cffd1edcdd5d | note | Acceptance Criteria: Ensure line and level are within tolerance: true plan position of posts ±20mm, line of w-beams from vertical profile ±10mm, w-beams from horizontal alignment ±20mm, posts from vertical ±15mm, orientation of block and /or post to w-beam +0, -15mm, dimension of holes +50, -0mm, top of bolt head relative to w-beam +5, -0mm, top of rail shall be within 25mm of level and 50mm of line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length.
53744d02-9bb6-52d1-9e2c-e82293c3ce67 | note | - - - - - - - - -
5400553b-1595-53a1-aed1-740b2ac5c29f | note | Reference Documents: IFC Drawings VicRoads Spec. Cl.708.08(d)
e55aad52-aa7b-5b3c-9c7a-6675f1ea5290 | note | - - - - - - - - -
a47b96ce-4c7e-50bb-8074-09347be49115 | note | Inspection / Test Method: Verify
92920c52-864c-5429-bcdc-45d505d175a2 | note | - - - - - - - - -
228a1db4-045e-55f6-9224-c7bafc43e469 | note | Record of conformity: Survey Records
367b020a-dec9-5fee-9882-4fdf3ae9da8e | note | - - - - - - - - -
1c3cd551-578b-59ee-9ad6-4abc34b7ed96 | note | SCP
93374db2-7ff7-5578-a930-8ec095c3a1b9 | note | - - - - - - - - -
e478a97b-51b4-582b-9628-f695e047f7cb | note | Responsibility: Site Engineer
| section | 4 - Concrete Maintenance Strip
| checkpoint | 4.1 - Dimensions and set-out
d36bdc20-9694-5d42-a59a-a3ec12dc6c17 | note | Frequency: After installation of guardrail
08f3aaf8-d5aa-54d6-86c5-2ae37199b2e4 | note | - - - - - - - - -
47ccafcf-f63c-5bcb-a8dd-e466c1858d86 | note | Acceptance Criteria: The concrete maintenance strip shall be placed parallel to the barrier, such that it extends a minimum of 300 mm clear of the rear of the post and 300 mm clear from the face of w beam. It shall be constructed with minimum 2% crossfall away from the road and shall be flush with the adjacent ground level so the finished level does not impede road runoff.
4d9df998-ba07-57ef-9ca2-d17b0b96d3a9 | note | - - - - - - - - -
55518ed9-6396-56c5-b0df-991804ae4d5d | note | Reference Documents: VicRoads Spec Cl.708.12
4f72dc8b-f5bd-544d-9963-9c00db386912 | note | - - - - - - - - -
37ab02e9-924f-5098-b635-ea8d5a3f26d1 | note | Inspection / Test Method: Visual Inspection
11ef753c-484d-5dde-a793-ed544033f2de | note | - - - - - - - - -
4d706467-63e9-5e63-9602-870806ea6fde | note | Record of conformity: This signed ITP
d5252230-1046-5f1c-bd7e-a04f27f2ff18 | note | - - - - - - - - -
efe73942-1fa1-5736-abe3-01a24aa03e89 | note | IP
35ef8e2e-20c4-5bac-a314-88ec46d7ef3e | note | - - - - - - - - -
273e1bfc-0cc4-5dc6-b727-5085fd616d26 | note | Responsibility: Site Engineer
| checkpoint | 4.2 - Bedding and concrete
019f5866-f0d2-5ace-b402-99af56465ec8 | note | Frequency: After installation of guardrail
6d2a049e-5dc8-5644-90f1-41ad27d197d5 | note | - - - - - - - - -
c6bda2dd-73f1-5980-a335-b71062e25462 | note | Acceptance Criteria: The concrete maintenance strip shall consist of 75 mm depth of N20 strength grade portland cement-based concrete or 20 MPa geopolymer binder-based concrete conforming to the requirements of clause 708.05(g), on 75 mm of compacted Class 3 crushed rock.
822ada61-8813-5f9f-8823-790becec2e08 | note | - - - - - - - - -
03a3998a-a7d6-5e0a-8c26-e9c537a1c97f | note | Reference Documents: VicRoads Spec Cl.708.12
e30c7d48-36eb-52ce-8e40-fe338d28eb42 | note | - - - - - - - - -
f6735d96-8e25-593c-9669-f3341fd9a4ed | note | Inspection / Test Method: Visual Inspection
4850677d-8234-5662-b1ee-37dcccc65c99 | note | - - - - - - - - -
bb3582cc-2f5b-54bf-aa84-e93d3d751ae9 | note | Record of conformity: This signed ITP
45b2a7e6-a84b-5dba-9953-f558b9888d22 | note | - - - - - - - - -
8a4c733f-600b-5bcb-9eef-6483fd752219 | note | IP
0fbf97ef-d048-55a0-8a65-bcebfd6ba3a9 | note | - - - - - - - - -
ef6bd466-7118-534c-8e28-2808059f2ba7 | note | Responsibility: Site Engineer
| checkpoint | 4.3 - Separation from Kerb
58185e1d-99c5-5ed1-9917-06284b906cc0 | note | Frequency: After installation of guardrail
99e19b8f-8be2-5959-94ee-750f87a1d2cf | note | - - - - - - - - -
5285bbb0-d13d-54fa-96a2-aa09eead30d5 | note | Acceptance Criteria: Where the concrete maintenance strip is adjacent to kerb or pavement, separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative) shall be produced. Full depth expansion joints shall be provided perpendicular to the line of the steel beam guard fence 200 mm each side of every post.
7590c166-00dc-5a22-b2c9-fda3330df3f3 | note | - - - - - - - - -
fa8a8c7f-8750-5235-8c1d-09d8c1191e2b | note | Reference Documents: VicRoads Spec Cl.708.12
49b746fe-fb9b-54de-ac51-308d2ac824d5 | note | - - - - - - - - -
bc3300ed-7cbc-5363-a731-b77ba4189718 | note | Inspection / Test Method: Visual Inspection
f75b8a0f-9a9e-593e-9d93-83140d6891f9 | note | - - - - - - - - -
19f527c6-98b9-537a-b341-bef2180b8691 | note | Record of conformity: This signed ITP
5b3b3d9c-ee27-5aa7-b9e4-218c5d70f946 | note | - - - - - - - - -
1f87d8c5-9913-50bc-9ccf-e975ea4cf4a1 | note | IP
cdaacf61-a41c-585b-8b41-7fa96350fef1 | note | - - - - - - - - -
7efc3d92-af90-5c0a-9d6e-5c9f1ee7ee91 | note | Responsibility: Site Engineer
| section | 5 - Audit
| checkpoint | 5.1 - Compliance Audit of Barrier System Installation
5db1259c-0bdb-59c2-af2e-428fb512c72a | note | Frequency: Prior the issue of the Certificate of Practical Completion
1732d062-817b-54c9-84ee-4e039ec82610 | note | - - - - - - - - -
3fdfbe3d-a1eb-5644-898d-8e96b65c0b72 | note | Acceptance Criteria: A safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract shall be undertaken and a report prepared by the Australian Licensed Supplier of the safety barrier system. A Certificate of Compliance shall be provided certifying the product and for end treatment installed. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
91288a67-1a0b-5f22-962c-befb152a65a5 | note | - - - - - - - - -
ce454fde-3f03-5a00-ad4d-7c35296d1f67 | note | Reference Documents: VicRoads Spec. Cl.708.10 Project Specific Specification PS3090.07(f)
484caffe-9fc2-5a6a-b4d3-3db72dbcfb1f | note | - - - - - - - - -
539accc9-18b2-5f6e-ab3e-b9feb84f5021 | note | Inspection / Test Method: Safety Audit
2faf58c7-c7d3-58cd-8bdd-534d03227ace | note | - - - - - - - - -
3b625ee6-2e86-556e-843e-b650f3579eb0 | note | Record of conformity: Certificate of Compliance for each treatment installed Product and Installation Manual
d6f0005a-73e6-560e-9f46-8216591c189b | note | - - - - - - - - -
37ef39e0-e48e-5b85-a403-c65ae7f82c01 | note | HP
5e3eaa22-741d-5e1e-a881-5baa8a82126c | note | - - - - - - - - -
5a4506ae-272c-5e21-a072-2007a0a64d1e | note | Responsibility: Project Engineer/ Superintendent
| signoff | HOLD POINT
| section | 6 - Completion
| checkpoint | 6.1 - Delineators
f3ee5dc2-696f-57d2-bbe4-388a3bb9c431 | note | Frequency: Once installation of assets completed.
e4af4e62-a674-5e8e-bd53-f2b118acf886 | note | - - - - - - - - -
da5f94d8-6d2c-5781-b1c6-a51be26ea855 | note | Acceptance Criteria: Appropriately coloured delineators fastened to top of w-beam, comprising flexible plastic mounting brackets fitted with 100 cm2 of Class 1A retro-reflective material, as defined in AS/NZS 1906.2 The delineators shall be arranged so that vehicles approaching from either direction at night will only see: Red delineators on the left side of one-way and two-way roadways White delineators on the right side of two-way roadways Yellow delineators on the right side of one- way roadways Delineators not to be installed when the guard fence offset if greater than 4m from the traffic lane.
86f22dde-f3a9-50fa-aeee-15d99e132674 | note | - - - - - - - - -
e05f873f-1be1-54f6-a7db-50101bf4718d | note | Reference Documents: VicRoads Spec. Cl.708.11
72b0c9bc-8f2d-557b-9f40-344b00d8ba4f | note | - - - - - - - - -
52a21a06-4c92-5e26-8d03-2df7fcc744bc | note | Inspection / Test Method: Visual Inspection
e1022277-e745-528c-9b33-53fe3ee47544 | note | - - - - - - - - -
167b6db4-2567-5daf-aaff-c21ca94de9f2 | note | Record of conformity: Site Photos
6497d9c7-55e6-58e1-9a17-b7a6e7f6f6be | note | - - - - - - - - -
6dc9d8be-e0b2-5506-8911-af8fbdae01fc | note | IP
61db144c-3a25-585f-95b3-bcd897bee5d2 | note | - - - - - - - - -
d8d1e000-5c26-5368-aa3f-0df90a36d609 | note | Responsibility: Site Engineer
| checkpoint | 6.2 - Grassing of disturbed areas
927a544c-889d-5fa8-9a66-487531c72de0 | note | Frequency: Once installation of assets completed
4881e0af-4ea1-572e-a3e7-ae1dd622ebf9 | note | - - - - - - - - -
752bfbd6-7fe7-5bb2-b02e-3b66a6cd2d71 | note | Acceptance Criteria: All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser. A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
8cc5a1ba-2d02-5841-ace1-9d51b8a9e0d4 | note | - - - - - - - - -
9e92b691-ae78-5a89-9414-174f60304c04 | note | Reference Documents: VicRoads Spec. Cl.708.20
6d819dd5-4dc1-52a1-a3d4-c0b25a29d675 | note | - - - - - - - - -
de9e32b1-24be-5535-9175-53cce995f06c | note | Inspection / Test Method: Visual Inspection
c4814206-7e16-5412-bf31-3eef02624105 | note | - - - - - - - - -
9404ccf5-1d7a-5cce-a034-0dce14b930e1 | note | Record of conformity: Site Photos
c8370e69-b998-5c8e-97e0-13daae585b16 | note | - - - - - - - - -
a38a2e28-4152-5803-a138-ae98c01add9b | note | HP
d200b612-b630-5aa7-a0f1-1163f9499c14 | note | - - - - - - - - -
6035e71f-dd60-569c-8765-4120856efdde | note | Responsibility: Site Engineer / Superintendent
| signoff | HOLD POINT
| checkpoint | 6.3 - Quality Assurance
95060dd8-c701-5bb1-9c06-83ba105ed90e | note | Frequency: Completion of works
75ce7d51-de3e-52e1-bb6e-3646ecf05a21 | note | - - - - - - - - -
07f1b1c6-ef5f-5535-829b-7ffb2678f2a3 | note | Acceptance Criteria: Submit all quality assurance documents to the superintendent including the following items: (i) As built information including changes to location of traffic barriers on site and details of loads used for assessment and design of any collision protection. (ii) Time and date of when traffic barriers were installed (iii) Certificate of compliance signed by the contractors representative and the licensed supplier, certifying that the proprietary product systems have been installed in accordance with the manufacturers installation manual and this specification.
546cc984-ae77-5148-9f84-35ec8218efff | note | - - - - - - - - -
8ced54b2-c89b-5275-947d-445297fa1956 | note | Reference Documents: IFC Drawings Project Specific Specification PS3090.04
4f62e982-1b94-523e-8e58-2679d51eab2d | note | - - - - - - - - -
6a823d3d-13c6-5e6b-8223-ceed7f3aa9f1 | note | Inspection / Test Method: Document review
92f0e154-9922-531b-981c-ca1d0d444f3a | note | - - - - - - - - -
9c9528e0-0a60-5fe8-9ce2-986e5aa25df6 | note | Record of conformity: As built Records and Certificate of compliance
29c80bc2-51ca-5c8b-a444-d6e2b259946f | note | - - - - - - - - -
f2e2c43e-bffb-5b70-b6eb-b86bd7fb160e | note | SCP
edffd43e-c510-5784-827d-2c463422af11 | note | - - - - - - - - -
9d32f74a-d4b3-58f0-afd9-99dee94e1a1f | note | Responsibility: Project Engineer
| checkpoint | Final Inspection
27f450db-b85b-5c5e-92a9-ca770eda9a91 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9b6c5f93-5d17-5f25-b774-a0ec8306c26f | textbox | Print Name:
76bc44c2-d47d-5f3c-8f42-b77b91508641 | textbox | Position:
319d8c50-a87a-5783-b6b5-53b31a5f2530 | date | Date:
31e0bbbb-36d4-56fe-b231-9afe2a83a655 | date | Work Completed On
| checklist | ITP 0040 - Gas Protection Works | itp | ITP-040-UT-LOT-XXX - Desc | 434f7c4e-fcde-4b90-a0e4-21f3328d4cba
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
a5dce85b-5fbc-50d9-a6f4-08d222aaf242 | note | Frequency: Prior to Commencing
6056eaf4-8ff5-56ac-82e3-96a40572c29e | note | - - - - - - - - -
45d5f042-1f13-5edf-9395-566a2711bb50 | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
29cb3bb0-d98b-51a4-9bea-bcbc9383cdc3 | note | - - - - - - - - -
eda7a460-ab19-5e29-81e8-e28c40634bb0 | note | Reference Documents: PMP Inductions Register
b8ab1f52-8c4c-5d94-afdf-6ab2a987bec9 | note | - - - - - - - - -
4eaf508d-7f4e-5941-a236-8d2f9f62844a | note | Inspection / Test Method: Document review
22022f00-b401-5d2b-9f9a-69a47ea4fc29 | note | - - - - - - - - -
d6425480-3600-5bab-8ef0-9204463f8ca4 | note | Record of conformity: Site induction signed.
281f4071-1547-59ea-936c-8b40b0be724f | note | - - - - - - - - -
0eb31741-1ec5-586a-a93b-d86bbc7092ad | note | AP
bca12838-e24a-5850-afec-b3aefd91a0bd | note | - - - - - - - - -
866a2312-8037-5f81-ae85-02c571a23fb1 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
5c248b42-aeab-511d-a898-9f9b3ddfe032 | note | Frequency: Prior to commencing
3383e6f7-fdb2-5b12-81c5-4ec051e22f3a | note | - - - - - - - - -
29dadb7c-0983-575b-9606-538b62e9be6d | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
464abdd8-27ec-56a4-bd65-59bcbaffabeb | note | - - - - - - - - -
edbf9506-018d-52de-90ce-dc6d0bbd1940 | note | Reference Documents: Health and Safety Coordination Plan
0c964057-7959-5f76-b989-2aa98643cf39 | note | - - - - - - - - -
ccaee862-b4a9-5c5e-bece-c86f934068c4 | note | Inspection / Test Method: Document Review
207ffd24-a563-58d3-b4a5-95adbe60ae1f | note | - - - - - - - - -
e8522089-8d07-5f54-bc86-1d96f82639ed | note | Record of conformity: SWMS(s) signed
a3d831a7-2018-53ef-b17d-ca2bc631bd91 | note | - - - - - - - - -
75724241-d3cd-584e-ad47-1114faf4c497 | note | HP*
7283788d-cccc-5607-b811-7a48fa17dd20 | note | - - - - - - - - -
25b3cf83-ddb5-5a8f-86ad-e356cc388b8c | note | Responsibility: Site Engineer, Site Foreman
| signoff | HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
cf542234-3614-5b81-a646-96b5e2603904 | note | Frequency: Prior to Commencing
841046d1-5249-5fd9-87dd-ef9cca9f2528 | note | - - - - - - - - -
c6a64d86-010e-5894-acd3-d7d88b0077c5 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
e1e35304-8277-5f8b-9cea-6ffed620e07e | note | - - - - - - - - -
bb13ceaf-cc36-57d8-a8ac-8fce50c64967 | note | Reference Documents: Project Drawings / Drawing Register
29236646-cfbd-5e7e-96a5-af2f10a13ee3 | note | - - - - - - - - -
d7f66dc8-4387-55a2-9a85-45f1080d4b5e | note | Inspection / Test Method: Document review
6771573d-55c7-52a8-8173-116e9676b524 | note | - - - - - - - - -
f5b5907c-efc5-5a80-a229-3842d87e422a | note | Record of conformity: Latest Revision Drawings
82cc52e5-6276-5bdd-9994-d88427a1bf8a | note | - - - - - - - - -
fa3a89dc-f94b-5f40-862e-1929c10fac98 | note | AP
b06869e5-d14b-53f3-8bc3-faf397791abc | note | - - - - - - - - -
23d735a0-c73d-569e-897d-d45d4d6476a4 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
54dfbedc-7e44-54ea-8df8-501d715c7cc4 | note | Frequency: Prior to Commencing
5c43a774-ff33-5250-a748-ec3d692d1b0c | note | - - - - - - - - -
43e42398-fea6-5965-bdb1-b6fcd17141a6 | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
6e770e69-617b-5b55-a001-69c4f0e5e66a | note | - - - - - - - - -
33593e63-c2ba-5cfb-96be-df832c2ff0bc | note | Reference Documents: EMP, Site induction
aa8989e0-190c-54c9-8acb-af94aa339498 | note | - - - - - - - - -
a654e6b1-c7c3-534b-a8c9-09e6c12d51cd | note | Inspection / Test Method: Document review & Site inspection
920df541-da50-5631-a63c-2950c687c917 | note | - - - - - - - - -
2abfc106-e7d0-5641-9139-210cf5b32527 | note | Record of conformity: Signed ITP
f26e3561-bdab-56b6-89b8-3d5a5310e470 | note | - - - - - - - - -
f67377d1-6055-540d-b265-0f746f6035c3 | note | IP
de5c988d-1174-568c-ac49-e4b7f6da7fd8 | note | - - - - - - - - -
a4820990-cdb6-5018-8680-de6742b53603 | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
9b520a93-fb28-5cae-a88d-57919bc8dd73 | note | Frequency: Prior to Commencing
f54c7df0-1a82-5e76-a359-5fd8664fc5b8 | note | - - - - - - - - -
764445c3-3939-5824-a98d-aca085c5123b | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
b9c34c19-c45d-5e24-913b-c1a5adf132e0 | note | - - - - - - - - -
b0c9c5c0-b10b-53c5-996e-0b83d5aaf9e3 | note | Reference Documents: MRPV- ITC Delivery Contract
dc92eef3-dc4a-5151-89d4-4b17fd0f0954 | note | - - - - - - - - -
e012e14c-5728-54d6-a1d3-a0e690867459 | note | Inspection / Test Method: Document review
9081b0df-b97c-53d6-b500-2b4c119f0b18 | note | - - - - - - - - -
321b9a2c-0633-5662-b217-09df21fd1fc2 | note | Record of conformity: Signed ITP
6196824f-91f6-5145-a229-319e1b7ed007 | note | - - - - - - - - -
b47f96c8-b58a-5c5a-8dcf-79931cd2e965 | note | AP
f426d2dc-6d4b-5c42-99f5-1f6767d761eb | note | - - - - - - - - -
2311875b-1ca3-5eb0-81a6-148a4fea9939 | note | Responsibility: Site Engineer
| section | 2 - Procurement
| checkpoint | 2.1 - Approved materials ordered.
948513b3-cbef-5e11-96cf-a65bbc43d265 | note | Frequency: Prior to excavate
e8cdbb9b-3665-57a3-8251-ac261a974a1f | note | - - - - - - - - -
5cc5a9dc-7fbe-580c-815d-c0104044006e | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
157824dc-f714-5dba-b1fd-9e6e2d0c114e | note | - - - - - - - - -
f386ff64-d1c4-5aa0-8d49-2ed74ed41899 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
8e154739-9735-52bb-bf14-a579abe77509 | note | - - - - - - - - -
962f6b23-058b-53ba-8daf-5ee5ad532a7a | note | Inspection / Test Method: Site Inspection
919fc636-cfe5-565e-86ce-a3719d53ef32 | note | - - - - - - - - -
39986a0f-79bd-56a5-abc2-2dbec856bb5c | note | Record of conformity: Supplier's Declaration of Conformance.
3ab4a1b5-901c-5d66-b8ce-d42114e658dd | note | - - - - - - - - -
e46b3115-378c-5dbc-a228-066c146260ca | note | SCP
1675c568-3741-5871-bd55-ab430ee183e2 | note | - - - - - - - - -
e0d87231-0a64-5822-ac65-ff6ceca0f559 | note | Responsibility: Site Engineer
| checkpoint | 2.2 - Receival and Inspection of products.
c7c270cb-a744-5f78-92e2-046796cecbbc | note | Frequency: Upon receival
3002420d-f4e7-5d1a-a7c4-8f43446f6a40 | note | - - - - - - - - -
ecf43d79-2b34-560e-ad9a-f47383bd8b75 | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
8480bb78-e8ce-5ca0-bb2e-dd2a7eb34d20 | note | - - - - - - - - -
317c5102-1c9e-5696-8d77-0f6c14d93e0d | note | Reference Documents: Receival & Inspection Checklist
45fb9dc3-e013-5620-aed4-e8c21b99b040 | note | - - - - - - - - -
2ea0c4a7-f1b6-5a96-8bb4-744ac3ca7e93 | note | Inspection / Test Method: Site Inspection
aa858698-af4c-5964-8a91-ee544477737b | note | - - - - - - - - -
e6acdef9-1d88-532e-90c3-9376156bfae1 | note | Record of conformity: Completed Receival & Inspection Checklist
47f35468-9515-5ab7-aeeb-8b4f889b5a65 | note | - - - - - - - - -
88d8b380-fbfc-5d0d-bd77-61b20d4df0bf | note | WP
bae76db0-8036-5760-85ed-a303601de4e7 | note | - - - - - - - - -
28882dbc-7402-5c8d-b3e0-cb71a17b6b43 | note | Responsibility: Site Engineer
| section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
| checkpoint | 3A.1 - Survey set-out
643ecc9c-b57f-5b4c-82d0-57dadbb2690e | note | Frequency: Prior to Commencing
4d602b8d-8468-5781-bd24-48838f304993 | note | - - - - - - - - -
f14f362a-cd6f-5db4-b0ee-15edafce6a1f | note | Acceptance Criteria: Latest available revision used
dabd3de2-ea96-59e0-8264-bdb5a528c1c8 | note | - - - - - - - - -
51096811-fe85-574e-91f9-654ad1228040 | note | Reference Documents: Drawings
64c1a1f9-96fb-5e87-a0cd-a6816f43eb87 | note | - - - - - - - - -
586347e4-1739-502b-ab99-6fad11cc864a | note | Inspection / Test Method: Site Inspection
5035556a-5837-5494-85ad-2be03fb1b7f5 | note | - - - - - - - - -
14b18f73-8b81-5e85-8c8a-e620986cbcf8 | note | Record of conformity: Survey records & pegs on the ground
da6a528b-9b67-588a-87ed-c6df4cbb816f | note | - - - - - - - - -
3c668652-cb9b-5c55-8b1e-982962378cb9 | note | SCP
0b2f6213-806e-59d7-a7c4-7ac5f27f13b4 | note | - - - - - - - - -
73b98680-022d-59fa-a73f-f58bd30e1449 | note | Responsibility: Site Engineer & Surveyor
| checkpoint | 3A.2 - Excavate and expose Pipeline
4426bf33-f40c-50c1-a7d5-a615061a5f59 | note | Frequency: During construction.
f79c2db1-72f3-5164-a763-9c7a47892e75 | note | - - - - - - - - -
c6876a49-6292-57f9-a7af-7615c0a604f0 | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
9f77518a-e7e0-583c-9e14-9c1520444de8 | note | - - - - - - - - -
ab1d919c-0976-5d06-84b5-dd7f8d97f62a | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
9db1839f-03ad-5f33-8fad-9fd48b994e9a | note | - - - - - - - - -
36bdd697-eec3-53ca-8ea5-a1415d860e4b | note | Inspection / Test Method: Document review & Site inspection
6b574ac2-f7b4-59c2-b13c-b868f13a6025 | note | - - - - - - - - -
90bb8f37-e0cd-5912-a769-8b0998d1b639 | note | Record of conformity: Signed ITP
28215bd5-d7b5-5dc4-9138-c4032a2536a7 | note | - - - - - - - - -
bd0627c2-45eb-5d07-b367-52102caabefd | note | AP
75004a74-49c6-55e3-a49f-45538dc4f06e | note | - - - - - - - - -
fd4515dd-5bb5-5ea6-a7ba-cdddf3cca078 | note | Responsibility: Site Engineer
| checkpoint | 3A.3 - Survey pick up
ec072f3b-1ed2-5733-ae60-8508dda36bf7 | note | Frequency: During construction.
495c196f-5d28-5ccd-8bff-73b5acb17863 | note | - - - - - - - - -
9df012fb-b2bc-57fe-a85a-bb08beedce7e | note | Acceptance Criteria: Once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset.
12688a45-3069-56f7-8a7d-509e2d1f4695 | note | - - - - - - - - -
7f972b69-8205-571d-a1aa-8323d978b44a | note | Reference Documents: As Built documentation
123f626d-abde-5db5-81ca-09a987dd28b8 | note | - - - - - - - - -
bf2fe72c-dc58-5fdb-bbf2-bedbd24f1441 | note | Inspection / Test Method: Site Inspection
2e35e74d-9ddc-58cf-8abc-4d0670f45c36 | note | - - - - - - - - -
d45e23b1-795d-5d5b-9f9a-48ef83f9fa99 | note | Record of conformity: Survey records
a07973c2-d045-5e0d-af80-47babc093fb5 | note | - - - - - - - - -
1ccbfbf3-1c18-5cc9-a127-6765e5816718 | note | HP*
056572e2-efcf-5266-8e85-f1227a6da6d0 | note | - - - - - - - - -
c2f08a94-b319-5812-b3a7-bfad5ca5d5d7 | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.4 - Place pipe protection material
ce3eb18d-c714-5fd7-9bdb-399891ac2156 | note | Frequency: During construction.
e1995181-9b00-5d04-86be-51878d40bc6c | note | - - - - - - - - -
96e8613d-0da8-57cd-8f5d-9abb4135f9cc | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - 300mm either side of Pipe, 150mm below pipe and 450mm above pipe. Marker tape to be placed above protection.
6ba176f1-bc7c-5a71-bbc3-e99e4538a103 | note | - - - - - - - - -
8031cda5-5c5c-565c-b13b-c2847ef7f00c | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
e27809b8-e036-5063-9608-b9d87600104e | note | - - - - - - - - -
90e242fb-02c4-5561-a535-b7f7f2d56d7b | note | Inspection / Test Method: Visual
c31db8ad-f545-5534-91a0-9afad1e01087 | note | - - - - - - - - -
5efb3600-ace2-5f47-a438-97c137880e86 | note | Record of conformity: Signed ITP
3102f1c4-a153-5814-9e47-06ebc6a1da90 | note | - - - - - - - - -
f4c1cd25-ff66-54af-997c-80cbc09556c5 | note | WP
ed95c614-5543-50bb-afa1-d5adc699e23f | note | - - - - - - - - -
fa041d2c-c37c-567f-aef5-9547e5dd31b3 | note | Responsibility: Site Engineer
| checkpoint | 3A.5 - Survey pick up - Encasement of Asset
a7b70192-fbcb-5b07-ac1c-f6448c7a4b6e | note | Frequency: During construction.
88f78b34-5935-5359-b48b-5ee3655a0b72 | note | - - - - - - - - -
b0e5dd25-d471-5b67-a130-856eae043bdb | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is complete a survey pick up across multiple points on top of asset protection.
9956b24e-1927-545e-b90f-041e2339d0a4 | note | - - - - - - - - -
6001f6e7-d3fd-5277-848d-dd75db16b5f5 | note | Reference Documents: As Built documentation
103fa29e-bb4a-5416-9134-1cb59d046c57 | note | - - - - - - - - -
14b30791-3391-5491-9cd4-a74622dede1a | note | Inspection / Test Method: Site Inspection
7c659967-a852-5b99-902e-e1da30df93eb | note | - - - - - - - - -
313bd7ca-7926-577c-8907-994dc63b9881 | note | Record of conformity: Survey records
c66ca762-8889-57a0-9b5f-cecdb3c6078f | note | - - - - - - - - -
81331ccd-dab6-5c84-9e8b-6708e7c0cdcd | note | HP*
603ed611-83cf-584e-b523-dd0b04470d98 | note | - - - - - - - - -
3c76e6a4-1fe2-5d6e-99e5-da39d2bc5f4a | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
f872660e-79b1-5c65-a603-f8456e81c6e2 | note | Frequency: Each Lot
8f60d5bf-5b1e-5784-b467-5c14e8fe79ed | note | - - - - - - - - -
c1b8c2d9-37d3-5f0e-a61b-03d5de0afc5b | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase layer - Not less than 98% Compaction Layer directly beneath bituminous surfacing 100% Compaction
17631535-24fa-5f5a-91b4-16153a62cc6f | note | - - - - - - - - -
eabb470e-74d0-56d7-bf2e-91ed69b4829b | note | Reference Documents: VR304 Table 304.08
6c8e93a1-1f73-5b5d-99ae-293dfe4c8c56 | note | - - - - - - - - -
84d7411f-6a5f-5978-baba-b2258c2483dc | note | Inspection / Test Method: Compaction Test
94fff31b-30ab-55ec-a6f2-9f1cf8ebcc61 | note | - - - - - - - - -
72f0e758-8e27-5610-a6b9-d0d6b8646b94 | note | Record of conformity: Test Results
9b8d7987-c64e-5d0a-b7d4-7e0afc6192b9 | note | - - - - - - - - -
ff73b306-6124-5849-be78-4f7d14023845 | note | TP
b74c1e57-35f4-5a2c-9f31-538bd6679dab | note | - - - - - - - - -
af510152-508d-56f7-b115-38b6a7154d88 | note | Responsibility: Site Engineer
| checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
571ab156-05af-5b0c-bf49-65ca2de430ae | note | Frequency: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
aa456df8-a3d6-5335-988a-fcc8db753adb | note | - - - - - - - - -
6e6e768a-78a1-5e35-a5ab-be40eb91b549 | note | Acceptance Criteria: Grading and plasticity testing to be conducted post compaction
a1cc1a39-b079-5c6b-b860-10f909695ea8 | note | - - - - - - - - -
2d59440e-255e-5c5d-8592-cb8291036a9e | note | Reference Documents: VR304 Table 304.08
814f5221-3f3f-5fb4-858d-f69673f582f6 | note | - - - - - - - - -
8475eb59-e17b-58a4-9ea5-01604eabc5d1 | note | Inspection / Test Method: Compaction Test
c64d112d-2720-5e43-b8fc-b7b6a0665e77 | note | - - - - - - - - -
e16c67da-008a-5a75-bb04-b886a5f0ac76 | note | Record of conformity: Test Results
26bb005d-2148-5840-bb56-435986d067e3 | note | - - - - - - - - -
f965be53-fc95-5293-a48d-2ed9c560d320 | note | TP
cf06d49f-e617-5055-b5ae-954c9044533a | note | - - - - - - - - -
58923f55-14e3-5f65-9b3f-df15c9fd8b20 | note | Responsibility: Site Engineer
| checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
a830a5cf-2a29-5651-ad52-68d45f31b035 | note | Frequency: During construction.
eee45d20-496a-544e-bea4-7312ec462e63 | note | - - - - - - - - -
a772d1f0-fad9-5237-a032-423f832024b9 | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG-2126 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
a48ff5f1-1e02-5349-af82-23dde5e085a8 | note | - - - - - - - - -
eb49ef34-2bb1-540a-8744-3cb258d4f652 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
44dce49c-5aab-5c3e-9357-be5c0eb58adf | note | - - - - - - - - -
7f25e4df-674a-5063-b08f-bb8954e0c4ce | note | Inspection / Test Method: Visual & Test Reports
dbce6008-0eed-5f96-a670-83cbeddfafe0 | note | - - - - - - - - -
2a57792e-9b79-56dc-ba3b-8a39f4c44319 | note | Record of conformity: Signed ITP
2f2304a6-08a6-5bb8-8d99-9762ab3abc50 | note | - - - - - - - - -
27199674-4c82-57b1-8a6d-f94031141471 | note | IP
743ec5f7-3934-507f-adc7-8045752af625 | note | - - - - - - - - -
632fbfe4-9b19-57f0-b9fb-55c77eb7ec5f | note | Responsibility: Site Engineer & Superintendent
| section | 4 - Completion
| checkpoint | Test Requisition
cb3d3966-a9e7-5160-835a-80581d133c90 | textbox | Test Requested on
2812f0f9-575c-5095-b2a1-941b6fd5faae | textbox | Location
8f074d86-a8d1-5cad-87e6-dce28ca32b9b | dropdown | Material Type | Type A,Type B,See comments
3e14e837-fcc5-56b2-a283-a61db8f40c2d | dropdown | Material Source | Holcim,Boral,See comments
24c01b45-2fc4-5195-8e31-861a30b72fc5 | tickbox | Compaction Test (Standard)
7b38f9ca-0e22-55a5-8b96-0bf31ab33fc3 | tickbox | Compaction Test (Modified)
24bb656d-cfc9-51eb-88fb-5fe2727cf886 | tickbox | Maximum Particle Test
3fd86082-aacf-5e82-ac4a-76457a449b8b | tickbox | CBR/Swell Test
c0918b70-d646-5187-90b7-4d2e3ee3e297 | tickbox | PI Test
40ff92f5-4f23-5fc0-b060-8252a69f0782 | tickbox | Permeability Test
d78d8b3b-dfc6-5712-9a4a-34a841913de7 | tickbox | Grading
e6000dc2-4b20-5cbb-974d-8e4498514a2a | tickbox | Moisture
fbb86395-922c-5327-b081-30040439a4c1 | tickbox | See comments
e9332f0c-bee9-5446-88d1-c0cc3d87de1d | textbox | Test Level/ Layer
| signoff | Test Requisition
| checkpoint | 4.1 - Surface Reinstatement
b89def98-e8e8-57a9-beb4-bb0c2cef728a | note | Frequency: Completion of works
09442995-3164-5c18-a33e-5aa5a44ce706 | note | - - - - - - - - -
f78b0c35-3987-53db-b1f4-f38ccfe675fa | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
b3c35de9-aab8-564f-a1c1-5d8d4b34db62 | note | - - - - - - - - -
27ef2102-581e-58b9-8087-27df91baddd6 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
4f161ce5-ca24-53ee-a8e4-5edcf433786a | note | - - - - - - - - -
9535e301-5f66-5a35-9616-de1cb60e6757 | note | Inspection / Test Method: Visual
a8ee00db-12ac-5be4-9e13-c4ad98dff8b6 | note | - - - - - - - - -
70e796ed-ad88-5506-850b-eb73b56b9021 | note | Record of conformity: Site Inspection
4b80b3d5-e7d8-5603-93e4-2b18c748cae7 | note | - - - - - - - - -
937b0c27-9c4b-571d-a22a-9271ae48a382 | note | IP
c3f93a8d-465a-54f1-b013-add7231edf8f | note | - - - - - - - - -
c745529e-9c52-5a01-b03b-26831d6af553 | note | Responsibility: Site Engineer & Superintendent
| checkpoint | 4.2 - Survey data captured for as-built purposes
d390fa51-de91-5175-ab91-3b3a619de94b | note | Frequency: Completion of works
f1308124-b6bc-5917-9400-73752cec293b | note | - - - - - - - - -
6df739b0-c238-5fb9-a465-995c7d026491 | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
f4851bde-ef08-581e-b7c9-2bf4eba11fd2 | note | - - - - - - - - -
527f2bf8-7529-5fc1-ac90-2a79947766da | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
cc176986-f91e-527b-b8fb-2943cb67e042 | note | - - - - - - - - -
47bf9d18-faef-576e-9120-a7b05413bbef | note | Inspection / Test Method: Document review
c49b84d0-c810-5579-836f-2f06c0654db6 | note | - - - - - - - - -
62f468f7-64c5-5c89-82e3-2cab6bddb325 | note | Record of conformity: As-built survey records
f1227df4-6c02-5108-a9a6-a4a4ef454ffc | note | - - - - - - - - -
1dafdc7f-c7af-5643-8b42-d439698d4c1d | note | AP
bccdb242-bc1e-5708-bb93-672488a973b8 | note | - - - - - - - - -
044c0a64-17c0-5053-817b-db610076d4b9 | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
393fc759-acd0-5541-bc29-b2ba632de0bd | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
c0beb703-dac0-5f8c-80bc-7ae22f90a774 | textbox | Print Name:
6a9c61a1-ffb5-55c9-abcd-fb2b0f7a0ac5 | textbox | Position:
e447ad69-edc9-57c7-b743-65c89a7b26f3 | date | Date:
90f78467-d547-5571-ace1-3da9d5bf848c | date | Work Completed On
| checklist | ITP 0041 - Water Protection Works | itp | ITP-041-UT-LOT-XXX - Desc | d40a78c4-a119-4ac5-9937-293b64db9f84
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
b131dea4-7060-5337-98d8-4b67c840291d | note | Frequency: Prior to Commencing
7c4873a4-ce18-5cb8-b9a7-380074d0f034 | note | - - - - - - - - -
848cc756-3d16-5bfe-ac42-90098376bfee | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
c9eb1708-59fd-5f21-b194-7f0bb7009249 | note | - - - - - - - - -
87953ca6-70b7-5092-b0bb-160653b2c137 | note | Reference Documents: PMP Inductions Register
239a1e60-238c-5355-838f-3b538b212ea1 | note | - - - - - - - - -
d06d58c7-25d8-5102-a8c2-46f54ed363b6 | note | Inspection / Test Method: Document review
44f7be6c-6313-59d2-8216-bd23dc56f83b | note | - - - - - - - - -
d9ba6d2a-3fc1-59db-8787-f76c152873a9 | note | Record of conformity: Site induction signed.
8532b302-5b6b-58c0-85b7-56fb972ca8fd | note | - - - - - - - - -
b7679fd8-3831-5359-bbb6-ca3b2833723f | note | AP
c30e3075-f19d-5a97-be22-165b57d80551 | note | - - - - - - - - -
3eb12b3d-04f4-5c77-9e88-4ece6c133d8a | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
c2030f98-d6c9-5300-a2b1-700cb9b94dc4 | note | Frequency: Prior to commencing
f2f894ee-7937-5f1b-9368-b8001a37f4ac | note | - - - - - - - - -
107f9853-ceef-5470-b3d4-a983bb6137db | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
da66f60c-d68a-52bd-9b01-e48d7c256e9a | note | - - - - - - - - -
004c547d-6d50-53dd-87a3-d61bc2a42b19 | note | Reference Documents: Health and Safety Coordination Plan
3ac7ff09-4547-5710-b5fa-6a984d1de5bd | note | - - - - - - - - -
fe39fb7a-2f51-54d1-89a9-58b73794cc6a | note | Inspection / Test Method: Document Review
70f114fb-fcd4-5d3b-8072-f959b0f7d9a6 | note | - - - - - - - - -
354c8067-279e-5adc-87b8-bf0b25032f5f | note | Record of conformity: SWMS(s) signed
d490e1c5-ccae-5ebf-af1a-a1ef318d3b3f | note | - - - - - - - - -
37b76164-b4bd-59b5-86dd-1fa369e35f77 | note | HP*
5834c914-9ba7-514b-a0de-28a96db39f64 | note | - - - - - - - - -
26d33566-d643-5672-afa2-52459f099b83 | note | Responsibility: Site Engineer, Site Foreman
| signoff | HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
a276e0e0-310f-54c8-9586-ff7c3e398d48 | note | Frequency: Prior to Commencing
39805658-cad1-5759-98b4-e86f8b678c56 | note | - - - - - - - - -
613c2cb6-389f-5bba-af70-3f9bd7356b87 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
fa938320-2733-54e9-af82-5568154488ea | note | - - - - - - - - -
21a9d48b-5794-5ce5-8287-0e5007dc69b7 | note | Reference Documents: Project Drawings / Drawing Register
2a25e717-0990-5330-b819-95bf7645eca1 | note | - - - - - - - - -
dbe40d67-03e6-5db6-ad98-bc5746351b45 | note | Inspection / Test Method: Document review
4dcd6a3d-b8dc-5e4f-b9f4-1090d4ffcfa4 | note | - - - - - - - - -
6aced582-44b7-59f8-93c2-f3a629ce1fb8 | note | Record of conformity: Latest Revision Drawings
a678ddb3-2636-57cb-85e1-343251b636cf | note | - - - - - - - - -
fbdd7b92-2341-5567-815f-21b3e8d2db11 | note | AP
e83a9a7e-0344-5cee-954b-51a02ec422e0 | note | - - - - - - - - -
d8f21a3c-ab02-556d-84f0-6cca6de7fb97 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
73b8bbbd-29ec-5e68-a05e-e7c0469fe856 | note | Frequency: Prior to Commencing
80ce3c16-54d1-5912-b8c6-2c993b139321 | note | - - - - - - - - -
adc95aa2-c068-5413-b104-cc5f6f9948e3 | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
9fab5559-31cc-5a51-bd1a-cedac28d586a | note | - - - - - - - - -
fac8a329-20e7-5781-ba7d-8b59821904fb | note | Reference Documents: EMP, Site induction
cf47c0bb-66a1-5e85-8c85-329456277613 | note | - - - - - - - - -
c1dc0939-65c7-5a80-b54f-93fa4aae9e3a | note | Inspection / Test Method: Document review & Site inspection
85ef5699-5f2a-5b82-b2f3-63bec9904bf4 | note | - - - - - - - - -
1d7ee3ae-fe70-5ea7-8cfb-d3a47f7e554f | note | Record of conformity: Signed ITP
b042e3e6-8471-5ea1-acbd-3a0911dc4ee8 | note | - - - - - - - - -
5bdc7729-0732-583c-b7e2-e3a160c19e9b | note | IP
cab7d17d-43e5-51d4-8c7f-d7b9f0e6291b | note | - - - - - - - - -
a13019b5-9a37-5490-a968-197212cb3d20 | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
30142dbf-6d59-5c98-9f7c-99cf7fe20b25 | note | Frequency: Prior to Commencing
ce9037e5-6c6f-530c-b651-df11fb0bf57f | note | - - - - - - - - -
e68c9351-b054-515f-9dd7-68f660259b21 | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
b9b4a1fa-8b0e-50a7-a832-7d67497787d9 | note | - - - - - - - - -
fdb2a064-fbff-5e7e-8696-e11c93e1720a | note | Reference Documents: MRPV- ITC Delivery Contract
fbff81eb-ebec-51aa-b0bb-bb88b1b90d1c | note | - - - - - - - - -
7c16f6ce-6783-51e6-a5f1-eae210303325 | note | Inspection / Test Method: Document review
00a512df-2bab-54b1-875a-44db52c7a002 | note | - - - - - - - - -
f94f3ca1-16d9-536b-aa32-5afd5fa04c52 | note | Record of conformity: Signed ITP
be76156d-5956-58d6-80cc-73c906bf5df6 | note | - - - - - - - - -
eafbe0c4-018e-5dff-9734-7fdb85d29b7b | note | AP
474d299c-63be-5452-9e21-d38247d503e9 | note | - - - - - - - - -
9b5beade-4908-51b9-a497-bbd74ac0001c | note | Responsibility: Site Engineer
| section | 2 - Procurement
| checkpoint | 2.1 - Approved materials ordered.
14ba5a61-4632-5fd8-a338-8dc34f670578 | note | Frequency: Prior to excavate
18570bed-fc1e-5e2d-b7dc-1e550737c32d | note | - - - - - - - - -
90093e68-4e08-52f5-9a88-24d31fee10f6 | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
101a6313-2152-547b-94ef-a48d98d6b806 | note | - - - - - - - - -
125e5073-80cc-5804-904b-38e661cbb2c1 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
8ad04686-f7bd-5f57-9509-4bebedf90d38 | note | - - - - - - - - -
c5ee146d-fcba-5908-a4bd-d74edd8f12fe | note | Inspection / Test Method: Site Inspection
dadf2e38-86a1-5261-9a14-d3399b532b82 | note | - - - - - - - - -
e1ff4913-d227-5453-a4ce-e91775cc90f1 | note | Record of conformity: Supplier's Declaration of Conformance.
53482e43-8bb5-5253-9812-08c82a538d2d | note | - - - - - - - - -
93cba574-974d-5dd9-96d8-7c5e4530e166 | note | SCP
b38b2531-edc6-5a26-9bc6-69d6e5a64863 | note | - - - - - - - - -
c2f0166b-9f34-5060-a9da-06e9e335c032 | note | Responsibility: Site Engineer
| checkpoint | 2.2 - Receival and Inspection of products.
1694c1c1-88d2-53c2-97cd-0273424dbaec | note | Frequency: Upon receival
cd8ad6dc-1cb4-5f56-b028-323cf999377b | note | - - - - - - - - -
27a66c63-dd88-53ab-91e2-9963de9e836d | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
5c3d373c-8b4d-5dc8-9e70-bd45a50aecec | note | - - - - - - - - -
742ce207-47a1-565b-9bb2-fee6ece0fd40 | note | Reference Documents: Receival & Inspection Checklist
909d9a52-6ae8-50b1-b167-cb0135657748 | note | - - - - - - - - -
462ecfc7-ea4f-5583-bce7-13356c17da94 | note | Inspection / Test Method: Site Inspection
690b3046-8efa-540c-a44c-154c752a1149 | note | - - - - - - - - -
5d54c6ed-699f-5678-a0f6-2f58b1526654 | note | Record of conformity: Completed Receival & Inspection Checklist
0ce47b38-2e7d-5298-9fde-076cd2ceea8c | note | - - - - - - - - -
d50c3d74-ec25-5c12-a757-bc1438d12586 | note | WP
7b3fa231-67d1-55c8-8ff7-5edea6242afd | note | - - - - - - - - -
1cea5b82-5148-5907-bf20-815614e4fb23 | note | Responsibility: Site Engineer
| section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
| checkpoint | 3A.1 - Survey set-out
a5ef31ef-19d7-566e-ad9d-72cef54474fd | note | Frequency: Prior to Commencing
985ade2a-749c-5470-a897-919ac6b4304b | note | - - - - - - - - -
d38e9765-30a8-5fdf-88b3-8f53e721534f | note | Acceptance Criteria: Latest available revision used
b17ed2b6-8424-5d19-928b-c45c41300dd7 | note | - - - - - - - - -
c6083a2c-a273-57f5-a4f2-eb5ec529784a | note | Reference Documents: Drawings
4988efe9-8c01-5b8a-93eb-07ff82c4f8c7 | note | - - - - - - - - -
1f901470-9e81-5b43-8911-804d0e837b2b | note | Inspection / Test Method: Site Inspection
55aabb69-a250-5a35-af17-68832f8371e5 | note | - - - - - - - - -
77f49ccf-4a8d-5b1a-b254-2c4763cec6da | note | Record of conformity: Survey records & pegs on the ground
afc08682-5fe2-552b-95b4-a8236c86b6e6 | note | - - - - - - - - -
b21c913f-1095-5f81-8406-ecf8c950bf8f | note | SCP
c8e5e502-fa24-5513-b431-2ccae3dff28e | note | - - - - - - - - -
2eedaa38-f387-5142-95d0-b4c0d6f20c06 | note | Responsibility: Site Engineer & Surveyor
| checkpoint | 3A.2 - Excavate and expose Pipeline
d51f8a1d-bc5f-5758-9e46-9cd32145c418 | note | Frequency: During construction.
6f45a9f6-ab85-5c6f-b6b0-92adabed0cb1 | note | - - - - - - - - -
2c25dfe3-1a6a-5500-8b64-26b960d11a53 | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
77be4f5a-9276-5678-b5db-b39956887d24 | note | - - - - - - - - -
535a1b50-0c66-5746-adb8-5bc31480a8bf | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
032ab50e-1822-53be-a027-96de302c0854 | note | - - - - - - - - -
2259abf7-82e6-5c89-a189-93df61bec77f | note | Inspection / Test Method: Document review & Site inspection
e7fa64db-e6ae-56d0-a558-6f451613cda8 | note | - - - - - - - - -
94ddb1cd-3be7-5032-bc2e-ee7242e48a6d | note | Record of conformity: Signed ITP
d75433b2-b3fc-5d7c-a45e-b9c7cbe1f377 | note | - - - - - - - - -
94edf095-4d0a-5e87-89f3-52268e5331fc | note | AP
8ede8405-9f8c-5601-9b1f-e6295c8d7d58 | note | - - - - - - - - -
0e21b44e-13f4-5c1b-8572-94ebecdd34fa | note | Responsibility: Site Engineer
| checkpoint | 3A.3 - Survey Pick up
f1a19da7-68f1-50c7-8e2f-f4bdcc256c17 | note | Frequency: During construction.
552afe6d-fa82-5e56-a187-b8e2eb187e54 | note | - - - - - - - - -
382ef7d7-384e-5730-8b1d-5005b132e904 | note | Acceptance Criteria: Once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset.
93b208b2-7c92-504d-b335-503952aba26b | note | - - - - - - - - -
89f4bc79-ee20-545f-a5c4-be02845a9c47 | note | Reference Documents: As Built documentation
273e39ac-4228-522e-820c-164c6936e06d | note | - - - - - - - - -
2f168490-3d53-5af1-8555-82ca29c5abf9 | note | Inspection / Test Method: Site Inspection
05b93908-c67a-59c9-874a-45d1473d9e04 | note | - - - - - - - - -
7e5b951b-3945-5d52-b32d-ffb26eea9b19 | note | Record of conformity: Survey records
60228357-e11c-5c77-80db-467734fffcbb | note | - - - - - - - - -
2559a74c-95f4-5d05-8fd2-507e2d4a1a8d | note | HP*
1fe152f2-3626-5858-afb7-d23c953d4534 | note | - - - - - - - - -
eb7c8171-fe45-58c6-b732-907e692b92f4 | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.4 - Place pipe protection material
484e9129-5d1e-5d77-a6cd-411d5b254492 | note | Frequency: During construction.
b2f3df9f-4625-5407-b087-4134b3e08f79 | note | - - - - - - - - -
793ca166-ac69-576c-bf7e-45a4f364b933 | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - as per MRWA-W-202. Marker tape to be placed above protection.
1c23f4ef-40f3-5c42-941b-75468424680d | note | - - - - - - - - -
ffac7ccd-effe-5f44-9ba2-dd88933e3fc5 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2116; MRWA-W-202
3e496bc4-9843-5e22-8d0d-a1a2b8bc08ad | note | - - - - - - - - -
7e512442-99f3-5354-9c9d-41b1943ea229 | note | Inspection / Test Method: Visual
f25751d7-97a0-59f0-8894-ab626207ee0b | note | - - - - - - - - -
9aa3083f-94eb-5130-ad08-5a84726bfe9f | note | Record of conformity: Signed ITP
51cfbad9-69f9-5fb4-b18d-0d72f38b2a68 | note | - - - - - - - - -
c14f02f6-f891-5109-a8af-8ae37e8a2d3a | note | WP
08a3e2ae-cf6d-5d44-819e-a6fa2d951599 | note | - - - - - - - - -
d5c7157b-4dfc-52c1-9a02-502b4ebd6f7e | note | Responsibility: Site Engineer
| checkpoint | 3A.5 - Survey pick up- Encasement of Asset
94ce0cd8-c686-54f6-a5ae-39c6858fea8d | note | Frequency: During construction.
1e67e70c-5962-5935-8e1f-5cd79fa9ecd7 | note | - - - - - - - - -
01ae5f67-2cbe-5eaf-98eb-f6f809772e8d | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is to complete a survey pick up across multiple points on top of asset protection
a4f2d7d6-637d-54c6-af4b-afaeca66d856 | note | - - - - - - - - -
829017af-9b65-5ae6-9375-ac56d86d9a8f | note | Reference Documents: As Built documentation
5f29a8fb-0385-503b-81f8-61a052f09bd3 | note | - - - - - - - - -
4231f972-cd47-5d3b-b8e9-44e156063660 | note | Inspection / Test Method: Site Inspection
8cf2a5bf-b755-53b7-a53f-47c1646d0099 | note | - - - - - - - - -
5b2e77f1-afee-540e-b9e9-88ff646e2393 | note | Record of conformity: survey records
cecaca83-5b6a-50e7-865f-29ea58c9e3dc | note | - - - - - - - - -
025ee293-4439-5375-9629-2e82eaeaf78e | note | HP*
ff7adbb4-fe22-5cd1-90ae-1bf81bb23fb9 | note | - - - - - - - - -
99d5cf02-e36e-5696-a677-641e8d9e421d | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
95d9649d-85d5-5470-aa81-945965335d85 | note | Frequency: Each Lot
880c287b-d3c5-5df7-a91a-2327669b2bce | note | - - - - - - - - -
5ecb6feb-5e9e-5dd6-9750-343704b8ee00 | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase layer-Not less than 98% Compaction Layer directly beneath bituminous surfacing 100% Compaction
116db504-a0eb-5b02-917e-ab85b20e39b4 | note | - - - - - - - - -
c33939e7-ad61-5313-8a2a-d100118fef52 | note | Reference Documents: VR304 Table 304.08
ec4595f1-dee4-556a-9860-ccb91017276f | note | - - - - - - - - -
b37c80b1-1f25-5fa0-8175-6a9844ea1f39 | note | Inspection / Test Method: Compaction Test
5a97c601-41a3-5272-8c90-f0fc5db131d3 | note | - - - - - - - - -
1cfef7b2-5c80-587c-9024-7bbacf79836e | note | Record of conformity: Test Results
48609c30-6bba-5608-9a2f-d400bc0a082f | note | - - - - - - - - -
e29c7f47-b466-5598-a8a5-b180b6a6357d | note | TP
bc7cd0df-e147-5d7b-9921-1d729514138a | note | - - - - - - - - -
9d51ef5d-f769-5f3e-b0ea-bf5105e216ce | note | Responsibility: Site Engineer
| checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
046473c4-2de1-5626-80ae-b3a968a8565b | note | Frequency: Refer to table 304.111 for various minimum frequency or testing for Grading or PL
12d6e8e6-747b-5b23-9d95-e4d92456b0f1 | note | - - - - - - - - -
ea07254f-8bc9-51e8-a591-be34db9208d6 | note | Acceptance Criteria: Grading and Plasticity testing to be conducted post compaction
053be9db-9e55-5072-abd1-c9168b56a1df | note | - - - - - - - - -
1c567e74-4091-5c4b-9a1d-e91d528e724c | note | Reference Documents: VR304 Table 304.08
863d0aac-7c2d-5318-9f36-6cd50e8bc908 | note | - - - - - - - - -
1af50f57-6068-5a45-84ee-f06a13f929d9 | note | Inspection / Test Method: Compaction Test
0032af5d-bc91-5738-a655-237620cf10d3 | note | - - - - - - - - -
25fefca3-d31f-5dd6-89d0-51e95a117985 | note | Record of conformity: Test Results
8ba0e943-cac0-5c64-b66c-266e5c66a7fd | note | - - - - - - - - -
d309f0f6-4133-5ad1-8086-928386a21343 | note | TP
9c3a786e-fd79-5a14-a9ee-e5e7f2526f67 | note | - - - - - - - - -
ed6b01a6-f3d1-5f02-a595-323636267f83 | note | Responsibility: Site Engineer
| checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
3ef0ab8d-f0e0-55ed-b1a0-55cfe2df2673 | note | Frequency: During construction.
ff46147e-d28c-5f89-a29a-de7ca7c3774f | note | - - - - - - - - -
687beda9-2255-5712-bed6-9bba27aa1fd8 | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG2126 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
2a0199bd-f863-5954-a246-8ab5e1d3fcf5 | note | - - - - - - - - -
35982683-0ea9-55e6-afab-c7f262e7a70e | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
cb718750-81d5-5a96-bec2-ed32c4616476 | note | - - - - - - - - -
f12b09c5-0d9a-50ff-9b09-9cbada80280b | note | Inspection / Test Method: Visual & Test Reports
97e1bdbe-3372-5583-9a47-e2e50c084a3a | note | - - - - - - - - -
e7509ffd-cade-51af-99b1-28cf3b1d6750 | note | Record of conformity: Signed ITP
fda1f66b-5260-5eca-a87b-56cf8f8e2a2c | note | - - - - - - - - -
a47048a7-0c51-55f6-b538-565070da5dbc | note | IP
025b10a9-4a23-5482-9ac8-a226a35a5f5b | note | - - - - - - - - -
bd5ab417-3adf-5ffe-9f28-6c75f5c1e7b1 | note | Responsibility: Site Engineer & Superintendent
| section | 4 - Completion
| checkpoint | Test Requisition
ab7a4528-397f-5ca3-ba82-9c25b8e109be | textbox | Test Requested on
228c5303-1906-5eba-9bdb-9dfd871b15b0 | textbox | Location
b3155c65-8237-5964-8867-a0ce8640bc21 | dropdown | Material Type | Type A,Type B,See comments
adfaea73-3976-518b-a0a1-01dcb118b376 | dropdown | Material Source | Holcim,Boral,See comments
71718492-a3d2-5942-871b-87cf83009219 | tickbox | Compaction Test (Standard)
3db1803a-8f22-547b-8067-b21a7e942a36 | tickbox | Compaction Test (Modified)
6184f0ba-0bae-500e-a64f-2129285638da | tickbox | Maximum Particle Test
8e8412ae-acae-58bd-aaac-deb5faab995d | tickbox | CBR/Swell Test
4b00e7ae-9cff-5851-8d14-1d0d408d6537 | tickbox | PI Test
92baaa1b-6433-5979-9220-40d0fba59a2a | tickbox | Permeability Test
b9033816-69ff-5482-9987-9763a24bbc27 | tickbox | Grading
7f28e43c-54ac-56b8-a9a5-9a644c6f9b0a | tickbox | Moisture
85f09edd-75d1-5b52-8501-0023dc3c76f8 | tickbox | See comments
bc6faa3f-bae3-5715-a239-c5195d559acc | textbox | Test Level/ Layer
| signoff | Test Requisition
| checkpoint | 4.1 - Surface Reinstatement
be65d777-2412-5ade-96a2-a590c8415649 | note | Frequency: Completion of works
73ec6e5f-bdf8-5145-8f3b-5826422e9247 | note | - - - - - - - - -
4e69b5d2-0bf7-549e-84ea-4b98ed508cd2 | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
c5ca1a06-de98-5481-933d-f650bd0a145f | note | - - - - - - - - -
a5cae9e4-fff6-5eaa-a194-c8001a0db9fc | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
e3bf20e1-1df3-5fda-937d-5900590c87b4 | note | - - - - - - - - -
dcf082c4-3f47-518e-93a4-40d60a1f15df | note | Inspection / Test Method: Visual
fa134e9e-7c77-5c1a-9d29-892d504e1ce2 | note | - - - - - - - - -
2a3c3584-90e9-5f03-a7c2-ebc730f89f82 | note | Record of conformity: Site Inspection
db6a4cb4-87a9-5153-9cda-b22ff89d8d33 | note | - - - - - - - - -
01b43f49-5de3-5508-8274-aa04c3d7a797 | note | IP
dc9c7ca0-f255-57fa-9b01-1fb36a242092 | note | - - - - - - - - -
45fe2137-8919-5c4b-9068-121f4e6e330f | note | Responsibility: Site Engineer & Superintendent
| checkpoint | 4.2 - Survey data captured for as-built purposes
4c892123-ee62-5e90-a9be-a17035da1f27 | note | Frequency: Completion of works
c2e4b60d-e212-579e-a331-aed8a3f5010f | note | - - - - - - - - -
6dc817a6-f1c8-5fa4-9b66-c86bc4dfd0fd | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
4bfca2c7-e388-5a95-bfc2-2200530a29c5 | note | - - - - - - - - -
f6a83e8b-e65f-5659-98ec-f7e8fbef3237 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2126
7b6b202c-9bac-50cd-abb1-e9091b9fe5f6 | note | - - - - - - - - -
98d46d56-a99d-5182-aaa3-cb9fac095819 | note | Inspection / Test Method: Document review
6d21ab52-d565-5ecc-8d5f-44aa383ed1e9 | note | - - - - - - - - -
3c937135-65ba-5745-bd34-2c6fc9d65d23 | note | Record of conformity: As-built survey records
45c64c5c-6722-5078-ab80-a02c01b2380c | note | - - - - - - - - -
a04d4bbc-5544-5350-b888-c58143854c14 | note | AP
98f461c4-3999-559d-a923-c205162e580d | note | - - - - - - - - -
f663a37e-2c86-586b-b400-78a0908b1502 | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
4dde93dc-608f-55ec-bc61-45624228c1cf | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
771a6864-2481-5908-b5d5-702e763e4762 | textbox | Print Name:
859a7ec7-3878-5da0-a602-b06f2168a343 | textbox | Position:
fd010bf4-0ca9-5689-9f69-bd65fcd8e040 | date | Date:
a7012071-a1a6-534a-82cc-70e91b97a431 | date | Work Completed On
| checklist | ITP 0042 - Comms Protection Works | itp | ITP-042-UT-LOT-XXX - Desc | e5db8193-8a06-4551-9a35-1904855a0c9e
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
5977cf84-dce4-56e8-87f0-bfab13417a07 | note | Frequency: Prior to Commencing
670760aa-13e7-531c-9dbb-2461d27fc374 | note | - - - - - - - - -
3137f51e-81c4-5e15-87e7-9e029ed65e6d | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
c79dd234-932e-5b75-aaf2-1517ee83dbcb | note | - - - - - - - - -
da078658-4991-596e-9012-d72cfbaa7e6f | note | Reference Documents: PMP Inductions Register
1d72a602-7afc-5ad2-ac89-dcf38c8d7fca | note | - - - - - - - - -
3c6781ff-f523-5d39-adf1-ed4a8bee80ef | note | Inspection / Test Method: Document review
76cf415d-8442-589e-b623-028cb57cfe62 | note | - - - - - - - - -
0b723ec2-1263-5ada-b265-e51be24c0efb | note | Record of conformity: Site induction signed.
6e39e2a3-e694-5ebe-8011-9419ed390b37 | note | - - - - - - - - -
c69ec5a4-5907-579a-8a01-a074247f3ad5 | note | AP
b3434831-37f1-5048-a19b-067b64f3e54a | note | - - - - - - - - -
42966574-3a63-5c30-afc1-02bde4591822 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
bc46a152-9c65-5ec3-af03-09d5a4313e4a | note | Frequency: Prior to commencing
c7b1886c-3595-5188-92bf-ba3976b5e202 | note | - - - - - - - - -
05d9dbe8-3861-53d9-8c08-cf69fe2e110e | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
a0970032-2ecf-54b8-8730-a70fc1f0d9bd | note | - - - - - - - - -
7d7bd8c3-ebd7-528e-ba7f-c8374b4bce7d | note | Reference Documents: Health and Safety Coordination Plan
51283858-92b5-5e03-93de-5e7f5af58f08 | note | - - - - - - - - -
1a4a4699-804b-5bf4-917b-f6731d0fa54b | note | Inspection / Test Method: Document Review
35799286-d031-50c1-80e4-d5a4a6feab28 | note | - - - - - - - - -
58f1d730-38f4-5dc0-babc-a785dd042637 | note | Record of conformity: SWMS(s) signed
6defb39a-ca66-59ec-95d2-6ab610444b18 | note | - - - - - - - - -
1d8a6b16-e859-5ac2-92e4-18c8618bfa88 | note | HP*
ee6f01be-718c-5ad1-87f7-3cb7d228679d | note | - - - - - - - - -
431e6f42-7390-5f66-b054-7326fc4c9802 | note | Responsibility: Site Engineer, Site Foreman & Superintendent
| signoff | HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
e374e500-a088-5793-a849-2949549d5390 | note | Frequency: Prior to Commencing
00fffbde-729d-54d2-a247-5af4344fcf23 | note | - - - - - - - - -
c851d363-7392-5262-af1b-6b0e28723bb6 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
e90045e6-546d-58dd-b6b6-3ba06d780648 | note | - - - - - - - - -
eb63eb73-968e-50af-91a6-f8c3e81165a5 | note | Reference Documents: Project Drawings / Drawing Register
5acb574b-b713-54a8-b1ff-b81c5f0adf12 | note | - - - - - - - - -
a11d4cdf-5cd5-519c-b461-9c2bcf4ddc40 | note | Inspection / Test Method: Document review
1b1dcd92-11ba-58c2-88ab-a0364955f6d0 | note | - - - - - - - - -
1a883298-f4d7-56d7-a357-8b9ee906d876 | note | Record of conformity: Latest Revision Drawings
dfb031ab-49c5-5b70-be55-6925d60b2245 | note | - - - - - - - - -
a63a303f-4c10-53aa-a901-f516503ca42a | note | AP
9d2c5855-adcf-588a-84d2-daad42ee41b6 | note | - - - - - - - - -
b3e7885e-249d-594d-bef9-4fdcf7143ad3 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
0ebf17a5-e0ec-5fae-b3c1-f9b3e1321c9e | note | Frequency: Prior to Commencing
6c8ef3b4-bec3-50a2-a6f8-3d179210d9f2 | note | - - - - - - - - -
dc06ae9a-2797-5e5e-9562-4ecc12ad702e | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
765b7b85-c7a0-5fa6-95b1-ba61af0a7ff9 | note | - - - - - - - - -
f95e9182-ec0d-5fc2-86c0-95d27dfb8848 | note | Reference Documents: EMP, Site induction
75b43f9f-cc1d-5686-a2f6-48e0a21a8ebf | note | - - - - - - - - -
c29a2c57-e26a-5289-b312-acc65d6d5155 | note | Inspection / Test Method: Document review & Site inspection
ad245197-1ba9-590e-abcd-ab86bfcf7038 | note | - - - - - - - - -
9b951d62-fa7e-5913-a203-8d9239ccf28e | note | Record of conformity: Signed ITP
22d64889-9fd1-588c-99e2-fc82c07e9f63 | note | - - - - - - - - -
6c0047a7-c3b2-5967-ac65-477eedacbb12 | note | IP
e2c21fac-614e-580c-8a20-6c7005b55007 | note | - - - - - - - - -
b153fee5-8379-5861-b593-ee00a4fe2548 | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
706a884c-810e-51fa-aac8-5770bfff11a1 | note | Frequency: Prior to Commencing
84ffb983-08bf-5076-99ce-f0398f41eabe | note | - - - - - - - - -
1e089061-c50a-5c21-ab43-757d76eaab18 | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
7032bf04-7d77-528d-a083-9229f7ae5920 | note | - - - - - - - - -
c102965e-e1cc-5e3e-9540-5fe84ab89295 | note | Reference Documents: MRPV- ITC Delivery Contract
1f18ddcd-e911-5321-a8ca-e357cef68380 | note | - - - - - - - - -
693e5770-d527-57e8-b9fb-33be15e8784e | note | Inspection / Test Method: Document review
d3a7dd75-38a4-551c-ad88-b6a1fafeece5 | note | - - - - - - - - -
6c58eca1-6f95-52bd-ac49-6e95b2ac7465 | note | Record of conformity: Signed ITP
cd3de8d0-7003-5ecc-9ff0-963c55adccbe | note | - - - - - - - - -
c68c2580-9fcf-5afa-8b4d-afdd9659ebab | note | AP
3d8f2e08-0454-575c-9af1-5206defc787e | note | - - - - - - - - -
51ce1732-6aad-5481-8562-b1c603a3cb4c | note | Responsibility: Site Engineer
| section | 2 - Procurement
| checkpoint | 2.1 - Approved materials ordered.
1fb9b6c9-a798-550d-a0a5-a6a53296bab7 | note | Frequency: Prior to excavate
b6ddde2e-cce8-571d-8629-92be6493c4ed | note | - - - - - - - - -
ca456894-85c6-5c6a-812c-c60fb36ac88e | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
2ab20825-16cd-524d-b920-be66c3aa4b70 | note | - - - - - - - - -
e0943827-fb19-54c7-bf95-2d78025c1cc7 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
5ef088bb-c8a7-58ae-bd59-542001e5e871 | note | - - - - - - - - -
a45d152d-b23d-5686-8704-bfc8c6281d6f | note | Inspection / Test Method: Site Inspection
b53548ad-06d1-52aa-ac8c-e3e7ed015dec | note | - - - - - - - - -
d48ec6fc-fdfa-505b-b622-58e779379c3a | note | Record of conformity: Supplier's Declaration of Conformance.
ce9992e1-928d-58fc-a837-0501387094d1 | note | - - - - - - - - -
76eeafd7-5a3c-51a7-b421-0cd5119c17b9 | note | SCP
85a995d0-4a30-5259-9a22-74574a85ff1e | note | - - - - - - - - -
ba7c4b5e-6cc1-5e14-bb1f-ca673f949558 | note | Responsibility: Site Engineer
| checkpoint | 2.2 - Receival and Inspection of products.
48a1a722-d2d6-5d49-9925-862ee761e642 | note | Frequency: Upon receival
f2eb6cec-a96d-50e2-8693-cf45129f6968 | note | - - - - - - - - -
c542ca21-749a-5db6-99fd-ecfa711059ef | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
e5174b7b-c2c0-5017-a42d-7e082af7a6c5 | note | - - - - - - - - -
151797ca-1211-5fd3-82d3-bbd0353c371a | note | Reference Documents: Receival & Inspection Checklist
5e9bd0eb-0c7c-5a41-ba70-b67a3ce3e8a8 | note | - - - - - - - - -
315c4f6c-f065-5375-93ff-97bbf876bb2a | note | Inspection / Test Method: Site Inspection
25768a1e-f09c-549c-b1eb-53d4e5caf24c | note | - - - - - - - - -
3ab8406b-e74a-54cb-a5ab-808640053786 | note | Record of conformity: Completed Receival & Inspection Checklist
ec67d1c1-a370-5a70-9e52-53a8d8f83b62 | note | - - - - - - - - -
f5d56d67-7597-56ce-85ca-41e5467468ce | note | WP
80c8850e-75be-5386-b51d-eed368d3ea3f | note | - - - - - - - - -
2a500b45-dcd3-5f2e-99fd-2cda5152f093 | note | Responsibility: Site Engineer
| section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
| checkpoint | 3A.1 - Survey set-out
7c9e934a-9f05-5c24-af5a-bcf34c6b45d7 | note | Frequency: Prior to Commencing
56de8085-d095-5be8-9265-22476aff5792 | note | - - - - - - - - -
016545ee-1808-5598-b309-bf3383ae1638 | note | Acceptance Criteria: Latest available revision used
eba82a16-e2b2-52cd-b7bc-46223bc5e3a6 | note | - - - - - - - - -
666653e0-da28-5bcd-bedd-6c7ad0c3654f | note | Reference Documents: Drawings
0f844480-2673-5a6d-b6cb-1e1b80d851a2 | note | - - - - - - - - -
aad9c085-9598-5b36-a436-b8df448ebc34 | note | Inspection / Test Method: Site Inspection
6d7b9c33-1490-55c1-ae3c-b9660d65d1be | note | - - - - - - - - -
1ae611ff-b284-56a6-b310-a1bfdd7ad189 | note | Record of conformity: Survey records & pegs on the ground
fdd2b56e-132b-5ef5-b36a-e366017d0fbc | note | - - - - - - - - -
53ef4247-e1ae-5232-bfc2-107cea9c3305 | note | SCP
a839bd97-cfd8-58fc-8f39-f58cb46b57e4 | note | - - - - - - - - -
9815253c-0ff2-5cb7-84ca-819fdab3cdcc | note | Responsibility: Site Engineer & Surveyor
| checkpoint | 3A.2 - Excavate and expose Pipeline
c8535b14-778f-5e3f-9986-dbc5602d3366 | note | Frequency: During construction.
9efccc9d-9eab-5e0a-ad1d-16084e692e80 | note | - - - - - - - - -
b057d594-a65b-5662-989c-d35cd23ea5ee | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
2a1bf6c6-392d-59fe-b26e-f85add183ada | note | - - - - - - - - -
3d0cbab4-1dac-5ac7-8e6b-4ddf2843fdc6 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
6d5150e3-4ed3-5c53-9e89-3aeccc44ef98 | note | - - - - - - - - -
d6b721a8-171f-5a4d-aaf6-40ecf32c2410 | note | Inspection / Test Method: Document review & Site inspection
7872029c-06b0-5175-abe8-9926e9e7d7c4 | note | - - - - - - - - -
a6ab2a08-25cf-5e15-b0b5-268879df82f8 | note | Record of conformity: Signed ITP
a42365c3-58fe-505c-8718-c30c34ae460f | note | - - - - - - - - -
d1f8b06a-5627-54e9-a009-2075576b929b | note | AP
b78b9c59-2b9f-55fe-9635-dbbb8b850326 | note | - - - - - - - - -
ba751286-d56a-5fcf-9523-61a42cb435da | note | Responsibility: Site Engineer
| checkpoint | 3A.3 - Survey pick up
40de84c8-ca8c-5ba6-8b80-aec3c770ac79 | note | Frequency: During construction.
af6bfa2b-9afe-5211-8e2c-c50a6ea2ee7c | note | - - - - - - - - -
96716668-44af-56c1-bbc2-161280448b52 | note | Acceptance Criteria: Once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset
2e9a8c06-8efc-5796-9179-f0bcd8783cb7 | note | - - - - - - - - -
beb4e512-658a-54b3-afbb-64d11c3cc284 | note | Reference Documents: As Built documentation
bc80da29-6c61-545f-bf77-3f091af6ca42 | note | - - - - - - - - -
9d62b863-5ca5-57d2-a716-cba7b97390e5 | note | Inspection / Test Method: Site Inspection
c87a3330-369e-5961-a4e3-859e6babada7 | note | - - - - - - - - -
fdfd7069-ed29-515a-b8ab-3352dacef40a | note | Record of conformity: Survey records
6a2265f2-8886-57d6-87be-54dfc5b72c20 | note | - - - - - - - - -
46aa8961-7bff-5b4d-803a-fa76f173357e | note | HP*
946ef9b3-ed61-555a-b5e2-3a764547057f | note | - - - - - - - - -
64ef5084-9d18-5b1f-9539-9302353428c9 | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.4 - Place pipe protection material
074fe982-20d8-5dd5-b108-f0954a6574de | note | Frequency: During construction.
5fdd29a6-f9c8-56bc-a7ea-d792d450eaab | note | - - - - - - - - -
baf0e076-fbb8-5986-8680-7ec1173e7f62 | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - 400mm width of trench, 100mm below pipe and 150mm above pipe. Marker tape to be placed above protection.
d93158a2-4f1b-5cfb-bc2f-daeb2b4019e3 | note | - - - - - - - - -
27b31d53-b96f-5db6-92de-3c53932801e3 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
f2005665-0ee6-5356-b10e-c93a4cc5ac72 | note | - - - - - - - - -
7c89e5f7-d455-5077-af91-56b63cd8c98f | note | Inspection / Test Method: Visual
1f9562cf-04c5-564f-a881-c39fac5e6739 | note | - - - - - - - - -
62fe6b83-430e-52cb-abf5-7059ed5ec9dc | note | Record of conformity: Signed ITP
879fd5b9-bfdc-53d2-8019-266b52f2beae | note | - - - - - - - - -
661e228e-210c-5f2d-a56d-f06274eef279 | note | WP
0afc664f-468e-5b35-97fe-fce83ffa7c3f | note | - - - - - - - - -
bbc8aa04-f9fb-5ca8-af47-0ae511406189 | note | Responsibility: Site Engineer
| signoff | HOLDPOINT
| checkpoint | 3A.5 - Survey Pick up - Encasement of Asset
9a473809-a83b-5533-b1f2-64b76d8dbe80 | note | Frequency: During construction.
6447f683-8094-53f4-b20e-7d7465e644c2 | note | - - - - - - - - -
4dd8fc17-1484-569c-af3a-36d6fa4b1c9d | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is to complete a survey pick up across multiple points on top of asset protection
39f091e8-b42f-59e8-9c21-e7919dc3787f | note | - - - - - - - - -
2187bd65-a15c-5480-9e5e-dba8d956b552 | note | Reference Documents: As Built documentation
eaf5f6d4-44ae-5824-8ddb-b350574bdb8c | note | - - - - - - - - -
00719488-2850-597d-aead-a27c630daf25 | note | Inspection / Test Method: Site Inspection
1d07d78d-4a13-54d4-bd2d-69a1e17506b6 | note | - - - - - - - - -
f5004f8f-adf8-5aa5-a80d-c9c0adde60fb | note | Record of conformity: Survey records
e21f262d-d8ce-57d6-8118-6761e2e3bc03 | note | - - - - - - - - -
49fadb75-9e87-597e-a629-6f3934a5ffc8 | note | HP*
61422b0d-1db5-5287-9fd8-1e50cb0fbbd5 | note | - - - - - - - - -
e744dddd-37a0-5cb5-a16d-d18d66f30d45 | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
6f0fae11-2d15-5436-ba5d-2bf8f5a3f817 | note | Frequency: Each Lot
291643e7-9c44-5444-b59c-de0f87f7f8db | note | - - - - - - - - -
c363da58-1359-53f1-bc2f-20a82c0d5f82 | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase Layer - Not less than 98% compaction Layer directly beneath bituminous surfacing 100% Compaction
a544175e-5f0b-5185-880a-4243669d07d4 | note | - - - - - - - - -
f7521fe3-ac46-51dd-8401-014ba6f245fe | note | Reference Documents: VR 304 Table 304.08
29c653c9-09df-5ca0-9a57-992a15fbea1f | note | - - - - - - - - -
51c9e4e2-1026-523d-8cf0-6117b256bcf8 | note | Inspection / Test Method: Compaction Test
86b49d45-d48d-5daf-9e29-ac0fcb4b735c | note | - - - - - - - - -
4c006092-b579-5f13-af64-3b0758098c84 | note | Record of conformity: Test Results
5cd8f058-7785-55c5-b95e-ff0e1bb0236e | note | - - - - - - - - -
12dd382e-6eee-5181-a0c3-a33d0de1a355 | note | TP
bee673e3-16df-57fc-8f12-975411781847 | note | - - - - - - - - -
57db4a25-3bce-5fcb-aa02-00affc7e01f5 | note | Responsibility: Site Engineer
| checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
5bb9c051-644b-5f41-b2a4-ec55fb35466f | note | Frequency: Refer to table 304.111 for various minimum frequency or testing for Grading and PL
ef51d2ad-67cd-54e1-8404-494cf4770d8b | note | - - - - - - - - -
7a05cec9-b908-5e27-8b6f-62f396b9ed55 | note | Acceptance Criteria: Grading and Plasticity testing to be conducted post compaction
e5591b25-fe77-50d1-b659-adfdeb23ec3c | note | - - - - - - - - -
b041f36e-2a33-59cf-a25a-1d5338203137 | note | Reference Documents: VR 304 Table 304.09
b34950c4-ef55-53db-a9c1-c71e24e26895 | note | - - - - - - - - -
afa484d3-8b9c-546a-8273-b837c91f7819 | note | Inspection / Test Method: Compaction Test
80633d37-210f-53a6-abee-722755b883db | note | - - - - - - - - -
b71b7adc-dbdb-54df-a841-0ddebc48f06f | note | Record of conformity: Test Results
1b352756-dd32-5e15-a694-bb7fbb512e55 | note | - - - - - - - - -
654ce7f3-7478-522e-9be7-01c53468637d | note | TP
acb17cd5-05f5-5395-ac3b-4f3b3301aea1 | note | - - - - - - - - -
7d25528f-d956-5851-af27-57dc537750e3 | note | Responsibility: Site Engineer
| checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
458ab3aa-8a62-5094-a0bd-502a10638809 | note | Frequency: During construction.
43debd91-4d73-5a34-a5f3-23685575876e | note | - - - - - - - - -
17bd523f-7a7d-5f66-b639-60b842d9b798 | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG2127 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
819b8d05-ffb5-5d8f-b61a-6858e92e070d | note | - - - - - - - - -
8c288616-a2c1-503b-a981-56970e6fbaa3 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
d8353374-21d1-5ae0-a0e3-8ac5e09d23da | note | - - - - - - - - -
92aacbbc-c378-5a20-ab6e-8a1628f88e25 | note | Inspection / Test Method: Visual & Test Reports
e0ef76d9-ff97-506f-95a3-e6607d05e06f | note | - - - - - - - - -
196a3ff8-b008-545c-ab4d-700aaf9ccbdd | note | Record of conformity: Signed ITP
b0fa81f0-cdab-57ed-b878-daa483bb26ee | note | - - - - - - - - -
7e6a0f68-49f5-5994-956c-f4ea5b818218 | note | IP
173cfcce-58ce-5237-b965-59e89d076547 | note | - - - - - - - - -
69f43c81-f03f-5745-800f-dd8463ddff3e | note | Responsibility: Site Engineer & Superintendent
| section | 4 - Completion
| checkpoint | Test Requisition
1c653c2e-fe2d-569b-bc1e-c1ffde3e7008 | textbox | Test Requested on
781a74b7-37ac-56b9-a484-55f06e6dbf14 | textbox | Location
6a4c37e8-b6a1-5e31-9dcf-6c2b90d4ccdf | dropdown | Material Type | Type A,Type B,See comments
58cd4984-6e7f-5ac7-a692-7f128a3e6b5c | dropdown | Material Source | Holcim,Boral,See comments
1fcd9df5-7582-5e74-a8aa-523a8d3952a3 | tickbox | Compaction Test (Standard)
9e8aaea0-f42d-58de-b7d9-616492c4f571 | tickbox | Compaction Test (Modified)
b6146fa3-bdf7-588c-aa01-c6e4cf2df9c4 | tickbox | Maximum Particle Test
c4f8b4c8-3b15-5ebe-bb56-bf250b0d1f43 | tickbox | CBR/Swell Test
a08711a4-4228-5c1f-a572-9d78381e74e8 | tickbox | PI Test
5f9acdd1-803a-5fba-bd19-91fa409e1b65 | tickbox | Permeability Test
2c263634-9f57-5ece-af95-04851578b1d8 | tickbox | Grading
732c7523-b8c6-5cf8-8496-3f7bd8467e9a | tickbox | Moisture
7b640d10-7ead-5187-b140-f813e1630654 | tickbox | See comments
dd02c81f-8dda-52ec-ba35-0f737534031b | textbox | Test Level/ Layer
| signoff | Test Requisition
| checkpoint | 4.1 - Surface Reinstatement
100a6ef3-a2fe-527c-ba7a-5fa8d4c36246 | note | Frequency: Completion of works
ad2743e8-99be-5d36-9ec1-fee177666110 | note | - - - - - - - - -
cc75a14d-a347-5e04-8d70-d1ac5cbc9eb3 | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
c0bb68a3-aeff-53e9-8193-83b03f93e3f9 | note | - - - - - - - - -
f3d0e375-d37f-5b71-945b-202fef7d54b7 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
773868aa-07d1-5a4b-a31f-143a7f703246 | note | - - - - - - - - -
e550f153-17bb-584b-8d97-370dd1198ffc | note | Inspection / Test Method: Visual
d2e5b5f9-bbf3-5857-be62-5dd2777ede52 | note | - - - - - - - - -
b51380c3-fb57-570e-8cf3-b02a9c381d7e | note | Record of conformity: Site Inspection
357992a0-8f5d-5f87-8271-07d97d64b35c | note | - - - - - - - - -
9413b4d3-631b-5b50-aa94-01797bfe2ea1 | note | IP
17b7fade-f6fe-58b5-bf1e-68590f8a8fb7 | note | - - - - - - - - -
748d5d9e-ad10-5631-a47d-2f8298ac91c3 | note | Responsibility: Site Engineer & Superintendent
| checkpoint | 4.2 - Survey data captured for as-built purposes
d13448c7-d29e-5693-b421-04b1b3835aa3 | note | Frequency: Completion of works
d7a7ddc7-3135-57eb-a799-7fe0fac74072 | note | - - - - - - - - -
e3e39824-0ff4-5bd8-8c51-12cabab13da0 | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
3b6e6cf6-95bc-50fa-ae9b-3d04c0a8339d | note | - - - - - - - - -
4607a97e-3df2-5936-bc6a-0f8002fdb419 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
6ef3ca9f-e432-566c-be38-8f01f5884df1 | note | - - - - - - - - -
1337af9d-4fae-5c39-97be-7f385e015f5d | note | Inspection / Test Method: Document review
ab7ce194-80f9-5467-ba14-1472e2cfd7e3 | note | - - - - - - - - -
4cdeb118-19f3-50fa-a799-cfc5bb0e4d10 | note | Record of conformity: As-built survey records
d08655f8-abd7-5638-a604-c24e18b79df2 | note | - - - - - - - - -
53f69d7e-cfee-5c70-93a9-644a6bdbd83a | note | AP
50c1b415-a1fa-5a18-b30e-8b688ac701c5 | note | - - - - - - - - -
42206ceb-6273-5653-8f52-fc023b8f7799 | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
2123716e-b93f-593c-9929-23c2738e408d | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
07ad2f77-97b3-5164-9b35-ff1001a945de | textbox | Print Name:
5f44e8a7-2040-5134-b1ac-0c9120bd4182 | textbox | Position:
8c5070e9-7f84-5708-b180-37bc39e4d9f6 | date | Date:
ba84cd9f-31dd-5fde-911a-59955b4d5dcd | date | Work Completed On
| checklist | ITP 0043 - Electrical Protection Works | itp | ITP-043-UT-LOT-XXX - Desc | e616592a-16ca-430e-9462-0e1d32a621b6
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
3c5cd2e2-b943-5e31-bdce-278c045f54d0 | note | Frequency: Prior to Commencing
e1afeafe-3bf6-5c8f-be08-fb4d1e5e6854 | note | - - - - - - - - -
2572c78e-aae0-5816-a6a5-073a9a3449f8 | note | Acceptance Criteria: All personnel on site have been inducted to the CRU site
a9470fe2-b5d5-5928-b3e1-085affd928d1 | note | - - - - - - - - -
bd745d6c-d2fd-5e60-8d10-12adf4b98c7b | note | Reference Documents: PMP Inductions Register
09290c6f-e1cd-5882-9ed3-46894b79133e | note | - - - - - - - - -
e5e9b89e-ef78-5b03-9824-d39ee6bb4e9b | note | Inspection / Test Method: Document review
0bd20f42-1f85-57b5-834f-4781b09bbfd8 | note | - - - - - - - - -
e2098667-e227-50f1-a850-61b5f50744a3 | note | Record of conformity: Site induction signed.
3dad20fc-63b8-5223-857e-92bd0e8ab9b6 | note | - - - - - - - - -
1bf39ea5-2c15-5dfc-9c56-fc3204d3ac0d | note | AP
4a5ccee2-5a90-5be6-9a31-b730fa4f4349 | note | - - - - - - - - -
3e310d01-ff5e-590f-beb3-e94b573f5528 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
7b84c6f4-b303-5376-bd4c-fdea304752eb | note | Frequency: Prior to commencing
5f941eca-e37f-55f2-a541-a713cb2288aa | note | - - - - - - - - -
5278d7fa-c0a2-53c8-834e-e06b6256f958 | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
6bebbc9b-57fe-5a07-b308-421af305567d | note | - - - - - - - - -
d6f782ba-71b5-537d-89bb-d047dff96c5b | note | Reference Documents: Health and Safety Coordination Plan
4ddb996a-e870-5cb4-9f71-2f838c9e2411 | note | - - - - - - - - -
db2a8640-147c-5d60-b82f-3ac836d87218 | note | Inspection / Test Method: Document Review
7c3c138c-4cc9-59ba-9016-92abab7fbf69 | note | - - - - - - - - -
5f9b2ec6-48fb-5443-980d-b11c90f46511 | note | Record of conformity: SWMS(s) signed
ca6d773d-efa0-5652-b969-9bed1fba2438 | note | - - - - - - - - -
64eacdb7-886a-5bd0-bd01-b884406e7130 | note | HP*
dec5a761-51b0-5914-ad12-2820c1cfabb1 | note | - - - - - - - - -
e27fd96f-3fb2-5af1-ab82-fc9dbbf41d42 | note | Responsibility: Site Engineer, Site Foreman & Superintendent
| signoff | HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
e93845c7-c6b7-5c01-ac3c-7c0d242cfa2b | note | Frequency: Prior to Commencing
919afead-410e-5828-9f40-4bc6141410b8 | note | - - - - - - - - -
c0eae80c-e880-525f-a125-9e69f0a0941a | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
1bf96c28-ff34-5411-b4e7-b529acee190d | note | - - - - - - - - -
18929d8e-87f9-56c1-af15-9544d137685e | note | Reference Documents: Project Drawings / Drawing Register
5bb16add-5bd7-5dce-912c-7705d232044c | note | - - - - - - - - -
6ef65277-cb92-55c8-aa0c-3467362ff799 | note | Inspection / Test Method: Document review
9c660ff3-1717-5f0f-8951-a6af20665476 | note | - - - - - - - - -
fe42d3f8-01a9-5329-9401-be4bcca0275d | note | Record of conformity: Latest Revision Drawings
9343788a-dd13-5402-a25b-852f85c86bb4 | note | - - - - - - - - -
9388387e-d68d-579d-bf22-949f7ed427d3 | note | AP
91daefc7-99fb-5d66-b5fb-c17578501171 | note | - - - - - - - - -
dd7e5440-f066-5cd5-a8ae-005cb18a7acc | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
c6e759da-2a38-5d72-ae6e-747a9c14baa4 | note | Frequency: Prior to Commencing
e1cf0a87-a393-5517-ada4-aa555a8d1a60 | note | - - - - - - - - -
6ce92a7c-02c0-51f1-b417-3da8e5075bec | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
a7dd1a36-1a00-556d-9567-b22e5d091bf8 | note | - - - - - - - - -
4a15287d-13d9-53b3-a59c-dd396b6ade7b | note | Reference Documents: EMP, Site induction
cc5b17a9-ceee-5b56-9c4d-cc07a4922265 | note | - - - - - - - - -
e74162e0-7f21-5afd-8d64-682a4a643853 | note | Inspection / Test Method: Document review & Site inspection
873c707e-7c79-5953-afae-ee4d162217ab | note | - - - - - - - - -
5ed94c16-3770-5e46-9026-58f7da401016 | note | Record of conformity: Signed ITP
058d97ce-146d-52bf-abd2-9f277188cc58 | note | - - - - - - - - -
e41628db-783e-5df6-a242-a28799c92cef | note | IP
ea8356e7-9eec-5b38-b9e6-2cacf58b0411 | note | - - - - - - - - -
1a435091-2afa-513e-9d73-aa4eb2c89225 | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Confirm suggested Asset treatment has been approved by Utility provider
fc586b9a-463c-5ce2-acc4-73e04a6d273f | note | Frequency: Prior to Commencing
ffc8d62c-c5db-5617-a019-f33ac0003248 | note | - - - - - - - - -
03d81051-02ea-5db6-a3e3-29de7d4f971e | note | Acceptance Criteria: Ensure that adequate notice is given to the Utility Service provider and Superintendent prior to utility asset protection as per PS3120.06 part C Date of Notification: Date of Utility Provider approval:
6370794d-81b0-5469-a9d7-9bfe600ae02d | note | - - - - - - - - -
a788e5e4-0fbb-5cbb-9419-2dce09b55d9d | note | Reference Documents: MRPV- ITC Delivery Contract
a68cea63-efd4-57a5-9fb3-cb5ec8d03ef3 | note | - - - - - - - - -
e80b5c35-0c0e-5b2b-a62c-fcfae9be66c1 | note | Inspection / Test Method: Document review
0c52205d-4aea-5e4a-9f7b-8fb39762f0f6 | note | - - - - - - - - -
9afdc400-baab-53b2-ace8-ae22299ccf8e | note | Record of conformity: Signed ITP
7bceefba-4295-523b-bb78-74dc903bb4f6 | note | - - - - - - - - -
a8195e4d-8873-5997-b513-7ea531c41634 | note | AP
9f96dab2-d0c8-5e55-9fd5-59223939ec2d | note | - - - - - - - - -
a8fdd5b8-d94c-5604-a3d5-c6cd654809be | note | Responsibility: Site Engineer
| section | 2 - Procurement
| checkpoint | 2.1 - Approved materials ordered.
34a943a4-bd4d-554b-b766-87735eee4ef1 | note | Frequency: Prior to excavate
cfbc2953-e4ed-5377-9c23-3f632230ba65 | note | - - - - - - - - -
159c6527-e718-5432-b1e3-faac83175243 | note | Acceptance Criteria: Complying with AECOM Utility Protection Detail Drawings
aa0f15e4-2890-57b8-b22c-9f3de9ccd046 | note | - - - - - - - - -
16a9dcd7-e8a3-558f-8e10-6ac5ad4d92fd | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
b637ec2c-9b67-55ed-81c2-e733a3fdffee | note | - - - - - - - - -
6da0006a-e963-5195-962f-4f1d798a65f0 | note | Inspection / Test Method: Site Inspection
bb855ee5-aadd-5658-b9af-ae414b180c1f | note | - - - - - - - - -
8f5da69b-bcef-5ca1-926c-e0f38157df91 | note | Record of conformity: Supplier's Declaration of Conformance.
4c048ac4-c80c-528b-a019-d631a8a6fd6e | note | - - - - - - - - -
1860259d-cc68-551a-a1fb-aa63eeb08149 | note | SCP
abd006c4-b7b2-574a-ae8d-a35f3595e197 | note | - - - - - - - - -
a3a21b83-fa20-50d0-a4ee-256229e34007 | note | Responsibility: Site Engineer
| checkpoint | 2.2 - Receival and Inspection of products.
82c6cacd-d6f9-5efa-a42a-3e089a44d72b | note | Frequency: Upon receival
a4bedfd2-decd-5cdb-9671-93b4f89c43b9 | note | - - - - - - - - -
80ebfb47-8448-5f44-b26e-9d421b82c3fc | note | Acceptance Criteria: Approved Product and supplier. Right dimensions / specifications. Defect Free.
acb881d3-d70e-5303-9718-1fb043891a0f | note | - - - - - - - - -
b505033e-4bd6-53d6-a4ce-ae52635c6bd0 | note | Reference Documents: Receival & Inspection Checklist
23f6d482-c52b-5599-b475-b4a57c3dfa89 | note | - - - - - - - - -
cf04672f-742c-57d8-bb7d-4b9c5f07ebdf | note | Inspection / Test Method: Site Inspection
42d97771-45d0-5afa-9c78-16c2b4be39a1 | note | - - - - - - - - -
6046c804-1eab-5f33-9fdf-d9a7ec6db430 | note | Record of conformity: Completed Receival & Inspection Checklist
b8872a3d-9aff-584c-a756-eeaffe4f1912 | note | - - - - - - - - -
60600cca-f191-5e2b-9e02-f213ba1ff3c7 | note | WP
53c8630f-2e64-5084-b45f-7b8d7ea19324 | note | - - - - - - - - -
ae1bba8c-a7ee-58f1-8a3a-17631f0c83d7 | note | Responsibility: Site Engineer
| section | 3 - Construction Works - Detail 1 - Stabilised Sand Encasement
| checkpoint | 3A.1 - Survey set-out
a08726ca-14c0-5024-95f5-1212c3c16d99 | note | Frequency: Prior to Commencing
8ca67e1c-ae6e-5869-af2e-c0ceff2063ae | note | - - - - - - - - -
bd367a66-07f9-50a0-b720-a6265b4a3c2a | note | Acceptance Criteria: Latest available revision used
30076c6a-e913-51e5-92ec-698f86fe6708 | note | - - - - - - - - -
46253555-281c-5f26-83bb-88444c63f78b | note | Reference Documents: Drawings
da3cd963-aaca-56ac-9c83-ea94a5532b9c | note | - - - - - - - - -
542148fd-a916-5e81-97dd-d5ea545432b8 | note | Inspection / Test Method: Site Inspection
6e4ea93c-3932-5824-acaa-16c95504d34b | note | - - - - - - - - -
03713635-77fd-5256-822a-88fe72fa042e | note | Record of conformity: Survey records & pegs on the ground
604beaa9-552e-560f-b359-1bebb3f772e7 | note | - - - - - - - - -
7518ac04-ce0c-5953-acd9-2e33d49e3b54 | note | SCP
96cbf395-028b-5b18-850a-aa63ed9c6d00 | note | - - - - - - - - -
28400af7-e6a5-5917-bdb4-c46ff3eccf6b | note | Responsibility: Site Engineer & Surveyor
| checkpoint | 3A.2 - Excavate and expose Pipeline
37156a63-4b5c-5fe5-a35b-c2e26d172b3c | note | Frequency: During construction.
d05ef5f2-0fdc-5d47-bd35-c745e191001d | note | - - - - - - - - -
2e2c79dd-f263-5e63-a2aa-72156771864f | note | Acceptance Criteria: Ensure that the minimum cover requirements, horizontal and vertical alignments are within tolerances.
e6a106f9-ebba-5753-85d8-976479c7efe5 | note | - - - - - - - - -
250ba29d-ab3c-52e1-aec7-41a3136ad7dd | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2116
694c8ddf-d91e-5ae2-aa15-c174ce673092 | note | - - - - - - - - -
5cd44e13-e1b5-56e1-8ef2-079fe6dbc437 | note | Inspection / Test Method: Document review & Site inspection
929d7bff-5f42-5b38-b20b-f9b56b6d4e62 | note | - - - - - - - - -
afb4278e-db80-5dee-aa48-da048e8ee2e0 | note | Record of conformity: Signed ITP
96d6d8d5-296e-5cdc-bae3-01b0efc5a84e | note | - - - - - - - - -
3b5e492b-2f24-5302-91c7-b0a37ffe8301 | note | AP
b97b1a75-f8c3-53e9-88cf-1ee49d20a8ea | note | - - - - - - - - -
a376ec13-ddb7-58bf-a972-98be3c2db4f7 | note | Responsibility: Site Engineer
| checkpoint | 3A.3 - Survey pick up
4273c463-362d-52ad-8e15-b0482938b84c | note | Frequency: During construction.
b8c929c5-23da-5d6f-b044-113809e0829b | note | - - - - - - - - -
9042e5e8-147b-591f-a110-1e8b37c8a79b | note | Acceptance Criteria: once asset has been completely exposed surveyor is to complete a survey pick up at multiple points across exposed asset
f6a4b923-b2e5-5238-b460-a9e7ec0110d9 | note | - - - - - - - - -
b95770dd-0120-56ed-8ba3-5149c7f4c15c | note | Reference Documents: As Built documentation
2828c87c-4674-574e-8f97-d8802f92163d | note | - - - - - - - - -
7a8923a1-7051-5e38-887b-9c3a9ba71c7b | note | Inspection / Test Method: Site Inspection
90edb35f-7e44-53c9-8ea8-51d62844792c | note | - - - - - - - - -
a33444f4-7559-5dbe-bd4a-1eea80baff94 | note | Record of conformity: Survey records
d3ed15d2-ec0a-506b-a28c-32390574356e | note | - - - - - - - - -
135a8f05-5aa8-555e-b8dc-bce19ab66bfb | note | HP*
8d052b6b-cbc5-5613-b6fa-bb962ab49566 | note | - - - - - - - - -
619f14b1-d7ef-5855-acdd-4792044ae565 | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.4 - Place pipe protection material
12523a05-51ce-5eb3-b114-43508694abf3 | note | Frequency: During construction.
28a9e8d6-8112-52a2-8c52-739a5b4c530e | note | - - - - - - - - -
4f237f75-a1a7-552a-933e-ee519326b358 | note | Acceptance Criteria: Detail 1 - Place 5% stabilised sand uniformly along length of pipe, work into place under pipe haunches. Min cover requirements - 400mm width of trench, 100mm below pipe and 150mm above pipe. Marker tape to be placed above protection.
65923cf3-7ea9-5204-a5cb-86f24e5c0b36 | note | - - - - - - - - -
a2fbc8ad-b70b-5839-871b-5a907dff4359 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
28a1b9a2-83cf-5a92-b12c-ed0855838593 | note | - - - - - - - - -
2bb705a9-323f-56ed-b6f0-804c5f578fe7 | note | Inspection / Test Method: Visual
714faa8f-b7a6-573c-bebd-b991f0256e2d | note | - - - - - - - - -
60c2a1fb-6b38-58fe-85d3-f3779415e485 | note | Record of conformity: Signed ITP
c5b74cbf-5982-5a52-9f26-eebf13133342 | note | - - - - - - - - -
f00af42a-e4b7-58cf-b2f0-f405616f54ba | note | WP
4219e952-3e32-593e-aac6-c1ac451a8c24 | note | - - - - - - - - -
cdc4989b-90d5-52b8-b193-a74e66fb0442 | note | Responsibility: Site Engineer
| checkpoint | 3A.5 - Survey pick up- Encasement of Asset
07a7e374-fc76-5dd7-b6cf-063073961dc2 | note | Frequency: During construction.
ea8ca1e0-6ae3-5244-a66a-2a74697fb3b8 | note | - - - - - - - - -
88909c0a-6bf1-5384-af9f-84eb9467ace0 | note | Acceptance Criteria: Once encasement of stabilised sand has been completed the surveyor is to complete a survey pick up across multiple points on top of asset protection
ad167363-8c6f-5138-8a3f-b27d6d49e86d | note | - - - - - - - - -
483bfa8c-9b3e-56c1-ae41-8f82fb821a1a | note | Reference Documents: As Built documentation
8f713892-b40e-59ae-a3f3-c6a28cb2e980 | note | - - - - - - - - -
e7820c10-4060-515b-bf36-c37496ffdc72 | note | Inspection / Test Method: Site Inspection
5e2f5b75-b5da-582d-b327-820a4dc4df01 | note | - - - - - - - - -
b6c9c7ea-d35f-5e57-b761-92c909ab5b27 | note | Record of conformity: Survey records
429b0306-5cd9-5e39-b16a-67c29d93ac7e | note | - - - - - - - - -
4f61612c-577c-57e3-8200-bd83b3f4ab45 | note | HP*
8e8e5361-9413-5b2c-9c13-f9797d6401e5 | note | - - - - - - - - -
fabdd7b3-74cc-54a9-a8de-98e565234157 | note | Responsibility: Site Engineer & Surveyor
| signoff | HOLDPOINT
| checkpoint | 3A.6 - Compaction Testing (where granular material forms part of permanent pavement)
1192b1e9-5516-5e2b-b8db-f442ca1cf290 | note | Frequency: Each Lot
a9c3b1f7-f7a9-5f71-9d4f-b7bb3df81c3a | note | - - - - - - - - -
1187234c-eadb-5460-930c-e5e2d39db100 | note | Acceptance Criteria: Material during compaction shall have a moisture content of not less than 85% Compaction Scale A requirements apply Lower & Upper Subbase Layer- Not less than 98% compaction Layer directly beneath bituminous surfacing 100% compaction
f4410983-19f8-545e-96be-648ebffa5d6a | note | - - - - - - - - -
8b69d0a1-09b9-5b77-8ad6-c9121cce073b | note | Reference Documents: VR 304 Table 304.08
cdf8eb44-4b30-53f1-9468-5ec07a830740 | note | - - - - - - - - -
55a54a17-947a-5ade-9352-169c9fc9372c | note | Inspection / Test Method: Compaction Test
366d0322-84c0-53a6-a053-029be336d326 | note | - - - - - - - - -
ab346c01-25b6-5c2a-9b83-f3b8b2b5dc20 | note | Record of conformity: Test Result
4a6b740c-36e3-5448-8cf9-bdccbaefb9e1 | note | - - - - - - - - -
2654b83f-cf1c-5bfb-bea4-7efe97c463c4 | note | TP
bbf3fdde-e008-5d8a-84c9-cd211828f3b3 | note | - - - - - - - - -
0dedc6de-bbf6-50ad-924b-89a8d14b053a | note | Responsibility: Site Engineer
| checkpoint | 3A.7 - Post Compaction Grading (where granular material forms part of permanent pavement)
9095431d-c047-50d2-86c9-1b2535626f6f | note | Frequency: Refer to table 304.111for various minimum frequency or testing for Grading and PL
9890646e-fe63-56c4-83e0-f40668d7c4e1 | note | - - - - - - - - -
9bb462aa-e82d-5541-af36-f9cdbdbdf0a6 | note | Acceptance Criteria: Grading and Plasticity testing to be conducted post compaction
9a0c74b4-afce-5e7b-a699-69ec39a523ea | note | - - - - - - - - -
4d8cdbaa-64ab-5023-9c68-11595014740d | note | Reference Documents: VR 304 Table 304.09
d8b0696f-7f37-54ea-b642-84bdcfe8c642 | note | - - - - - - - - -
f3ee235e-ea04-5a18-9a49-8b79579afef4 | note | Inspection / Test Method: Compaction Test
b558fd64-5d53-5448-a538-13828ca10322 | note | - - - - - - - - -
ffd08bbc-f889-545b-8a68-0153a97698bd | note | Record of conformity: Test Result
aa62d190-5651-56b0-851e-a5f61264593b | note | - - - - - - - - -
df177034-63b9-5c5c-933b-b83fa1e7ab81 | note | TP
181024d0-2890-56eb-b8cd-cfa1e520f1f8 | note | - - - - - - - - -
ed650d21-ffe1-54f5-b15f-bc7f0c3a419d | note | Responsibility: Site Engineer
| checkpoint | 3A.8 - Backfill Trench (where material forms part of permanent works)
f0ceb052-652f-51b7-baae-5eee55b478cb | note | Frequency: During construction.
6951b08b-d1d3-5e6f-86ac-7222e751bddc | note | - - - - - - - - -
2bde47bd-d7bb-5d41-afc2-d15d68869dd7 | note | Acceptance Criteria: Superintendent approved backfill material is to be used for backfill asp 1145-C201-ACM-CVP-DRG2127 Backfill is to be compacted in layers to achieve specified density uniformly throughout the depth of each layer. Material: Inorganic fill material with 75mm max. stone size (non trafficable) 95% Dry Density Ratio @ 1 test in each 900mm of fill & each 100Lm
7296b91e-e037-5b87-9162-9e1cb4fef8cc | note | - - - - - - - - -
6cdae927-f084-5297-bc3a-24c57971df1e | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
d16a3635-da19-5f57-b0b9-2f6d31f1e821 | note | - - - - - - - - -
4c7566ac-ad68-5967-90e1-e79ae6ff1398 | note | Inspection / Test Method: Visual & Test Reports
8f995ed3-9297-571a-9a20-b7893d6d2784 | note | - - - - - - - - -
34d60867-d851-50c8-97e0-52e40d670442 | note | Record of conformity: Signed ITP
e3cfaa09-6145-566b-a380-38b43d1dc1b0 | note | - - - - - - - - -
6ba5bf41-e890-5010-a6d3-279fb4b96174 | note | IP
037b43a2-0944-5921-9262-8ad4771b942f | note | - - - - - - - - -
208954ae-147a-5605-a6f8-b85e3606387d | note | Responsibility: Site Engineer & Superintendent
| section | 4 - Completion
| checkpoint | Test Requisition
3d053ce1-8cfd-5a7b-bd3d-4fb190767abe | textbox | Test Requested on
286a0826-84a2-5b5e-b059-2863a46bea1b | textbox | Location
37317299-cb66-5832-9c20-da4e874a10bf | dropdown | Material Type | Type A,Type B,See comments
14958777-f1d1-5779-8ecf-92f1e4af4405 | dropdown | Material Source | Holcim,Boral,See comments
02d10ed8-3def-5343-8f3e-7a704462d823 | tickbox | Compaction Test (Standard)
75d6318f-bb56-5046-a3ed-64ffafd9899a | tickbox | Compaction Test (Modified)
b9e85009-e44a-5bc3-afb5-a6bdfedd4610 | tickbox | Maximum Particle Test
f6a18e84-1da3-531f-bfb2-7cf8e913c34a | tickbox | CBR/Swell Test
c54a83b9-d453-51f6-9309-84d64a6fddcc | tickbox | PI Test
b1aa6fad-1be8-515a-bedd-5cb959170e70 | tickbox | Permeability Test
65716a32-f6f1-58d2-99ff-e9be35a26111 | tickbox | Grading
da2fb165-dd90-5831-9e0c-10e51669325e | tickbox | Moisture
9242f0dc-afae-53ca-99e2-667963a4ef09 | tickbox | See comments
44d39716-ccfb-5a52-8846-29161cfc2214 | textbox | Test Level/ Layer
| signoff | Test Requisition
| checkpoint | 4.1 - Surface Reinstatement
398bc2ee-2bc9-5dae-9211-c6266b076d05 | note | Frequency: Completion of works
052b5f7a-14d4-56e8-a2b6-da3c02c86cf9 | note | - - - - - - - - -
a5c1d861-6017-52ff-b413-a1001826c6cd | note | Acceptance Criteria: Surface reinstatement similar to adjacent undisturbed materials, visually accepted by Superintendent's Represented
cef8f171-58c2-57bd-ba0b-a097b0815dc8 | note | - - - - - - - - -
c1c500b0-3f99-522c-8183-d56480ddf713 | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
ffa0997b-4ad9-5b17-8f44-0c30aa61c58d | note | - - - - - - - - -
3ad62202-657b-5baf-89d6-5ad726a6b042 | note | Inspection / Test Method: Visual
ab1cfd2c-539f-55c4-a7ba-b5ecc089a97c | note | - - - - - - - - -
24d4112a-c845-5f63-b795-7303dee17a4a | note | Record of conformity: Site Inspection
304331b0-0d8c-54d2-ae7f-9fae389ab5bd | note | - - - - - - - - -
4fbb7756-daea-5234-92b8-d884df2ad65c | note | IP
fbff98a1-b149-54b4-8097-c83865ad1eeb | note | - - - - - - - - -
c7bee3b8-f14c-59da-8c22-8554855db667 | note | Responsibility: Site Engineer & Superintendent
| checkpoint | 4.2 - Survey data captured for as-built purposes
bf1c2d81-a1e2-5d4a-87e8-cbace83c905b | note | Frequency: Completion of works
5f90a1c8-a07c-5825-b7f3-c0cc80fc99ce | note | - - - - - - - - -
08c62764-7174-5a81-89de-bec2fedfb3bd | note | Acceptance Criteria: As-built Drawings Tolerances as per WSA 02 - 2014-3.1
f041b7a0-fe55-52f8-800b-907c9cb9aab2 | note | - - - - - - - - -
93e57511-e67e-512c-a027-791f5af4c78b | note | Reference Documents: 1145-C201-ACM-CVP-DRG-2127 & 1145-C201-ACM-CVP-DRG-2128
fa771e30-b913-54a3-8e22-fbf2dd4cbb6b | note | - - - - - - - - -
1425a8ef-b5e8-5768-9100-ef64bc7f836c | note | Inspection / Test Method: Document review
a79e9412-38e8-5ef7-a79d-59f0769907d6 | note | - - - - - - - - -
95dce106-0c2d-5585-912d-2fb7bc995bd7 | note | Record of conformity: As-built survey records
3cb897e1-d61e-5381-9998-aa2d55a18f37 | note | - - - - - - - - -
d1f9db6f-b2cc-540d-bc15-43356db5057c | note | AP
77bcc053-2afd-5781-9f31-2fdbd182798c | note | - - - - - - - - -
bb732d2f-48d2-5bb1-8bc4-c80a07b0ba49 | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
d9aa975b-4aff-5775-85e8-05249143c20e | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
9b0ddb46-075b-5a24-bad9-174229bcd99d | textbox | Print Name:
8f919253-1a5b-5138-8e4d-45973cd741e3 | textbox | Position:
ec5ee3a0-991f-5e0d-afaa-6aedef0985f4 | date | Date:
ab832dba-b536-5d85-8a06-1e3094c19973 | date | Work Completed On
| checklist | ITP 0045 - Installation of Traffic Signals | itp | ITP-045-UT-LOT-XXX - Desc | 52a975ec-c750-4831-a360-236ebacac6d5
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
bc9b1ac1-be95-5afd-b288-0ee5896ac88e | note | Frequency - Prior to Commencing
c409cceb-5f22-5b70-bc30-3bc47f2efa6c | note | - - - - - - - - -
829ee597-6f21-5005-9449-06d34c55a99c | note | Acceptance Criteria - All personnel on site have been inducted to the CRG site
3472e516-32b3-551e-8511-8dd19c62fad1 | note | - - - - - - - - -
fd36123b-e0f2-5277-89f2-81f1b8023d7f | note | Reference Documents - PMP Inductions Register
d5f0be26-3ba5-5714-b19c-3b8a491dcc1e | note | - - - - - - - - -
e78feccc-4195-5680-8e97-8a799d3e6203 | note | Inspection / Test Method - Document review
5b24ba77-b915-565b-b300-1acdc8efae0d | note | - - - - - - - - -
53a34937-2e50-5b42-8aff-3ff5252b8465 | note | Record of conformity - Site induction signed.
57f94bc2-b0c5-5a52-9ce2-ba8d79dd619e | note | - - - - - - - - -
307c57ee-38f5-5b24-b63b-266f7d640ac3 | note | IP
ce9b4132-cbf6-57c8-b6f8-4e2a27d9a584 | note | - - - - - - - - -
f60d983a-7dcd-5438-b45c-18677adc5b10 | note | Responsibility - Site Engineer / Site Foreman
0ad2545c-6fe7-5fc7-8fc8-72df5ae6d2ee | note | - - - - - - - - -
84d42be9-b8b8-5556-ab08-0404d50e9dc8 | date | Date Completed:
| checkpoint | 1.2 - Check that current revision drawings are being used
b349009d-6ed1-5a1b-be25-4255e7c3ce7f | note | Frequency - Prior to Commencing
5e41fefc-5465-5c20-97dd-27d55c7e9ee7 | note | - - - - - - - - -
877031e1-de9a-5007-aaf8-7635fdaf76d6 | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
1c93fe0a-2c61-5263-b671-5bc015365054 | note | - - - - - - - - -
de9b2c79-155e-5a20-9ed3-b2f986147356 | note | Reference Documents - Project Drawings / Drawing Register
b649b362-807f-560a-a6a4-1f4447e0e03e | note | - - - - - - - - -
415ede9f-1d63-5e3b-bb50-f0c97c54ca19 | note | Inspection / Test Method - Document review
4e9af4cd-30b8-5cf3-b657-864e9f62afd7 | note | - - - - - - - - -
2875821d-3672-52e7-9299-3bf7b67e8555 | note | Record of conformity - Latest Revision Drawings
63da0948-0970-538f-add8-9a3312240676 | note | - - - - - - - - -
04ede952-6e3d-5c8a-8b9c-233a135e5ee6 | note | IP
6232c9bb-e94d-5593-beb9-079ac7d99488 | note | - - - - - - - - -
8ab53368-397f-5919-909b-2e374bb65d04 | note | Responsibility - Site Engineer / Site Foreman
48df6bf8-5736-5eac-9034-7d4f2126f610 | note | - - - - - - - - -
4bb215c7-c4c1-5ef3-a6f2-6e7ab21574a4 | date | Date Completed:
| checkpoint | 1.3 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
ba98c806-eb97-50be-b652-416f3bb0c3cf | note | Frequency - Prior to Commencing
384906d4-440f-5152-8093-cfdc8d873465 | note | - - - - - - - - -
592c1b04-c0bf-5a81-86b9-80c8147c3180 | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
52bf50b7-d4b8-544c-97af-ff3299e8e430 | note | - - - - - - - - -
d1076647-7e2c-5d41-b724-0263acc94d87 | note | Reference Documents - EMP, Site induction, Project Specification Cl. 1200.03
eea52508-181f-5ad2-b3b9-52ef01ce555b | note | - - - - - - - - -
7dd92a91-8dfe-5faf-a14a-610c90b091ff | note | Inspection / Test Method - Document review & Site inspection
478f4a15-26d3-50b4-b776-b6a89a0bd790 | note | - - - - - - - - -
3a446fb1-f1a2-5fd1-a3a8-ef34591dfae7 | note | Record of conformity - Signed ITP
f31eb526-be3a-5155-8f62-947ec69c2c51 | note | - - - - - - - - -
f8da4179-34bb-5f64-9c3b-7ed2216451e8 | note | IP
7a8e553a-51d2-5ac0-a2ff-00b39b73d2f9 | note | - - - - - - - - -
3d377efd-3268-5035-86b7-2c61b2d28339 | note | Responsibility - Site Engineer
f8d36116-8749-5120-9d19-d6051c9807a4 | note | - - - - - - - - -
1f16ab6a-928e-5628-abae-63fd3131f457 | date | Date Completed:
| checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
87638ccc-198c-5d32-9b68-c09d4f8fdaab | note | Frequency - Prior to commencing
8e266c76-8bca-5623-b9eb-084974459415 | note | - - - - - - - - -
826726fa-1c44-5eed-9f9a-ca06bb151c63 | note | Acceptance Criteria - As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
07cda80c-f1da-5d44-aff0-8d38dcceb835 | note | - - - - - - - - -
2889f99d-40f4-50e4-be04-959d81961e79 | note | Reference Documents - Health and Safety Coordination Plan
5ae6a093-dee6-5182-8ce1-8140bac9eade | note | - - - - - - - - -
f75cca91-cf16-5412-87e7-ae1462cc8232 | note | Inspection / Test Method - Document Review
d95c7ec8-2f05-5734-aa0b-e99c892e8ff8 | note | - - - - - - - - -
4cefa32c-e165-5375-8227-bbfd3c1dac20 | note | Record of conformity - SWMS(s) signed
8c8849e2-0d73-5bff-8ac4-f84e56006888 | note | - - - - - - - - -
2e380ddc-dd79-5b64-8f6a-1b5c8bea8656 | note | IP
36b1b6ff-312e-5043-898a-27379a49196b | note | - - - - - - - - -
b656ca9b-de9c-571a-8054-3ca655a3c72c | note | Responsibility - Site Engineer & /Site Foreman
251dae14-510d-5bc1-a919-b3bc3d4eff4d | note | - - - - - - - - -
5d89cc2b-ff0f-500a-869d-4c4880ef51cf | date | Date Completed:
| checkpoint | 1.5 - Ground Penetration Permit issued
184ecc22-9d19-53d1-9d1a-22cf3ba76cf4 | note | Frequency - Prior to Commencing Work
fd975519-ba48-5ada-ab52-68c03b3d57ad | note | - - - - - - - - -
f892829a-28ca-5f60-8397-31fbca212e3a | note | Acceptance Criteria - Current Ground Penetration Permit signed and specific for the area where works will be executed.
3f9b5506-14df-5f5e-a308-9c492038e389 | note | - - - - - - - - -
7485b168-81ac-5cbe-a490-76503636f8d3 | note | Reference Documents - Excavation Permit
5db36e95-b91c-5219-9708-4f4fa81fbcd0 | note | - - - - - - - - -
8063cac1-c2fb-5431-8825-2adf406f1903 | note | Inspection / Test Method - Document review & Site inspection
9f281c9a-dd45-533a-8a2b-bac3b6682f78 | note | - - - - - - - - -
c66bef9e-f22b-5eb1-ac50-d6882139f2ec | note | Record of conformity - Excavation Permit #
cfbdfd29-0e96-5733-ae55-29a92cb95188 | note | - - - - - - - - -
55aff8de-5fa7-5cfc-bf78-4ab23a9cf8bd | note | HP*
5eb3449c-139b-5b29-a839-89bbfd416f0c | note | - - - - - - - - -
b882800e-51e6-54ea-a426-04ad4b40f8ae | note | Responsibility - Site Engineer
66042783-75e8-5573-bdb9-5c283163e93f | note | - - - - - - - - -
7f4817c9-5270-5376-890d-59b33c8780bf | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Installing Traffic Signals
| checkpoint | 2.1 - Civil Works
3397a726-47ae-5f3f-8000-f0a48bde58db | note | Frequency - Following Preliminary Works
7063d4c9-b9ee-542e-86fa-830498af507d | note | - - - - - - - - -
d71be1c2-c46f-5439-958f-a3304c7c66e0 | note | Acceptance Criteria - Works completed and subcontractor DoT Report completed in accordance with Section 730 & 733 of the Department of Transport Specification
42cb2182-93e1-51f8-97fe-048c33eb27db | note | Pre-installation meeting conducted HP Sec 730.08 c -DoT Pre-Installation Report
affb87ab-29ba-5e74-ba55-735ec83ca2dc | note | Alternative foundations noted in Pre-Installation Report
72e68caf-9f9d-50d5-bb1a-4a5084b324cb | note | HP Sec 730.11-DoT Pre-Installation Report
9263a2f3-8e2c-568c-878a-f515631d92df | note | Proposed boring to be discussed, agreed and noted on Pre-installation report
aefce0b4-ccad-5a4c-a5d2-5e38a8abbad4 | note | HP Sec 733.03 - DoT Pre-Installation Report
da52a84c-10f0-5111-838b-200f8f5ee27a | note | Pre backfill inspections (conduit / foundation) carried out and signed off
2450f77e-3f04-5d5b-808c-8a0bc8b39aea | note | HP Sec 730.11, HP Sec 733.03, HP Sec 733.06 -Healey's ITP FO41 Pit, Conduit, Foundation Installation
0c92a347-608f-5cff-b6d5-46c8a6404cb0 | note | Pit lid Surround pre pour inspection
fa9967e4-92da-5e8e-b434-331078e0e682 | note | HP Sec 733.07 (c) -Healey's ITP FO41 Pit, Conduit, Foundation Installation
5cc71032-a781-5ac9-b70c-7e40815b8ee4 | note | Grouting of bores to be inspected
4127729b-a414-52ad-aeea-f2ac1eefe054 | note | HP Section 733.03 -Healey's ITP FO41 Pit, Conduit, Foundation Installation
3f9536e2-33e8-59fa-9f17-9596f7ca68d5 | note | Concrete testing completed (Slump and Compressive Strength) In accordance with Section 610.16
e36e5620-ecd0-5528-aea9-9e0ca7ff9b8e | note | - - - - - - - - -
a6c98a29-32c7-5ee8-bbe4-50787fb81277 | note | Reference Documents - Healey's ITP FO41 Pit, Conduit, Foundation Installation
a750aae0-b47f-55d5-9156-f9425251b000 | note | (DoT) Pre-Installation Report
d9a8d54c-3273-5a9d-9ca3-cfb68a13b505 | note | - - - - - - - - -
810bd9a8-0141-57f2-aaeb-37fb3edfb10d | note | Inspection / Test Method - Document review & Site Inspection
a7384abf-1970-5020-904b-77d8b1c13c58 | note | - - - - - - - - -
aca20eeb-bb71-54a2-a544-59d735a61ab5 | note | Record of conformity - Signed Pre-Installation Report
0629dac4-7c41-5ce9-bfff-9acc668b65de | note | Completed Healey's ITP FO41 Pit, Conduit, Foundation Installation
8f9c63ce-cd69-568a-8f96-24be53c68186 | note | Concrete test reports
dc980d8c-9d47-5484-ac53-18807e4433af | note | - - - - - - - - -
29cf49f0-ded8-5a13-97dd-b969219c0e68 | note | HP*
8f611838-d348-5529-a91e-8904da12e646 | note | - - - - - - - - -
5d3c0bb3-3b60-5dee-b804-01e093f2ae5e | note | Responsibility - Site Engineer & Sub-contractor
f7d92cc8-0887-5e35-b46d-7bca45b8ecb0 | note | - - - - - - - - -
39fce3db-fcdb-5823-8a1c-537bdee56bce | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Electrical Works
a4721b7a-b310-57b9-adf8-5a5066e06c89 | note | Frequency - Following Civil Works
52563495-41cd-5001-acb6-06a0975d338d | note | - - - - - - - - -
ab850f18-4c28-5d1f-ac58-1ecc1fe352e1 | note | Acceptance Criteria - Works completed and subcontractor DoT Report completed in accordance with Section 730 of the Department of Transport Specification
71f3b7f2-96f2-53af-8024-fd6cfb7c3a67 | note | 1) Traffic hardware inspected HP Sec 730 14 - DoT Pre Commissioning Report.
836cf63d-f8c7-592b-a3ce-930027387270 | note | 2) Cabling Scheme agreed HP Sec 730.17 - DoT Pre Commissioning Report. - FO83 TSIR Electrical Checklist Inspection & Test Plan
84d9263f-890a-5cc7-a878-5a975b8d2fb5 | note | 3) Electoral Tests & Flash Test performed HP Sec 730.17 -DoT Continuity, Insulation, Pre-Commissioning Reports, -HEALEYS - FO83 TSIR Electrical Checklist Inspection & Test Plan
db14cb76-ea8c-502f-836f-43ffc88e6890 | note | - - - - - - - - -
2acb2817-c5dc-5b1c-8f42-f0717813a748 | note | Reference Documents - Healeys ITP FO83 TSIR Electrical Checklist Inspection & Test Plan
e3245b7d-7d13-53fc-af59-fb240589d340 | note | (DoT) Continuity Report
0072a345-fa0b-595c-9191-58c6612be4cd | note | (DoT) Insulation Resistance Report
58154bc9-13be-55a8-a14b-ba971d6142d1 | note | (DoT) Pre-commissioning Report
fc0baa16-6551-57ee-8e0d-ba0b8a6fea85 | note | - - - - - - - - -
ba1aa281-6f8d-5778-b41c-5000cb77a60f | note | Inspection / Test Method - Document review & Site Inspection
a0c7c434-596e-5921-bb3c-3aba3c2adf2c | note | - - - - - - - - -
6610aa80-8858-519f-9ee2-f4cd0abcedd6 | note | Record of conformity - Signed & DoT Reports
e89741c1-67c4-5801-82d8-44c859678f92 | note | Completed Healy's ITP FO83 TSIR Electrical Checklist Inspection & Test Plan
2b132198-473b-5529-9fc3-60dfc807a0b6 | note | Concrete test reports.
25bd9519-aedb-57a9-a9bd-d5ca49ee6b05 | note | - - - - - - - - -
2e5b6b25-84ed-55ad-b66f-6ec540bc5069 | note | HP*
0569a5cc-dcab-57b4-b9ae-e16704fc2336 | note | - - - - - - - - -
73cb8d3c-65c3-5fb4-b63f-2963d78bc5e4 | note | Responsibility - Site Engineer & Sub-contractor
b86fdf0f-cbaf-5724-86be-03e4b3fe19c5 | note | - - - - - - - - -
db0742ba-a9b0-5531-8ff0-bfd221565ab7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Completion of Works
| checkpoint | 3.1 - Completion of Traffic Signal Works
830e6066-b6d2-5547-81f0-be1148c08cf1 | note | Frequency - Upon Completion of all Works
8d0d0117-a2a9-5bf3-bb14-5ada64439614 | note | - - - - - - - - -
5a675070-e35a-5cd0-a326-40a43a30aa9a | note | Acceptance Criteria - Works completed and subcontractor ITP completed in accordance with Section 730 of the Department of Transport Specification
adf0a7cc-f85c-5a34-9850-ff5dc3c78e79 | note | Reference Documents - (DoT) Commissioning Report
8ea2181d-0a7a-5fad-9d02-77a3e8678d1f | note | (DoT) Power Consumption Report
3887dedd-9d08-55f9-a1b1-7497ddd505fc | note | - - - - - - - - -
492fc5b7-ed2c-54c0-942e-f52a6a07cf0c | note | Inspection / Test Method - Document review & Site Inspection
11101cd1-b7e3-5c89-929e-85ecd414d030 | note | - - - - - - - - -
4f9b04d7-d892-51fb-8a26-259591c95b6d | note | Record of conformity - Signed ITP
42589ad6-8912-5c2e-a6f5-860e6815cb54 | note | - - - - - - - - -
609e7c51-e931-592e-813b-e46add334dfd | note | HP*
1d53cec4-0fea-5824-a6a7-a74ab22d5968 | note | - - - - - - - - -
346063b8-9524-5b62-8768-6b68d6f35dfc | note | Responsibility - Project Engineer / Site Engineer
1439d4ac-ea4f-583e-a838-f0a88ef8510e | note | - - - - - - - - -
3f24fb28-6a1f-550a-8549-74214aff6325 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
0ca5bc6c-b6d1-50de-b025-03ae793dca35 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d0efaa67-07eb-5150-a510-524ca9676175 | textbox | Print Name:
784b66fc-75a1-5512-b832-1bab0c0b1a68 | textbox | Position:
60039129-fd09-515f-965e-7e318cd4ecef | date | Date:
47b84fb4-efa1-5e9e-9463-113cf84eefb4 | date | Work Completed On
| checklist | ITP 0049 - TOPSOIL PLACEMENT AND LANDSCAPING | itp | ITP-049-AX-LOT-XXX - Desc | 2a942257-01a4-4006-96cc-0e3796632cb4
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check that current revision drawings are being used
6b145ed4-9019-5978-9d42-96e31f85ceac | note | Frequency - Prior to Commencing Work
53c0919e-faf3-5901-8e6d-fd25ba28e2b7 | note | - - - - - - - - -
65c47f61-1759-5f68-8028-8fbca2f7ef15 | note | Acceptance Criteria - Refer to latest drawings and latest available revision used
98a44c38-045c-56d9-b1d9-7211db3224a1 | note | - - - - - - - - -
72325eb9-abcd-55bc-b863-9f95234c8082 | note | Reference Documents - IFC Project Drawings / Drawing Register
26edd15b-4b1c-57f7-8533-ae2af80ad6d5 | note | - - - - - - - - -
89b0a92c-39b3-56d9-98de-e920c5004ad1 | note | Inspection / Test Method - Document Review
4b7806dc-22fb-59e3-a660-6b6b853ba58a | note | - - - - - - - - -
956855d3-9e0d-568c-90d1-ceb2a2d5bdec | note | Record of conformity - Latest Revision Drawings
a8433bff-9fd6-5a1a-a340-ca9c922a8952 | note | - - - - - - - - -
e08e1cd0-04e5-5646-b049-6a36dab3700e | note | IP
fbe8d406-6a57-5b51-9e6d-6f3f15aca255 | note | - - - - - - - - -
6d2dfb88-1718-54f8-9b0e-0a8301a19dc9 | note | Responsibility - Site Engineer / Site Foreman
89166a8e-4b4e-560f-8b05-11785c79259e | note | - - - - - - - - -
a7d9f653-bc00-592f-ba4e-d3f8553f8e1e | date | Date Completed:
| checkpoint | 1.2 - Submissions and records
aa08b65d-e370-5c68-89c0-dd772bcf9ee7 | note | Frequency - Prior to commencing works
e40e17a5-5793-561d-a28b-9e86d5cc5a8a | note | - - - - - - - - -
28173e3b-a8e2-5ee5-8c51-8aa7bc6cc474 | note | Acceptance Criteria - Samples, records and certificates shall be provided to the Superintendent at least 10 working days prior to bulk delivery.
63274200-6ef1-5524-ad00-ffa10e52219b | note | Following information shall be provided to the superintendent:
1937dac9-f3cb-51ce-a2d6-b8b40be61218 | note | Inspections:
822a0fd0-833b-55e3-9019-cd3499eb0395 | note | • Plant stock for all plant species
4f7ff59e-df01-5c91-a212-303a6cc8d760 | note | Samples:
c62c81c8-0ec9-5b5f-9ab4-67d717a46d3f | note | • Mulch
e7423df6-36af-564f-a985-f4985b7a1c81 | note | • Imported topsoil
52414ff9-1e2b-59a6-a863-5f21e8e84b75 | note | Records:
d164b02c-61b2-5636-8bab-4bbefd8b18a2 | note | • Evidence of origin of indigenous provenance plant material
3ac76571-3ca8-5c5d-acdb-3bbd2914d223 | note | • Analysis certificates for grass seed
459a6985-066b-56c8-830e-5cf4f8d37aed | note | • Details of suppliers
e13fded2-2340-5668-9c9d-646225b2bdaa | note | • Soil tests on imported topsoil
22a8b357-e318-5efd-8e92-1f1f93bf37e7 | note | • Copies of fertiliser labels
8a606d24-7e20-51b9-99dd-98bd259cbddd | textbox | Enter Teambinder Approval #:
fa6c6089-eed4-5ca1-b1ac-f40ebde11767 | note | - - - - - - - - -
af3b834c-08b2-543a-a4ad-b0deb6be58ff | note | Reference Documents - VicRoads Standard Section 720.03
b023bb91-b044-5e25-89a4-e884dd1c825c | note | - - - - - - - - -
cbea8032-8a78-5eaf-ad7d-a78316f2e17c | note | Inspection / Test Method - Document Review
43b3788a-b0af-5168-9609-08f884ad7a5d | note | - - - - - - - - -
d3639994-1bfd-59d9-9d68-fafa90bd79d0 | note | Record of conformity - Records & Certificates uploaded to teambinder
0feda0b9-2a9c-5fe8-86c0-2bca05f1bba9 | note | - - - - - - - - -
04689d80-c9fc-5236-9aeb-5fcc425b8f97 | note | AP
1ebcc416-2ddb-5141-8c99-d659da0622ac | note | - - - - - - - - -
9632bdd7-4ad1-54e8-92d1-e5f22d0beb0f | note | Responsibility - Site Engineer / VicRoads Superintendent
b72a3c28-deed-52d0-bbd9-3a357e15628b | note | - - - - - - - - -
5da67de3-5caa-50b5-8318-396ba281a669 | date | Date Completed:
| checkpoint | 1.3 - Supply of mulch
419c12fd-969c-5e8a-b11d-688b70ae526a | note | Frequency - Prior to commencing works
90e73abd-781c-5057-80af-28aac319085f | note | - - - - - - - - -
2e6c347f-fa8b-5bd0-8429-80a61163d1e1 | note | Acceptance Criteria - Site mulch available from the chipping of on-site indigenous or non-weed vegetation shall be used where possible.
b5c6a740-bd78-52bd-852b-fd177d63569e | note | All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454, and shall comply with Table 720.044
0b60b3c7-c877-5b52-9b99-051568579548 | note | - - - - - - - - -
2a21274d-69bb-56cc-80a3-9318ab8e7b03 | note | Reference Documents - VicRoads Standard Section 720.04
b080d980-3358-5086-95ed-7a18fdc6c9e4 | note | VicRoads Standard Table 720.044
c8da597a-31e1-5f7a-a964-018c24044ea3 | note | AS4454
e7c9a324-4772-544c-9c13-56d3ddee6153 | note | - - - - - - - - -
f8f1a862-4f32-5f26-aa1e-96f62f40e5e9 | note | Inspection / Test Method - Verify
19c83178-5478-513e-a234-915798f08936 | note | - - - - - - - - -
a616fd65-5b3a-58f5-9b88-49d3cd0a4226 | note | Record of conformity - This ITP signed off
d25f1196-08c0-5b12-a085-44609c59a10e | note | - - - - - - - - -
09ee2889-189a-5f7e-be5a-f7488f7fd758 | note | IP
5fc68c3d-18c8-5e17-917d-661e5bb033fb | note | - - - - - - - - -
73adf851-f2e4-5436-abc0-9fc9bd25fdb7 | note | Responsibility - Site Engineer
c298dbc6-44b9-5c5c-b729-5f8cd123eeaa | note | - - - - - - - - -
28de5e49-f848-5fc4-86ee-0eee9f752d6b | date | Date Completed:
| checkpoint | 1.4 - Supply of topsoil
efd86f98-8603-5d38-ac62-0445bee5d9d6 | note | Frequency - Prior to commencing works
6af886db-9fa7-540d-88fb-0bce4df019a1 | note | - - - - - - - - -
aee2436b-7404-52bc-a1cb-c4edbbafdf14 | note | Acceptance Criteria - Site topsoil shall be used wherever possible, in preference to imported topsoil.
a38f97ba-777a-5d29-8aa8-17479bc348ba | note | Where imported topsoil is used, the topsoil must conform to the properties specified in Table 720.042
4c01420e-5dec-5d09-8839-b44e6b7e38c0 | note | - - - - - - - - -
0a037ae8-a1da-5091-901e-4b77b0294a6d | note | Reference Documents - VicRoads Standard Section 720.04
d3eeba41-3aa0-5b11-9d80-7c800b7360af | note | VicRoads Standard Table 720.042
a1892069-5eca-5612-832b-85f359cd5e31 | note | - - - - - - - - -
fbf35eb4-8d85-5b92-a630-aecf79a95645 | note | Inspection / Test Method - Verify
cdd70ac9-4430-5fab-9d91-a0f4b422c297 | note | - - - - - - - - -
31aeef9d-5cf9-55d7-ac3e-284b701ba7d7 | note | Record of conformity - This ITP signed off
d05da224-35f5-513c-991b-c7cded0f0672 | note | - - - - - - - - -
26f11bc8-9221-5f08-a399-eacd12a76fa6 | note | IP
7f75751c-7b81-52a1-aa82-5a497722e24d | note | - - - - - - - - -
b41f8637-8fdc-54f9-a399-5b3577c64a35 | note | Responsibility - Site Engineer
050b8680-31c5-5c74-b063-158db3536e29 | note | - - - - - - - - -
d5e16e12-6cee-5f9d-9281-ef61865cb808 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting out planting areas
568ea008-340e-58db-86fe-c79d06e50d33 | note | Frequency - Each applicable lot
33f0eaf4-9b7a-56f1-8940-e074a87a8d17 | note | - - - - - - - - -
6963543c-5f5b-50b6-9620-7162d97ea5a9 | note | Acceptance Criteria - Planting areas are to be set out to the location and shape specified in the landscape drawings.
03ab80de-2727-537a-92d4-37f4a8e449ca | note | Plant density requirements and planting offsets established in the plant schedule are to be adhered to.
dd048e3c-5394-517b-9dc4-b3938574765e | note | Plants shall be placed as shown on the drawings.
6263c6a8-3c0f-594a-a4e2-f833a53934e8 | note | - - - - - - - - -
35242c58-c61f-5cbe-be9a-f366463247ad | note | Reference Documents - VicRoads Standard Section 720.06
f92dc157-d0da-57fa-ae3f-469159d7eb12 | note | - - - - - - - - -
f91574c9-c3a1-5946-b314-97b13e99d37a | note | Inspection / Test Method - Verify
f511cd94-e6fa-540f-8cf0-2796c91c85be | note | - - - - - - - - -
8846a9c7-2588-5e80-a604-9424693b351d | note | Record of conformity - This ITP signed off
94b54c7a-9011-5b47-9362-926a167ae764 | note | - - - - - - - - -
87d102a4-c57e-54f5-8c1e-0dc6e0ba1c00 | note | IP
9550fa5d-4f81-5412-9aae-c0abc1e3504e | note | - - - - - - - - -
68b1326c-b26f-5847-9d96-92297c723f31 | note | Responsibility - Site Engineer
69739001-12c4-55f5-901f-248fd6272675 | note | - - - - - - - - -
1e3a026b-05e3-56d1-8c55-7a71ee5db9df | date | Date Completed:
| checkpoint | 2.2 - Site Preparation
30a54162-5b5f-595d-8871-dc233feb4e4d | note | Frequency - Each applicable lot
4bd84563-a154-51bb-9fc1-f41f8578589f | note | - - - - - - - - -
9ab2a3a1-31c6-5128-b060-424bae51347e | note | Acceptance Criteria - Soil preparation shall be in accordance with Table 720.071
89fb0237-cabf-591b-9c69-e23f9a9e020a | note | - - - - - - - - -
d384d9fe-12ff-5632-ae64-5ff0cfec53da | note | Reference Documents - VicRoads Standard Section 720.07
6d7f1f49-b4ae-5d5f-a6e6-c75a5d8dad58 | note | VicRoads Standard Table 720.071
adbfce9a-80c3-5e0a-aa7d-bbb8aa8fc9f4 | note | - - - - - - - - -
9c547fda-6758-58d7-9814-94606012b111 | note | Inspection / Test Method - Verify
2c47bdbf-867c-591f-9d31-00dbd126928d | note | - - - - - - - - -
8707a4f4-1a1a-5457-96db-1058e5fba7d5 | note | Record of conformity - This ITP signed off
38eb58fc-2ea5-5e28-a5aa-2fd469a23659 | note | - - - - - - - - -
3b4b308a-f201-5629-9c32-f7d6ddc8b32e | note | IP
af1e5193-f1a8-5521-913d-7d8b1bd0de62 | note | - - - - - - - - -
7ffc1907-ed16-5071-b60d-c81d4cb4d0e7 | note | Responsibility - Site Engineer
d2c4f932-2507-5449-90c0-c60f7c0eabf1 | note | - - - - - - - - -
238ea748-789e-5937-ac16-79241824986b | date | Date Completed:
| checkpoint | 2.3 - Ripping of subsoil
03a8e753-7e3f-5c6d-a3ae-ff015854f5e9 | note | Frequency - Each applicable lot
e958a858-0a3f-59e8-97ca-df4158fc1eaa | note | - - - - - - - - -
384cc5da-4f22-5d49-9561-fda40bc5e878 | note | Acceptance Criteria - All ripping works shall conform to the requirements of Cl 720.07 (b).
9c27d07e-73e3-5300-938d-479429d2a881 | note | Ripped areas of planting, individual tree planting and grassing are to be made available for inspection prior to mulching, planting or grassing, and shall not proceed until the Superintendent acknowledges requirements for ripping have been met.
0f55123d-8256-5e90-bfbb-9af145e86cb3 | note | - - - - - - - - -
065224e7-1cde-54a4-9e77-705bed36c060 | note | Reference Documents - VicRoads Standard Section 720.07(b)
334ac4cc-b5ee-5d2b-984e-31d6cc546a90 | note | - - - - - - - - -
4481ee75-fa43-5372-903f-1366b17d60fd | note | Inspection / Test Method - Verify
260ac9ed-507f-5608-8a8b-465f4db23f96 | note | - - - - - - - - -
440c400c-d70f-5183-a382-926c42a3f908 | note | Record of conformity - This ITP signed off
f884d9d5-99af-5f5a-b42a-396d99b5f546 | note | - - - - - - - - -
5e4b47ac-adec-56d5-bdc0-52b2c1958ffa | note | HP
597c3324-dc34-52b8-b2d4-3d004172ff3c | note | - - - - - - - - -
3475835d-c4a0-58b3-944d-6f3086b27957 | note | Responsibility - Site Engineer / VicRoads Superintendent
cccfcdb3-0d1b-57a6-9575-cdb385d471cf | note | - - - - - - - - -
0bd5c28c-f289-5c33-98a5-c91b790bfbe5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Topsoil Placement
82441c42-b977-5bdc-824a-17ec61e5209c | note | Frequency - At completion of works
5d6cff71-372b-5e4d-add9-c8eb46747f5f | note | - - - - - - - - -
ba99bcd5-41e5-5331-b357-48dbca395e3a | note | Acceptance Criteria - All disturbed and/or not paved areas shall be topsoiled according to Section 204 of VicRoads Standard for Roadworks and Bridge works, to the following minimum depths:
9dcdfff2-87fc-50f7-9e30-e02e114677ef | note | • Batter slopes > 2:1 = 50mm
bc600e57-ea2d-5895-8105-906c0c3cd612 | note | • Tree and shrub plantation bed areas = 100mm
7fc80a78-426d-5c91-9f14-37f4d769f571 | note | • Verge, 50mm outer edge / 20mm when within 100mm of the edge of seal or asphalt surface treatment
4fe27ab0-f43a-5f0c-9f06-f75877d93a77 | note | • All other areas - 75mm
d66f9bc0-d4f2-5208-9b87-bb040dd26519 | note | Following subsoil preparation, topsoil shall be spread on planting areas and grassed areas. Topsoil shall not be compacted.
c31426c9-2f33-5031-8b26-c20e12c49e8a | note | - - - - - - - - -
e6e68106-e75a-5399-9dc2-afe3930696c0 | note | Reference Documents - Project Spec. Cl.3020.07(k)
4535d08e-53d4-5cc3-9bed-820e08ad2e52 | note | VicRoads Standard Section 204.17
a2a51c7f-f611-59e6-ad70-e07d57829b1d | note | VicRoads Standard Section 720.07
ba22120e-d29d-563e-8e8a-f7a5bda16e2e | note | - - - - - - - - -
b392e5eb-850b-5151-9bd5-d94431fe74c9 | note | Inspection / Test Method - Site Inspection
7bd27989-9eab-5a6a-bc86-4c63fcc56204 | note | - - - - - - - - -
137f850d-fd9d-52ea-bfb6-1619c22a4c9a | note | Record of conformity - Signed ITP
13d82815-88ef-516e-8c1c-11802db400d4 | note | - - - - - - - - -
044c751a-f9ba-566b-9fa0-bf352316179a | note | IP
9c9c91b9-b6fd-5e83-b2b5-e4874b26f60b | note | - - - - - - - - -
5ed06d1c-e25b-5dd6-b8ba-c851271744ec | note | Responsibility - Site Engineer
f3710540-80cf-5e84-99b5-57e67f861633 | note | - - - - - - - - -
8fce9bcd-b11e-5ce6-9815-48373108da54 | date | Date Completed:
| checkpoint | 2.5 - Cultivation
a99ffc75-d706-5711-8701-918c88262eb4 | note | Frequency - Each applicable lot
b0e139e8-833c-54bd-850f-7cd850a60a4a | note | - - - - - - - - -
2f150780-bf04-597d-b277-292da41febb4 | note | Acceptance Criteria - Cultivation shall be undertaken to break soil down to a tilth with 80% of the volume composed of clods less than 50 mm in diameter
c91a5537-dbe6-5484-9222-64826ad09672 | note | Prior to mulching, planting or grassing, area to be presented to Superintendent for approval.
03dd073c-f89b-54c8-8201-e9972b0cf4f7 | note | In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
a2c6cb68-e5fa-5e85-9355-33b9b30b6666 | note | - - - - - - - - -
54d4289e-7bac-5610-9e93-cb7646548d08 | note | Reference Documents - VicRoads Standard Section 720.07
471ff738-dd9e-5626-8d42-42a594e538be | note | - - - - - - - - -
3964bd2d-8d8f-5ceb-9e42-7022d0bfd6a2 | note | Inspection / Test Method - Verify
732fa617-7a46-5fff-95d1-970ee3391741 | note | - - - - - - - - -
08cc6052-c567-5314-bc4b-a03f87322eea | note | Record of conformity - This ITP signed off
d84eacb7-243a-59d9-8a76-1325d53a1d25 | note | - - - - - - - - -
347980aa-f3b5-5a7d-98b9-96648ef29e93 | note | HP
72d87840-6c7a-5eac-95f7-599bf02ed66a | note | - - - - - - - - -
f542b246-c388-58d3-b5ed-78d294aef61e | note | Responsibility - Site Engineer / VicRoads Superintendent
45ea228c-d487-5f4a-b622-55092fc6add8 | note | - - - - - - - - -
f0ec52dc-9fa9-52a0-aa8e-ea48a4426759 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Bulk density of soils for planting and grassing
0faf4d71-f4c9-58f8-8bce-80a8644b8db8 | note | Frequency - Each applicable lot
9eba3ddf-ff91-5bdb-98ee-7b5e586774ba | note | - - - - - - - - -
d50cf9dd-0876-5126-a26c-97727a248ec7 | note | Acceptance Criteria - After cultivation and trimming, the Contractor may lightly compress topsoil for stability on slopes.
07900e9c-aae5-5260-8f37-5fbee58bc64e | note | Vibrating plates shall not be used. Ensure the dry bulk density does not exceed the limits in Table 720.072
ef2a27a1-067c-59f8-bc00-63c23dd4db2f | note | - - - - - - - - -
9b7168ae-3121-5263-9eda-6a3711f3a5ae | note | Reference Documents - VicRoads Standard Section 720.07
ff143f88-10e8-55f6-883c-d109c593518b | note | - - - - - - - - -
f34e42bb-3ae0-5410-8dd4-5fa56b96e341 | note | Inspection / Test Method - Verify
d9727fc9-19c4-55a2-b6e4-4616169adc21 | note | - - - - - - - - -
74901c0b-fdf6-51c7-9784-9618a42306f5 | note | Record of conformity - This ITP signed off
d54a5388-7ec2-5b0e-aa21-9b91dfacb75d | note | - - - - - - - - -
235c5a34-918f-5fc2-8616-439d5b3fdbdb | note | IP
bb4ce2a4-100a-5b5d-91ad-f6df753dba90 | note | - - - - - - - - -
939b61b6-cba2-5229-bdd8-46f91fa35383 | note | Responsibility - Site Engineer / Site Foreman
6408c77e-79a9-5445-a5d0-15c0541881b9 | note | - - - - - - - - -
72dfb785-d53d-57f4-9c5d-49e3160f1753 | date | Date Completed:
| checkpoint | 2.7 - Topsoil finished surface levels
7ed852a1-ca77-50f2-a639-fb19dca331e5 | note | Frequency - Each applicable lot
632de927-a4fa-5529-8670-90d6b63cfbc5 | note | - - - - - - - - -
3c9f9ac8-3b0f-5d78-9645-e3be694a8d09 | note | Acceptance Criteria - The finished level of grassed areas shall be:
7751abf8-7db4-539c-8440-7a7a87baa738 | note | (i) not higher than 125 mm below weep-holes or damp-proof courses in adjacent walls;
342980dd-cb34-5538-b179-82bea5c051fd | note | (ii) level with the bottom of fence plinths;
a1a04428-2288-5baa-82d8-6c279cf5dbb4 | note | (iii) level with adjacent pavements, kerbs, pits and other structures.
d90e1488-b879-57d8-8c51-7f0b07a5f6f4 | note | The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
47551a6d-7c8e-506c-b4ca-9a44dcb97d0a | note | - - - - - - - - -
54bc2151-1df3-5693-b1d8-02ad71e1b327 | note | Reference Documents - VicRoads Spec. Section 720.07
f299ce9e-a57c-57c3-a903-dea9ff6b8224 | note | - - - - - - - - -
1ccbe017-3183-506e-b055-35179c156ab6 | note | Inspection / Test Method - Verify
2b96f422-0809-59b6-a363-0b563a53ed61 | note | - - - - - - - - -
08bd9cdc-5b05-5b4d-bf7a-2e795715420d | note | Record of conformity - This ITP signed off
a056cd7a-644a-5149-a99b-0af28f72af68 | note | - - - - - - - - -
a8211ab5-3ed1-5233-b1f4-ece641863a91 | note | IP
5892463d-fc0f-59e7-abed-070bc6668454 | note | - - - - - - - - -
ec694295-7a34-5a21-a9e3-c091744e85c3 | note | Responsibility - Site Engineer / Site Foreman
4f585f52-be4d-596b-badf-6f3483d36445 | note | - - - - - - - - -
4b565732-7ff0-5187-a3f2-817178e1144d | date | Date Completed:
| checkpoint | 2.8 - Planting
66c12b4c-35ff-5791-9b79-4cdc554a873b | note | Frequency - Each applicable lot
0f60da17-c467-5a1e-b9a7-9fd7d417fb2c | note | - - - - - - - - -
c2860a4f-0a83-5282-b14f-f325cdad045c | note | Acceptance Criteria - Holes in heavy soils or on batters shall be prepared so as to ensure adequate drainage.
fe71a042-e132-5c50-92dd-96507c2d1a1e | note | Planting holes shall be backfilled with friable topsoil free of debris, rocks and clods greater than 50 mm in diameter.
8bc6b842-6369-599f-93c3-f1739d7097a4 | note | - - - - - - - - -
5d2e5e91-008c-5c71-9000-c143babe194c | note | Reference Documents - VicRoads Standard Section 720.09
b8fd09cf-2fbe-5bdb-b550-4608fedb304e | note | - - - - - - - - -
9c89efe9-de4b-5a67-8ea7-dba987f9ecba | note | Inspection / Test Method - Verify
09a895fb-233f-565d-9f94-c092aa78f6de | note | - - - - - - - - -
2084f5b8-b3a8-5fda-bdf3-2e0e70fd5c8d | note | Record of conformity - This ITP signed off
aa9136b3-4f75-506f-b7c3-457db7ae8a26 | note | - - - - - - - - -
99e3b704-138d-579f-b68e-0fe7d28bfca5 | note | IP
162a5e54-8395-523c-a2ad-b78a3a665a1f | note | - - - - - - - - -
05d42d05-e992-575f-a1b4-9bfec7f216e9 | note | Responsibility - Site Engineer / Site Foreman
4f67a6b3-d146-5155-962d-14c1e9e3fadc | note | - - - - - - - - -
122a1655-9614-575d-9198-8a1cf383dad9 | date | Date Completed:
| checkpoint | 2.9 - Mulching
f0072455-480c-5183-89d9-60ef08f27b2c | note | Frequency - Each applicable lot
0b9e4552-889d-5b0b-a4a8-412cb3c39812 | note | - - - - - - - - -
2a7497fd-e3c6-5fbf-a3ef-e031a435d7a8 | note | Acceptance Criteria - Install wood mulch to all Planting Areas unless otherwise specified.
fb348c10-e768-50a7-ba29-0523ec4a0213 | note | Mulch shall extend at least 1 metre beyond plant centres at the outer edges of all Planting Areas. If space does not permit this in median, separator or splitter-island planting, mulching shall extend to the back of kerb.
32f632b2-887c-5999-a227-377a266f20d6 | note | The Contractor shall install 2 metre diameter mulch rings around all Individual Tree Plantings.
7b15254d-edeb-5d77-ae31-fdceed69a8fa | note | Mulch depths in all situations shall be a minimum 75 mm and maximum 125 mm.
e1f9fd18-9423-5657-a2a4-f3b6bbd221e1 | note | - - - - - - - - -
89be3c98-5207-5cce-80dc-bd3f6139b001 | note | Reference Documents - VicRoads Standard Section 720.08
3c96604b-db6f-5660-ac46-f39587dc7dc3 | note | - - - - - - - - -
89d4a5b8-95fe-5e05-bb22-09cb8f81fce7 | note | Inspection / Test Method - Verify
ac82eaeb-d507-5a9c-9104-350a219bc3f1 | note | - - - - - - - - -
cea7360a-5985-53a0-9b1b-ef137df317f8 | note | Record of conformity - This ITP signed off
f43ca6b4-511e-538a-884c-a93f14d0f53c | note | - - - - - - - - -
9ed3aa38-e43a-5a14-a717-e0a0832f9b47 | note | IP
64e1c859-2d92-58cc-819d-216332ac79e1 | note | - - - - - - - - -
e4e00021-6305-544c-ab2c-99c1197f18fb | note | Responsibility - Site Engineer / Site Foreman
9a868ac7-a566-52be-9262-2080b31f6f49 | note | - - - - - - - - -
33cac7ff-d0db-5b94-a08d-650f0160d370 | date | Date Completed:
| checkpoint | 2.10 - Grassing of disturbed areas
c5cd3834-7351-537c-a198-b6e3a7d785a0 | note | Frequency - Once installation of assets completed
96f38644-f486-561a-b8a4-db1fa1341a8f | note | - - - - - - - - -
c6327ac5-3c2e-5e31-992a-c71fcd714593 | note | Acceptance Criteria - All disturbed areas shall be topsoiled and grassed, all areas to be cultivated to a minimum 50mm depth, and moistened prior to the application of grass seed and fertiliser.
48d6c7f4-5d0c-5535-b5d1-396ef1295732 | note | A joint inspection of all grassed areas shall be carried out between the contractor and superintendent three months after sowing has taken place.
07861679-66fa-5a51-8726-7b4b2ca53e35 | note | - - - - - - - - -
3ca51e26-b232-53c8-8486-b6953a1335a8 | note | Reference Documents - VicRoads Spec. Cl.708.20
19504d75-c1cd-546f-971a-68560c00c3ad | note | - - - - - - - - -
bae244db-a999-5eb3-bb1b-c92c27067138 | note | Inspection / Test Method - Visual Inspection
02f7b1fe-2827-5824-b3fb-80d398ab375e | note | - - - - - - - - -
fba2b825-cb30-5de1-8e40-08ecce6d0df1 | note | Record of conformity - Site Photos
ac0e07a4-a4aa-545f-91cc-66036a387c2c | note | - - - - - - - - -
e1048e00-6391-5cf9-86b1-97b5f76a8d1e | note | HP
5fc2136c-2696-5bd7-beed-37b77528c67e | note | - - - - - - - - -
d6555afd-5731-5a26-a234-905c88a1466e | note | Responsibility - Site Engineer / Superintendent
896ec323-1f42-57d2-94b8-b30f7ae5603a | note | - - - - - - - - -
0982f3ed-79af-54df-82aa-f14866676c67 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.11 - Grassing
cc26363a-112a-5beb-8cd7-6932eb36c5bd | note | Frequency - Each applicable lot
aa746b4b-0f24-57ca-998c-97f6e90bac47 | note | - - - - - - - - -
c7cba13c-bdd4-580e-936e-360f4d7a2edd | note | Acceptance Criteria - Grass seed shall be sown at minimum 100 kg/Ha (if drilled) or 200 kg/Ha (if broadcast), distributed evenly to achieve an even and dense grass cover.
6a041d29-7b60-59a0-85ab-89c4d429b9db | note | Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
14e05c34-caa1-5ad5-9397-672c4c55d58b | note | - - - - - - - - -
e94c51ef-1fdb-56d7-a1dd-056f084ca128 | note | Reference Documents - VicRoads Standard Section 720.10
65b51927-c6eb-5549-98e0-4867e0d0813d | note | - - - - - - - - -
2e873e9c-cf1f-52e3-97fc-d9cbd47b5577 | note | Inspection / Test Method - Verify
8b26afec-74ae-59d9-9b15-167d0c02459c | note | - - - - - - - - -
ac64c8ec-cb05-5d78-a4fb-84b2b75424c4 | note | Record of conformity - This ITP signed off
04529e3f-f211-5db0-adc2-d74855f7c0d1 | note | - - - - - - - - -
3dea45cf-6b67-5628-9bb6-aabcc30b6902 | note | IP
a2c0c58a-5f80-5465-93ac-26837a4f9f18 | note | - - - - - - - - -
f8d0720c-7d38-5512-b0d8-f2a606970fa0 | note | Responsibility - Site Engineer / Site Foreman
5f7e0ed9-f164-54ae-87ab-ec342a016ea8 | note | - - - - - - - - -
aaac0db4-ce3f-5953-a671-0b2b5f40428b | date | Date Completed:
| section | 3 - Completion
| checkpoint | Final Inspection
ac613a67-1280-5bf6-abec-38072b19e6cf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4e14966f-9b53-5256-a401-52cc0a1afd50 | textbox | Print Name:
6b59b68a-dfe0-5387-959d-5f167c55e5b0 | textbox | Position:
788d2991-b6cd-52b2-8f9e-915ec3bcb792 | date | Work Completed On
6857a5ed-61f8-5be3-a8fc-baa1a1e1fe00 | date | Date:
| checklist | ITP 0054 - TRAFFIC ISLAND, MEDIAN ISLAND & DRIVEWAYS | itp | ITP-054-AX-LOT-XXX - Desc | 3e3afbb9-cb21-409a-857e-8dbc0fdcc277
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check that current revision drawings are being used
0a8de265-3b7f-5303-9ca0-2e42db0bc759 | note | Frequency - Prior to Commencing
d01d2011-9369-596e-951b-f3474f5d0241 | note | - - - - - - - - -
df9adb09-de54-5d9b-83cf-d894052a65ab | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
31348f6a-0fa7-5546-a4c6-b23e41bbb2ca | note | - - - - - - - - -
03439f9a-691a-5c27-9465-6cf154226742 | note | Reference Documents - Project Drawings / Drawing Register
04513cbc-7c81-570a-8465-272b334c2ae1 | note | - - - - - - - - -
2e779324-b3c7-56f2-b02b-79e1506f5824 | note | Inspection / Test Method - Document review
343b4295-badb-5d7a-8977-01be6a7a734a | note | - - - - - - - - -
9f71bfff-d6f4-5916-be81-2433ee09928b | note | Record of conformity - Latest Revision Drawings
9c697f71-83c9-53da-80d6-e03ac358d395 | note | - - - - - - - - -
3feec88a-ec7b-557d-9da2-4df1753e32ca | note | AP
ffafe532-fd2f-5333-bc78-625eeb405c2a | note | - - - - - - - - -
cbeb5e73-723f-5cce-9c84-6d718e6c507c | note | Responsibility - Site Engineer / Site Foreman
0d3c4c9a-fb3a-592b-a899-c0609a49fed1 | note | - - - - - - - - -
735c118b-712e-5ecd-b3fe-6f34af54ba30 | date | Date Completed:
| checkpoint | 1.2 - Bedding Material / Base Layer
8017d247-ded8-5d40-a512-a1a176181793 | note | Frequency - Once, for each mix design, prior to placement of material
6cfb8b65-3d67-526f-aa1f-43b7269e2d88 | note | - - - - - - - - -
c357f0d0-a44d-5906-a149-cf3fe06f2018 | note | Acceptance Criteria - 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
707848d2-7bec-564e-8f66-73bf30780896 | note | Material is registered with VicRoads in accordance with Code of Practice RC500.02
93f779a8-6f94-5418-ad9a-f648a21d15f7 | textbox | Enter: Teambinder Material Approval number
eacdce78-576a-5754-a370-4d134cbb7ba4 | note | - - - - - - - - -
c1ded80d-3243-5ad6-8b44-11b2075cac19 | note | Reference Documents - IFC Drawings, 703.21, 812.04
1059ce00-f4c7-5e78-9d58-b5be8014b3cc | note | - - - - - - - - -
a6a1aa2c-6e23-5105-84c9-d1320e9bf6b6 | note | Inspection / Test Method - Document Review
3631abe8-d428-51a7-be50-98f7bfdd3a63 | note | - - - - - - - - -
098f1519-6a82-575f-9005-f314dd32bbc7 | note | Record of conformity - Teambinder reference number
6578fa45-a901-5eb4-a658-c2d79e3b17f9 | note | - - - - - - - - -
bc9a050f-0ca3-5043-aa97-fec76affd48f | note | IP
9d280418-ec3e-5ad7-a941-549cd9356358 | note | - - - - - - - - -
01ca8965-51f9-5343-917e-de4742dc45bd | note | Responsibility - Site Engineer. Superintendent
2b3ce1f3-1ad7-58f1-8bd0-a207590be714 | note | - - - - - - - - -
b52fb808-a386-5acf-ba89-7ec78094c092 | date | Date Completed:
| checkpoint | 1.3 - Concrete Mix
c4005100-645f-5932-84d6-7bdf1e9e2712 | note | Frequency - Once, for each mix design, prior to placement of concrete
e51e8cfb-2016-5ef2-bc44-bf4d5a3ea7b4 | note | - - - - - - - - -
1c3cfafb-15f7-5ce9-bcdd-2f82dd89b618 | note | Acceptance Criteria - Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
5400a84c-e99c-5c6e-b67f-fb3fdfb939eb | note | Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads.
e8c2bfce-d522-5944-9a4d-f16227b9dec9 | note | No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
043d150b-20bc-565e-a89e-87e09eac960e | note | Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
a62a236f-9d9c-5d66-acb8-5ce9cb386041 | textbox | Enter: Teambinder Material Approval number
f9d54e9e-90d8-59cc-aa73-b8676c526740 | note | - - - - - - - - -
e76879f8-2aa6-532e-a944-86e16fdf7e27 | note | Reference Documents - IFC Drawings, 703.05 (a), 703.07
8e8c7d4d-48fd-520d-a618-8ce8f8667901 | note | - - - - - - - - -
3cea36a2-bccd-59f8-b569-78ac0f35aacf | note | Inspection / Test Method - Document Review
94fc7b0c-241b-5617-9024-51387be9f24a | note | - - - - - - - - -
7ec08238-b193-5e09-8b28-f42fb6d7ca03 | note | Record of conformity - Teambinder reference number
ade8a154-c73a-58b9-af15-1dddd6c0bc18 | note | - - - - - - - - -
2aa28823-5d25-5a65-b211-8827d95d540b | note | IP
99df415e-48d0-5531-9f80-8b3278694da1 | note | - - - - - - - - -
70819973-fdcb-5a94-b5e8-0f9bca4f0853 | note | Responsibility - Site Engineer
847f48dd-0361-534f-a87c-1af0c5f383a5 | note | - - - - - - - - -
62c6aa91-07ea-555d-9560-a22ea5551351 | date | Date Completed:
| checkpoint | 1.4 - Evaporative Retardant
da41ded5-e34b-5f1d-a286-27d42de5a73c | note | Frequency - Once, for each product, prior to placement of concrete
b541ee2d-397d-5e47-bc14-0e926691d927 | note | - - - - - - - - -
bacd79cc-7a39-5f54-b208-c8a7354a61f4 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
9b99490b-daf2-58d2-b788-cd77577ae34a | textbox | Enter: Teambinder Material Approval number
e1366c16-30f2-5dbc-99ef-40d900effca2 | note | - - - - - - - - -
7c33399a-ceba-5c2e-aede-eb69e1aca7d0 | note | Reference Documents - 703.09
51467fb3-c880-55e5-bc8d-a8b40c4f5027 | note | - - - - - - - - -
019a5252-51a6-5dce-b82c-7f06f4a31b5c | note | Inspection / Test Method - Document Review
87c9c3fa-593f-5a23-9b1c-2b2fb65ba769 | note | - - - - - - - - -
dadc9120-4c7c-5ef6-87f5-fe6d893df66a | note | Record of conformity - Teambinder reference number
a38218ef-763c-553e-9516-4dfa25db5ea6 | note | - - - - - - - - -
fe493841-4321-507d-a642-664bfe63e843 | note | IP
f9da8a4f-b7f6-5fa4-878a-223c41354f2c | note | - - - - - - - - -
95e3d1bb-320c-55c5-8957-014b49e73c7c | note | Responsibility - Site Engineer
0e6b7a87-aee2-5c45-8fec-388471c81232 | note | - - - - - - - - -
b71b1150-a544-5f7e-a4fb-2f8f1743ac9e | date | Date Completed:
| checkpoint | 1.5 - Curing Compound
f1141184-5370-57eb-a05c-098ceb86ff03 | note | Frequency - Once, for each product, prior to placement of concrete
78b41f12-12ac-591f-8fda-518309f950ab | note | - - - - - - - - -
36b4d1cd-4de2-59e0-ae4a-628d2ef86420 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue,
3239ca00-c550-52aa-a473-c48e0f6fb0a9 | note | to be submitted for review to the Nominated Authority.
d5efb84f-a817-59a6-823e-ea50f9c0dce0 | textbox | Enter: Teambinder Material Approval number
038d2c0a-a43e-55d1-b158-1b8b6fa5fda6 | note | - - - - - - - - -
4e93fc38-57a1-5ffb-88d3-a1371df574ff | note | Reference Documents - 703.10 (a)
8665172d-6535-5349-8e54-6b11705c26e2 | note | - - - - - - - - -
422fb35b-8ec1-5d11-b647-54cf401ef6ec | note | Inspection / Test Method - Document Review
d493ae0d-3bb0-5dd6-8ff1-06dd29d288c0 | note | - - - - - - - - -
fa945912-eb25-5007-aee4-e49b940202ea | note | Record of conformity - Teambinder reference number
e7da8ef2-38bf-52b6-9031-ed9aaa80ffdb | note | - - - - - - - - -
01f99143-8c40-545d-91c4-e28f2b14a1f8 | note | IP
9bc26fef-dfac-52f6-a6d3-5b3993511b83 | note | - - - - - - - - -
f8446c1d-3941-522d-966a-24898745c905 | note | Responsibility - Site Engineer
055ca730-d4a8-52f3-8484-0409cc8e4c5b | note | - - - - - - - - -
954b732b-7087-54fe-b2b3-886ada7ac7f6 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
e4f2bbf1-24cf-54f8-b399-617e3a8728ad | note | Frequency - Prior to Commencing Work
12810e06-3d0c-5404-adc2-e797ec3bfd7b | note | - - - - - - - - -
06e690e6-6204-5af9-8898-80a8b1329d85 | note | Acceptance Criteria - The Superintendent will review and confirm the set out.
50dee203-eb5f-56bb-a19b-628f32709763 | note | The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
d66f1200-bd75-5bf5-9240-f5489151aefb | note | - - - - - - - - -
bfc2cba0-4121-5763-95fc-331fa30b8de4 | note | Reference Documents - VicRoads Spec Cl.703.17
ac6e3484-8dd1-5a2e-9bd7-cf135d71f980 | note | - - - - - - - - -
a7197bde-6715-56ca-bbcc-d70a25bec562 | note | Inspection / Test Method - Site inspection
32eee2e3-f5be-5fb1-9f02-9c5ad02f8056 | note | - - - - - - - - -
204e5e1b-ebb9-515a-b235-5f5d810d7ff2 | note | Record of conformity - CONQA Hold Point
5cfcc07f-2e8f-5223-a325-feaeda88fbd3 | note | - - - - - - - - -
b4e54627-6942-573e-a315-dd956046a8c8 | note | HP
2533a500-ac40-5cff-ad4e-68c1cee724f4 | note | - - - - - - - - -
973622bc-59e7-5345-96bb-5ff9ac6efa9f | note | Responsibility - Project Engineer, Superintendent & Surveyor
9d0565a8-df25-5ace-a550-71e508296602 | note | - - - - - - - - -
ec9e9dcd-fecb-5cf8-bf85-824d91b5a9fd | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions (if required)
a10c6351-54c7-5150-ba10-c38dbaf864b4 | note | Frequency - Prior to Commencing
2842195c-335d-5ef3-b6c3-35c5b53d6ff8 | note | - - - - - - - - -
aa7768bf-5b4a-57e3-a7b8-22d74744e84d | note | Acceptance Criteria - Before obstructing any waterway, channel or culvert, the
5b7c02a9-3f45-5ce9-9311-f890bc95f6b9 | note | Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority.
668ec615-59d3-59c7-8cac-49c6aa50b142 | note | The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction.
0d44e10d-f998-5a64-b3c2-7d7f4d34b83c | note | - - - - - - - - -
1729a16c-be79-501c-94de-b70dce099f8c | note | Reference Documents - IFC Drawings, VicRoads Spec Cl.703.18
09e2fc1e-06d0-52cc-a880-052460fabbe1 | note | - - - - - - - - -
e5aea98a-b6ed-5c00-9f5e-f10a9ab0d579 | note | Inspection / Test Method - Site Inspection
83428047-2374-5b44-8007-7ee7387d235d | note | - - - - - - - - -
10496ed7-dc2b-5ef3-9720-54ff913923d5 | note | Record of conformity - Written approval from relevant waterway authority. ITP Signed
dfe7b7bb-ffae-5159-8b8e-33b9da9994bf | note | - - - - - - - - -
d58e88f1-af39-5485-90f2-8a2379c1cb3f | note | AP
9b506653-8dfe-55ca-a4f9-41c2be04c95d | note | - - - - - - - - -
1f75ac71-3de7-5604-b728-390ea6dfc3a6 | note | Responsibility - Supervisor / Site Engineer
f91a44a2-ccb2-53b8-8d87-3e498fe018f8 | note | - - - - - - - - -
01a1e625-9f54-5c82-b3af-151a32080c09 | date | Date Completed:
52ea5409-183c-567c-b78d-dedca2f82d16 | note | - - - - - - - - -
| checkpoint | 2.3 - Pavement Thickness Increases for Crossings
bc43df87-420a-5814-bf73-8f4735cf8494 | note | - - - - - - - - -
36b30e98-54e6-55f2-954f-d41856be671d | note | Frequency - Prior to Commencing
cb804fa7-44ae-52da-9644-b42f2cca8025 | note | - - - - - - - - -
a71830b2-a668-5b0a-8551-4a6cfc2dae77 | note | Acceptance Criteria - Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
43830fa5-cd2e-545d-a42e-1f1e952eb4eb | note | i. Pram crossings
16bde5c5-2837-554f-9ee7-306e8fb138a2 | note | ii. Vehicle crossings (residential and/or commercial)
f3880ed1-b40f-5163-95f1-9a422c0b8d20 | note | iii. Established / existing mature trees
a1f0b238-2c73-54c5-9319-27383c9318a4 | note | Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
5bb5f747-57eb-5ef6-8180-c26c444545eb | note | - - - - - - - - -
45bf4654-a002-51ca-8401-53931e4f80b2 | note | Reference Documents - IFC Drawings, VicRoads Spec, 703.16, 703.24, Relevant Council Drawings
5bde7cee-d9a9-5574-9481-f62ab6ba53dd | note | - - - - - - - - -
82f499cd-8b9b-5b09-b939-5b18bec2f07f | note | Inspection / Test Method - Site Inspection
bd4dca1a-71af-5ffc-ab48-4c154889face | note | - - - - - - - - -
2d2e15df-251d-564b-ac7f-f4f6bac95079 | note | Record of conformity - ITP Signed
55959c2a-98ad-5462-8143-a4d285b10c58 | note | - - - - - - - - -
5ad419e0-31d5-541a-9925-9ed96ef7664e | note | IP
d4d74894-7ef8-5504-a9be-950cf777ae01 | note | - - - - - - - - -
970a1b66-9217-53f5-8f63-727f0a28e989 | note | Responsibility - Superintendent/ Supervisor / Site Engineer
22a348b5-b832-56ec-8e8b-7dbd686dc19c | date | Date Completed:
| checkpoint | 2.4 - Bedding Preparation
c2dbc52d-d468-5adb-8acb-5cbf500a0c32 | note | Frequency - Each Lot
34563cd0-90dd-53b3-9b5c-04659b020895 | note | - - - - - - - - -
b725902e-5386-558b-b7e0-f6b162987f8b | note | Acceptance Criteria - All bedding material shall be as specified on design drawings.
14e4545a-036a-5a53-9e92-d64fda533ec4 | note | Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or
996e1ff1-145c-5d34-8697-6aeeb0a360e4 | note | Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
919c7fb6-41f9-52f0-bf86-55295d2c09b6 | note | Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
46568274-4fbd-58c8-b6c0-e2805b4fe1da | note | - - - - - - - - -
ad86f034-775f-5028-8862-05bb76f9fac0 | note | Reference Documents - VicRoads Spec, Cl.703.21, 812, 820, IFC Drawings
602f1346-fa2d-588f-a945-a33cadd34561 | note | - - - - - - - - -
619672a0-d3ad-5708-a8a9-635c9b278672 | note | Inspection / Test Method - Site Inspection
4a3fb8e9-fca7-5001-8e85-ecff8916c03a | note | - - - - - - - - -
66ed89ad-a6e5-53ff-8393-be90478a26d0 | note | Record of conformity - ITP Signed
3649c2a3-d514-5a54-b502-ef93c768a382 | note | - - - - - - - - -
4885048c-d564-5e22-adb9-dfe3c7590d46 | note | IP
c446c3ca-9def-5e97-abac-1ba4ff4ba11b | note | - - - - - - - - -
3128d14b-518c-5c07-9648-f437db6953f2 | note | Responsibility - Supervisor / Site Engineer
9a9c3149-c005-569e-a5d6-c469ee44f1ce | date | Date Completed:
| checkpoint | 2.5 - Formwork
25ca0c3d-2287-5b2b-902b-e8305e3a7049 | note | Frequency - Prior to Commencing
3d50063d-ae23-50bb-8f97-58a69d1080c1 | note | - - - - - - - - -
b0b06027-2c40-57a9-9e06-3c9f51693e39 | note | Acceptance Criteria - Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
2f695878-05f2-59d3-a6d3-660344a92c3b | note | - - - - - - - - -
2611d218-cacf-5822-b298-bfb7412dde65 | note | Reference Documents - VicRoads Spec Cl.703.12
6b364d9d-c023-518b-b6a3-925ae74e9955 | note | - - - - - - - - -
f016d536-5966-56ed-9972-265231850bb2 | note | Inspection / Test Method - Site Inspection
ed206b9e-f4fc-5762-95b4-f85529ac9a2a | note | - - - - - - - - -
0579ae34-6fc0-54a7-8a61-140f8e0d1b0e | note | Record of conformity - ITP Signed
afb2a352-d119-59f3-b4f4-e1a6f4be8c9b | note | - - - - - - - - -
5d99b370-1048-5cec-8434-9670e8a040c4 | note | IP
ed0dbdef-cb66-5322-a486-ab2cff5d4cee | note | - - - - - - - - -
ff62d2d2-9d16-57dc-b732-45a0c34e07fe | note | Responsibility - Supervisor / Site Engineer
e7ff4d62-f4c5-5ea0-94bf-79b04c23a24f | date | Date Completed:
| checkpoint | 2.6 - Steel Reinforcement
9032f35d-6fff-52b3-9047-1eb6d0fbfa37 | note | Frequency - Prior to Commencing
bb976308-7aa5-5e61-8eb4-f043212637d4 | note | - - - - - - - - -
e4ca29ed-3e90-513d-85d8-41dbbd01a0c1 | note | Acceptance Criteria - Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671.
9a51cc91-b53a-5df0-b63a-2c24de66f755 | note | If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16.
3446331e-af5b-5bf0-9fd9-5d97fad2ee0a | note | The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings.
eaba4a02-06f1-5ad6-aec7-9e46e7aa86c5 | note | Reinforcement shall be supported using either concrete or plastic chairs.
caacb467-c042-590e-a17c-ee55e7f7eb81 | note | - - - - - - - - -
3cc7cc8d-39bf-5e0d-b389-d30fe6686ecf | note | Reference Documents - VicRoads Spec Cl.703.13 & Cl.703.13, AS/NZS 4671
bb7efa89-9b6f-56f1-a99a-25dcb1c3757c | note | - - - - - - - - -
93a3a339-e165-5a6f-8ac4-6aec02fea70b | note | Inspection / Test Method - Site Inspection
4fe77b0d-8610-52bc-bc8a-d22003fdb5cc | note | - - - - - - - - -
55aaee0a-1878-5a3f-bf82-7ecd0ceba65a | note | Record of conformity - ITP Signed
d4475cea-41a0-582d-a529-c748357f4cfe | note | - - - - - - - - -
0dbeb828-62ef-58d6-b178-36e8af7b5c3f | note | IP
07eed029-c220-5735-a6a4-72f44eee7aee | note | - - - - - - - - -
eec689db-96b1-54e9-9867-f2ab8d281244 | note | Responsibility - Supervisor / Site Engineer
925942a9-2bab-5f32-b835-0e7bf83f1ef4 | note | - - - - - - - - -
74a954b4-6b0d-5659-85e6-92618f29300f | date | Date Completed:
| checkpoint | 2.7 - Pre-pour inspection
16c34612-da84-5f54-b578-0109ef8f2b88 | note | Frequency - Each Lot
66bfd63f-0958-5a0c-b445-340573f93175 | note | - - - - - - - - -
0b61bbb0-836c-52b3-a5a7-dd7d98b0bc5c | note | Acceptance Criteria - Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings.
8f45390a-18e6-574f-bead-9e12baf559f7 | note | - - - - - - - - -
84eafb04-9ba3-508a-9201-6e1f28b5afb6 | note | Reference Documents - VicRoads Spec Cl.703.05, Cl.703.09, Cl.610.17 (a)(b) (c)(d), AS 1379
3816d0e6-ab56-55ee-bdf2-ac1ae86a14a8 | note | - - - - - - - - -
fb575314-a2c1-52cd-9fcf-c7b7bf6fd43a | note | Inspection / Test Method - Site Inspection
a74f9bdb-ae08-51bf-83fb-f7f1520efd45 | note | - - - - - - - - -
b28e9e84-6a91-51df-8e89-99ab441b27f1 | note | Record of conformity - ITP Signed
2b315e0b-c810-5488-ab3b-bafa8e60c1e2 | note | - - - - - - - - -
c3228b97-ad7b-5ed2-a52f-f26917a6db06 | note | HP
4f621e3d-46e7-5422-ba9b-0a14576770cb | note | - - - - - - - - -
529252cd-9bec-5da5-ac4e-435f08f84b56 | note | Responsibility - Project Engineer, Superintendent & Surveyor
c109249a-51df-58c8-a251-5f700c4f5b82 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.8 - Concrete Testing
a6d67c9a-867c-592d-8b81-c108d81d32eb | note | Frequency - Each Lot
9d28c679-9ead-5644-9754-82877eeff742 | note | - - - - - - - - -
2082627f-1d09-504b-a49d-0ccd9ebe68ef | note | Acceptance Criteria - Concrete Testing Frequency: 0m³ to 50m³ = 1 sample
cdd8dcb1-f497-5c55-8ce5-81d7e7c5e42a | note | Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
c06d3eff-8403-5f78-9fa9-5a899a5ff81b | note | Compressive strength cylinders = 2 no. 28 day strength.
080572a4-35c2-5c88-8ef2-4c5ea6be7256 | note | Slump Testing Tolerances:
97be1011-d6bc-585c-993b-a8dd1e293432 | note | <60mm = ±10mm
aac1fea8-f20b-5bcf-968e-7309026cf908 | note | ≥60mm to ≤80mm = ±15mm
a956f123-25a4-51fd-97d1-d4a19138cec9 | note | >80mm to ≤110mm = ±20mm
10051e93-0df1-5943-bdea-891ca916c51b | note | >110mm to ≤150mm = ±30mm
db782e60-b52d-5809-82de-89b7140c7dcf | note | >150mm = ±40mm
77a506b6-e0b3-5493-962b-6889d2ea6abb | note | - - - - - - - - -
fa8ce1b6-8125-5072-8f07-a40721641ca0 | note | Reference Documents - VicRoads Spec, 703.11
6eb82d2c-3c14-5cae-8845-e761ec5d5ec5 | note | - - - - - - - - -
0dcb4cf9-a5e8-563c-a4cc-bf1ff8f5d6ee | note | Inspection / Test Method - Site Inspection
4b6e8c8b-4f22-5912-b121-f906d5dbf98c | note | - - - - - - - - -
14a347f4-7b91-5930-98cc-660e43a6dd98 | note | Record of conformity - Concrete Pour Record, ITP Signed
b93ba8f2-0f51-59a9-8cdf-f81572bcf422 | note | - - - - - - - - -
391f96fe-8b70-56a6-aef0-84e5cf494238 | note | IP
3bf655a5-9fc0-5eef-aa1c-5f022c96376b | note | - - - - - - - - -
f529ba51-653c-5e05-8c9f-de57322aa577 | note | Responsibility - Supervisor / Site Engineer
582fd0c1-38b2-51e3-ae8b-88af0d951f8f | date | Date Completed:
| checkpoint | 2.12 - Curing
ac323fe4-3982-51b0-b509-d0f591dcf81a | note | Frequency - Each Lot
b642360a-a72e-59aa-8f68-5a0440051abf | note | - - - - - - - - -
a5f4ecdc-0aeb-5a37-99db-2974abc915a8 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and
462b0ce6-e341-5023-b1a0-bc1cdf3523c9 | note | shall continue uninterrupted for a period of not less than 7 days after placing the concrete
2b75b0bb-b729-5b23-9cb1-3350f2bf7fca | note | Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these
de9724e1-3850-58a1-95bc-d75a66b7cb50 | note | - - - - - - - - -
35908968-eeb8-5fab-bc53-10ce594a4f4f | note | Reference Documents - VicRoads Spec Cl. 703.10
f19d01b5-aca7-51ab-bea5-6282e36e74c5 | note | - - - - - - - - -
4674374d-515c-5157-afb0-9f603af25055 | note | Inspection / Test Method - Site Inspection
6a5944da-a1d3-5973-84b2-18f6aaba74e5 | note | - - - - - - - - -
ce91a78a-359c-5f93-8413-9961193d4f52 | note | Record of conformity - ITP Signed
99f41e27-7300-5f35-9db9-93ec91af9310 | note | - - - - - - - - -
c31899e2-e5b1-5059-9e4c-c2f4af6c03d0 | note | IP
204c6e18-1890-588f-9047-a151291b5831 | note | - - - - - - - - -
6e8201f0-58a2-564c-8791-b965edecc743 | note | Responsibility - Supervisor / Site Engineer
1c36284b-e0fb-5f13-859e-69c8c5e96509 | date | Date Completed:
| checkpoint | 2.13 - Tolerances
65910317-8f5c-5293-a3fa-f6adbe28b24f | note | Frequency - Each Lot
1f16c1b1-e23a-5fbe-987b-65a78a18a311 | note | - - - - - - - - -
d413a169-7bdf-5e07-8158-9dcc48778531 | note | Acceptance Criteria - Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm. Deviation of finished work shall not exceed;
4457ee09-493e-5ba6-bc9a-df09dc81b5d9 | note | 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas.
c9382095-35b0-5c6d-842b-e8df7488ba4d | note | Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
6283d217-3fe1-5cd6-ace2-13bdec61de64 | note | - - - - - - - - -
b426485f-2c84-5516-91d2-85fb8ba801ad | note | Reference Documents - VicRoads Spec. Cl 703.15
95232fc2-dd96-53bd-9e1e-3f26c0a231a8 | note | - - - - - - - - -
42364d38-6143-5390-bd35-de64ba236476 | note | Inspection / Test Method - Site Inspection
ec483153-951c-57a4-af7d-2f07699d587d | note | - - - - - - - - -
8bf5b0e4-a01f-5b2c-bc78-7488490c702d | note | Record of conformity - ITP Signed
0e14d333-0238-525e-8010-b90f45549796 | note | - - - - - - - - -
2eef51cb-8126-51ef-b993-eba7326a59bd | note | IP
00f484b0-60c5-54cd-aec3-6881fe0b72dd | note | - - - - - - - - -
dc0d7e44-17bc-5e9e-a1d9-99f3aebd54fd | note | Responsibility - Supervisor / Site Engineer
274a0c93-38ca-555e-a70e-1d76bd39a587 | date | Date Completed:
| checkpoint | 2.16 - Joints
0005ad43-4996-5f54-9fe1-70a66a233475 | note | Frequency - Each Lot
a44dd2f7-0c6d-5d4a-a1c0-255d9fef968d | note | - - - - - - - - -
69b2401f-0ffb-5c09-a7df-2d747bde5ea9 | note | Acceptance Criteria - Expansion Joints: shall be placed at intervals as specified by the drawings.
63fc2dfd-b6ab-5b3e-a62f-482526f6fcf3 | note | Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at
6515a22b-b7e6-5062-9ef9-ce84e8a935df | note | 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths.
aad1161b-d850-5001-acf1-3b94fc4a501d | note | Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and
d3575329-ffb1-5221-b281-a927ede69d97 | note | the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex).
9c88dc6d-e726-58d2-a2c2-0346bb650fe2 | note | - - - - - - - - -
defec39f-91f9-5adf-b456-e014be6b0552 | note | Reference Documents - VicRoads Spec Cl. 703.26 (b)
ddb5825d-0804-5115-a298-bf8d23896ae5 | note | - - - - - - - - -
74f3fe09-6455-5174-a27b-a7f5867ec5b7 | note | Inspection / Test Method - Site Inspection
27b61dc3-fa6c-5afc-bc1c-01f90effcaf8 | note | - - - - - - - - -
4e2da9c1-b43e-5280-b3a9-48459fa94650 | note | Record of conformity - ITP Signed
27ec4978-113a-599d-997c-2ddd226d20fd | note | - - - - - - - - -
b79e66bd-2754-5af8-852f-4b2ced869552 | note | IP
d6adc45b-55ac-5619-a1de-b6a5da3bb2ba | note | - - - - - - - - -
ac2e10ae-7aeb-53dc-8020-4d8b980938ba | note | Responsibility - Supervisor / Site Engineer
dd7932e5-8e14-56f2-becd-c485e5e0a51c | date | Date Completed:
| checkpoint | 2.17 - Stripping Formwork
95fc868f-1692-50a4-9e82-b0a7d1923704 | note | Frequency - Each Lot
90becfae-06b1-5349-a78b-c2c99933bcbb | note | - - - - - - - - -
ea71313f-332b-518a-a46f-4948c3b7ab16 | note | Acceptance Criteria - Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
8b159063-d85d-5d82-b8ab-cb5d130ee9c6 | note | i. 2 days for vertical formwork on external surfaces; and
18028dad-3521-5856-aabf-cb87ac3e3f8c | note | ii. 1 day for vertical forms on permanently hidden surfaces
a6c7007e-d324-5136-b7e1-a4a6ca113141 | note | - - - - - - - - -
c50f7c01-fced-52de-afb3-5863ae43e4d6 | note | Reference Documents - VicRoads Spec, 703.12, AS3610 Table C2
6c77a567-e10e-59ee-b189-091e2e8098ed | note | - - - - - - - - -
ee42a151-9379-53c5-af59-d8f63ca14ed5 | note | Inspection / Test Method - Site Inspection
db0ed55f-7291-507a-bbe2-aec323a287ac | note | - - - - - - - - -
6b2a5df6-968b-539e-ad3e-d0da6271d860 | note | Record of conformity - ITP Signed
4ce6425e-078e-5946-adaa-b4b9b8d3db72 | note | - - - - - - - - -
1f5dd5a1-b778-5d2c-bc96-4a1375dcd23a | note | IP
fc6052db-e6bd-5198-95f9-10d9da1036c8 | note | - - - - - - - - -
b1701361-b53c-5ff3-9f29-0009848e25f5 | note | Responsibility - Supervisor / Site Engineer
c66f68a5-e53a-56c2-a929-4615d6678ef8 | date | Date Completed:
| checkpoint | 2.18 - Protection of Newly Poured Concrete
3f186282-2a75-558e-aaf8-082c2139fc26 | note | Frequency - Each Lot
3856f278-8a3f-53ec-b1fd-aa8f26e0f722 | note | - - - - - - - - -
e0f06546-256a-526b-92d8-6eb02a613978 | note | Acceptance Criteria - All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
bd82b11f-5952-5fc6-849c-bbeafe37d6cb | note | Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or
3c23c017-14b5-58c5-9c04-2244bc67d5ba | note | commercial vehicle crossings a minimum of four days after completion of casting of the concrete.
0ecd4a4f-bca5-5f1c-9376-5654e85e36ac | note | Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
fd65be55-5740-5b57-93a5-d184f69e9486 | note | - - - - - - - - -
55c9418c-7d02-570f-9b14-7ce099e122f4 | note | Reference Documents - VicRoads Spec, 703.27
c56bb3b9-f9eb-5bb3-a307-345f8ed543f5 | note | - - - - - - - - -
f4137e94-4a38-5c77-a6d4-57a9f1dee533 | note | Inspection / Test Method - Site Inspection
b4aaf8a5-24e6-51c4-bd43-78e87770ff8c | note | - - - - - - - - -
12ab818a-feeb-5d26-8d24-09970b972564 | note | Record of conformity - ITP Signed
c2847402-89f0-539b-aa3c-6e6a525d2751 | note | - - - - - - - - -
60ce6204-c4e7-5d6f-99c2-d326d9eb029c | note | IP
1b832d6c-3642-513b-bf4d-8462512fe070 | note | - - - - - - - - -
d789b07e-a9ea-5629-a620-7a4bb857b313 | note | Responsibility - Supervisor / Site Engineer
ed8b44ca-5411-5a62-997f-dcd4f6772498 | date | Date Completed:
| section | 3 - Post-Construction
| checkpoint | 3.1 - Survey data captured for as-built purposes
d33480be-7f83-57de-b8f2-261ced5fc5cd | note | Frequency - Completion of each lot
faaa105b-3c3d-5b7c-850f-bdc29eef88d9 | note | - - - - - - - - -
cfef3d39-0dec-5e6b-b341-0a47b9c6d0ec | note | Acceptance Criteria - Survey to ensure and validate that all works meet level and location requirements.
ccb3b412-0539-53ff-997e-e97aba6ae078 | note | Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
318ed303-c06c-5cac-a94f-88438f7e4fd8 | note | As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
78c88bb9-8657-56a4-922c-ef7ec90bf23c | note | - - - - - - - - -
68bd91c2-3c32-5891-b555-70f4db813d33 | note | Reference Documents - IFC Drawings / survey records
e38eb52e-b29b-50cf-a9bc-b86dea4902fd | note | - - - - - - - - -
95fb71b5-d5d1-5034-9904-16390874eddc | note | Inspection / Test Method - Document review
178e620c-8ed1-595c-8e59-0c643d319c0d | note | - - - - - - - - -
f608e92f-a87c-5eae-a19d-a415298e1175 | note | Record of conformity - As-built survey records
2353c1c2-5efb-5411-ad5b-2f2395c86af9 | note | - - - - - - - - -
802200fc-16e9-54cb-b6ac-d7326a2044f4 | note | SCP
8b798ee0-7dc8-53d0-86a2-7191bf04741a | note | - - - - - - - - -
a811375e-0af2-5471-a77c-3a7d38894b1f | note | Responsibility - Project Engineer
7dc0dbc7-75e8-5a32-aad0-161034fe1e86 | date | Date Completed:
| checkpoint | 3.2 - Cracking of Concrete
f71a0589-8833-590a-b23b-4f8e15cc2f45 | note | Frequency - Each Lot
6db0b6b9-1625-53ac-9785-c463302bf755 | note | - - - - - - - - -
44f04c88-6b01-58f3-aee3-6840205bc893 | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
1252df53-c234-58df-bb99-b782ccc0af9e | note | Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
0964163b-d6bd-5859-a061-7d8fe2837539 | note | - - - - - - - - -
f29eec7b-a01a-5a08-96ed-4ad1e8bbe18b | note | Reference Documents - VicRoads Spec. Cl. 703.30, 687
e861e3e0-14ee-5439-9756-863170f73926 | note | - - - - - - - - -
b6077d83-4586-5dc7-a3f2-abbb031a105f | note | Inspection / Test Method - Site Inspection
25dad343-57d2-57cd-89e4-16e998392067 | note | - - - - - - - - -
f2b7feb8-30c1-5904-80b5-3262bdb2bfc8 | note | Record of conformity - ITP Signed
c5ea889c-56b9-5f0b-891f-13045b176d81 | note | - - - - - - - - -
7f556818-a76d-5b6e-bfd5-df4df894e908 | note | IP
cc35f8bd-92c9-5508-ba68-344d7d2e631e | note | - - - - - - - - -
e43f5466-097f-55ff-b516-d1b01d9bc976 | note | Responsibility - Supervisor / Site Engineer
7a157dba-9334-55ef-83f2-5a031dd213d4 | date | Date Completed:
| checkpoint | 3.2 - Compressive Strength Test Results
7e54a8e0-7da3-5c0f-9d7e-e7331f997f49 | note | Frequency - Completion of each lot
12045f94-a520-5daa-bdac-3b659b2062b8 | note | - - - - - - - - -
ba29699e-9c33-5aff-b6dc-bd610881b158 | note | Acceptance Criteria - 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
6efe9a0f-b4e4-5cba-ad6b-ad44c2e61178 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
8b59c590-b0f4-5391-8f42-d3f94980393b | note | - - - - - - - - -
a8f72cdf-9151-5f2f-931e-0f108bff5540 | note | Reference Documents - IFC Drawings, Relevant Council Drawings, 703.11, Table 703.111
ca9f0e67-b3c6-57ab-8eb3-9b793056198f | note | - - - - - - - - -
867f3a61-2500-5b9e-ac2f-d23a551d6b83 | note | Inspection / Test Method - Site Inspection
f53fd410-3e21-5ad0-a51d-08acf94d2303 | note | - - - - - - - - -
6bb088af-0e52-568f-ba24-9c2993ad75e5 | note | Record of conformity - Attach: Compressive Strength Test Results
123cbb8f-e0ae-53b5-9035-aae3d095cb76 | note | - - - - - - - - -
623194e3-43d7-522d-98da-c3b2d9166b9d | note | IP
5b9fe20b-e941-5527-aae0-c0478b88af7e | note | - - - - - - - - -
8f7367a1-9c2a-54a6-8446-afa90c3fca91 | note | Responsibility - Supervisor / Site Engineer
0ba48a76-2af3-5cd1-b128-ac9623047a98 | date | Date Completed:
| checkpoint | 3.3 - Backfilling
68a4ee2b-b328-5f47-9602-0ab36c76eb2c | note | Frequency - Completion of each lot
c7617002-53e4-56a1-8ed1-dca4bd879176 | note | - - - - - - - - -
67992337-2829-5a4c-9a34-e2e63ea5048c | note | Acceptance Criteria - Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing,
8f4d3bc3-fd00-5e96-95d7-9c4520eb077c | note | topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging.
9ebf80c0-d1ec-53da-8ff1-ebd5f8998aba | note | - - - - - - - - -
d80fb1a6-c879-5907-ab12-6895e54772da | note | Reference Documents - VicRoads Spec. Cl 703.29
43a48b69-2d4c-5353-aa47-275b28e3227e | note | - - - - - - - - -
08d873fe-4bc2-5b68-a356-b188067fb6d4 | note | Inspection / Test Method - Site Inspection
ffbd0db1-617d-5212-abcf-171dd76ac457 | note | - - - - - - - - -
ba5903bd-18a7-5cf3-8827-7b48f938b2d3 | note | Record of conformity - ITP Signed
0ce3ce9e-2d7b-53fd-8e9f-8b1d19543847 | note | - - - - - - - - -
3c87db92-32fa-5217-abab-37585296b92c | note | IP
58673e78-7092-5e3b-8ba8-22ca1387559b | note | - - - - - - - - -
664b2cce-f755-5472-aeeb-6fe4bcd590f4 | note | Responsibility - Supervisor / Site Engineer
67b4f123-8bb0-5e78-a594-375fbc7ed1c0 | date | Date Completed:
| section | 4 - Completion
| checkpoint | 4.1 - As-built Survey
5f758c05-f6c2-5ba3-9f13-1efb81e3eb20 | note | Frequency - Completion of each lot
8ec35792-8221-5389-aea1-d50990ae3a27 | note | - - - - - - - - -
f103af81-3d45-5293-b70b-ed9a14453a6a | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that
691830bf-a13b-5f65-975e-777f8f0f0d95 | note | all Works meet level and location requirements within the tolerances below:
024a1da1-4dbb-5469-b8d7-81e1e4c702d8 | note | Departure from RL = ±10mm
0b804a81-8064-529c-9780-883b527d5294 | note | Departure from alignment = ±10mm
01e6c705-93fa-5fee-9ce2-1fd038be73f9 | note | Rate of change of deviation from RL or alignment = 10mm in 10m
4cc1d59e-fd1a-5dc0-b62d-f7a257da4c8b | note | Irregularities in alignment = 5mm in 3m
8105cf12-82a2-564c-bb27-36bce4848888 | note | Section dimensions = ±5mm
e13ece53-dbff-5a29-9770-b1c46217b0da | note | Section dimensions (less than 25mm) = ±3mm
ff8d809a-0e63-5eee-8b6d-652ca43518d0 | note | Width of pavement = -5mm, +15mm
110d54be-0256-5b3d-8296-00ee18fceb10 | note | Where median surfacings are to be constructed between edge sections of the same level,
f8b0fdf8-cf34-594a-93b2-c7bdc86730ca | note | paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
0dea4726-02d2-59f8-a2cc-544563cc6115 | note | Attach: Survey As-builts / Survey Report
f9d2c014-9a65-508c-b51f-c21ebe7da78d | note | - - - - - - - - -
825f8216-420b-5d48-9174-ccee35732578 | note | Reference Documents - IFC Drawings, VicRoads Spec, 703.15
38d9f864-c321-53e0-bab4-d5a351055469 | note | - - - - - - - - -
a7fc1b22-22d5-53b1-ab67-40d5e293fd97 | note | Inspection / Test Method - Document Review
c75bc282-568d-5da6-8c98-a63a00593c30 | note | - - - - - - - - -
3970c441-0d44-5539-b3f9-f7522d5236ae | note | Record of conformity - ITP Signed
1517adb5-c1f3-5c1b-8e5d-3aa53882c551 | note | - - - - - - - - -
e62afbf7-ea71-53bb-8023-0aab043d8d7e | note | IP
fe95474a-217a-5630-a5f7-0048ae9d8c17 | note | - - - - - - - - -
5a2bfb8b-44ff-503e-aa5c-3641adac89ce | note | Responsibility - Site Engineer
abf1ce49-e71f-5936-8e21-e870e84d4fe9 | date | Date Completed:
| checkpoint | 4.2 - Red-Line Markup
8c93feb9-ec76-5453-b76c-d31afb5c7097 | note | Frequency - Completion of each lot
1cbe2c9e-62b1-5cbd-990c-71bc52c57789 | note | - - - - - - - - -
25d37f04-2f3a-5422-97ea-9355d4562677 | note | Acceptance Criteria - Capture any changes in design or RFI's as per approved red-line markup procedure
0db9b059-9ba1-5669-88a6-a607cb34ed40 | note | - - - - - - - - -
e4b3b06a-26c0-554b-899b-4617a3a5cde5 | note | Reference Documents - Quality Management Plan
74dc53fd-94bc-5146-b81b-975d4b5dd11b | note | - - - - - - - - -
e8bfd4e9-40dc-57bc-a252-0b37bf008e0b | note | Inspection / Test Method - Document Review
35d5f25d-04c1-5f42-8faf-5d1d6f1e2e95 | note | - - - - - - - - -
62d208e4-2a10-5f51-87e0-5bb5807db64b | note | Record of conformity - ITP Signed
6c5dec41-c223-5cc5-bf36-2681a4411812 | note | - - - - - - - - -
efc69a88-1b72-504c-b55b-f54dca5a32d8 | note | IP
a80cdd4e-3727-5fbb-a1f0-8f908a2531ff | note | - - - - - - - - -
0247c993-bc17-5ff6-8d0b-572b71191f22 | note | Responsibility - Site Engineer
f6a4ce51-4a8d-5920-ada1-3376cdd09394 | date | Date Completed:
| checkpoint | 4.3 - Non-conformance Report (NCR) Closure
6b67ac39-a397-541c-b1b7-b9f51c967c2b | note | Frequency - Completion of each lot
01cf9565-5733-5b3b-9ac1-f308827ac4bf | note | - - - - - - - - -
78668a24-b38b-5252-b7b2-501909fab053 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
1872d1b4-5698-50f6-8dd2-403b1bec4af9 | note | - - - - - - - - -
9618d7a6-2e73-50eb-8ef3-205681ad649d | note | Reference Documents - Quality Management Plan
26e69eb5-4246-5388-888c-fd3bac338fda | note | - - - - - - - - -
bcf961d6-3edb-5dcd-97ce-148e858081a9 | note | Inspection / Test Method - Document Review
f760b9e8-ef2d-57d4-9aaf-cf105aa463e8 | note | - - - - - - - - -
9aaf9366-9d80-5b14-a501-6ac7908815d9 | note | Record of conformity - ITP Signed
aeceb307-b08a-54c8-b0a9-5c8dcc76a5ec | note | - - - - - - - - -
25b82f10-1fd4-5bf7-9c9a-f8a54d37720d | note | IP
daff46e5-cfaa-5972-8bb8-d7a2c50eb77f | note | - - - - - - - - -
86b15532-ab7e-58f7-98fa-7c3385f093ac | note | Responsibility - Site Engineer
45ef173d-a91a-50d0-b883-a06ac7be02f7 | date | Date Completed:
| checkpoint | Final Inspection
f174f5e3-47cd-5f88-aaab-8c3fcabac5cf | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
41c9e182-b381-5040-852e-0d9c14ba5202 | textbox | Print Name:
e3de0e06-af01-5503-94b3-97dcbfecc3c3 | textbox | Position:
72673ed7-aea1-5aa7-b1b4-3fd5eab2b024 | date | Date:
f8029f05-ae81-56ee-9fd8-f47235af8baa | date | Work Completed On
| checklist | ITP 0060 - Installation of Unmetered VESI Public Lighting | itp | ITP-060-UT-LOT-XXX - Desc | 0eceab60-fe48-457b-9a4d-57d9fbc4d528
| section | 1 - Preliminary Works
| checkpoint | 1.1 Authority to commence contestable construction (ACCC) issued by Jemena
b2aa3bee-757f-5a39-a108-9b4a00fc2cfe | note | Frequency: Prior to Commencing
1b6bab62-6915-5016-9e23-649b5d8b0582 | note | - - - - - - - - -
5576b17e-704d-5368-8228-d32682fe0429 | note | Acceptance Criteria: Notification from Jemena
aba9c413-9685-529e-bf2a-cf1bbe5974bf | note | - - - - - - - - -
8e0e2528-caf6-5631-8c90-dc338e9802a6 | note | Reference Documents: Record of notification
45646b64-37ac-567f-8e2c-516e08d1d9a9 | note | - - - - - - - - -
30fffebd-16e1-51b5-b962-d8267cf8db85 | note | Inspection / Test Method: Document review
2e18ccc5-91c2-56fe-a262-acca86cdda21 | note | - - - - - - - - -
a328bde2-599f-5938-b747-5be53c32d97e | note | Record of Conformity: Saved correspondence
fffe43fe-ac3e-52ad-8150-e3b1880e272b | note | - - - - - - - - -
a1da2cc0-7d5c-54b2-81a4-bbd6fd3d2754 | note | HP*
daa3aa19-274e-5f7e-9759-cee7bf0c6573 | note | - - - - - - - - -
b6f229da-615d-5083-a046-95a47808f81d | textbox | Responsibility: Project Engineer /PM2
| checkpoint | 1.2 Induction
f2edf5f6-4161-5774-aebb-edade9a97fb0 | note | Frequency: Prior to Commencing
f40e0650-504a-5ea9-873d-967fe7035c96 | note | - - - - - - - - -
8afbf9d8-385a-5ce4-9b17-a0ec702b9751 | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
83a884bf-5f65-5e5d-bc3e-d7a250bfe570 | note | - - - - - - - - -
542a5e53-d9d5-5af9-92cd-8d141461c1f5 | note | Reference Documents: PMP Inductions Register
d63418a9-c90f-5367-a7a5-81f90c5f4dda | note | - - - - - - - - -
5d5cf723-d43f-520b-8cd1-b73bf4265701 | note | Inspection / Test Method: Document review
6f808f9a-9837-5272-bfb9-e14c039956d0 | note | - - - - - - - - -
ba7dda6f-69b1-5d2b-ae53-519ffa231d2b | note | Record of Conformity: Site induction signed.
13e2da94-57aa-5a44-bc31-e9e937f0cfed | note | - - - - - - - - -
3c75be6a-b303-5ec8-9eb7-07d19601d5e9 | note | IP
971efdac-6790-5df2-b4b8-fb8b00b2f4ce | note | - - - - - - - - -
d2dd7c4d-322c-5988-b5eb-7474e8cdc5b1 | textbox | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.3 Check that current revision drawings are being used
8d0e1c8e-5abd-50f9-aaf7-bdca4cacf6a7 | note | Frequency: Prior to Commencing
79865807-cb05-50e7-8289-a85c9f940cfe | note | - - - - - - - - -
39d21b9d-35ca-5961-96ea-d5f8cc867bec | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
e003659f-32a1-5a47-8f22-598367766851 | note | - - - - - - - - -
51613a67-f777-54a1-9376-2703afa31efe | note | Reference Documents: Project Drawings / Drawing Register
e7a709d1-7b1c-58e8-bd97-5013bd576fe8 | note | - - - - - - - - -
eebc98aa-0750-59ca-8ceb-05e7d3166c9d | note | Inspection / Test Method: Document review
3f771cdf-0a72-5739-b816-9832248f4fae | note | - - - - - - - - -
42f5b6c8-b31a-5c08-9c40-4409550df0df | note | Record of Conformity: Latest Revision Drawings
c657ed8c-3e76-5669-a317-b51099e90ff5 | note | - - - - - - - - -
6683349e-b3bc-58bd-a952-1370b9b618d4 | note | IP
57c8cf59-edf2-5a30-b108-ca45e92547ab | note | - - - - - - - - -
9512b003-3bab-58f8-98a9-0f1047d02063 | textbox | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.4 Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
0dde77da-db6c-5765-ba6c-481109bb5c02 | note | Frequency: Prior to Commencing
fddad270-1d03-5eb1-94df-311a5dd7a96e | note | - - - - - - - - -
b1b34fac-1978-55ed-b92b-65bb00a8e9b2 | note | Acceptance Criteria: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
f17eea6a-6a45-562f-90b3-d50cb153df2d | note | - - - - - - - - -
c03dc63b-f6b5-55b8-b293-80cf715ecece | note | Reference Documents: EMP, Site induction,
0fdd3c29-0991-5d37-a29d-31e635e5e530 | note | - - - - - - - - -
04389e33-7799-5b14-8020-97ed1bf7fcd2 | note | Inspection / Test Method: Document review & Site inspection
ebc90de0-dda2-5efc-aad6-4407fb1f7aaa | note | - - - - - - - - -
794d484e-6c5d-5126-9c32-0732a39a6c0f | note | Record of Conformity: Signed ITP
bb9a5cfc-8040-577c-b5bb-960fcc2fb537 | note | - - - - - - - - -
4d44c8ba-acb4-5df3-9df3-8dde56541c73 | note | IP
5d4d555c-cbef-5f63-a56d-1729dfa7c6e3 | note | - - - - - - - - -
97d15f82-280c-5e6c-a44f-ed0bdad77fb0 | textbox | Responsibility: Site Engineer
| checkpoint | 1.5 Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
c371cbac-24fa-56f5-b5ed-34ab8b60898c | note | Frequency: Prior to commencing
7ea7e35e-290d-5ea3-ae25-707241cd0c1a | note | - - - - - - - - -
ed81a084-1809-50ec-8965-fc099b463fb4 | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
be40ebf4-a56f-5650-b672-3c0a30edeab1 | note | - - - - - - - - -
1c54fe88-c3c9-5f0f-9b06-e05b00321149 | note | Reference Documents: Health and Safety Co-Ordination Plan
0ab72076-8f6f-5774-a2f8-e73136b4d99f | note | - - - - - - - - -
15a0c0c8-f6a0-5c2f-aa11-59e7bd1efa26 | note | Inspection / Test Method: Document Review
044e097b-e4f3-53e6-abce-9d84e12aa62d | note | - - - - - - - - -
9faaa1bf-3ae6-5e3e-be28-5027ab1f1951 | note | Record of Conformity: SWMS(s) signed
9be30772-d3d7-5ed8-b2e9-4a50a338dab5 | note | - - - - - - - - -
1fd390b0-c7b9-5369-a91f-d523c55ff559 | note | IP
d2ae00a5-33f0-5e03-aab6-552e7327d7a9 | note | - - - - - - - - -
60e73220-f34f-56a0-9e6f-c1dd1caa8316 | textbox | Responsibility: Site Engineer & /Site Foreman Superintendent
| checkpoint | 1.6 Ground Penetration Permit issued
00000e43-39e3-59ac-b853-9e772f85ecc7 | note | Frequency: Prior to Commencing Work
8bed18fa-c68d-5955-9bae-fa24826d0c1f | note | - - - - - - - - -
ff8f14bf-ae7c-53aa-8a72-e682b89ba7cb | note | Acceptance Criteria: Current Ground Penetration Permit signed and specific for the area where works will be executed.
6792fad3-942c-5126-96b9-33401fd17c95 | note | - - - - - - - - -
89541fbb-b4d6-52b0-82fd-c4f5bc34df3a | note | Reference Documents: Excavation Permit
ad3d071a-bd44-5899-8fa8-b79febd85cb7 | note | - - - - - - - - -
e4ec4283-2eea-5b20-9e85-f2a846c05f21 | note | Inspection / Test Method: Document review & Site inspection
c3459787-0285-59c3-ad1b-4418c4fd8f03 | note | - - - - - - - - -
087e62dd-9d2e-5570-8b2d-21188c82c67c | note | Record of Conformity: Excavation Permit #
5a2fdf19-8e56-5521-958f-c6aa7fb3f927 | note | - - - - - - - - -
f9891e7b-6264-5143-9b73-13a53d945661 | note | HP*
29d92607-1f10-50b5-9bcb-1a1f013be838 | note | - - - - - - - - -
39a773d4-632d-5ad4-82aa-107ccf0246e4 | textbox | Responsibility: Site Engineer
| section | 2 - Installing of Lighting
| checkpoint | 2.1 Staged Construction Audit - Civil Works
455258f9-c775-5a2f-b023-e2ef24c9ecb1 | note | Frequency: Following Preliminary Works
395900bb-baa0-57f6-a853-6da2ef81b95d | note | - - - - - - - - -
797c737d-430a-5951-bc89-8cb09141c842 | note | Acceptance Criteria: Passed staged Construction Audit
63553ebf-b16b-5c78-be13-927283b9bd77 | note | - - - - - - - - -
e77151e7-ab05-559c-b88d-92b7c3e39f4e | note | Reference Documents: Sub-Contract ITP/Checklist
356b7ae7-880e-5a63-ac1a-62268dd79f09 | note | - - - - - - - - -
782edab9-a65b-5cc8-89c3-ad72d71e7d4d | note | Inspection / Test Method: Inspection by Independent Auditor
bcce9b0f-be8a-51d5-b9d6-4e64d5089e39 | note | - - - - - - - - -
45ec245c-d635-56d9-aa58-93023d3c2947 | note | Record of Conformity: Audit Report
fa50b165-fb63-5c76-9ec9-3f07b6ca3da5 | note | - - - - - - - - -
e86fd19f-aaa6-5bf6-99f7-7ce6e74f09cf | note | HP*
72a85166-5943-5eaf-b325-c1ca79efb5c9 | note | - - - - - - - - -
148f4207-5581-5bfe-89d2-636391998f91 | textbox | Responsibility: Sub-Contractor
| checkpoint | 2.2 Staged Construction Audit – Cable Works
96be8bcc-0063-5dcb-9297-5382ab6d2b25 | note | Frequency: Following Civil Works
2011edb1-8bc0-5b99-9224-7e71c6282408 | note | - - - - - - - - -
dfb51bf5-d800-53d6-995f-2b6f88b434fe | note | Acceptance Criteria: Passed staged Construction Audit
addb932c-1f50-5e7a-9d67-db14b9a3da0d | note | - - - - - - - - -
9b249e41-7037-5be2-a78b-e9ab8c7bc0f3 | note | Reference Documents: Sub-Contract ITP/Checklist
6d3e9a8a-7d41-5acd-8d04-a7402043353e | note | - - - - - - - - -
75645ac4-1d09-59bc-9b12-f8f1256cce65 | note | Inspection / Test Method: Inspection by Independent Auditor
42d26dcf-c454-5c7d-b23a-7250881ec799 | note | - - - - - - - - -
3ea08c41-4277-56e6-b4f5-9665a61faa07 | note | Record of Conformity: Audit Report
9573483d-c53d-5b80-9d53-782b7c69c2e3 | note | - - - - - - - - -
5167a8a9-665b-5017-aecc-87f956b608ce | note | HP*
3690bf91-aace-5623-8208-089238ff14de | note | - - - - - - - - -
d979cad7-c74e-5e1a-8104-edee84aca61b | textbox | Responsibility: Sub-Contractor
| checkpoint | 2.3 Staged Construction Audit – Handover
38fef0ef-dede-5bd2-980d-edc7a8c93acd | note | Frequency: Following Cable Works
2960b1d3-7b6c-5ef2-bdb9-ba8eb63207d6 | note | - - - - - - - - -
c1f0110c-84a2-51d6-995e-42c6f719cacd | note | Acceptance Criteria: Passed staged Construction Audit
344b5c4d-b309-5e8f-b750-1356ac0e6b85 | note | - - - - - - - - -
59ccdaaa-e3c7-5f7b-ae9d-f0cc4f912e6c | note | Reference Documents: Sub-Contract ITP/Checklist
f71b78ea-9dbd-59de-bac4-a8d6feefba0a | note | - - - - - - - - -
968fb838-51be-5046-b822-79061a3bfc3c | note | Inspection / Test Method: Inspection by Independent Auditor
bb5d8be3-7b9c-58a4-83f1-40e2003723b8 | note | - - - - - - - - -
840a1523-63b1-575d-b22f-1e5821af1450 | note | Record of Conformity: Audit Report
853cb330-e874-58de-b8df-b9129a135dae | note | - - - - - - - - -
de8e4c44-08f2-5398-b06a-745b886a1687 | note | HP*
bb1c106f-c068-574d-a47c-720753addd03 | note | - - - - - - - - -
4cbafbd0-112c-5b1e-b410-fee9ae82d2d3 | textbox | Responsibility: Sub-Contractor
| checkpoint | 2.3 As-Built submission to Jemena
cfc139b4-a4dd-5c59-9f6d-c24384d4ab3d | note | Frequency: Following Cable Works
d96aa334-61a6-589e-8128-e5d0f26e95fd | note | - - - - - - - - -
27970f7c-acde-5e22-8796-a7dff106a165 | note | Acceptance Criteria: Passed staged Construction Audit
5eb35bcd-6ab4-59cf-89d7-71b7060a488a | note | - - - - - - - - -
adefc321-6385-58ea-b1c3-26e0d19dd8bc | note | Reference Documents: IFC Drawing
da5df6e4-6995-58f9-84dd-ec15ba262b6e | note | - - - - - - - - -
77cd4dfa-44a1-5ee6-a862-e8e571500f39 | note | Inspection / Test Method: As Built Drawing
e6e82e0e-0f52-58df-b885-17d1a87d1659 | note | - - - - - - - - -
9151660a-1263-5e0d-a088-31c8d4fc9d1b | note | Record of Conformity: Acceptance by Jemena
e4e65b4e-2e93-5307-9fd2-94fe4f8f4272 | note | - - - - - - - - -
9cd74b02-2624-582b-8a02-e8611e01c7b7 | note | HP*
6d4810c7-a791-5289-8a0f-bd33ef7b164f | note | - - - - - - - - -
8452f01f-63e0-59c3-8996-7c7a3a2c243e | textbox | Responsibility: Fulton Hogan / Powerplant
| section | 3 - Commissioning
| checkpoint | 3.1 Pre Commissioning Audit
18df7a1a-d2cb-5d00-8db4-4ce24e1ba4a0 | note | Frequency: Following as Built
4fda8da6-ecb7-59d1-900d-99f334b19bb5 | note | - - - - - - - - -
8276570b-77ba-57a8-bfd0-bf68b3e7ab70 | note | Acceptance Criteria: Passed Pre Commissioning Audit
f1be2f6d-3dc7-5e81-af09-583ce23de08e | note | - - - - - - - - -
1615d89e-0e94-5d4d-8204-1e41f6523bec | note | Reference Documents: N/A
4c6710b2-bbdf-5ef6-8bec-73dbb3e1ffbd | note | - - - - - - - - -
1e68517e-0efe-597e-897d-ad31cf199bb1 | note | Inspection / Test Method: Inspection by Independent Auditor
ae804e6f-101e-50a8-8392-add60a5c0220 | note | - - - - - - - - -
a37d8247-c334-5524-bbac-cbccecf444c5 | note | Record of Conformity: Audit Report
21dc1afe-182a-55f8-96b0-567fbba05530 | note | - - - - - - - - -
d3f86a53-521e-5c1e-86d0-239cb4cf026b | note | HP*
255c2fff-25e0-557c-b093-8a3b7f650b5b | note | - - - - - - - - -
dafaf1a6-1ebd-5942-a326-e24b74d5f8f0 | textbox | Responsibility: PM2 (Powerplant)
| checkpoint | 3.2 Commissioning
4cd659e8-a2fe-5864-8d5e-a6bab79ccc36 | note | Frequency: Following Pre Commissioning Audit
02ce1c84-1a6c-5143-b1eb-ecc97b041ebe | note | - - - - - - - - -
f9c002c8-2842-5ffb-bb52-1791c569a24f | note | Acceptance Criteria: Energization
ebf10329-a035-5fcb-88b7-c0f01de949b6 | note | - - - - - - - - -
cc3be79e-f578-529b-8804-c4d218ade98f | note | Reference Documents: N/A
268988e7-9e75-57dd-a9a2-6d2ef4d6e051 | note | - - - - - - - - -
242e5702-229b-5966-a292-e2d8e8c00c31 | note | Inspection / Test Method: Inspection by Independent Auditor
ca7063c3-b99d-5592-a758-988da42744cf | note | - - - - - - - - -
32903d16-0f68-5e31-b3fe-dbab274bef33 | note | Record of Conformity: Switch on
5a724d31-4961-56b4-8bf4-d75b7116a1cf | note | - - - - - - - - -
77adee57-bb75-524c-acb8-eed6ab1c83e5 | note | HP*
f01c448b-b5ba-51bb-b4ee-774d95c373af | note | - - - - - - - - -
69682a8d-49aa-53db-8f4c-90c40d216a83 | textbox | Responsibility: Sub-Contractor
| section | 4 - Completion of Works
| checkpoint | 4.1 Final Audit
5a4f46f7-199d-5728-bcaa-4b5a77b55a17 | note | Frequency: Upon Completion of all Works
a5867fb6-4580-5d53-8a46-bfbc6f126923 | note | - - - - - - - - -
b9867554-14b8-5c59-b64c-856ae2aba42a | note | HP*
c7c02cc1-0ea1-5969-a52b-31fff7bfb1d0 | note | - - - - - - - - -
3a7a410d-fb9b-5b78-bf6b-9a2de2274c4a | textbox | Responsibility: PM2 (Powerplant)
| checkpoint | Final Inspection
391e0d16-28e2-5d5e-8beb-05c29057e6a4 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
bedcb97b-48cb-55d5-b02c-be94fe9db483 | textbox | Print Name:
581c1234-8822-5c2c-9b92-77acab46a1b0 | textbox | Position:
ed3a4637-01a7-5b31-a482-299ae6d2acc3 | date | Date:
9de415d2-09cb-5208-bb9c-f8099c4c73b1 | date | Work Completed On
| checklist | ITP 0063 - PERMANENT LINE MARKING | itp | ITP-063-AX-LOT-XXX - Desc | ef4e3052-d979-4368-98c5-f3636ee15c58
| section | 1 - Preliminary Works
| checkpoint | 1.1 Inductions
e74dd060-62b8-5f45-8700-ce88d7a78d70 | note | Frequency: Prior to Commencing linemarking works
99f75bac-81c9-5515-a0b3-62445801bbcb | note | - - - - - - - - -
4a9efcbe-acd8-5d57-acd2-1bc5a890ed12 | note | Acceptance Criteria: All personnel on site have been inducted to the CRU Site.
154b32b7-e2f3-53ce-87b9-3db335a43d4a | note | - - - - - - - - -
144e2ccd-8487-528b-983a-5f9d72aaa2c4 | note | Reference Documents: Inductions Register
f3afdfad-8818-5944-a4e5-ef4bfc7289f1 | note | - - - - - - - - -
8c4b6fbb-90be-50f2-98d5-51bd0223cd2c | note | Inspection / Test Method: Document review
403909a0-a9bc-5c43-a83a-f0e0570b7656 | note | - - - - - - - - -
0b6f107e-6c14-5dc7-bb1a-0d4b652886c4 | note | Record of Conformity: ITP signed, Site induction signed.
654ae767-d932-5497-ac98-2b62dfbbf1cb | note | - - - - - - - - -
162a86f7-5aee-56e9-9e00-fb14843c1831 | note | IP
e1687f23-6575-5224-b1ad-aefcf39d6309 | note | - - - - - - - - -
6b3c125d-b62c-5d7c-9079-20abbe9733be | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 Safety measures are in place, SWMS undertaken
c765cfc4-9009-59b1-90f9-e7fe6f619cc9 | note | Frequency: Prior to Commencing linemarking works
ce51ee83-26d0-5918-bfe9-45534f295c3f | note | - - - - - - - - -
bf618fee-336d-5962-81c0-00b646b881f0 | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
7e13eeb4-37aa-5fe4-86ed-7e213111ca69 | note | - - - - - - - - -
5edd80f2-1844-517c-801b-99737ab2d784 | note | Reference Documents: Health and Safety Co-Ordination Plan
5a4214d2-e1da-50b5-a83a-2a100c30ff8d | note | - - - - - - - - -
83017589-cba6-5789-bdd3-f938713b1628 | note | Inspection / Test Method: Document Review
0fea00ed-3a9f-5c83-a49b-5773909284ea | note | - - - - - - - - -
aa18529c-ff19-5400-ac37-6cedbfec44f0 | note | Record of Conformity: ITP signed, SWMS(s) signed
027333f3-e18d-540b-ba45-6c68d5154b6d | note | - - - - - - - - -
5bfc0219-19af-520c-ab4c-27e3af2386f2 | note | IP
24711503-b767-51a5-8d0b-35541c5a4a97 | note | - - - - - - - - -
7efdaf0f-fd9f-573c-81a1-513550d11691 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.3 Check that current revision drawings are being used
23301dd8-bf27-5b4b-b1c1-54a871e5dada | note | Frequency: Prior to Commencing linemarking works
d79011cc-2ca7-58bc-aef0-75ff756c6e86 | note | - - - - - - - - -
9d5fe02b-94b0-5d57-9a26-15632cc208cf | note | Acceptance Criteria: Issued For Construction (IFC) drawings, & latest available revision used.
0b74e196-1c81-5e5f-b9a1-2e774dc3a815 | note | - - - - - - - - -
756d3e7e-3246-5301-8256-dfc413efd461 | note | Reference Documents: IFC Project Drawings, PS3070.04, PS3070.06
67c75924-2b8e-5cc6-b660-8a90b0f49b21 | note | - - - - - - - - -
fff9f221-eb89-50ad-81bf-2a3d1904b82d | note | Inspection / Test Method: Document review
887f20ba-d83c-5f8f-9da4-0ae34085fcd2 | note | - - - - - - - - -
1dcfb743-75b7-5947-b65d-1950138af162 | note | Record of Conformity: ITP signed, Latest revision IFC drawings
edc20b56-26c7-51a5-9f6a-d806b7fcf536 | note | - - - - - - - - -
c7f52a88-4450-5bce-88ee-bd3c5b86c2a3 | note | IP
d0cb25b0-03bc-583d-b20a-bea0238ec261 | note | - - - - - - - - -
0481b885-f675-538d-9e47-1383699e675b | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.4 Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
20339aad-2e1b-5cf5-aad5-e13f97a8cc95 | note | Frequency: Prior to Commencing linemarking works
3dd23bf5-8694-5803-b4fa-560da1a2f7ef | note | - - - - - - - - -
aec4bf5c-0eb5-5956-a999-e6eaa3a351f8 | note | Acceptance Criteria: All environmental measures to be implemented as per construction environmental management plan
6a0384a2-0979-50e8-91ad-90b531a3612f | note | - - - - - - - - -
63e8c685-8b69-51f9-837f-33a6873b3b1c | note | Reference Documents: CEMP, Site induction, PS1200.03
73ea91bc-be6c-51fe-a8c6-84cbca8fcb83 | note | - - - - - - - - -
200c45e9-3486-51d5-a0d0-bb51837ba828 | note | Inspection / Test Method: Document review & Site inspection
0c009fa7-4067-5408-a7e4-670a307250a9 | note | - - - - - - - - -
7b45fc2d-c58c-5c03-b525-84cde799960d | note | Record of Conformity: ITP signed
0dea83ea-1428-50b8-b391-adafddc044ed | note | - - - - - - - - -
fcd1b6b6-d548-51e4-b48a-43dbf9d9f0b9 | note | IP
9aba0f7d-80cd-5e59-8b40-359581ba41ce | note | - - - - - - - - -
bead2ab8-91ec-5e60-a0ee-384a5f172ca4 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.5 Traffic Management (When required)
d5a85e83-b97e-5117-9533-0b5880840650 | note | Frequency: Prior to Commencing linemarking works
30c0d654-e313-5481-88da-8886c1d1d346 | note | - - - - - - - - -
0de79d21-1222-54cf-8b35-c7d500adbfd9 | note | Acceptance Criteria: Approved TMP and MOA in use
9e548b65-2830-52bb-8068-1da42eb0e685 | note | - - - - - - - - -
1c3e95a3-5436-59c1-b06f-62d18d46a699 | note | Reference Documents: Applicable TMP, PS1160.012
2387a6a7-f459-5c9f-956d-ccee4b7fd636 | note | - - - - - - - - -
8a59c311-09ee-5b70-bc6a-e5262075ae35 | note | Inspection / Test Method: Document review & Site inspection
1981540c-8d1b-5668-88b9-727cd18ea35f | note | - - - - - - - - -
78052009-a992-5daf-aaca-b9f34f0cf0a7 | note | Record of Conformity: ITP signed, Approved TMP & MOA
cdddf0d3-be55-579d-a380-3cae1d2a644b | note | - - - - - - - - -
9fe075e4-92b7-516c-996e-8edd6bbbe4b7 | note | IP
31e9b8ed-2185-5d1d-afc4-005b9a7a0934 | note | - - - - - - - - -
09aacc33-0f58-5377-9b50-761d56c2c2a1 | note | Responsibility: Site Engineer / Site Foreman
| section | 2 - Linemarking Works
| checkpoint | 2.1 Verification of line marking material
cd6165de-1da4-53e0-aa06-6e335b5ec8ff | note | Frequency: Prior to commencing site preparation
2da26fd0-2d80-53a8-a2c2-548cab8638f8 | note | - - - - - - - - -
84fc3360-be3d-5583-b41e-08c352b992f4 | note | Acceptance Criteria: Line marking material to comply with minimum requirements as specified in VicRoads Spec 721.A05, VR721.A13, VR721.A14, & PS3070.05
de157f38-3119-5e46-9187-af62e6184992 | note | - - - - - - - - -
07142f6e-2677-5a50-af43-ebfdde29234f | note | Reference Documents: PS3070.05, VR721.A05
b0b376cb-8c67-5731-baa3-6b5be90df8a5 | note | - - - - - - - - -
0d4bbd8c-5f6c-5c51-9543-b2ef5db5a019 | note | Inspection / Test Method: Document review
f49fd26d-4ad7-5ca0-b196-648a676d61d0 | note | - - - - - - - - -
2c7c5b77-cabd-54b4-9584-10a59702219b | note | Record of Conformity: ITP signed, Material compliance
a5c9d3be-c645-557f-b9a8-c2ba1da5bfda | note | - - - - - - - - -
57d8bc64-f25f-53c4-9332-b3af84e35310 | note | IP
616c584c-c1f9-5e79-aa9c-9f2eb237934c | note | - - - - - - - - -
9bf3159e-122a-56b4-ace5-6c785b69530b | note | Responsibility: Site Engineer
| checkpoint | 2.2 Site preparation
477b0f27-181b-5122-ad09-d0e774a0fd7d | note | Frequency: Per lot
88175f51-a273-5064-bbb8-f5789e8e0553 | note | - - - - - - - - -
223226aa-6d5f-56bb-99b0-1faba03acb91 | note | Acceptance Criteria: Site to be prepared by removing any foreign materials and debris within reasonable limits.
7bd2000c-ada9-5468-b877-ec11938d319c | note | - - - - - - - - -
90733091-a2ac-55db-b052-d746426f5b32 | note | Reference Documents: PS3070.07C, VR721.A06, VR721.A08
eef74902-eba2-5d17-890c-ac6a18098041 | note | - - - - - - - - -
53952b6e-1ac8-52a0-8ac4-5dfcf52c9259 | note | Inspection / Test Method: Document review & Site inspection
a1f881e9-1695-5f14-a2eb-7be171db808f | note | - - - - - - - - -
09fd93dd-4a39-5e4d-96e7-c878eb52cad2 | note | Record of Conformity: ITP signed
917d68e1-2b5d-5006-89bd-b5d4ae1d338c | note | - - - - - - - - -
87df5a3f-3044-55e1-9951-836a15eb53fc | note | IP
fd6bb253-e883-56a0-8f81-96f9ab3c50ad | note | - - - - - - - - -
3c41a89d-5eb7-5d93-b449-58e46fc75861 | note | Responsibility: Site Engineer
| checkpoint | 2.3 Removal of unsuitable/redundant markings (If required)
8cdffc1c-ee18-54ee-ae3b-c2fa05960ad8 | note | Frequency: Per lot
ebb6c150-7585-5194-8a35-d71f041c5166 | note | - - - - - - - - -
97ab563e-c9e6-5105-a239-b9835e69c764 | note | Acceptance Criteria: If redundant/unsuitable pavement markings to be removed, removal methodology to be approved by superintendent
2a3f29f6-be8f-50f4-9dc8-02bfcd39cf9f | note | - - - - - - - - -
763db3e3-8162-5895-ad3a-e6b93cc4e169 | note | Reference Documents: PS3070.07C, VR721.A06, VR721.A08, VR721.A12
d79a6971-2bdc-5cc4-81f5-7f7d9d370a62 | note | - - - - - - - - -
83c0ca80-a88f-5e36-b446-f37ee9a015a0 | note | Inspection / Test Method: Document review & Site inspection
fb793eda-1fd5-5ec2-8a82-6c7a90603da4 | note | - - - - - - - - -
805ff30e-e2f5-5272-a897-dc6c6276a33f | note | Record of Conformity: ITP signed
5416bcaa-e6d8-5979-8526-50704e8f4a53 | note | - - - - - - - - -
3afa922f-17eb-5331-84bd-c85190bdcf79 | note | HP
5a431e31-2c17-5c40-b2e4-541d3ba78cfc | note | - - - - - - - - -
15ed6fd8-cd4f-5c89-8be4-6d376b2c1ef7 | note | Responsibility: Site Engineer / Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 Set out of line markings; dimensions and spacings
dac2b8bc-68aa-5708-a961-f2b62f90f069 | note | Frequency: Per lot
4d9df194-9aac-5705-9dbf-bf6d0227eb5f | note | - - - - - - - - -
01469810-2b00-5fc9-b9eb-c532ae029baf | note | Acceptance Criteria: Painting/application of material shall not commence until the Superintendent has inspected the setout and installation timeframes are adhered to.
2bf757fe-2a2b-52cc-98c9-ba032cf23a58 | note | - - - - - - - - -
7c213e11-41ff-5431-b3ba-794e99b64507 | note | Reference Documents: IFC Drawings, PS3070.07D, PS3070.07H, PS3070.07J, VR721.A09, VR721.B05, VR721.B04
2d38f142-f0c1-59e1-91d1-3376ea2cd91b | note | - - - - - - - - -
0989f873-c951-58da-b567-ae314562678f | note | Inspection / Test Method: Document review & Site inspection
097d48f4-bb94-58c9-a805-d10a0b67a71b | note | - - - - - - - - -
942e4c35-ab9b-5beb-88b3-428608a3e1bd | note | Record of Conformity: ITP signed
42905651-20f0-563b-b8a9-96745d0be350 | note | • Consent to proceed by Superintendent OR written exemption granted
27797c17-1398-5ee4-ae29-d1b038da3486 | note | - - - - - - - - -
2bb71496-193f-550b-97d1-20350abe84a8 | note | HP
8a3ee628-f5b5-59a5-b5cd-c73891fa89bb | note | - - - - - - - - -
d7fcf39f-d82c-5981-a5db-c02efd1fb747 | note | Responsibility: Site Engineer / Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 Painted pavement marking application (if required)
46b87c3a-c2c7-5cac-ace2-8e609a6ee99d | note | Frequency: Per lot
a60636d8-7ef0-557f-8055-e57f2d4fcaae | note | - - - - - - - - -
434f1c45-2071-5941-964e-12113b21b60c | note | Acceptance Criteria: If required, Council approved painted pavement marking is to be applied by a self propelled machine, with the minimum requirements for paint, glass, and skid resistance to be as per Material TDS
5b265536-deae-5b67-b132-a561521dd7a1 | note | - - - - - - - - -
24e9ca75-97c8-5800-9b66-e4271390cb80 | note | Reference Documents: Material TDS
902c712a-0e6c-57ab-9575-660897270fcd | note | - - - - - - - - -
281445c4-4add-580c-a01e-8b6bacabcb62 | note | Inspection / Test Method: Document review & Site inspection
ac9ca991-6cc9-50a7-8da6-78d63eec9117 | note | - - - - - - - - -
7230bd9f-1d4c-519c-a22f-a5ad906ea9be | note | Record of Conformity: ITP signed
4beaccc4-f863-5ebf-9e74-52cadecfe3e6 | note | - - - - - - - - -
06ae6b93-a602-541e-9c0f-df8b1ee2c6fd | note | IP
3242e410-7b04-570b-bc3d-32895c990f8e | note | - - - - - - - - -
7b500b1a-068f-5a35-9440-941fb5e20059 | note | Responsibility: Site Engineer
| checkpoint | 2.6 Long life pavement marking application
058577b9-22ca-5b3f-9bde-413823bde937 | note | Frequency: Per lot
76ede703-a602-5dfd-8f95-fb2557c7a842 | note | - - - - - - - - -
ff3ae6bc-26d6-52ab-8054-b9f5a1cd801f | note | Acceptance Criteria: all line marking shall be applied using a self propelled ride-on machine including statcon marking unless otherwise approved, with the minimum requirements for long life materials and glass beads to be as per table 721.E021 & Material TDS
e1f39727-b40c-51ad-89bb-53c758ea8adc | note | - - - - - - - - -
203a9279-04d1-5960-ad87-34fa30c9b7b5 | note | Reference Documents: VR721.E01, VR721.E02, Material TDS
cfd1eed9-3b5a-5de8-8241-f0921705c222 | note | - - - - - - - - -
6d4dbedc-10bf-540e-912d-fc35ff42b555 | note | Inspection / Test Method: Document review & Site inspection
c306696f-5712-5fad-919f-c6d2e1f03fb5 | note | - - - - - - - - -
e5ce4cfe-3d24-5558-9ac2-14cc07554a57 | note | Record of Conformity: ITP signed
c7b4cac2-35ad-56d0-85ed-fa36628f6ed0 | note | - - - - - - - - -
f84eed37-d7b1-5084-894e-65cd2aa3857e | note | IP
144515fa-14f9-5c27-be8c-2aee907ee688 | note | - - - - - - - - -
5ed9473e-2f54-59f5-9f22-7faab7959d65 | note | Responsibility: Site Engineer
| checkpoint | 2.7 Protection of works
7adae1c7-013b-5c97-815b-91c2224786bd | note | Frequency: Per lot
0d8e8fc4-d0da-5ea5-b0ed-23ae42391edc | note | - - - - - - - - -
23638c1a-c592-50cd-adad-743f48bded05 | note | Acceptance Criteria: Work to be protected by appropriate means until it is trafficable.
24dae342-3369-538b-8355-b8951205b67a | note | - - - - - - - - -
5390a4a5-c3b2-5935-8d78-dba71755118d | note | Reference Documents: VR721.A11
76ad8005-84c7-544e-8727-0360904231f8 | note | - - - - - - - - -
3bd8bf72-f401-5657-beb9-3f5a90091537 | note | Inspection / Test Method: Document review & Site inspection
4ec06b21-4b40-56fa-803a-ee109aa454b4 | note | - - - - - - - - -
b0b88634-c051-5a8e-9d08-10da60413012 | note | Record of Conformity: ITP signed
a9af7824-6745-57a0-b841-a93e406cfa60 | note | - - - - - - - - -
76206ca7-0338-55ed-93ed-5cdafddf0070 | note | IP
ccb54cf9-711e-57d5-87a8-f8e03c4c0830 | note | - - - - - - - - -
3f0a217b-6aa7-5059-8dff-535c7d71cc65 | note | Responsibility: Site Engineer
| section | 3 - Testing
| checkpoint | 3.1 Acceptance of retroflectivity
b8aea1b2-5cd8-5512-bbe3-ab8d1285188c | note | Frequency: Per lot
61cc30cc-5ba6-5f7b-99d8-5dbb87e8cea7 | note | - - - - - - - - -
45e1e8e8-aba4-5d67-b7b4-30761c506f73 | note | Acceptance Criteria: Contractor to measure level of retroflectivity, with the average of six test site retroflectivity values for each lot.
d4b0f9e5-c48e-55f2-8155-941da60af0e5 | note | - - - - - - - - -
1793f1f5-7430-588b-8ce9-648305f04d53 | note | Reference Documents: VR721.A13
eb3625ce-93d1-5423-90c4-bc7bd28e1724 | note | - - - - - - - - -
8747db7a-08a1-533f-ad1a-d9d17c208f89 | note | Inspection / Test Method: Document review & Site inspection
53dfdb6c-5c18-5c5c-afe7-a00e0b6a9ae5 | note | - - - - - - - - -
2c3cdc86-fea4-55be-bdbf-6d6f490344cf | note | Record of Conformity: ITP signed, Test report
89ee0296-529b-5722-a98b-3821cab06eff | note | - - - - - - - - -
a48dded6-0cea-59ae-b0b4-764e070b5007 | note | TP
47e3681d-8088-5b78-9edc-d2ff87b3aa31 | note | - - - - - - - - -
816a5af4-72b0-5db8-9b99-eb94a8c8eba9 | note | Responsibility: Site Engineer
| checkpoint | 3.2 Acceptance of colour
d92b050d-0cb2-5a3b-bd13-ec2d2cbfa332 | note | Frequency: Per lot
d2fb1d3b-04d5-5e47-8bea-bc70e1c204cf | note | - - - - - - - - -
806ee5e2-fcd8-5d24-9734-57c234f04f96 | note | Acceptance Criteria: Colour match tests for white & yellow markings to be conducted as per 721.A14, with results forwarded to the superintendent no later than 5 days from testing.
92f829f1-ed34-595b-a27c-9550f8d3d189 | note | - - - - - - - - -
eba52051-7ab2-5bea-9b06-9f36d194209d | note | Reference Documents: VR721.A14
386c1892-1463-580f-877f-2aada60ae677 | note | - - - - - - - - -
61ea9c01-26e8-5b0b-8628-5f9e2c47b982 | note | Inspection / Test Method: Document review & Site inspection
acb1bf32-53a4-50b8-be21-71ed4b8fe59d | note | - - - - - - - - -
557a076a-7563-5a81-af89-e478c18f14ba | note | Record of Conformity: ITP signed, Test report
0ac2fd73-80e5-5491-9d11-47aeea8e3990 | note | - - - - - - - - -
1d5f9708-553f-5596-be52-a2c9875cf4ff | note | TP
96212a66-eb0d-5c32-b317-8011deed7b61 | note | - - - - - - - - -
70d84d10-f545-58c9-b0d9-a8e66e621d5c | note | Responsibility: Site Engineer
| checkpoint | 3.3 Acceptance of tolerances
c6b3ca7e-c5da-5a8f-9622-8da2fdf16fab | note | Frequency: Per lot
ea72fe63-3d22-5669-990d-c1ca87b4e586 | note | - - - - - - - - -
cc8257f8-75f2-5674-8b39-f513aa6309d7 | note | Acceptance Criteria: Survey conformance report to show line marking applied as per tolerances shown in table 721.A101.
25acf5b3-67c1-55c0-8aba-4ad42c2b1732 | note | - - - - - - - - -
18377abc-8ff1-5854-ba11-4f8ca575e5a2 | note | Reference Documents: VR721.A10, VR721.A101
56277e5c-bd28-5121-9a3c-0d750fa46305 | note | - - - - - - - - -
2461ad1e-2290-5b27-a61e-702920b5def5 | note | Inspection / Test Method: Document review & Site inspection
2bb7089e-9409-5f19-8ee9-455dfa3c076c | note | - - - - - - - - -
5e39e663-a12d-501e-b91f-50474747fdc0 | note | Record of Conformity: ITP signed, Survey report
80e9660b-8a93-5a49-9969-3de6c25dce92 | note | - - - - - - - - -
c8a47aaa-a4e0-5b79-b461-3dff60ca50d1 | note | SCP
9b23ba12-83fe-52c2-b27d-bbe7be016821 | note | - - - - - - - - -
5aafddd7-cf56-59a6-8aae-acaba7a7f1eb | note | Responsibility: Site Engineer
| checkpoint | 3.4 Acceptance of work
5a9b9a69-f266-54e9-8140-99f961371323 | note | Frequency: Per lot
84761193-c583-5010-baf2-afac5580bc5c | note | - - - - - - - - -
526fde7e-44fb-5296-9ee2-3800628b4415 | note | Acceptance Criteria: Work to comply with specified requirements as detailed in VR721.A12
5f3a80e6-b53d-5330-8e65-603f89be7521 | note | - - - - - - - - -
22ca94f1-21ab-5fa5-abd4-c0a265b4fe1a | note | Reference Documents: VR721.A12
8d2c4b44-b9e2-550b-9ec9-f7dfefc50dce | note | - - - - - - - - -
d2353fbd-8769-5aea-956b-641e156f2466 | note | Inspection / Test Method: Document review & Site inspection
edaac096-da78-5154-83b1-d07510e3a098 | note | - - - - - - - - -
09793a7b-fdf9-50d5-88a9-f1efc0c4f9ac | note | Record of Conformity: ITP signed
4e29a21a-86c6-51ea-a889-77ebf125cf43 | note | - - - - - - - - -
e8c9fd3e-2fb1-5a64-8c71-09613dd3f8d7 | note | TP
fea19fbf-db83-5156-a78e-b4fe11f9f28d | note | - - - - - - - - -
f11d5992-b50a-58bb-a919-5a360fa554f7 | note | Responsibility: Site Engineer
| checkpoint | 3.5 Records & reporting
e3c41226-f1a8-511b-943e-9f6a69c0ca50 | note | Frequency: Per lot
4d291c80-5ac4-5c0f-a24c-6f152edff298 | note | - - - - - - - - -
beeb8fcd-3e96-50e7-80fb-e43a85d4737a | note | Acceptance Criteria: All new markings to have job completion report forwarded to the superintendent, with a retroflectivity report completed and forwarded to the superintendent showing the retroflectivity for each test lot.
6e97c225-9e7c-521d-93eb-d2bada705fc8 | note | - - - - - - - - -
c1260daa-2777-5cac-b199-49176189e92e | note | Reference Documents: VR721.B06
0d439603-9cce-5f44-be78-0ce8efd71f73 | note | - - - - - - - - -
85d70655-10b5-5940-9055-3f1382f6edf0 | note | Inspection / Test Method: Document review & Site inspection
cd175569-99ff-5bf2-be92-22461c1630a0 | note | - - - - - - - - -
ff647658-c985-5a91-8b0a-49a884a2a059 | note | Record of Conformity: ITP signed, Reports
68b19243-71eb-5dc4-90fa-b9193a3a2b89 | note | - - - - - - - - -
b8f1cd5f-da45-5d06-83ae-d93b975c41cc | note | TP
5ebec07b-b714-5e99-9414-73825278a72f | note | - - - - - - - - -
6f17701c-0419-5ade-9f5b-8c09ee1054f0 | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
455aaf0f-1aaf-59e0-a042-0d595d554a47 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
90cfbdd7-1296-5a86-bce1-25b857a5d32d | textbox | Print Name:
ea0465e8-b610-519f-9bdc-695408248bfa | textbox | Position:
62e16efb-d9b8-5021-aa3b-8b1b7d670f2a | date | Date:
6557a8a2-8976-5955-9884-5e36abbcabc0 | date | Work Completed On
| checklist | ITP 0065 - Wire Rope Safety Barrier (WRSB) | itp | ITP-065-AX-LOT-XXX - Desc | 604cb2eb-a424-4ff2-89d1-768603b3507a
| section | Referenced Documentation
| checkpoint | Referenced Documentation
157dcc5b-b952-5719-9cb4-8802a49b4079 | note | Document Title: ITP-001-AX-LOT-XXX - WRSB Install - CH XXXXXX - CH XXXXXX
b8ff1536-b555-5ab4-a27f-cfbea2ce0b05 | note | ITP Description: Supply & Installation of Wire Rope Safety Barrier
1cb6d8b8-a62e-504a-aac6-45062496135a | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0065
c147ca5d-d38b-5474-9087-3e81a74e2daf | note | Revision Number: 0
bd11ea67-e4bf-52fc-9bf8-f94795d05de1 | note | Revision Date: 16/11/2021
9c82bc79-294f-561f-b855-033e84c3cc36 | note | ITP created by: Omar El-Khub
18f98735-8922-579f-a7a3-d06042b1f86f | note | ITP approved for use by: Beakal Likassa
32142d0e-23e7-5dc0-a46e-d36a93ee7a2d | note | 1.1 VicRoads Section 711 July 2017
110321b3-1af1-5dc9-a310-b4ff84528dd0 | note | 1.2 VicRoads Section 703 April 2019
| section | 2 - Preliminaries - Materials
| checkpoint | 2.1 - Material Test Certificates
ed474b4e-5adf-5cd0-92e6-4c04a2cf621c | note | Frequency: Min 14 days prior to commencing
20f0d8b2-1c43-5be4-91d3-acf7a9cd9ce5 | note | - - - - - - - - -
1d16d5d1-1cf5-5b08-94b2-6ebeb16d10f8 | note | Acceptance Criteria: Only Safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. The installation of the WRSB shall not proceed until the signed statement and certificates of compliance have been accepted by the Superintendent.
e5fb2dc1-e1a2-508c-909d-5704553ebd11 | note | - - - - - - - - -
4d1eefe6-bb4d-539b-b818-3896aab6c097 | note | Reference Documents: Project Specific Specification PS3090.06 (c) VicRoads Spec. Cl.711.05
02b5e2ef-9276-5622-94e0-3d6d318787bb | note | - - - - - - - - -
7e6d1378-3e83-5790-9639-f8f533f0d5ab | note | Inspection / Test Method: Document review
16573860-21eb-532b-a978-5252168ce0b0 | note | - - - - - - - - -
d05e28d1-f142-5e47-ae43-a42e86036d45 | note | Record of Conformity: Material Test Certificates
44c1262d-b0bf-5ab4-8540-63b833ce2874 | note | - - - - - - - - -
854074bc-6609-5dcc-b5f0-c95f9b7b486a | note | HP
e09c5418-b705-5c4f-b395-0f407c3cb28d | note | - - - - - - - - -
adeb9100-1639-5cfc-8d28-a79fe0b162fe | note | Responsibility: Project Engineer/ Superintendent
a9bd0947-a6d5-5563-a7d4-eebd155af46d | note | - - - - - - - - -
341d2992-332f-5419-8a38-b2e97c299332 | date | Date Completed:
| signoff | HOLD POINT
| checkpoint | 2.2 - WRSB Material Properties & Protection
2eb950c3-31ff-53a8-a725-70ebfea3ff2a | note | Frequency: Prior to Commencing
e2974243-e5e2-5f76-bd00-5c73f3ce4c3d | note | - - - - - - - - -
9fbbf422-df48-5313-b71e-f9ff52a20c95 | note | Acceptance Criteria: WRSB material shall meet the requirements as specified in VicRoads Section Cl.711.04.
6a1b5aa5-e1b4-59ed-b149-842aabb6afae | note | - - - - - - - - -
6af57aac-7685-566d-86c0-5d7e43a8334b | note | Reference Documents: VicRoads Spec. Cl.711.04 Cl.711.11
286867b0-12e8-5e18-a23d-1213ee3e3a54 | note | - - - - - - - - -
177b0e96-9e2c-5dfd-a300-c45b0ef5cca6 | note | Inspection / Test Method: Document review
1df51202-affc-549e-9a2b-5be54d49af62 | note | - - - - - - - - -
75267d3e-d153-5d35-8b65-eec41b6bb950 | note | Record of Conformity: Data Sheets, Visual Inspection
42f8241a-18ff-5808-8adf-0d295b584534 | note | - - - - - - - - -
352fc0d2-efee-5851-b662-4bf1144ccb9f | note | IP
fb091fe8-d01f-51fe-849f-002ed4e18248 | note | - - - - - - - - -
029fad53-9530-5bb7-b58b-60c0820a35cb | note | Responsibility: Site Engineer
4a1780dc-70e7-5890-bc99-d759d917c18c | note | - - - - - - - - -
28467c62-6c03-51c3-8434-1b36be3b821c | date | Date Completed:
| checkpoint | 2.3 - Concrete mix design
af613c5c-b80d-5623-87b8-35359734a665 | note | Frequency: Prior to Commencing
a34e5008-b18f-5e7a-8d9d-ce44e34466e8 | note | - - - - - - - - -
2c7424a6-091d-58f9-9d09-ba8cd5961f27 | note | Acceptance Criteria: Concrete Mix is Registered with VicRoads. Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings. Where the soil is solid well compacted in situ material as agreed by the Superintendent, the crushed rock can be omitted and a minimum 100 mm depth of N20 strength grade concrete placed for the maintenance strip.
be850b48-13c1-5903-91b5-b71e2108bdbb | note | - - - - - - - - -
be30d5c0-9b5f-5517-a412-2c84753ab1c6 | note | Reference Documents: Project Specific Specification PS3090.07 (b) VicRoads Spec. Cl.711.15 (a) VicRoads Spec. Cl.711.07(iii)
78f31bbd-d621-5b2f-b74e-9ad61237c9a9 | note | - - - - - - - - -
1c42863b-f836-56ad-a70e-4ce97446e7fd | note | Inspection / Test Method: Document Review
466c39dd-781c-5a28-b82a-e315fd4788ef | note | - - - - - - - - -
83c9854f-c1b6-5157-9bb6-f9c65991c42d | note | Record of Conformity: Mix design approval
0bc0df41-a5f8-558d-aae3-4fa8cd51ee3d | note | - - - - - - - - -
5ce400c9-bdbf-59c5-bd3d-6609b584d707 | note | HP
6e0a3ffd-b8c4-5b5b-bc39-9c3586c1add8 | note | - - - - - - - - -
9f2833bb-16a6-58af-bf26-a612d7b48ee8 | note | Responsibility: Project Engineer/ Superintendent
c720ad3d-8e4d-5839-bad5-a066012513f5 | note | - - - - - - - - -
d7fc0f57-11be-55e1-a8f7-3cae31375139 | date | Date Completed:
| signoff | HOLD POINT
| section | 3 - Pre-Construction Activities
| checkpoint | 3.1 - IFC Drawings
6bccb36d-cc5e-5870-89e0-31cf4eb0277d | note | Frequency: Prior to Commencing
34fb6403-a617-57b4-adfc-960776f74d49 | note | - - - - - - - - -
06039c8d-e6bf-5b9e-a25f-d1f5bf2d1b79 | note | Acceptance Criteria: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
6829a414-7a81-5ad0-986c-b9d4b8036fe9 | note | - - - - - - - - -
f68a0f32-12cb-5d87-bbad-e880b7ac46fe | note | Reference Documents: Project Drawings / Drawing Register Quality Management Plan
496ca9c8-2654-550b-87f2-ffdcbb424e2b | note | - - - - - - - - -
f2c4cf60-bfe8-5eb6-a521-f6199fc25428 | note | Inspection / Test Method: Document review
fbdfc8e9-45c4-5375-ade0-9c5ec108269a | note | - - - - - - - - -
65f21bc5-560e-5cef-91cf-6625a59c1c66 | note | Record of Conformity: Latest Revision Drawings
a3f1a208-f6e4-5789-8229-554a0d1175d6 | note | - - - - - - - - -
9462c69f-8946-5d64-8092-d96c79d45a18 | note | HP*
afab3b2a-f98f-5bc3-95d3-81d366f0b097 | note | - - - - - - - - -
5564906a-8deb-5889-9c09-22ad665ed421 | note | Responsibility: Site Engineer / Site Foreman
9e2a19f2-4dfe-5b3a-aeca-cd970802322f | note | - - - - - - - - -
b276e78d-4413-51f4-b22f-2cad6ee07ec8 | date | Date Completed:
| checkpoint | 3.2 - Survey Set-out
37953296-c242-51c9-8068-206442f3f6a4 | note | Frequency: Each element
90980a21-aaf9-5bd6-bc4a-d245a0572a90 | note | - - - - - - - - -
dd49748c-6d88-5362-969e-218bfc27a60c | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per cl. 711.08. The WRSB shall not be installed until the set out alignment of the posts has been reviewed and accepted by the Superintendent.
692c8622-1cbf-5c23-b609-855b9ebc76bc | note | - - - - - - - - -
11559784-c542-5058-aa84-88386cea1943 | note | Reference Documents: IFC Drawings VR 711.08 VR 711.07 (c)
ebbfbf57-73b7-5f22-9e25-6866e0931fd3 | note | - - - - - - - - -
97e9a1de-d238-51e5-942f-5262f86219b7 | note | Inspection / Test Method: Measure, Visual
8d7d5f44-6c9d-5691-8d1e-27a44bd439f7 | note | - - - - - - - - -
7d810538-2f25-5421-a192-9c7ae0b3e92e | note | Record of Conformity: As-Built Drawings
d78186be-1151-53cf-a9bc-690bc8824b6a | note | - - - - - - - - -
cf0adabe-937d-5d0e-8a05-3db189f064b4 | note | HP
b60ac286-882e-54f8-8a38-cbb5972724d7 | note | - - - - - - - - -
25132833-853b-5120-b7c7-eec6e515a1c9 | note | Responsibility: Project Engineer/ Superintendent
ec2c0231-c938-5c19-9951-22f9c1e1ea1b | note | - - - - - - - - -
167a2aeb-41d2-59f1-aa41-76c9548111ef | date | Date Completed:
| signoff | HOLD POINT
| section | 4 - Construction Activities
| checkpoint | 4.1 - Post Foundations and Anchor Blocks
6da16a38-53a0-551e-96c9-cff648958334 | note | Frequency: Prior to Installation
0e10202d-570c-51b4-9951-f2e2bad792f4 | note | - - - - - - - - -
76fefab0-e45a-5114-adcf-1c1eb6d42d6d | note | Acceptance Criteria: Anchor blocks and post foundations shall not be constructed until the design and manufacturer’s acceptance has been reviewed by the Superintendent. Anchor blocks and post foundation shall not be cast until inspected by the Superintendent.
ad84d689-c47f-529d-93b2-3eab478f0e65 | note | - - - - - - - - -
d48aad3c-5230-5292-b1cd-408a5f05e3c7 | note | Reference Documents: VicRoads Spec. Cl.711.07 (b)
d100aaed-2896-5fac-96a1-d8e5237cf689 | note | - - - - - - - - -
82fb1211-5b22-5a5a-bd2f-1d28c150894f | note | Inspection / Test Method: Document Review
18eaa776-78cf-582b-a60b-5d514c883a95 | note | - - - - - - - - -
379a8a1f-c0ff-55ec-bd76-4a80c10788b7 | note | Record of Conformity: This signed ITP
296b8651-36d9-5714-b54d-f4d86dd11c03 | note | - - - - - - - - -
751d421a-310f-5124-8309-ba3ef066a552 | note | HP
c01128ba-7229-5837-b7fb-a986ee6a53bf | note | - - - - - - - - -
af8fd73a-910d-5817-9ea1-500731912b5b | note | Responsibility: Project Engineer/ Superintendent
ffeb3acc-f11c-5467-ab11-a5594e82a108 | note | - - - - - - - - -
42e7b653-541d-5276-bdb9-5d2cd8c41f0e | date | Date Completed:
| signoff | HOLD POINT
| checkpoint | 4.2 - Tensioning of the Wire Rope
2d021bd3-4389-5755-afc0-5d3444b0ca10 | note | Frequency: During construction.
7d334919-769f-5488-ac2e-8bbb9d66613b | note | - - - - - - - - -
be6ce327-1023-5a1c-b46b-9719934c8c7f | note | Acceptance Criteria: Each wire rope shall be tensioned in accordance with the relationship between rope tension and ambient temperature, applicable to the proprietary WRSB system as per the manufacturer’s specification.
042de469-a485-5aab-9546-8d43040a9521 | note | - - - - - - - - -
30d9b117-94b2-500b-ba42-74f0acbe8be6 | note | Reference Documents: VicRoads Spec Cl.711.07(e)
7a38b89f-fcec-5653-acb5-6fac90fb0b8b | note | - - - - - - - - -
80d92c2b-d9ce-5708-bd56-0e889f6333f3 | note | Inspection / Test Method: Visual Inspection
5867a653-328e-5881-a880-e8c1b3403d00 | note | - - - - - - - - -
55c11123-4eb8-5a88-ba31-1b78c85439c0 | note | Record of Conformity: This signed ITP
e5f770b0-c1f8-5b8b-925f-345a1963643f | note | - - - - - - - - -
696c85b8-0457-53b6-9ed3-38155e8a2192 | note | TP
f798ac21-8039-514b-b49b-1ba09299600a | note | - - - - - - - - -
42dee79e-a037-5a34-9038-5088dd8ed271 | note | Responsibility: Site Engineer
e7b01bdd-5572-5d81-b283-b55e39a0b5cc | note | - - - - - - - - -
0b911865-6444-5fd5-903f-1e173288d67b | date | Date Completed:
| checkpoint | 4.3 - Construction Tolerances
3f41d50a-15d5-5972-868c-d23d5b61f932 | note | Frequency: During construction.
0e97f35c-4e2b-5aaa-9ca5-ed4150c26b7c | note | - - - - - - - - -
318314a2-e1f9-5472-86b7-648a4f583562 | note | Acceptance Criteria: Tolerances for construction of the WRSB system shall be in accordance with the lesser of the manufacturer’s specification or as follows: (a) vertical tolerance on the height of the WRSB shall be ± 20 mm from the design line (b) longitudinal line tolerance for the WRSB system shall be ± 20 mm in plan view (c) tolerance on post spacing shall be ± 25 mm. WRSB height shall be measured from the road pavement when it is located within 1.5 m of the edge of pavement. For distances beyond 1.5 m, the WRSB height shall be measured from the ground surface at its location.
a59494c0-c317-5cc7-89ff-e7a781b2b32f | note | - - - - - - - - -
6620dec3-261a-5bd0-8c94-77bce8418c05 | note | Reference Documents: WR-STD-064, WR-STD-050 VicRoads Spec. Cl.711.08
df702035-b181-5fd3-9505-81ad2e2fa0c7 | note | - - - - - - - - -
37f14eba-fabd-5708-a3b3-15fe24328ae1 | note | Inspection / Test Method: Verify
d682f570-00e4-569a-959f-cce0898ed7aa | note | - - - - - - - - -
9b4e654f-c806-5459-b2ef-e64497d45987 | note | Record of Conformity: Survey Records
d01cf934-6b24-5dd8-9d86-27eb059a1268 | note | - - - - - - - - -
a8088676-a4d4-5c01-9fe4-eabe0af2923f | note | SCP
ab0ead7d-1501-55e9-a248-f0de7a083ef0 | note | - - - - - - - - -
b74f121f-dda6-5c58-8f45-32aff6ab31bd | note | Responsibility: Site Engineer
3300061a-0cb6-5320-811c-47864b6afcd7 | note | - - - - - - - - -
4477bb35-f839-5973-b689-37396d46e317 | date | Date Completed:
| checkpoint | 4.4 - Concrete Maintenance Strip
7019862d-3739-52f2-9bc9-9a22ad717576 | note | Frequency: During construction.
56cd36ec-54bf-55f4-b922-7b96c2fdee7b | note | - - - - - - - - -
43113dfe-5eef-5970-9a9a-02ae22a46d7f | note | Acceptance Criteria: Maintenance Strip beneath WRSB and terminals as indicated on drawing and/or as nominated in Table 711.151. The concrete maintenance strip shall be - Placed parallel to the barrier & have min 300 mm clearance to WRSB post. - min 2% crossfall or same slope as abutting pavement - Shall be constructed flush with the adjacent ground level - Shall be min 75mm N20 concrete conforming to the requirements of clause 711.04(b) - Shall rest on min 75 mm of compacted Class 3 crushed rock. Crushed rock may be omitted and substituted for min 100mm depth N20 strength grade concrete subject to Superintendent approval. Dummy joints at least 20 mm deep and 5 mm wide shall be formed at 2 m intervals across the full width of the concrete maintenance strip. Expansion joints shall be placed at intervals not exceeding 12 m.
bf8edb3b-cec9-5260-8b2c-ce6e1fe274e7 | note | - - - - - - - - -
c11cc395-f67c-5fbb-a45b-2cb374b9c710 | note | Reference Documents: Project Specific Specification PS3090.07 (b) VicRoads Spec. Cl.711.15 (a)
8a1cd916-b177-5371-a04e-383913c48e13 | note | - - - - - - - - -
f3e41b13-7e11-5cb8-a9f0-767be16c079d | note | Inspection / Test Method: Verify
f925626d-680a-5a11-9451-4763ad5f8d6d | note | - - - - - - - - -
a608d665-55db-5ec4-b52b-3a50da77da80 | note | Record of Conformity: SCP & Test Report
921d79da-fb06-5dcc-bc74-105e6602d458 | note | - - - - - - - - -
ecda5803-1e13-5071-be3c-e129a399e915 | note | TP, SCP
ef91ba13-1646-5415-8f56-3d7f02d49d87 | note | - - - - - - - - -
e8e5ffc5-66ad-50d2-8ad3-3bf89bab4f10 | note | Responsibility: Site Engineer
d73a04b4-fccc-59f7-a5ff-f995f1f9390d | note | - - - - - - - - -
fa66d301-40f9-50d3-812b-ffb436cdde35 | date | Date Completed:
| checkpoint | 4.5 - Pre-Pour inspection
5afcfa2a-b4aa-550c-bb8b-88e9530eb373 | note | Frequency: Prior to Commencing Excavation
958441f8-f652-503b-a232-1f68bece7d8b | note | - - - - - - - - -
3a796207-f4b9-561d-a5e4-57fff77e8383 | note | Acceptance Criteria: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used.
e0660ce3-4749-58d7-bf4b-6104e694f681 | note | - - - - - - - - -
cea643ca-8f82-573b-9ba6-22bc754bc37f | note | Reference Documents: Project Spec. Cl.1190.06 Latest IFC Drawings
eae59889-7c84-57b7-9f7b-d8f47414065e | note | - - - - - - - - -
b0a861b7-d777-5211-86be-6730c39be288 | note | Inspection / Test Method: Testing
095b1295-72e8-5a53-8335-83ead1feb2e9 | note | - - - - - - - - -
51bc12bc-0479-5209-abae-a5ed7beb8cce | note | Record of Conformity: Survey records & pegs on the ground
60701294-1de3-5214-aff4-16f3ae67bc86 | note | - - - - - - - - -
eb4e5ab9-d705-5ac8-b603-a79e58e90c62 | note | SCP
504026ce-e8be-54d3-aa8b-88c37f8266f0 | note | - - - - - - - - -
45732f55-f7ee-5a06-83da-625fa22a9295 | note | Responsibility: Site Engineer & Surveyor
be5ee4b3-1b6b-58b2-a483-b2cd29318a13 | note | - - - - - - - - -
bbca4ea3-c3aa-58db-b458-8315a0240ace | date | Date Completed:
| checkpoint | 4.6 - Concrete testing
313c997a-19c7-5584-bc9a-77cb32b25147 | note | Frequency: Every 50m3 pour
d4f62249-3cdf-5b70-b2e9-4df16c7bb43e | note | - - - - - - - - -
a2f5f45f-736f-576a-a5ae-1991bfe0c821 | note | Acceptance Criteria: Concrete shall be N20 standard strength grade. Sampling and testing of the strength of the concrete shall be carried out. One sample shall be taken for every 50m3 of concrete poured for each strength placed on any one day. Test to include: - 1 x 7 day compressive strength - 2 x 28 day compressive strength - 1 x Slump Test
ba090c60-5918-5b99-aad7-b8e739bf680f | note | - - - - - - - - -
a2a39437-c03f-5722-9a92-45f7b2bd7144 | note | Reference Documents: VicRoads Spec. Cl.703.11
47252e93-61f8-59d3-b746-3a468f405fb6 | note | - - - - - - - - -
a07b3ffe-7d2d-5ae0-991d-8aa3f19462a0 | note | Inspection / Test Method: Verify
e4958156-eb86-5aa3-b57a-5e2f1bfbc9a5 | note | - - - - - - - - -
66b92dd4-da47-5f5c-98ad-60e320cc69a3 | note | Record of Conformity: Test results
6796213c-9e2f-579b-b541-6eb49620af63 | note | - - - - - - - - -
af205ed3-fb12-57ac-ab9b-a07fd3868682 | note | TP
93281c0f-1f32-5239-8370-a0b76230be43 | note | - - - - - - - - -
3c4fc632-f6f6-5250-a374-97e04710ff61 | note | Responsibility: Site Engineer
193ccb62-a961-5ea7-92e7-b4785516f524 | note | - - - - - - - - -
d319bd17-41ac-5e54-83fe-83050c7b6184 | date | Date Completed:
| checkpoint | 4.7 - Curing of concrete maintenance strip
da24e4d3-fee2-5e68-ace0-e2d9b00168c4 | note | Frequency: Each Pour
9158d298-e108-52ea-b1e3-56f0a26a9428 | note | - - - - - - - - -
61fe8c43-6fb2-5995-a670-2ab3041c3291 | note | Acceptance Criteria: Concrete shall be cured either by water curing, wet hessian,polyethylene sheeting adequately sealed against moisture losses, curing compound or combination thereof. Curing compounds to be in accordance with AS3799.
427fc9b4-378f-5ce7-9f68-f81bd86d294b | note | - - - - - - - - -
ec6d0a7c-3607-574b-a732-e5aefe01687b | note | Reference Documents: VicRoads Spec. Cl.703.10
8361e5f8-bfa0-5347-90f7-50f39b466375 | note | - - - - - - - - -
b5928dbe-35da-5835-9342-6fbb4d789dcc | note | Inspection / Test Method: Visual Inspection
af3675f7-a145-5911-9ac4-d3112b334178 | note | - - - - - - - - -
e6bf9916-572d-5063-b38a-463651aafce2 | note | Record of Conformity: Site Photos
de430efb-37bd-5831-b4f1-7c19c16eef98 | note | - - - - - - - - -
94f1241e-e710-5956-a691-b56e007a8b5d | note | IP
5cd553df-6c42-58d5-b025-bc3ed528cdb8 | note | - - - - - - - - -
a963d054-a07b-52bf-abcf-4c9888cfbc77 | note | Responsibility: Site Engineer
95f039cd-a0db-5511-885a-9c54995d4b3a | note | - - - - - - - - -
f6acf98f-c8e3-5533-996f-0fc7ce161163 | date | Date Completed:
| checkpoint | Test Requisition
c99f64fb-208c-5b87-884a-0845d2437136 | textbox | Test Requested on
8f13459f-dc05-5e20-9343-ad13516884e3 | textbox | Location
38e802cf-eee4-507d-bf7c-e34cf0c2aca6 | dropdown | Material Type | Type A,Type B,See comments
aa9da704-fe22-5a5d-964e-4c24e025bf5c | dropdown | Material Source | Holcim,Boral,See comments
6527d2f0-f577-50bb-88af-5a1bdda60106 | tickbox | Compaction Test (Standard)
0dee4e17-ef6e-574d-bc3a-150a001856ec | tickbox | Compaction Test (Modified)
6345eeb5-aa2c-56ed-924c-ea216101ac8f | tickbox | Maximum Particle Test
6469922f-3de3-5240-81c7-8447eca2d4d9 | tickbox | CBR/Swell Test
83c69c84-80a5-533d-81a8-66f34fb1becb | tickbox | PI Test
3ea87605-7a4b-5800-a0f2-98570230c811 | tickbox | Permeability Test
2e00d8f4-2f91-5970-851c-7051b8e0bb80 | tickbox | Grading
ed76b6db-7236-514e-99b5-3e84b8b60ac8 | tickbox | Moisture
f570bd01-bea4-5d8e-aa26-819f83972683 | tickbox | See comments
1697ec08-aea5-503f-9d9c-12df44fb65cd | textbox | Test Level/ Layer
| signoff | Test Requisition
| section | 5 - Post-Construction Activities
| checkpoint | 5.1 - Compliance Audit of Barrier System Installation
746bb6ae-6ef2-5c94-a1f4-27942fc9e081 | note | Frequency: Prior the issue of the Certificate of Practical Completion
289f18a5-64da-578b-b477-83e84ba5b3ba | note | - - - - - - - - -
33e21ecd-92a4-5ccc-a6da-e8f15b0b9ff2 | note | Acceptance Criteria: Prior to the issue of the Certificate of Practical Completion, FH shall arrange for a safety barrier compliance audit on all WRSB installations constructed under the Contract. A signed copy of the manufacturer’s Installation Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual shall be completed and submitted to the Superintendent..
0d0c5a92-2f82-5509-969d-b22006215f0b | note | - - - - - - - - -
4604cd76-3d1b-500b-b676-f1c15aba186c | note | Reference Documents: VicRoads Spec. Cl.711.09 Project Specific Specification PS3090.07(f)
8fed5fb3-dcc6-5488-8919-0bc7e3296a15 | note | - - - - - - - - -
3885e3dc-effe-5d52-8b33-2e06426b626a | note | Inspection / Test Method: Safety Audit
0eccd050-1002-578a-8476-40d200b92b9e | note | - - - - - - - - -
c2740ee6-6360-552a-8829-68301672cea2 | note | Record of Conformity: Certificate of Compliance for each treatment installed Product and Installation Manual
6c0d7e6d-5ef8-54b2-bcb1-856b3db70540 | note | - - - - - - - - -
c5713f99-e33c-554e-b641-2219423d2531 | note | HP
ad3eb72c-a8ea-5170-aad7-7114c78c0045 | note | - - - - - - - - -
0c3f2048-a09e-5286-94af-77a64c66dfe8 | note | Responsibility: Project Engineer/ Superintendent
010ff95f-4dc7-569a-a967-b9c50b0263b7 | note | - - - - - - - - -
c1d1cf46-688d-5713-9aac-2c8816279974 | date | Date Completed:
| signoff | HOLD POINT
| checkpoint | 5.2 - Delineators
f3e14268-5c1c-533d-a08d-0b8a7e288eab | note | Frequency: Once installation of assets completed.
751d8a2d-d77e-5979-9b9f-7391fb032fb5 | note | - - - - - - - - -
fc0bbfd9-8eeb-5f09-9158-b37d42cbdcb5 | note | Acceptance Criteria: delineators shall be fastened to the WRSB system, comprising post caps fitted with 50 x 100 mm Class 1A retro-reflective material, as defined in AS/NZS 1906.2, or placed on the front top of the post above the wire ropes. Delineators shall be installed at approximately 12.5 to 15 m spacing. Delineators shall not be placed on flared sections. The delineators shall be arranged so that vehicles approaching from either direction at night will only see: - Red delineators on the left side of one-way and two-way roadways - White delineators on the right side of two-way roadways - yellow delineators on the right side of one- way roadways Delineators not to be installed when the WRSB offset if greater than 4m from the traffic lane.
c0bb3b8c-dec9-5a63-aac0-f5e2c74831e3 | note | - - - - - - - - -
9574ce81-a1c7-57c3-81fd-c40e7e48992f | note | Reference Documents: VicRoads Spec. Cl.711.10
8bc27fd5-deff-503b-ae6a-4755316aea14 | note | - - - - - - - - -
3a55eb69-b681-57b5-a895-35b302027f5e | note | Inspection / Test Method: Visual Inspection
8fe93db1-0acb-504e-afd1-98b5fe788d9c | note | - - - - - - - - -
6f6af10b-9f33-5d02-969a-bbd0457e87e4 | note | Record of Conformity: Site Photos
ea43b156-ac98-58e3-8765-693f302c253f | note | - - - - - - - - -
96a566f7-8c8a-57fd-bbcb-ba836f784222 | note | IP
13ae17ca-fbd6-5267-a4ed-681148da70a2 | note | - - - - - - - - -
7f2748a2-57a9-5972-8f2d-1ab5d79640d3 | note | Responsibility: Site Engineer
dd067ebf-b3eb-5982-be0b-5a375877b0d4 | note | - - - - - - - - -
dc701bf0-cdad-5109-8ec9-8c6cf190107e | date | Date Completed:
| checkpoint | 5.3 - Compressive Strength Test Results
cfe3a6df-6131-51cc-b29e-3086961a6d6e | note | Frequency: Each cylinder
c8b40263-d5d2-5325-891c-e82873ec73f7 | note | - - - - - - - - -
613d9fd3-91df-5df4-8a3d-0acffda91c95 | note | Acceptance Criteria: 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly. 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength. Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
20d4247c-6f3c-5e88-99f5-c3a3c2df8092 | note | - - - - - - - - -
74fa82d6-81be-5813-b0d7-70b9e7f314cd | note | Reference Documents: IFC Drawings VicRoads Spec. Cl.703.11
74833130-9823-549b-a32d-597b00e5bed3 | note | - - - - - - - - -
cb03a222-0a45-58c4-a0be-c5164565e9b5 | note | Inspection / Test Method: Document Review
38906601-c40f-5ef3-ae5f-5484e1b7959d | note | - - - - - - - - -
c09aa7c0-c1e3-5fd0-89b8-329d8aa68bea | note | Record of Conformity: Compressive Strength Test Results
b0317baf-be17-52d4-9e1b-ce24570f4378 | note | - - - - - - - - -
18bdbb94-8cd9-581d-b1b5-7c52b60212e3 | note | IP
62c29249-941e-5e98-b10b-c913cf78a71c | note | - - - - - - - - -
87697ead-4734-5e1b-85be-0137fd75e6cc | note | Responsibility: Site Engineer
5f372323-54a1-56fc-933f-f421467d8295 | note | - - - - - - - - -
e39611d9-9129-50b7-aacb-5a94d5348307 | date | Date Completed:
| checkpoint | 5.4 - As-built Survey
33eb861c-9fc8-5879-aebf-d8a91ea32e10 | note | Frequency: Each element
b180d5cc-a990-572d-b170-47491bf29a84 | note | - - - - - - - - -
d4123d47-88f9-5be0-aa8f-c38271c873fd | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per 711.08 as applicable to the element.
671fd6a6-dbda-5a5b-823d-b722630aa942 | note | - - - - - - - - -
a18c0bd0-baef-59b5-b150-5a89e7760773 | note | Reference Documents: IFC Drawings 711.08 Survey As-builts / Survey Report
df95844b-d11f-5efe-ae8f-dcf9099bc308 | note | - - - - - - - - -
550ef6b9-f5bd-55c9-b51f-c63a54d984eb | note | Inspection / Test Method: Document Review
21be63c2-d9e1-5dbb-81ca-d9d98463a46e | note | - - - - - - - - -
405a8628-990e-56b0-b5f4-ef72ccd097c6 | note | Record of Conformity: Survey As-builts / Survey Report
9444f29e-b23d-5cfb-a7a8-94c99a92cdf7 | note | - - - - - - - - -
c7622eed-612d-5889-a372-95ff0d1a1b2c | note | IP
a07d9084-539b-5fdb-a35f-7cdc144c96aa | note | - - - - - - - - -
dd713c04-220e-5159-a144-0efd4f15d6e0 | note | Responsibility: Site Engineer
85050790-7040-512c-a7bd-dfe3dcebb6ef | note | - - - - - - - - -
173f947f-76ad-5c87-9e6d-6be9c717853b | date | Date Completed:
| checkpoint | 5.5 - Non-conformance Report (NCR) Closure
77ef09d1-2f2d-5adf-9c36-06a5c1673f4e | note | Frequency: Once, prior to closure of this lot / element / Work area
61dc6e40-95f1-5c6c-b17b-c5e4f9c9aaca | note | - - - - - - - - -
e5904829-4fbc-5add-b33f-26d0ef4dc667 | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
331174c5-5804-5d47-bba8-14e41a8d3968 | note | - - - - - - - - -
47a148f5-97ad-5003-810d-2858dd2dcdb2 | note | Reference Documents: Quality Management Plan
70ddf8a8-eac8-53c3-8f06-211d66dbf9e9 | note | - - - - - - - - -
a357cb1e-9f22-5f22-8723-b30ffddd0b8d | note | Inspection / Test Method: Document Review
25c45762-7725-50b8-9b4a-4a6bac457d05 | note | - - - - - - - - -
d97670fe-5431-5fc3-a1cc-321ec94e5c16 | note | Record of Conformity: This ITP
7c77cebd-a75c-5a72-8d41-49824f200d42 | note | - - - - - - - - -
8c9ad663-c80a-58fd-bddb-9084d3352066 | note | HP*
30f35d5c-cfa0-594c-abaa-efe93ecd4630 | note | - - - - - - - - -
867bd664-c82b-561c-914e-feac7fd931cf | note | Responsibility: Site Engineer
47de179e-3eac-5c80-b6e6-7798d5d8d416 | note | - - - - - - - - -
e417501c-07bc-5784-bdf2-c7a50c18ccc9 | date | Date Completed:
| checkpoint | 5.6 - Inspection of Grassed Areas
3fc0cf04-8b15-5fb2-b930-ea8070d1278a | note | Frequency: Each element
b5debbe0-7f15-5868-9c49-3ec644fb6a90 | note | - - - - - - - - -
4235758e-9b3e-5955-b140-95bb453a4c79 | note | Acceptance Criteria: A joint inspection of all grassed areas shall be carried out between the Contractor and Superintendent three months after sowing has taken place.
f6b8c065-f0fa-55b3-b710-077329d4530f | note | - - - - - - - - -
e78aa87d-acaa-5195-8528-53ea461185b7 | note | Reference Documents: VR 711.22 (a)
b73bb08c-98f1-5675-a8ed-0c7817d8b313 | note | - - - - - - - - -
04385ef4-c86e-5805-a439-aa78a3ea316a | note | Inspection / Test Method: Visual Inspection
523d64e9-bb35-5980-b38a-29e7d65fc9c5 | note | - - - - - - - - -
43c3c96c-b4f6-566e-afd3-546f0a136c89 | note | Record of Conformity: This signed ITP
1b2728da-353a-5d8d-956e-764ce50cdf76 | note | - - - - - - - - -
df304e0b-1383-53cb-ac19-f86a52144d7c | note | HP
088c1cb2-6a4f-5c84-94d4-0d8d14420183 | note | - - - - - - - - -
686c96d5-23ab-50ab-871a-ec986cf115af | note | Responsibility: Site Engineer/ Superintendent
d6d18319-d260-59b9-bc56-519b7a3c76a3 | note | - - - - - - - - -
6635065e-7232-53e8-93a9-9b1011a24aff | date | Date Completed:
| signoff | HOLD POINT
| checkpoint | 5.7 - MRPV Quality Final Inspection
b0cc6965-5275-5c60-87e7-dff16e1aaac9 | note | Frequency: Completion of works
4bff7a68-a929-5a30-a0ed-384aa78c006b | note | - - - - - - - - -
45719de9-0a3f-5e5f-aed4-3212b686a3f3 | note | Acceptance Criteria: Lot Signoff by quality team
496de039-25ea-5549-9af4-db70c1865127 | note | - - - - - - - - -
981b68cc-925e-5621-92fa-22f1f4489838 | note | Reference Documents:
0271fbe5-771a-5240-a2bc-4479f0baf704 | note | - - - - - - - - -
9a7c36da-7c1d-5d15-9dff-0e10b72a007a | note | Inspection / Test Method:
73672fdd-fb67-591c-80ac-66f67441d0d5 | note | - - - - - - - - -
d6cec57e-55c0-5adc-bf37-1ad316d15d12 | note | Record of Conformity:
95fb1211-701f-5edf-94c5-1a0f12f97a81 | note | - - - - - - - - -
87c60da9-82ce-58d8-a522-8f9a73c67b6a | note | SCP
00c1117c-96e7-5728-bf35-9e25facb2cb0 | note | - - - - - - - - -
ee83ad48-d498-5cde-93e2-46cab5d21f34 | note | Responsibility: Quality team
4fbaa68d-03cb-5a09-bd10-02a31ba7c14c | note | - - - - - - - - -
b6fade2d-47f9-5f9a-a0e8-a2bbcb87ed94 | date | Date Completed:
| checkpoint | Final Inspection
24d07c87-7136-50c0-aa10-4be827e3df40 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
c386c52a-2929-56dc-8466-bf8857b51790 | textbox | Print Name:
2060e62e-09e9-5f9b-9646-fc4394d606d5 | textbox | Position:
dc9d27a9-f4e6-5cf4-9a5f-c157af140592 | date | Date:
b5835fef-3c70-53f7-a865-70fe3071017b | date | Work Completed On
| checklist | ITP 0066 - Directional Drilling | itp | ITP-066-UT-LOT-XXX - Desc | 464e2bba-b167-4250-b5d1-2fedcd7a21ed
| section | 1 - Preliminaries / Pre- commencement activities
| checkpoint | 1.1 - IFC / Shop Drawings Submission & Approval.
066fff23-c351-524a-8a05-e387ff7b90e1 | note | Frequency: Prior to Commencing
e013947b-9160-572f-919c-592940aa11f4 | note | - - - - - - - - -
8b3be1bd-1ba0-54f7-9cb8-0bc570d61cc1 | note | Acceptance Criteria: IFC Construction Drawings & Most Current Revision.
8e6be179-6960-543a-af72-d50ee46688c9 | note | - - - - - - - - -
57c90699-2f1d-54b2-932e-596556ccf813 | note | Reference Documents: IFC Drawings
91d8cbf3-baba-5502-9ae0-d50341d37885 | note | - - - - - - - - -
64489d9c-4f7c-5e75-ad8d-656dd286e280 | note | Inspection / Test Method: Document review
4097d97d-a4f4-565e-95fd-85916e6f64e9 | note | - - - - - - - - -
78bc5823-b32d-5ff7-a9a4-05b6eaa89bb5 | note | Record of conformity: IFC Dwgs
def8868b-3bb8-5d34-9ade-c9cb06c57d33 | note | - - - - - - - - -
fbd77e93-456a-5817-aaab-2e9af2684d7e | note | HP*
b0da4052-3194-57f9-854f-0f92843ef825 | note | - - - - - - - - -
9211ba1f-3cdf-5413-a53f-b7a65c022213 | note | Responsibility: Project Engineer
| checkpoint | 1.2 - Survey Set-Out
50275f27-80a3-5681-a5bc-09af77aa9902 | note | Frequency: Where Required
3d968144-dd33-5b06-a774-250e85aa820f | note | - - - - - - - - -
12bfc581-24bf-58bf-8d74-4b7899f487d3 | note | Acceptance Criteria: Qualified Surveyor to set out extent of works on ground
4db49e08-0926-53c2-8ec9-d9a8d752d8a3 | note | - - - - - - - - -
b3da18e6-aa74-5643-8086-41387fc845c2 | note | Reference Documents: IFC Drawings
e4b4f735-41bc-553a-8683-0cdf1b54e1fe | note | - - - - - - - - -
11cc4b5a-b31d-5dc1-a822-716c31519bc2 | note | Inspection / Test Method: Survey
881d81e3-c9af-563e-add9-593c85ed9553 | note | - - - - - - - - -
9b78b166-5e24-5627-9c9a-e70dc4cc44c7 | note | Record of conformity: Survey Calibration Certificates
e0ef0084-6b5b-569f-9404-8f47a22ffb02 | note | - - - - - - - - -
69a1a44f-bdcd-5693-98b4-ceb3da657cb5 | note | WP
1e3d9789-26ad-5dbd-b0c9-32a2510d94dc | note | - - - - - - - - -
30d02e07-960d-5bc0-949b-e4b58e361838 | note | Responsibility: Supervisor
| checkpoint | 1.3 - Excavation Permit/ Service Location
b8b06b3d-1456-5a60-a840-8b5bc1036c64 | note | Frequency: Prior to Commencing
6eef006f-b9aa-5348-b402-488b2a30b5df | note | - - - - - - - - -
8c1a07b2-e44e-5aa5-9aa0-2db6c8d91c3b | note | Acceptance Criteria: Identify underground services NDD/hand dig as necessary. DYBD documents
788a4e13-ca3d-5d9d-8a87-60782d0b3567 | note | - - - - - - - - -
3e4c520c-0669-5c9f-ba64-9d2b4535ed3a | note | Reference Documents: Dial Before You Dig
b5752426-8d5a-5f88-91f6-2799da0ae0bf | note | - - - - - - - - -
1b7bdff9-766b-5bf1-a3ac-96d2554a8f48 | note | Inspection / Test Method: Survey
aa9dfc87-43ef-5639-93e1-a21d57c947ff | note | - - - - - - - - -
454ac3e6-c63f-5274-b397-b0d5c3be6c75 | note | Record of conformity: Excavation Permit
11d1bf36-8a56-5e72-9158-9304416a955b | note | - - - - - - - - -
8500da4d-a8a6-54fe-82fe-ca4e6622d746 | note | HP*
2c7bf04e-3d36-5d07-8d5c-56626f24e34f | note | - - - - - - - - -
6ab5a59f-b631-51ed-86a0-59114b4b784e | note | Responsibility: Supervisor
| checkpoint | 1.4 - Superintendent Notification
5e222402-f9ab-537c-8156-ade96f84357d | note | Frequency: Prior to Commencing
5ef08f4e-31e3-5879-a496-cbab97742186 | note | - - - - - - - - -
306d93c0-4a18-545a-98fc-7efd0397b24d | note | Acceptance Criteria: Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work
8b491862-ab91-51e9-844b-9dd39ff5c99b | note | - - - - - - - - -
717f7404-e745-5baf-b7d6-f49e018dc8fd | note | Reference Documents: VR 733.03
b125b69c-88b4-544e-8771-0721aa491132 | note | - - - - - - - - -
393d04bb-4548-5372-a2d9-f0dcd73ff2cb | note | Inspection / Test Method: Document review
0cc5c96d-b586-5858-b27f-352d6146f621 | note | - - - - - - - - -
62907807-7684-5caa-ba84-94860971c8f2 | note | Record of conformity: IFC Dwgs, This ITP
186b7af1-0265-5d6c-abce-4a6a4085bbc0 | note | - - - - - - - - -
6edbd5ee-14d7-5216-a466-f0b891f71fe1 | note | HP
c97c9c07-3c79-5bad-9f54-c83d8da0e6a7 | note | - - - - - - - - -
e6193f12-1253-5565-8b1a-5c3cee6fbc44 | note | Responsibility: Project Engineer/Superintendent
| signoff | HOLD POINT
| section | 2 - Materials
| checkpoint | 2.1 - Conduit Sizing
b621a40f-e2d8-56d7-99c5-a11e9415ea1f | note | Frequency: Prior to Commencing
c326283e-3c43-5c92-8f9d-e994dc70582f | note | - - - - - - - - -
d08624f0-1a78-58b9-ba59-4b1eb6b4daa6 | note | Acceptance Criteria: Conduit sizing to comply with VR table 733.021
d58b4e39-4879-54bb-b816-e393eb090c06 | note | 100mm HD UPVC
1971f7b4-fa2c-54a1-b406-61223aa49c70 | note | Electrical – 114.1mm OD & 101.7mm ID
0af0f6ad-29d9-5df3-8d61-e419e055ef09 | note | Comms – 114mm OD & 104.5 ID
2d9c4f7c-0d0c-5b61-a807-23803ff18f12 | note | Water and Gas
37831242-ae32-5a07-8369-75a3e36856df | note | Gas minimum size 40mm
bffb4938-e21b-5ff4-ace3-f824ed396ce4 | note | Water minimum size 40mm
56c750a7-c67d-5dbe-bddc-f81d64e3f389 | note | HDPE Continuous Conduit
de65b0fc-fb97-52a7-b01c-5d63e355d87b | note | Electrical – 125mm OD & 103mm ID
e885c96a-8a20-58ef-92b5-93f9af66fa3d | note | Comms – 110mm OD & 90mm ID
70ca173f-93d2-5c5e-9d26-2f9c84d9f30e | note | Water and Gas
a627810e-40fe-5178-9a3d-2ad26dab829a | note | Gas minimum size 40mm
563dce05-1971-541a-aea4-a164289143fc | note | Water Minimum size 40mm
866fe713-6ad4-5f3b-8a75-c79ebab6be03 | note | Excludes utility providers designs and requirements
a7b8c1b7-efbe-5f73-addd-1e922c38b9be | note | - - - - - - - - -
7cab9045-9af6-587f-8815-bcd82d78bd1b | note | Reference Documents: VR SS, Table 733.021
e0cd4536-8dba-53fd-9fd5-2019fa84f78a | note | - - - - - - - - -
c474bdf1-59a2-5810-89f5-7823f73d7b3f | note | Inspection / Test Method: Site Inspection
f20c513c-134d-5a52-ae65-81cf56b11b60 | note | - - - - - - - - -
299f6f83-5bcc-5956-a639-ac95f92aa42f | note | Record of conformity: This Checklist
0c4b15b3-5541-5330-8530-0507c2e3dd27 | note | - - - - - - - - -
69ecb6d0-12bf-5605-af81-acec996a69c2 | note | IP
d801e672-e2c0-5a4a-a2d8-ba9796c58a1e | note | - - - - - - - - -
f4c25ada-bf6e-53d8-9a0a-29cad11dadb6 | note | Responsibility: Supervisor
| checkpoint | 2.2 - HDPE Pipe Inspection
ec1008f2-320e-5675-bf2a-c3f2c411db82 | note | Frequency: Prior to Commencing
6fd2a179-3cba-5798-ba03-559bc5c087d9 | note | - - - - - - - - -
2f086d8b-6aab-5461-87f7-a6dcbdb4b614 | note | Acceptance Criteria: Conduits are to be excellent condition and inspected for defects prior to use
db65c4f6-6991-5f50-8930-80de25d5ed1d | note | - - - - - - - - -
8a4eea34-f87d-583d-b654-f2ffa5dd082d | note | Reference Documents:
81435b53-0b6d-5354-ab90-cbf014a034b7 | note | - - - - - - - - -
6c817d6e-5e1f-5e57-afdf-0d5fbd6877b1 | note | Inspection / Test Method: Site Inspection
fa3d6d91-1fff-5b7b-85b9-af8460f38dd7 | note | - - - - - - - - -
3f9df5c7-e0a8-52ac-ad0f-23d92d37507e | note | Record of conformity: This Checklist
e15116da-b122-5b6d-9639-326f1586d2c8 | note | - - - - - - - - -
c7c79498-c431-57da-868f-2b735d08b5e5 | note | IP
bb52b16c-1c6d-5e44-afbb-e4376db2974f | note | - - - - - - - - -
3d23a3ff-a345-55f0-b9e6-ab01f7ba9325 | note | Responsibility: Supervisor
| section | 3 - Excavation
| checkpoint | 3.1 - Entry/ Exit Points
cd4060cc-81e1-5bc3-a49e-12cdd9d40a30 | note | Frequency: Prior to Excavation
1bff47a7-d596-5a6e-95a8-4c6d01ace0b6 | note | - - - - - - - - -
a01be9b3-51e1-520a-a2ea-3c547235b062 | note | Acceptance Criteria: Entry/Exit points to be established
373828e0-1231-5905-827c-1a8ff4a50a3f | note | - - - - - - - - -
e8805ff7-0190-5866-ab3c-8c0c5ce42b4c | note | Reference Documents:
dfbeb9ff-2ba0-5600-8881-acdb78f6f458 | note | - - - - - - - - -
cd6cc1cc-321c-5d37-81d2-266f4dd080ea | note | Inspection / Test Method: Review
d8d4ad3e-d3aa-5de1-b272-4dac46a77b9a | note | - - - - - - - - -
1cb25a93-e54f-5ce0-8742-067113f15232 | note | Record of conformity: This ITP
4909450e-fb24-5269-bab7-63c04873d8b9 | note | - - - - - - - - -
16ea7fcb-d17f-5a42-961b-5c2d3e575534 | note | HP*
27e52879-b6b5-5174-8523-52c048f1c3a8 | note | - - - - - - - - -
30275e0d-24c2-5669-8718-bc232297b1a3 | note | Responsibility: Project Engineer
| checkpoint | 3.2 - Minimum Cover
bf299dd4-25fc-5e16-ac19-c618efd2480c | note | Frequency: Ongoing
30b98569-4c86-5250-9ac9-63b6d9a97de7 | note | - - - - - - - - -
a95d1c18-24c4-5a43-9618-e65e5fc8e15e | note | Acceptance Criteria: Minimum conduit cover shall apply as per table 733.031
8437f41d-3f19-50d7-bf2c-998fb142e2e7 | note | Under Freeway Pavement – 1200mm
a4481132-fc33-5c40-8a94-910a7fc15a80 | note | Under Arterial Road Pavement – 1200mm
e4a2a0cb-03a1-5e60-956d-17eb1dbd2966 | note | Under Local Road Pavement –600mm-800mm
f2f97429-8ae9-5ffb-8d59-2f847008309e | note | Under Open Drains – 750mm
01f17e6b-7127-5317-acc8-444cf9035d54 | note | Under footpath or unpaved areas (LV Circuits only) – 600mm
b3f870f3-9926-5cc1-8e17-eeec39ddd57c | note | Under footpath or unpaved areas (Extra LV or Comms conduits only) – 300mm
13c347d4-1fec-5399-aceb-2090cb4ea7c2 | note | - - - - - - - - -
707f86fa-9c63-57ac-a0c4-145c000d90fa | note | Reference Documents: VR SS 733.031, Refer Individual asset owners specifications
b9689664-2d7b-5ab1-82f8-85af0867d504 | note | - - - - - - - - -
6a0cb418-1119-5e1e-a68d-dd6b989ed62f | note | Inspection / Test Method: Survey
4f3ca3d8-a3e2-5753-bfce-fc2c42fa4196 | note | - - - - - - - - -
70c325ac-9fbe-526c-ba96-9314a36bd039 | note | Record of conformity: AS Builts
5512dbee-3462-5af4-bce7-987e63720d0e | note | - - - - - - - - -
11a42503-459d-50b7-8aa7-ca9135f8cda5 | note | SCP
645ca6d0-5a27-53ed-b9e8-b24d6f1938e9 | note | - - - - - - - - -
a3da5171-e63f-528c-9891-28a78f34ddf2 | note | Responsibility: Project Engineer
| checkpoint | 3.3 - Survey pick up / Bore Mark Out
27f98a10-e346-5edf-a8cb-367d63fdaeb2 | note | Frequency: During Bore
cd237da5-b7c9-5f5e-b2ef-0c9a237e6608 | note | - - - - - - - - -
4b3b766c-6475-555e-84cb-77b572b8f9a0 | note | Acceptance Criteria: Bore head to surveyed at approx. 2m intervals and tracked beneath road. Survey to also pick up as record of conformity
4a52f8f9-f063-5fb0-9e86-09d8a24051a0 | note | - - - - - - - - -
0d64d0c9-1662-5b52-a399-dc56be080f2f | note | Reference Documents: Bore Tracking Sheet. Survey
6c5f4432-250b-5e14-9550-4e601b574e33 | note | - - - - - - - - -
73055f9f-a50c-5b58-bf96-c9212f5138fa | note | Inspection / Test Method: Survey
d3267823-46d4-5d0b-a0fb-7eeac5382ec1 | note | - - - - - - - - -
adb666dc-5dda-593f-8a95-2b208137201a | note | Record of conformity: AS Builts. Bore Log
a8e5a871-7ad3-5273-bcac-d2bb24cfb7dd | note | - - - - - - - - -
3b68287f-f77a-5edc-a512-38fed1a74e29 | note | SCP
3e9a775c-f0b5-5422-b430-98544a55f1be | note | - - - - - - - - -
61af9ff8-7227-55fa-bea9-96d33dbda283 | note | Responsibility: Supervisor
| section | 4 - Completion
| checkpoint | 4.1 - Entry/ Exit Points
89f7fe56-b458-5604-913f-760876a75603 | note | Frequency: On Completion
38d9a0bf-581d-5aa2-8eb5-c3a0276b6401 | note | - - - - - - - - -
f875d21b-b7b5-525c-980f-197eb149342f | note | Acceptance Criteria: Ensure clean fills is used to fill in Entry/ Exit points
61c1b1b5-2dc1-51de-8c09-d4f1dd98357d | note | - - - - - - - - -
4e100bf9-432e-55cf-b459-d55b34a862fc | note | Reference Documents:
c9b0307c-3943-5458-9a69-d75a87b008f5 | note | - - - - - - - - -
8b648f26-7d5c-566a-966d-27efa9887aea | note | Inspection / Test Method: Review
6c4d046d-3d9c-55fd-8cd6-e847eef90766 | note | - - - - - - - - -
4807ee65-c7db-5086-9bd4-ae37377a9b5b | note | Record of conformity: This ITP
ea0fbf17-ffc2-5615-aad5-9882e10667c0 | note | - - - - - - - - -
dfd70f03-4dc1-5569-b17f-ffeb4ff67ce8 | note | IP
617f978d-f586-5c1f-8763-4979bb329a37 | note | - - - - - - - - -
8fa14dbb-de20-5ea2-b717-98ad827457bb | note | Responsibility: Supervisor
| checkpoint | 4.2 - Grouting
2ac31562-428c-58e7-8c5d-2d1f7b579768 | note | Frequency: On Completion
a79a1d0e-00b0-5c69-b513-3e7e9e36df94 | note | - - - - - - - - -
65b6d3f6-afe3-5688-ab18-f4458213ae06 | note | Acceptance Criteria: Unless specified on drawings, grouting shall fill the voids at the low injection pressures without causing deformation to the conduits within bore holes. The ends of the conduits shall be sealed watertight to prevent ingress of grout.
069d777c-f869-55ad-9afb-44784b849cc2 | note | - - - - - - - - -
db4db7d7-cff8-59be-ba6e-f3ecead875d3 | note | Reference Documents:
31e71811-da27-56e4-971a-89b559cae6fd | note | - - - - - - - - -
4d832a24-8c08-53b9-9761-0f543d141f7b | note | Inspection / Test Method: Docket
c690ab5c-0f35-5d80-b098-284af6d7db2c | note | - - - - - - - - -
f62ee604-5ce0-5c19-9ea9-b5f49720ddef | note | Record of conformity: This ITP
6387a80b-c37f-5b19-b54a-6a45d4916b92 | note | - - - - - - - - -
9b2dfff0-0403-5f65-801d-6015a01bd564 | note | IP
758824de-a2f3-55b8-a7bf-77be6db4b4c7 | note | - - - - - - - - -
9736af75-55b4-5de8-8a55-595b96008a56 | note | Responsibility: Project Engineer
| checkpoint | 4.3 - Backfilling
acf4209e-842e-5229-bb5d-40aba3c02176 | note | Frequency: On Completion
2831c533-070f-5122-bb14-231d60a31db0 | note | - - - - - - - - -
c70d9029-e75b-5c95-9d43-2b2bafcdbcde | note | Acceptance Criteria: Before Backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative
e291509a-bf5b-591f-9375-1d05bc2634db | note | - - - - - - - - -
ed3718b8-2a22-5081-b2be-a5ff84a6329e | note | Reference Documents: VR 733.03
9f93a2cb-152f-5bb8-9649-68c24f4c671d | note | - - - - - - - - -
23c243be-b723-51b1-93dc-deca1ec0b22a | note | Inspection / Test Method: Inspection
b509cbad-e51e-5b2d-b788-f54eeee70fdb | note | - - - - - - - - -
10f20761-1a3a-5a69-a1ff-218ec9d48a82 | note | Record of conformity: Inspection
5b574b7b-1e14-571d-8e04-b7040879a443 | note | - - - - - - - - -
a415119d-a0ab-5b28-ae3f-6baa0b797976 | note | HP
474b4d17-5007-5bfc-95a6-7cdcec21fccd | note | - - - - - - - - -
81881699-43b6-5a19-bb89-47bd1d2d032d | note | Responsibility: Superintendent and/or representative
| signoff | HOLD POINT
| checkpoint | 4.4 - Draw Cord
f2136f2a-387a-5cd3-8780-7a71fae80713 | note | Frequency: On Completion
7a8c3406-1ad4-500f-a9d7-e69af4fafdc7 | note | - - - - - - - - -
404253cd-0f02-5cd2-9d84-b133bc3cd6d5 | note | Acceptance Criteria: Each conduit for electrical wiring and communications cables shall be provided one synthetic draw cord not less than 3mm diameter and a minimum breaking strain of 1.6kN
d877edbe-02e1-5416-9ffb-9c4043125570 | note | - - - - - - - - -
e87d7042-c0e4-593b-9f6d-2c9983eff97c | note | Reference Documents: VR SS 733.05
b4187db9-a18e-553d-9aab-6b0f3ef7251a | note | - - - - - - - - -
28b08bb1-13e1-59a8-9235-0722c8d9d79b | note | Inspection / Test Method: Inspection
09e9a205-6559-5e41-80ea-b6404b1f3848 | note | - - - - - - - - -
8463822c-ca23-5037-bec1-5f0bf9417994 | note | Record of conformity: This ITP
2e58754e-0b5a-5b4f-ade0-48b510999e8c | note | - - - - - - - - -
a7308fcd-5b34-5ffc-862a-79ee3829f742 | note | IP
aa54601b-cd0b-5ca3-9145-f59e1f516da3 | note | - - - - - - - - -
1b47f47e-217c-5a31-8eb9-778a0773d043 | note | Responsibility: Supervisor
| checkpoint | 4.5 - Site clean up
76553985-59c7-5cf4-b1d8-bd6ec4cf935f | note | Frequency: On Completion
ff26e060-0e83-57b6-8772-028d25c7781e | note | - - - - - - - - -
a5683c54-1b15-526b-abfc-9efc6f0064cb | note | Acceptance Criteria: Ensure site is clean and all garbage has been removed
95174388-fb4f-57d5-98af-9c05d585bb31 | note | - - - - - - - - -
b9c77eea-f9be-5126-8b41-9a5c5d26640d | note | Reference Documents: VR 733.09
dfae66c2-d7c7-510e-a564-af387918f2db | note | - - - - - - - - -
36ea458c-22ed-5171-959b-a87d31ad0878 | note | Inspection / Test Method: Inspection
34a72e97-020c-5340-8b89-0eade6f4f271 | note | - - - - - - - - -
361b501f-4cf3-57d9-a3a6-f55329360e1c | note | Record of conformity: This ITP
2d84ece1-f59d-5871-8032-b0dbd1c3c20c | note | - - - - - - - - -
11a72af8-f304-5ba3-a3c4-ba2c04d7dae9 | note | IP
b3017a22-af2f-5fcf-bb79-ff5db41bf544 | note | - - - - - - - - -
88b0ad91-2594-5aec-8b05-57a3dd6a54cb | note | Responsibility: Supervisor
| checkpoint | 4.6 - Records
33dbfd6c-a69f-5d21-ab5c-6ffc2a1dfa4b | note | Frequency: On Completion
ac11f811-f29f-52a7-8593-2c53f883e53e | note | - - - - - - - - -
c455d24b-3bb5-566b-a0ce-5506c581101a | note | Acceptance Criteria: Bore Logs of the works to be supplied from subcontractor
159d00c8-17a0-5d88-b8d2-547dc71fea96 | note | - - - - - - - - -
af6a3a31-3196-5b0b-891f-74b5d60ed795 | note | Reference Documents: Bore Logs
111a990d-9dd6-5853-95c0-f794ee4127e7 | note | - - - - - - - - -
4e483537-2f0e-5465-8e02-344a280004ac | note | Inspection / Test Method: Document review
05d86901-fea4-5dae-90c2-38af4cb64a68 | note | - - - - - - - - -
56db3d1e-0f4f-56b7-8d6e-43068687295d | note | Record of conformity: This ITP
a7d81922-1750-55f9-8dd9-4a49253d40a0 | note | - - - - - - - - -
4f975ea3-c147-54f0-b421-9b5c8602538b | note | HP*
85cfba16-b859-54e4-bb4f-d18ab2e990aa | note | - - - - - - - - -
cb7312d3-9663-5dc8-9b30-d21ac532f453 | note | Responsibility: Project Engineer
| checkpoint | Final Inspection
dc11d6bf-96b3-5e8d-b1ee-40091793ee38 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
53d5ef79-09ab-567e-944d-ec3d344baa76 | textbox | Print Name:
c323b967-9b1f-574e-b8cd-afc63a856b90 | textbox | Position:
34a3c77b-4c5e-5dc9-968c-941b895a9d07 | date | Date:
83936d7b-c9e2-54a1-a14b-04f8c4e5b4ed | date | Work Completed On
| checklist | ITP 0074 - Installation of Fencing | itp | ITP-074-AX-LOT-XXX - Desc | d7f927f7-508a-4e63-b7bd-b65ce0a0c1b2
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check that current revision drawings are being used
8272ed9c-f676-51bf-b9f4-cad2aefda2a8 | note | Frequency:
f6e73758-70f2-57e4-b3df-aefa6b6d0372 | note | - - - - - - - - -
1d603eac-98fb-50cd-8a65-6d03027a785d | note | Acceptance Criteria: Prior to Commencing
44ef205f-ee3f-5e75-8cfd-0145d7792234 | note | - - - - - - - - -
4d8ff7a4-aa0a-5f2b-a1bd-11a5d6f8fd24 | note | Reference Documents: Issued For Construction (IFC) and latest available revision used.
e4542977-fe01-568f-b20e-6752966595c2 | note | - - - - - - - - -
7b4c65ae-1da7-5500-a2c1-7c9589f2accd | note | Inspection / Test Method: Project Drawings / Drawing Register
1f8a719e-12f1-5b88-a26f-1bc849dc011a | note | - - - - - - - - -
5b5cabf8-60b4-533f-b34d-3cdac8aa529b | note | Record of Conformity: Document review
fe961f74-b692-5a66-8033-b17378e685cc | note | - - - - - - - - -
5310bcb6-c926-5ffa-8087-7b328eb4e0ac | note | Latest Revision Drawings
ac140c3b-0763-588e-88e0-4b89497f8c03 | note | - - - - - - - - -
4d3655b5-2633-5e10-a20b-2373a9d0f768 | note | Responsibility: AP
| checkpoint | 1.2 - Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environmental controls are in place
77c199b9-8975-51c4-8a04-7b23ab72ce33 | note | Frequency:
614619a3-8e5d-5574-aee4-15a9b1b2cbd4 | note | - - - - - - - - -
98bb8caa-e7eb-554d-b74d-e524df237e5e | note | Acceptance Criteria: Prior to Commencing
3e60a630-8782-572a-a854-ff58b68a7e2b | note | - - - - - - - - -
2f3dc5fa-50a9-5202-adfa-79655f84ccc7 | note | Reference Documents: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified .
a9de1f7b-6e0a-579c-883e-3ae248392109 | note | - - - - - - - - -
8d8adf0a-af1a-5a36-8d88-25bc68ad8135 | note | Inspection / Test Method: EMP, Site induction, Project Specification Cl. 1200.03
07d26f75-eee3-5d41-b4ab-daeaaa5b0f07 | note | - - - - - - - - -
d97bc0b2-2df9-5a1e-b58f-076c4e3499be | note | Record of Conformity: Document review & Site inspection
3ac20a9a-487a-5bdf-b261-29c02ef3fcef | note | Signed ITP
8ec23993-0218-5dd2-8a99-ac8d9798bb78 | note | - - - - - - - - -
14c873c2-9cf8-5934-b099-78d93c6c459e | note | Responsibility: IP
| checkpoint | 1.3 - Excavation Permit Issued
38a7b493-c5fe-572a-b9b5-e501aad9c750 | note | Frequency:
223ac2dd-1d1b-5780-896c-16448427166e | note | - - - - - - - - -
c99e1abb-0acd-5139-9675-d4f6455c668e | note | Acceptance Criteria: Prior to commencing work
1252db41-e30b-58c5-a8ee-f6091b539923 | note | - - - - - - - - -
e854adfa-647e-58e7-8277-26dcbd6aca4f | note | Reference Documents: Current Excavation Permit (GPP) signed and specific for the area where works will be executed.
83fb636c-df1b-56a8-abb5-7da987a4381c | note | - - - - - - - - -
b4a81e3b-c887-559b-83c3-6edb6e7aef5a | note | Inspection / Test Method: Excavation Permit
f8d540bd-f8b9-500e-b10d-b92cf2ef0695 | note | - - - - - - - - -
848414e4-6be5-5f2c-9eba-719f2a6825f2 | note | Record of Conformity: Document review & Site inspection
45722479-fa10-59ee-a685-282d3dc3fdaa | note | Excavation Permit #
b9a6078a-ee60-5c6a-8d65-5cbe9ba92517 | note | - - - - - - - - -
89a358cd-e3b6-566d-b6b4-c72ca754681a | note | Responsibility: HP*
| checkpoint | 1.4 - Traffic Management (When required)
a42e5742-ef42-5988-ac0c-0d67891d4c97 | note | Frequency:
c0ed39e9-073f-537b-8a26-b879009fd105 | note | - - - - - - - - -
e4a34764-a9d9-50c9-a0a8-8c4c1bb8e002 | note | Acceptance Criteria: Prior to Commencing Work
67162e0b-31da-5999-95c8-c6110700ddf0 | note | - - - - - - - - -
97e9e497-080b-5c4a-9c7f-e14bafaa822f | note | Reference Documents: Approved Traffic Management Plans and Permits: TMP and MoA.
1e811a65-e4d3-5c54-9bf1-de5bf2b91fc8 | note | - - - - - - - - -
f4c0f02c-8a88-552e-ba54-59571f10de05 | note | Inspection / Test Method: TMP, MoA
c5a9123a-f7dc-5d88-902f-7b667275673a | note | - - - - - - - - -
d7a668fd-a35e-5218-8382-0cb18a59ca62 | note | Record of Conformity: Document review & Site inspection
129462c4-a82a-5559-ab11-58b0440ddd98 | note | Approved TMP & MOA
039473cd-dfdb-546f-b43b-66ebe711593b | note | - - - - - - - - -
c52c6dab-ee70-5e7e-bf29-40ad56103ae3 | note | Responsibility: AP
| checkpoint | 1.5 - Material Conformance
2c305bf0-f4ab-5d78-864f-8171ec6ba174 | note | Frequency:
81ee646d-4317-5a94-89ea-afd38798a999 | note | - - - - - - - - -
d8f63120-b167-5999-97f2-f1c7635d2ac9 | note | Acceptance Criteria: Prior to commencing
cf475b3b-422b-5f10-9b89-3b7b467539ce | note | - - - - - - - - -
6af016b9-f873-5c29-9e7b-f3f1b32efa7e | note | Reference Documents: The Contractor shall submit for review by the Superintendent prior to the proposed use of fencing materials, gates and connections to existing fencing, a signed certificate including relevant test reports demonstrating the compliance of the materials and components required for the construction of each type of fencing, gates and connections to existing fencing, comply with the requirements of this specifications.
85b2f397-3fcf-591f-9433-e58f7ffcbaa7 | note | - - - - - - - - -
593ee99b-58b3-5b9e-965e-284c2f41672b | note | Inspection / Test Method: VicRoads Sec 707.03
e0263d32-85f6-5977-8117-2bc4694a956f | note | - - - - - - - - -
de3d582d-31f5-5955-ad14-96995b4eb820 | note | Record of Conformity: Document Review
23368ac8-46c8-5290-9a82-fcd3e1362fd9 | note | Certificate of Conformance Relevant Standard Drawings
f74067de-b5a6-5d24-b6dd-63bdaa1f7a0a | note | - - - - - - - - -
568d8d62-9ba5-5cd6-b5d0-c700b2da7fc2 | note | Responsibility: AP
| section | 2 - Construction
| checkpoint | 2.1 - Site preparation
02423719-7ba2-58d4-9fd3-299cd249622b | note | Frequency:
13b61703-c336-5507-9734-1effc5d19d36 | note | - - - - - - - - -
b6d1f9d5-5c71-5e53-9e9f-64b43d2bdfa8 | note | Acceptance Criteria: Each Lot
58646f98-0492-5fe7-90f2-57cf8167143e | note | - - - - - - - - -
6f40beae-8a83-5f88-b471-989b666e508d | note | Reference Documents: All logs, stumps, saplings and undergrowth within 1 m of the fence line and all trees which will interfere with the proper construction of the fence shall be removed and disposed of. Any high points which interfere with the placing of wire or wire netting shall be cut down to provide the clearance shown on the detailed drawings, and any low spots shall be filled with surplus earth from holes and trimming
4fc26244-c8d6-5d45-a26a-90daa9441ce8 | note | - - - - - - - - -
d4c71fbe-c4af-56de-90ff-c2152d0ed2cd | note | Inspection / Test Method: VicRoads Sec 707.04
d3bbf3c7-bef9-5e6a-9981-9234acaefe59 | note | - - - - - - - - -
6476e4d8-fcc1-550d-a2fe-22b5a04612b5 | note | Record of Conformity: Site Inspection
3dfb01ff-a9e6-53e9-bdfd-ac366d6245d8 | note | Photos
7c2d4f1f-be3c-57bf-a8a5-c4c1ff61aed2 | note | - - - - - - - - -
21bee1be-c8d1-58fe-8b58-34b144333a8b | note | Responsibility: IP
| checkpoint | 2.2 - Fencing Set Out
9200e95c-4d0f-5bbf-9628-b33c403af564 | note | Frequency:
7a5b5ca6-68e6-5459-ae8a-c09aa9fdf553 | note | - - - - - - - - -
bccce6c7-a235-5cf2-bb46-887d8750224c | note | Acceptance Criteria: Each Lot
b4af4590-926a-53ec-9eb5-e1e29c75dc77 | note | - - - - - - - - -
cbbc50db-34b4-5d5e-bcf3-3120e9a11549 | note | Reference Documents: Surveyor to set out fenceline as per drawings and set out posts as per drawings if required. Cadastral Boundary Surveyor when in related to property boundaries, Right of Ways, and Titles.
8e176d98-f9d7-584c-8e0e-8ab314a01466 | note | - - - - - - - - -
b4d573b4-b2a5-5269-8b96-79b84188ff1b | note | Inspection / Test Method: Drawings
43a4e3ed-398e-5c87-ac53-32f62ce47c04 | note | - - - - - - - - -
d55fe73c-b39e-5a2c-96e9-ea8b1ee9750f | note | Record of Conformity: Site Inspection
6759745c-1344-5776-bc93-17e67b41052b | note | Drawings/ Survey Set Out
| checkpoint | 2.3 - Install Fence
dab0f6ca-b728-5afe-9b91-fa92be00870b | note | Frequency:
8259db89-3a67-5bce-9b60-111a310f7d27 | note | - - - - - - - - -
e3ebb72f-52d6-5a03-966d-7cc7964d89f9 | note | Acceptance Criteria: Each Lot
0acbe477-ae2e-502e-b70d-35bbe7db0dfa | note | - - - - - - - - -
14e458c7-7ad6-5b8a-a389-d74be8dc15f8 | note | Reference Documents: Install fence as per VicRoads Sec 707.04
b218dbcf-fb6a-5d59-a812-6845d31e5fb6 | note | - - - - - - - - -
3e06c7dc-26eb-56af-86a2-5d4ec5d3835c | note | Inspection / Test Method: VicRoads Sec 707.04
692d905c-5b30-5390-8266-9d2b500b71cf | note | - - - - - - - - -
8be0bbce-5c62-5f10-a8e1-96c78d78cbeb | note | Record of Conformity: Site Inspection
c781705a-c2bb-5e20-af87-c13cc86da694 | note | Signed ITP
ba763a5c-e016-5970-ac84-2ba1974669e2 | note | - - - - - - - - -
3b66e3ac-524e-53ee-9331-0987168bcf99 | note | Responsibility: IP
| section | 3 - Conformance
| checkpoint | 3.1 - Asbuilt Survey
edc50b88-7262-589d-8ea9-8f14edf25f57 | note | Frequency:
75b11437-4910-5c60-93bc-afbbc00e3a13 | note | - - - - - - - - -
ca9d236d-50ea-5125-bcda-fd01ddc20be6 | note | Acceptance Criteria: After installation
ecd643f9-00d5-55d1-9883-55a241c39a8d | note | - - - - - - - - -
ff1329a6-713c-5508-a71b-ab1ac44150a9 | note | Reference Documents: Construction Tolerances: the vertical tolerance on the height of the fencing shall be Â± 20mm from the design line. ( b ) the longitudinal line tolerance for the fencing shall be Â± 20mm in plan view; and ( c ) the tolerance on the verticality of fencing shall be 1 in 50.
04185027-2f60-55b8-bb32-d752bd16383e | note | - - - - - - - - -
98604e73-e159-5a71-ba06-b17eacc57db5 | note | Inspection / Test Method: VicRoads Sec 707.08 Asbuilts Survey Report
3b57d127-ef93-5d3e-9482-054940aa050e | note | - - - - - - - - -
33c00b19-73b7-5b25-9a7f-b8f574cd1783 | note | Record of Conformity: Document Review/ Site Inspection
f4c19a67-988c-584b-97e0-d1224686aa99 | note | Asbuilt Survey
395fe021-965b-512d-966a-f9ea10ec2ec3 | note | - - - - - - - - -
b8c01086-83ba-54cb-9a9e-b71627cf48bd | note | Responsibility: SCP
| checkpoint | Final Inspection
cec1b81d-c94c-57d2-b3ea-a368785084aa | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
27edbaa1-bb58-5753-8d0b-0a66809aebbb | textbox | Print Name:
5a2576fc-de2e-5f80-a4d7-be3aef7b5977 | textbox | Position:
edda6458-e4c4-58b8-9fb5-5b0ee06d4737 | date | Date:
85c2f737-dd83-5331-80f4-80bcfd361cca | date | Work Completed On
| checklist | ITP 0075 - Asphalt Placement | itp | ITP-075-AX-LOT-XXX - Desc | 9fb03d06-6160-4b7b-a83b-cfefade42822
| section | 1 - Preliminary Works
| checkpoint | 1.1 Submission of Mix Design
1b7bc405-ec7f-5a15-bdf4-c8e465bc2bd6 | note | Frequency: Prior to commencing paving
99809eb4-8047-5bdb-a5d3-682ab1547ea5 | note | - - - - - - - - -
836e698f-4948-5b83-bd66-b026aa4a63e5 | note | Acceptance Criteria: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
f5703050-e7ff-56ef-9e8c-60f52658c998 | note | - - - - - - - - -
a53eb7df-03ae-5117-bbad-c5b2bb99c4e6 | note | Reference Documents: VicRoads Spec. Cl.407.06
b0aed64d-18eb-5168-82ac-3b9f95efa441 | note | - - - - - - - - -
4f2d2ac6-a6ac-5e87-9329-c35df229f7ea | note | Inspection / Test Method: Correspondence of receipt of mix design
d91ff0d5-2a67-50ef-9ada-a19b82f4fea6 | note | - - - - - - - - -
316cc0c1-bd97-5e01-a4eb-eeb5b1dce1cb | note | Record of Conformity: VR approval Completed ITP
97eec926-02ce-5d3d-9bf5-0d66a24d2f7e | note | - - - - - - - - -
d673e282-1c3c-50fe-af56-0cfddd3a150a | note | HP
874039e7-8b76-554c-8d7c-e0fbd4d52f83 | note | - - - - - - - - -
bfc2a3b0-d3f2-56ac-90de-be62cb2b6a77 | textbox | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
| signoff | HOLD POINT
| checkpoint | 1.2 Ensure underlying lot conforms
2b930925-852c-5dfc-9595-e88b9d86b92f | note | Frequency: Prior to Commencing
5d5fc687-6b76-5b4b-88fd-d2c78bdc6a16 | note | - - - - - - - - -
30365570-37b1-5730-866d-d066b79a1ab6 | note | Acceptance Criteria: All quality information received for lot (includes levels, area and volume) and NCRs (BIRs) approved.
b7ec6abf-2511-564f-a935-f6fa08151c36 | note | - - - - - - - - -
13844e14-4ce7-5634-94bb-dc77f0d25781 | note | Reference Documents: Relevant ITP for underlying lot
0e5c313f-6649-55cf-a531-be948b4c2194 | note | - - - - - - - - -
da0ef21c-0bed-5d37-8dae-8bea3e9c5e56 | note | Inspection / Test Method: Document review
6d339af9-40b9-52a5-8289-901b3a5a2a26 | note | - - - - - - - - -
dacee665-29bf-51ab-9ca3-db3acffab0cb | note | Record of Conformity: Inspection and Test Plan
65bf06c5-f123-5f14-b55e-e38fc26af2a3 | note | - - - - - - - - -
ffe9ca3f-c17a-5524-b9d1-541a9fc2f76a | note | HP*
| checkpoint | 1.3 Visual Inspection of underlying lot
aaff4602-97a2-56f7-bd9a-746d3aa43a3e | note | Frequency: Prior to Commencing
198275b5-0a7d-5349-94ef-5eaab5827d60 | note | - - - - - - - - -
62e1cc2c-3fde-5c6d-9a06-a16d0be7801f | note | Acceptance Criteria: If the execution of any part of the work under the Subcontract is dependent upon the quality and completeness of an existing surface or work performed by Separate Contractors, the subcontractors shall visually inspect the existing surface or Separate Contractor's work for matters including the following:
1b7f582d-e784-566c-a2ca-37eeb83223e1 | note | (i) Homogeneous surface and pavement material
2ff35f40-48ea-5b7e-863a-cde69b8d847b | note | (ii) Uniform in texture
1d91882c-ab47-564c-94e7-c112069c7bcd | note | (iii) Free from tearing and scabbing
aa3a9148-20f0-5bee-8955-e2800b0f4b70 | note | (iv) Free from laminations
911fe582-5557-5d32-99e0-1ce19b5f2a56 | note | (v) Free from loose and foreign materials
0ee074ba-bad8-5232-80d0-49fe21fc0ed0 | note | and immediately notify the Contractors Representative of all matters discovered that a competent contractor who specialises in the type of works performed under Subcontract should have discussed by such inspection which in the Subcontractor's opinion render such work unsuitable for the proper execution of the work under the Subcontract.
55723bb9-b91f-5555-8670-31a4befcfcc7 | note | - - - - - - - - -
f5c37ad9-801c-58fc-b3fe-d0c05479b83a | note | Reference Documents: CTW-175S Special Condition 11 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
4be24681-2833-53fa-8f51-6d4544f5a544 | note | - - - - - - - - -
e5bb216f-37d1-50e0-8dd7-165d72d8e45e | note | Inspection / Test Method: Visual Inspection
422b1ff5-7d8e-5793-b4f6-60dc66a042b9 | note | - - - - - - - - -
0582fb5a-47b6-5b77-8d22-705add6281e9 | note | Record of Conformity: Inspection and Test Plan ITP Signed
9d287059-893a-52ed-9f22-3c9650ed9e30 | note | - - - - - - - - -
27a39220-ba25-5d35-97d1-e3b8506ed2ef | note | WP
aad5410a-5196-5156-8a86-f90b6ae55696 | note | - - - - - - - - -
a17501da-f65b-5eeb-a2b5-4d0dbf98e4a4 | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
| checkpoint | 1.4 Ambient Conditions for Placing
72d00199-f019-50fc-a402-d1483e5bd32d | note | Frequency: Prior to commencing paving
dd23532b-08fa-52e9-8a39-29625298785a | note | - - - - - - - - -
327557dd-8c13-566d-85ed-b12f346ba8b5 | note | Acceptance Criteria: The majority of the surface area to be paved has a temperature greater than or equal to the following:
207f3065-fda3-5fde-9fb0-056963b337c7 | note | Base & Intermediate Courses: 5°C for conventional binders or
793fcf66-6eb4-57eb-8a9d-181ef6f997dd | note | 10°C for PMBs & Class 600
191f024f-21ce-5034-91e2-5153f4ffe215 | note | Wearing Courses: 10°C for conventional binders or 15°C for PMBs
7b704b05-f21d-53ce-8eaa-0585d97529bf | note | - - - - - - - - -
340c1295-e6fe-5481-a057-b6c518829d38 | note | Reference Documents: 407.13
33ca463b-ad02-53a2-a788-0e4756a4a8e4 | note | - - - - - - - - -
d9cd0ea2-220b-5ed5-b4f6-f84c88ed5827 | note | Inspection / Test Method: Verify
0198cb12-b985-5f83-828b-174b46f22324 | note | - - - - - - - - -
09898ea6-3f4d-5cdd-bf1e-ea1f5f8e755d | note | Record of Conformity: Thermometer / gauge
c3e3b7cc-fa97-5435-829a-ef712d894639 | note | - - - - - - - - -
3e7ac92a-f3d8-5ff6-be97-262615157772 | note | IP
80719627-ae38-5228-97ba-845468143f4a | note | - - - - - - - - -
f07c976b-4735-56fa-a13a-32fe7387dc08 | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
| checkpoint | 1.5 Planning of Joints
c72d38d0-8f75-5ea2-b303-0bdcaf24f239 | note | Frequency: Prior to commencing paving
701478fd-b0fe-5d30-a754-da34e5f3a399 | note | - - - - - - - - -
7536df86-b75d-57ff-9965-c07191da1e90 | note | Acceptance Criteria: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client (MRPV):
bfb0d414-34a9-53d7-bd33-fe27c5261d87 | note | (i) Transverse Joints Offset from layer to layer by at least 2m
6240f938-0fb9-5fe7-8431-597cbb2489fa | note | (ii) Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. V
142500fa-7590-5949-9f1d-a30b9dbdbb80 | note | (iii) Wearing course shall be on lane lines.
bce5c6a8-5552-5f1b-96ec-88dfeeff2052 | note | - - - - - - - - -
62d9be92-52e7-58cb-9f24-35af6379a9e1 | note | Reference Documents: 407.17 (b) & (c) Pavement Drawings
28a2ddfa-5aae-5aca-9e0f-13fa6f7e76f9 | note | - - - - - - - - -
c18f4bed-870a-590c-806b-2525c28ef117 | note | Inspection / Test Method: Measure and mark out runs by tape measure or survey
bb9bb864-fc5f-5aa4-a8e8-2f57c4f3d12d | note | - - - - - - - - -
e56f0cb5-baaa-536e-9be4-4ed3d2a71b95 | note | Record of Conformity: Paving Plan
d47264ea-9b37-51af-a02e-92a4c97c8c3b | note | - - - - - - - - -
1960d1ba-6a83-5d08-8ecd-6e08ba2437f9 | note | WP
95e3e8aa-9b51-5253-8c7d-91a61bdcb44c | note | - - - - - - - - -
a431e0cf-b196-5d9e-9260-47401e2c0684 | textbox | Responsibility: Project Engineer/ Asphalt Supervisor Superintendent
| checkpoint | 1.6 Longitudinal Joints with existing Pavement
fde1c66a-e814-5776-9bc9-a10cf3f80ed1 | note | Frequency: Prior to commencing paving
3f442c34-d5cf-5886-acbd-8ccd41c12806 | note | - - - - - - - - -
3c85accd-0863-5691-b0b0-6d59bfdd54f5 | note | Acceptance Criteria: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each individual layer.
7cd74247-85e5-58d9-9123-40477c9509e5 | note | - - - - - - - - -
323d9aa1-7fee-58fc-a81f-d5280ba94ff2 | note | Reference Documents: 407.16 (c) Project Specs. Section 3040.06 (d)(vii)
4737c6ae-f0b2-5f57-a65a-bdeec6b7cb15 | note | - - - - - - - - -
d738f46a-d830-5250-be41-c45f48b7dacb | note | Inspection / Test Method: Visual Inspection
7ef66568-4127-5db1-83bc-e301d573c7ef | note | - - - - - - - - -
156574e4-50fb-5618-ae15-1aba8efabdf8 | note | Record of Conformity: ITP Signed
80c0e9a1-f058-569f-aec1-6d0f83c7e3c1 | note | - - - - - - - - -
da532611-bce6-549f-9d2e-d19d709e30ff | note | WP
b13f4a92-70ca-53a6-93c0-09d8bd6266d9 | note | - - - - - - - - -
aad81b11-88c6-5baf-9ebd-a607d7711b13 | textbox | Responsibility: Project Engineer/ Asphalt Supervisor
| section | 2 - Asphalt Placement
| checkpoint | 2.1 Commencement of placement
bd380ff1-1d6e-5bcd-97c6-5f26bfa6f44c | note | Frequency: Prior to commencing Paving
e8a3dc2e-479e-52ac-b711-9e273887511e | note | - - - - - - - - -
6adacc4b-3bee-5be8-a224-26527e5f3c7a | note | Acceptance Criteria: Approval to place asphalt on the sub-base or granular base for a new pavement or for an ordinary of an existing bituminous surfaced pavement.
42aa520e-3a02-5ed6-b972-08bfa6d453c2 | note | - - - - - - - - -
95f57fc8-5cc6-5375-a501-c2f579f3f167 | note | Reference Documents: 404.13 405.07 407.18 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
cfce967e-e8fa-5d7a-8ab2-f2e0417ba0cc | note | - - - - - - - - -
94970856-4b1f-5666-b15f-b386c8004072 | note | Inspection / Test Method: Visual Inspection
dbbb7971-7dff-516b-ac97-6b637cb5eb93 | note | - - - - - - - - -
efa9e288-b9b2-5608-8505-5c1e9ebafb10 | note | Record of Conformity: Inspection and Test Plan
d4a51404-3538-597e-acce-07036ecc7d46 | note | - - - - - - - - -
cba5a7eb-0939-5b3f-ad6d-fd925caa2823 | note | HP
ad31d05a-4442-5b66-978c-8e2f3afee684 | note | - - - - - - - - -
4ba9e079-5aee-5956-a50f-8b3d18450565 | textbox | Responsibility: Site Engineer/ Asphalt Supervisor / Superintendent
| signoff | HOLD POINT
| checkpoint | 2.2 Cold Weather Placement Management Plan
39d18939-83c1-536d-a2ab-695490b6b895 | note | Frequency: Prior to commencing Paving (Seasonal)
85016376-bcf5-5250-8392-05e6b845224f | note | - - - - - - - - -
9ee47e44-6d54-5b87-b5b8-c872676e95c6 | note | Acceptance Criteria: Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
c5071c69-364a-5736-9418-81c8c69b6905 | note | - - - - - - - - -
bc491a11-e967-57f4-8ef1-594bdfa780f2 | note | Reference Documents: 407.17C
dcb1e94f-9cbf-5db1-81c2-10375f00d5ff | note | - - - - - - - - -
f1696e4a-f2bf-5aad-a0c7-cf4354af43e6 | note | Inspection / Test Method: Document review
9a8177ae-ec16-5699-8962-8ff0ded5a8cf | note | - - - - - - - - -
299d9b61-435b-5523-9182-22dbcf306f57 | note | Record of Conformity: Inspection and Test Plan
caad0d50-393c-56b7-b26e-b24ddb1dfab1 | note | - - - - - - - - -
a83e3fdb-79fc-5cfe-b6a6-47f3d5430cd4 | note | HP*
b2f987ec-b954-5a49-9305-7bd27cfbb74c | note | - - - - - - - - -
aec6fbc2-7ad9-5b74-b6e6-603640ea2278 | textbox | Responsibility: Project Engineer/ Asphalt Project Manager or Engineer
| checkpoint | 2.3 Mix Design Confirmation
ebd75b7e-9672-58a2-9fe1-6ca4ff5d5e39 | note | Frequency: Each lot
505332fc-3b32-58a5-90e4-4369a1e063a5 | note | - - - - - - - - -
4a0e450b-e147-5e44-abca-f137d61b5c37 | note | Acceptance Criteria: Check correct mix design as per pavement design has been delivered prior to laying mix.
b3efbf6d-f4ea-5ba7-bcc3-ef63151172e8 | note | - - - - - - - - -
a8c02e2e-3530-5c20-a7cc-b401870c2e80 | note | Reference Documents: VicRoads Spec. Cl.407.06
c3f4bf24-3535-5d64-a849-0a2e4068df68 | note | - - - - - - - - -
28b8009e-5968-5d0a-871b-a21d69113d06 | note | Inspection / Test Method: Visual Inspection & Delivery Docket
05e5be36-fc65-52d2-b2b7-2469c79f9dad | note | - - - - - - - - -
3e9b52b5-8c18-53c1-889f-d04c6a5960b3 | note | Record of Conformity: Delivery docket Completed ITP
7c51c8e4-1dec-59ca-b671-f1b3b42b1e24 | note | - - - - - - - - -
13d709a0-565a-5176-8984-019c0afe69f5 | note | HP*
d5d677c2-e78d-558c-9440-88814c90d72d | note | - - - - - - - - -
53731290-e82c-50eb-a634-20038c768f66 | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
| checkpoint | 2.4 Running traffic on Placed Asphalt
1592859b-4913-50cf-8d23-4cac464844e1 | note | Frequency: During Construction
dd029045-2004-569f-8622-cc41eaffb3fe | note | - - - - - - - - -
022a43aa-7ee7-5907-8636-b646c04bfa36 | note | Acceptance Criteria: Traffic not to be placed on asphalt placed until Fulton Hogan agree the surface temperature is less than the required mix temp. (SMA 40°C) to receive traffic.
cb27388c-b02c-51f4-8215-e3a30cf2cc28 | note | - - - - - - - - -
b6b2be9c-7b08-5fa2-906a-006f81f16ae5 | note | Reference Documents: 404.14 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
de41dc82-2391-5c48-83e5-1cf22812cd85 | note | - - - - - - - - -
895aa249-bc28-5570-a541-fcd14e926a11 | note | Inspection / Test Method: Verify
e5c30ee0-4071-588b-8df2-1df50d194b9c | note | - - - - - - - - -
a962adaa-ba25-5b53-bd83-2fe3274a22de | note | Record of Conformity: Inspection and Test Plan ITP Signed Thermometer / gauge
81513d53-62a8-59cf-b639-ba054a6859bc | note | - - - - - - - - -
b343c188-6ea1-50bb-8712-fde2b95de838 | note | HP*
fc7ab151-3e0f-56aa-9b7d-bdde9813693c | note | - - - - - - - - -
3a647b1c-bd25-564a-9166-cae997f5ecc3 | textbox | Responsibility: Site Engineer/ Asphalt Supervisor
| section | 3 - Testing
| checkpoint | 3.1 Placing Material
df4cc8f9-348f-5d13-90f8-e34a04f4d741 | note | Frequency: Per Lot
89a51625-574b-5826-9b31-4130260c28fa | note | - - - - - - - - -
f972a175-fc8b-596f-ae35-f9f3155515ac | note | Acceptance Criteria: 407.21 - DGA as per 407.22 405.08 - RGG - not less than 3 passes with steel wheeled roller. 3 passes to be made within time to compaction cessation substrate (pavement) temperature is between 7° and 10°C.
937f2b59-76fd-541d-ac5f-d1e35dd3306f | note | - - - - - - - - -
77c7cca5-3feb-53ed-ad87-422d60df1486 | note | Reference Documents: 407.21 405.08 404.14 417.12 (Refer Downer ITP - 1145-C200-FUL-QAC-CHK-0001)
fa4f4dc8-45e9-5e66-b0bc-b0553640c2b2 | note | - - - - - - - - -
478db5f8-d179-5de2-963f-7f025b05a8ce | note | Inspection / Test Method: Material Sampling & testing
2c56a9ed-d782-50e8-a1a9-d7822aefd300 | note | - - - - - - - - -
79173c39-3725-5c41-b308-9794738d1f0e | note | Record of Conformity: Visual Inspection/ Compaction test results Visual Inspection/ Visual Inspection/ Field Report/
0d202948-b305-5de7-8ec1-b0af9fc16581 | note | - - - - - - - - -
6ec6aac2-915e-5a69-bea9-3954b4dce4f7 | note | WP
09aadf28-876d-51e7-995a-ff3aaf7fe795 | note | - - - - - - - - -
57fc325d-c265-5eb8-9936-27d70128738c | textbox | Responsibility: Site Engineer/ Asphalt Supervisor Superintendent
| checkpoint | 3.2 Survey Level Conformance
d46e491e-0ec0-5f51-a062-d61df1a79fbd | note | Frequency: Per 4,000m2 at completion of work
ff5b42f4-5e66-5115-af5d-0b33b8bfda0a | note | - - - - - - - - -
bb903d04-11d3-5654-91de-f1a4b98796fd | note | Acceptance Criteria: 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
59c0c244-068d-54e0-a9f2-e30624c6ebfa | note
d5a4e06a-d14a-53ea-882a-bedfdb97c2d4 | note | Scale of Surface Level Measurement -
7058371c-29f9-5b07-80fb-036e5e7f4195 | note | Granular or CT Subbase
411286ac-90a6-5cd7-92fa-af6b14465c3a | note | Range (mm) Max S. (mm)
f050e46d-cfcb-5f21-8213-94fe3bc3b568 | note | Scale A - +4 to -8 8
394dc754-a73b-5374-90da-07a061f5a13a | note | Scale B - +6 to -12 13
dc1aa46d-c6cd-517b-a3c0-5d8220d96cc8 | note
586dc592-5053-54cb-978c-2d37c47b23f7 | note | Asphalt Layers
0bb3535e-25a2-512f-8e0a-c6fbbc10df0c | note | Range (mm) Max S. (mm)
c48fee44-4eed-50a7-861b-aeae1eb69905 | note | Scale A - +/- 5 8
69f7e68b-a842-57a9-967d-ca91b538f63e | note | Scale B - +/- 8 10
1c8cddea-19e6-5311-97da-68ee40b8083c | note | - - - - - - - - -
4e3cfbe2-bb41-53f0-b8f6-00b1478cf679 | note | Reference Documents: VicRoads Sec 407.293 Surface Level Tolerances for Sub-base and Pavement Courses
87e1f692-e06e-59d5-b27d-7d3b0512fc81 | note | - - - - - - - - -
20de65b5-eddd-52e9-8d4f-33afcad7a05c | note | Inspection / Test Method: Document Review/ Site Inspection
1e12e947-6d46-5946-b43b-0ca576333e71 | note | - - - - - - - - -
37f481ee-5ff8-50cc-b7ae-d9fd803ab7dc | note | Record of Conformity: Survey Conformance Report
0e3da3a8-5c50-5fd1-95ed-33f81b8e7371 | note | - - - - - - - - -
61e20774-8f64-5f8b-aab8-003e849b95b3 | note | SCP
bd874cca-827e-5546-965a-89a9258d7af4 | note | - - - - - - - - -
74babae4-d9c8-5861-82bc-b3bcb904ad67 | textbox | Responsibility: Site Engineer/ Surveyor / Survey Manager
| checkpoint | Final Inspection
d9aa14ce-c91c-550b-b4c4-da6f98a628d3 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
c9c49635-fdf3-55e4-8bc7-edb64cf450a8 | textbox | Print Name:
4c29872d-52bd-53c1-b611-8114cec4c5c1 | textbox | Position:
fe782c80-70be-5a48-bca5-bc20cbe8023b | date | Date:
96b51711-8d1e-5fde-9a3d-4390851cb490 | date | Work Completed On
| checklist | ITP 0076 - Permanent Roadside Signage | itp | ITP-076-AX-LOT-XXX - Desc | 253d61d1-9266-4ec9-b862-bf62bb853847
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Inductions
fd3bd6cd-ddb3-515b-bec0-d4f5d4c15816 | note | Frequency - Prior to Commencing
33a6771d-01b8-5892-acad-e7d20ae3d3e8 | note | - - - - - - - - -
25387492-1af3-590c-b9e8-c6a5a68e9efa | note | Acceptance Criteria - All personnel on site have been inducted to the CRG Site.
0755ad78-504f-5cb1-8f46-8bf443f2587a | note | - - - - - - - - -
c7251ebb-fa0b-5fe9-9f0a-37cfd1c4afd3 | note | Reference Documents - PMP Inductions Register
1b5035f0-41bf-5204-a647-c3e3522997aa | note | - - - - - - - - -
a121a975-c592-539b-b761-733573480b71 | note | Inspection / Test Method - Document review
f46cc005-02b5-5861-bfef-13a81d185669 | note | - - - - - - - - -
a310fa92-a89d-56bc-89cf-5aeac107ab92 | note | Record of conformity - Site induction card
f9f36731-6d16-5700-a05b-1f060c416335 | note | - - - - - - - - -
d5ff2444-4b2e-5b85-8c5c-78613e0a6c84 | note | AP
101ec159-04fd-59f3-80ab-368f83866020 | note | - - - - - - - - -
3b68b68d-d883-55e2-86e8-67f11075e65d | note | Site Engineer / Site Foreman
9faee4f6-a7f3-5d14-8f87-63836f26cc98 | note | - - - - - - - - -
d9375499-56fa-50c3-8347-d0e32973be03 | date | Date Completed:
| checkpoint | 1.2 - Safety measures are in place, SWMS undertaken
7ab8037c-110b-5097-b1b9-a64e95c16d80 | note | Frequency - Prior to Commencing Work
0e6ed498-cd7e-5995-b3cd-d23d004e23ef | note | - - - - - - - - -
236189b9-8987-5c12-9131-71d266da43b5 | note | Acceptance Criteria - As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
82608e6a-c12b-52a5-8cf8-bdc87da9c0bf | note | - - - - - - - - -
2c18e56c-a8e1-5ec3-84a1-eaa015a1178d | note | Reference Documents - Health and Safety Coordination Plan
747214d8-6010-50c5-bc92-04cb0709d20f | note | - - - - - - - - -
cbb7def5-5a64-5e1a-96e4-6350983dc3c1 | note | Inspection / Test Method - Document Review
c1a53a65-adae-52e8-a469-30db41e3d3ec | note | - - - - - - - - -
5feee1cb-4dd5-51c1-b315-de918e3becfa | note | Record of conformity - SWMS(s) signed
7601331f-bf31-58e7-bf6e-cd3b3f966f22 | note | - - - - - - - - -
f76f8c39-e884-54ca-96a1-e52e387cb6de | note | HP*
088283d9-505e-512e-bcd6-51f95dfd517b | note | - - - - - - - - -
cf0b3dbe-ed32-5a48-892a-99e5b6c585a6 | note | Site Engineer, Site Foreman & Superintendent
0f5c873c-3af6-510f-bd56-105a398237cc | note | - - - - - - - - -
e0928a07-6ab6-5c4e-8c38-3b58e5f4f77d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
70ed377a-c63c-58fa-bc87-ae20d435542b | note | Frequency - Prior to Commencing Work
6c732abe-4ab2-5cb3-80d0-7b49dd42316a | note | - - - - - - - - -
b141d1f7-9707-5b16-8d28-0a6a21f65890 | note | Acceptance Criteria - Issued For Construction (IFC) and latest available revision used
315d0f40-543a-5cf9-91cc-8f09e16fe18f | note | - - - - - - - - -
3364ce47-7b69-5ede-a632-ffd6a002a1c4 | note | Reference Documents - IFC Project Drawings/ Drawing Register
686519b4-8be1-554c-aae7-4cb57316f137 | note | - - - - - - - - -
b53f026c-e703-5c14-8ecf-9c88878ebb92 | note | Inspection / Test Method - Document review
04de7547-72b0-5c94-b20b-5c9f72fecb07 | note | - - - - - - - - -
52beca64-c537-5385-b516-e514b90d24e9 | note | Record of conformity - Latest revision IFC drawings
85113cd6-6871-55c9-bb96-116db50ceb1d | note | - - - - - - - - -
dd605d45-d3e9-554a-b317-8e2d91efa880 | note | AP
986065fc-bffb-54c2-90a1-2d6dae49c6f5 | note | - - - - - - - - -
c6e078a8-2b8e-54cb-9c8a-502b636edb97 | note | Site Engineer / Site Foreman
e423e8f2-0be8-5955-a9ce-fa6fcbc32941 | note | - - - - - - - - -
78d570bb-79cc-5bec-b9c5-53cfdfcfff75 | date | Date Completed:
| checkpoint | 1.4 - Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place
02e1768d-54da-5c57-bf94-7480d96df075 | note | Frequency - Prior to Commencing
e300cdb6-ac48-5514-90ac-4128d72eb06d | note | - - - - - - - - -
e765a2ba-c51f-563f-b160-17885870b500 | note | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
3c167be1-205f-5d1d-8cb7-d5885c68904b | note | - - - - - - - - -
39698ef7-71bd-5cf6-b3c5-a871b0a931c9 | note | Reference Documents - EMP, Site induction, Project Spec. Cl.1200.09 Project Spec CI.1200.15
ae2743a6-0ed8-5221-a000-b09dbb089c42 | note | - - - - - - - - -
fbd97d3c-5850-53c5-96fc-7fed0ed8e101 | note | Inspection / Test Method - Document review & Site inspection
c12436de-4603-5424-bfa8-67e946f01f43 | note | - - - - - - - - -
5b9aed9e-7029-5f98-81b8-3ca511706558 | note | Record of conformity - ITP signed
a6c7c30a-62b6-5de8-8a31-289f63772c39 | note | - - - - - - - - -
e4be5872-2ce4-539d-abfb-b599d8dbfc6a | note | IP
0d3ea1cf-f536-5411-b958-b6b5e3fd8878 | note | - - - - - - - - -
e3e58a62-e0b7-590e-b509-c650dee98956 | note | Site Engineer
c8a43607-56c1-5e04-81fb-6ffa688e1d89 | note | - - - - - - - - -
c9dfc517-9889-505f-a5f3-c66c12538476 | date | Date Completed:
| checkpoint | 1.5 - Traffic Management (When required)
04186f91-95dd-567f-8470-5312de0b183d | note | Frequency - Prior to Commencing Work
8c2174ab-e8cd-5cc6-8b4a-e52880bee9c2 | note | - - - - - - - - -
26594091-74c4-5591-bc9d-558f38ed4793 | note | Acceptance Criteria - Approved TMP and MOA
c9287d8b-973d-5836-b50e-acf580b15536 | note | - - - - - - - - -
9d1f533d-376e-5332-86ae-3ae1c4b29a5a | note | Reference Documents - Applicable TMP no.:
6213b619-02d9-5f02-a29a-99509381953f | note | - - - - - - - - -
2303bb9c-4fde-5bee-aa27-80102de1327d | note | Inspection / Test Method - Document review & Site inspection
847d0199-db3d-5534-949c-352efb06bcfc | note | - - - - - - - - -
14149bcb-1e95-5e40-a778-d49b0492530d | note | Record of conformity - Approved TMP & MOA
dde3ff9a-1158-5656-a5c8-a35d33bd285f | note | - - - - - - - - -
fd6a9ab3-f0b5-5187-bfd4-4e4a9ddd14fb | note | AP
4672d7ec-c228-5db7-904b-23b8bded1a0a | note | - - - - - - - - -
b525e9af-dbee-5765-b879-d3af67b7198a | note | Site Engineer
9afa4d53-bbca-5a83-b792-ee30a5a1b76e | note | - - - - - - - - -
99c7ed2d-77f2-5080-8499-5b468ebac912 | date | Date Completed:
| section | 2 - Roadside Signage Install
| checkpoint | 2.1 - Set out posts and foundations
7171f8f0-a9a0-59bc-8be2-55d4f992c133 | note | Frequency - Prior to commencing install
436f0f23-d335-5e61-86a4-12371cb08984 | note | - - - - - - - - -
fb7c6cd2-3788-52c7-a554-83b19c4e8349 | note | Acceptance Criteria - The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
e16e0840-accd-55f9-bd16-9c9941683238 | note | - - - - - - - - -
7bb1d7eb-5ad4-5764-926d-7b6f416191e9 | note | Reference Documents - IFC Drawings Project Spec. Cl. 3070.03 VicRoads Spec. Cl.714.06
77c4b65c-e9cb-55e8-a812-d4cdfbbfe4d7 | note | - - - - - - - - -
56053fed-fb42-5524-938f-9b702651d9b2 | note | Inspection / Test Method - Document review & Site inspection
73856ee6-9de8-5b26-b8e2-ef72cdadc6c2 | note | - - - - - - - - -
bad50702-b144-5ba0-bdee-dca15ef8319d | note | Record of conformity - Consent to proceed by Superintendent OR written exemption granted This ITP signed
12227c2c-8462-57e7-bbb3-21675527b9b5 | note | - - - - - - - - -
b5b3648a-7a8b-5f6e-bb05-3cf808d4cfd9 | note | HP
0aedee08-c2c7-5798-bb96-6285aee5d7f9 | note | - - - - - - - - -
7e4add21-6f40-5fc3-8869-4ce027c06942 | note | Site Engineer / Superintendent
81b65fb7-ebb1-5c93-acf7-aa66224811ea | note | - - - - - - - - -
5aaf2f38-8fe5-5bd3-9fd7-9f32e2ff08da | date | Date Completed:
| checkpoint | 2.2 - Material compliance
57068490-d65b-54d7-8449-8aea7a970933 | note | Frequency - Prior to commencing install
1a5db3b9-7fbd-557b-81fd-dab793d28da4 | note | - - - - - - - - -
2aec6121-3ac7-56d9-b49c-ae8c3cc9070e | note | Acceptance Criteria - All road Signing must comply with the Technical References including the requirements of section 860 of the VicRoads Standard Specification Sections for Roadworks and Bridgeworks.
beb550e0-fa75-59bb-a20b-57cc739a74ab | note | - - - - - - - - -
f73bb742-3f00-5a5d-9215-61e0b5a9f2ec | note | Reference Documents - Project Spec. 3070.05(a) VicRoads Specification 860
6dea6534-64ca-59e9-9ae6-7de5a51b7ae2 | note | - - - - - - - - -
22fa8e77-19da-5acc-9caa-00bb12dc3ae8 | note | Inspection / Test Method - Document review
f3637dd2-3753-5fdc-86a8-e9cd088b2626 | note | - - - - - - - - -
5464f77e-b6d4-5fb7-a32a-d5ba125465a6 | note | Record of conformity - Material compliance This ITP signed
34576c2b-714d-5fd8-960b-f1e9f240f122 | note | - - - - - - - - -
d47c8ae7-1381-5767-8eff-0096e4918312 | note | IP
972f5167-313f-5aa3-9d8e-d0c0f69622f5 | note | - - - - - - - - -
a8b9f06d-95f7-51d0-aa03-5a19e53df799 | note | Site Engineer
d330a0cd-2874-524b-a513-567cdc695ae2 | note | - - - - - - - - -
4a69d2c6-15c6-5687-bf60-b1823ed74ed1 | date | Date Completed:
| checkpoint | 2.3 - Installation method
8783a1c9-43af-5951-8ecd-4617189ee6cb | note | Frequency - Once per lot
261744b9-a23b-51a3-856b-ea2ea4eb9bce | note | - - - - - - - - -
cb715ec6-9971-52db-8435-2a7872843ef5 | note | Acceptance Criteria - The sign installation shall be as described in the sign schedule and as shown on the contract drawings.
b20e0c91-b80c-5232-b592-1421eabfca69 | note | - - - - - - - - -
17eb7580-0656-58b2-8055-30e91cd77cf2 | note | Reference Documents - Project Spec. Cl.3070 VicRoads Specification 714.04 & 07
6cfe6177-38d3-5313-ac4f-dd67e894624f | note | - - - - - - - - -
6f348313-11fd-5be9-ae23-bfcd8fef9f4b | note | Inspection / Test Method - Document review & Site inspection
1c6878ef-5192-5ea7-8688-337c4477c624 | note | - - - - - - - - -
9a75b73b-5e60-579b-911c-b7b5fcd4e6fb | note | Record of conformity - This ITP signed
595546c1-67b5-5852-86b8-b2ba7aa92320 | note | - - - - - - - - -
eb9599bf-4713-5303-a520-9c112b6e10a1 | note | IP
50ffe66d-512e-5831-b30b-723bf3d5bb8d | note | - - - - - - - - -
c21f1bf8-fc96-588c-900c-6b4243cddda7 | note | Site Engineer
03728cc0-6705-5ae3-be01-0b69ad4a7712 | note | - - - - - - - - -
587a8cbc-1d3b-59e3-9ad7-8586425bf18c | date | Date Completed:
| checkpoint | 2.4 - Installation tolerances
281736e6-f506-594b-bf54-10f79653b063 | note | Frequency - After completion of works
05f8befa-45f0-52ad-becc-d1546180b6da | note | - - - - - - - - -
b503e5bb-8d98-546c-af8a-214917f8c788 | note | Acceptance Criteria - Verify signs were installed to tolerances stated in VicRoads Sec. 714.05
3fb69f34-79e6-558c-b738-2fd91c42ea9d | note | - - - - - - - - -
4a52bc40-ca04-522d-bf5b-8f4df6b8862e | note | Reference Documents - Project Spec. Cl.3070 VicRoads Specification 714.05
08b0806e-8078-5588-b5ae-af4a69df7f25 | note | - - - - - - - - -
57d3e3bf-3787-59c3-b87a-d25a2cd745a1 | note | Inspection / Test Method - Document review
ea87d552-7591-5739-9729-295897bc79b9 | note | - - - - - - - - -
a9216f9d-1199-59b9-93b8-797f99f7c258 | note | Record of conformity - Photos This ITP signed
7de5fe46-9174-51b0-9dad-1e51eff482fc | note | - - - - - - - - -
25021fbd-48ef-5407-83d9-7a88cfecbbdb | note | IP
4edc60a0-180b-51c7-957a-8f3646394401 | note | - - - - - - - - -
79597b29-c960-576f-8b5a-f859eec86208 | note | Site Engineer
d137eccd-daac-5258-9bd6-5df0dafbb19a | note | - - - - - - - - -
41fabadc-6cc9-5080-b281-c0926d3fe3e7 | date | Date Completed:
| checkpoint | Final Inspection
92a9dd54-76c4-5183-89ba-524c182a6789 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
662b2268-26c1-51b1-a031-42477336f130 | textbox | Print Name:
a1e901ef-6eae-597c-9eb4-0c42b2dd163a | textbox | Position:
2b01d31c-abd0-5743-a1df-de2cfb712840 | date | Date:
5d232172-bf32-5305-b3b5-3dde0f132ee6 | date | Work Completed On
| checklist | ITP 0077 - Electrical and Communications Conduit Installation | itp | ITP-077-UT-LOT-XXX - Desc | e6a95f20-1300-418d-af74-06386e5c1bff
| section | 1 - Preliminaries / Pre- commencement activities
| checkpoint | 1.1 - IFC / Shop Drawings Submission & Approval.
c79f3fae-5974-5ff0-846b-5df2f85f3dc6 | note | Frequency - Prior to Commencing
5392dc4b-bca2-5114-9a8d-ecec30178417 | note | - - - - - - - - -
5c6e57ce-ad11-56b4-89e3-4e97462125ab | note | Acceptance Criteria - IFC Construction Drawings & Most Current Revision.
442d6b5f-c80a-583f-a230-39603cf07999 | note | - - - - - - - - -
4c06c083-090e-5a65-a8da-a725962afdae | note | Reference Documents - IFC Drawings
e1c9d0bd-fc0e-5c71-9e8c-2f551983f2f9 | note | - - - - - - - - -
a4578401-881b-51ed-abc8-589f49f348b8 | note | Inspection / Test Method - Document review
b52a2d27-7f03-56a3-b5b2-e14fcfed160c | note | - - - - - - - - -
83a711bc-61ad-55c7-a0f5-78efeb0220a4 | note | Record of conformity - IFC Dwgs
ac2a65de-d5f1-5849-b7ad-66432f180811 | note | - - - - - - - - -
820d59b4-1928-50a8-abab-f31052340f9b | note | HP*
53cbac5c-54e1-59e6-a1dc-d7e8ac382153 | note | - - - - - - - - -
9846a6aa-96cf-583b-aef4-9be1c5b4fbd4 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
9129abe1-5acd-5378-bc39-f7efcde3d0d1 | note | - - - - - - - - -
58e09ca1-87fe-5f56-9b50-f4c7ff856dfd | date | Date Completed:
| checkpoint | 1.2 - Survey Set-Out
f2176854-83fc-5ff5-b36b-153e85d6c55b | note | Frequency - Where Required
937be4e6-31e6-5a35-8df8-18195dbb7ab2 | note | - - - - - - - - -
599386b1-8070-577c-9045-1480c18ee877 | note | Acceptance Criteria - Qualified Surveyor to set out extent of works on ground
b6e225ae-4518-583f-8c82-8fc97f59232f | note | - - - - - - - - -
b8d56710-02e2-5a76-ac50-d80d6ce3cd0f | note | Reference Documents - IFC Drawings
e393b250-e05b-5548-873c-7499df076208 | note | - - - - - - - - -
6207e2df-313b-5737-b237-6eec21545b26 | note | Inspection / Test Method - Survey
d33c8941-c60a-5777-b432-0ae81db30f48 | note | - - - - - - - - -
7efbbb59-e2be-58f8-b983-2b3396d31fd9 | note | Record of conformity - Survey Calibration Certificates
bc133a8e-1fa9-53f5-bb99-0caf1a1512a2 | note | - - - - - - - - -
6eaecdf5-3d9f-56b2-9a7c-6ec7d0964185 | note | WP
66926059-cc7c-56ed-9438-8c95bd7aae92 | note | - - - - - - - - -
c7860635-18a8-5f3e-a597-e6e9a175a1fd | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
e76142c3-2cd2-59ef-bdfb-b4b399ac39a5 | note | - - - - - - - - -
1ccdf3c6-9ce4-52eb-92a3-6a4362a5e520 | date | Date Completed:
| checkpoint | 1.3 - Excavation Permit/ Service Location
741c7bc9-ff21-55c4-b305-ddc0b57e93bb | note | Frequency - Prior to Commencing
57ffbe00-6bc4-5d48-9c58-665fc3ae7cd3 | note | - - - - - - - - -
dd93fbbc-77a4-53af-9119-a5ab63fb62ae | note | Acceptance Criteria - Identify underground services NDD/hand dig as necessary.
3d6214d4-f017-5343-a54e-249dd55b750e | note | DYBD documents
80cd77d5-ddd8-57d3-9fe0-ab831228cd4f | note | - - - - - - - - -
dddabf27-e0fe-5e91-98e1-530e50e74081 | note | Reference Documents - Dial Before You Dig
692add77-6c64-5f68-896e-dbe94f9cae7f | note | - - - - - - - - -
9deb2aa4-fb73-5684-bad3-1e88489de3e2 | note | Inspection / Test Method - Survey
e7696428-feb0-54ef-89a4-bd3817cae345 | note | - - - - - - - - -
c159d8a3-e045-5cb3-a667-65fa6d953b5d | note | Record of conformity - Excavation Permit
2d5c8a2c-344e-5c45-ae0c-dc94101461a0 | note | - - - - - - - - -
2bdc3cc7-2906-5b41-a8b8-3530e51720f6 | note | HP*
5973d9e0-da08-5847-880f-7a21e41c90ea | note | - - - - - - - - -
eba269c2-8ff8-5cd9-9e20-99d29171a26e | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
e70ca3b6-8f0e-5429-8f17-01a49e0d6f2a | note | - - - - - - - - -
f45aeba0-3f6f-5585-9ae5-eba547591398 | date | Date Completed:
| section | 2 - Materials
| checkpoint | 2.1 - Conduit Sizing
abb25a5b-6de4-571a-a40b-9cd874c017cc | note | Frequency - Prior to Commencing
4fd897ad-fbbb-5449-889b-f85b006359c8 | note | - - - - - - - - -
8e05a705-f5af-5762-8686-b96d134b400a | note | Acceptance Criteria - Conduit sizing to comply with VR table 733.021
9cfd3091-de74-5d2b-9ced-02ff48442efb | note | Excludes utility providers designs and requirements
4272a7c2-7dd6-57c5-a42f-21899006bc35 | note | - - - - - - - - -
7021c8dd-005f-5228-a477-b084d1dee49a | note | Reference Documents - VR SS
b35f6fc4-db8d-517b-9d51-0654962f9f4b | note | Table
f73a2f94-73a5-5b14-afb4-97768b71d7d6 | note | 733.021
d9eecf3c-60be-5723-9141-ce6cc906da35 | note | - - - - - - - - -
d1bb6e10-7105-516d-804f-0896e0c3149f | note | Inspection / Test Method - Site Inspection
b299ae34-7be6-5445-b136-7890fdde9444 | note | - - - - - - - - -
88755103-49ee-5aee-972b-8da4000110bf | note | Record of conformity - This Checklist
299d9f1e-958f-56bd-bf10-7fe81a445b53 | note | - - - - - - - - -
1a97cfce-0454-5cc6-ba8d-2356a28de4bd | note | IP
5bd28cf8-4914-55c8-9009-68aeefc819b0 | note | - - - - - - - - -
b033dbc3-3535-56c6-ad27-8441dc1bd262 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
9514f07d-71ba-578e-a874-bc34a52547aa | note | - - - - - - - - -
75d59d7e-e6a2-5879-8dff-ac2147dc7637 | date | Date Completed:
| checkpoint | 2.2 - Material Backfill
c7cc4db7-33b4-534d-9d83-1f846a1740ac | note | Frequency - Prior to Commencing
c10f5423-149c-5071-9a86-98baec196e87 | note | - - - - - - - - -
2b1db58c-90b8-5e88-b862-3f22b3241752 | note | Acceptance Criteria - Unless otherwise specified, materials used for bedding and backfilling shall be uniform in composition and free from perishable matter and shall comply with the requirements specified in Table 706.061.
241fd3a7-5b6f-59e5-bf71-b46b3256bb00 | note | - - - - - - - - -
e3284bb3-41ec-5fe8-bb53-3abcbc0490b9 | note | Reference Documents - VRSS 706.03
97aa54b1-0cfe-5784-a8f4-be5d8c9f7e2c | note | - - - - - - - - -
79ef9c45-93a3-5f1b-892a-ea4f5d730fbe | note | Inspection / Test Method - Site Inspection
090ccac0-5dc7-50b5-b072-7ac9a579962d | note | - - - - - - - - -
b4c16a55-878e-5afe-8a5e-e39666f951b1 | note | Record of conformity - This Checklist
8cdd3738-7ac2-5136-abc6-5c8448815c95 | note | - - - - - - - - -
464fc88d-f591-5a54-83d5-add2070aaf6e | note | IP
66257eab-0f37-595e-95d5-4a36dcc96696 | note | - - - - - - - - -
3d0c5dc8-9f35-5ef2-90ca-b725679ddce7 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
759ee671-35c7-5786-9427-dab5a08ac69c | note | - - - - - - - - -
622e3b80-a01d-5300-8209-f97b8a44ccf6 | date | Date Completed:
| section | 3 - Excavation
| checkpoint | 3.1 - Entry/ Exit Points
48c1cf06-ecf0-571d-92c5-1514b69d9b6c | note | Frequency - Prior to Excavation
c8a82891-cd6a-56e6-8556-d89097598836 | note | - - - - - - - - -
811048bd-104f-5318-9ccd-ad7db0214a77 | note | Acceptance Criteria - Entry/Exit points to be established
febb4034-dd6e-54e3-9e12-9b05d0530ec7 | note | - - - - - - - - -
e2439fe4-32d9-5ba9-8aad-0a505d7793d6 | note | Reference Documents -
344d49bd-9700-55dc-9faa-c655ca64fbfe | note | - - - - - - - - -
5358b53e-6e48-5289-97f4-6080cd5d2979 | note | Inspection / Test Method - Review
62070dae-a893-5273-9cd0-d1de2775b9a4 | note | - - - - - - - - -
fea1ed07-19b1-5cc3-8dec-34f6f76bb760 | note | Record of conformity - This ITP
72cb1922-16fa-5cbb-a5ca-0805bdf2941a | note | - - - - - - - - -
92aeb10e-a31b-5fdc-ab48-353a4f8f8628 | note | HP*
0ff0909b-5c72-5f79-8c3c-20c36c4a5f21 | note | - - - - - - - - -
de1a147d-06ba-5f6b-b27e-542fb1fb3dbd | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
db7c301c-d169-5f90-b4dd-089678b9f117 | note | - - - - - - - - -
3abcf085-6004-54fd-807f-6714573886c6 | date | Date Completed:
| checkpoint | 3.2 - Minimum Cover
051a7baa-0df7-52f9-88f8-bfdfe2e43c78 | note | Frequency - Ongoing
df3cbbb8-fe75-57ad-b11f-5cc37ab4e4b7 | note | - - - - - - - - -
55e94d2c-1dfe-56c3-8fc9-20e3bcfa92ee | note | Acceptance Criteria - Minimum conduit cover shall apply as per table 733.031
0d4a158e-5443-5ea9-b378-2ba29ad87a7d | note | Under Freeway Pavement – 1200mm
179eb480-66f6-5694-bbb6-2d0736f8e128 | note | Under Arterial Road Pavement – 1200mm
fec3bb11-f133-5d58-8853-d7937a04f32f | note | Under Local Road Pavement –600mm-800mm
34817a83-1bea-5048-a26c-7ad13b4156d7 | note | Under Open Drains – 750mm
6a3f20de-9e66-570a-985a-e4464bfdfd48 | note | Under footpath or unpaved areas (LV Circuits only) – 600mm
48a600f5-357c-5896-a5cf-d0e54a74c205 | note | Under footpath or unpaved areas (Extra LV or Comms conduits only) – 300mm
15c0809b-5715-576e-a40c-6e8034b1f8a0 | note | - - - - - - - - -
304a8a53-bfb5-576e-973e-089ba24f0f8e | note | Reference Documents - VR SS
5f4ff1f0-a47f-5a86-9bd9-67bde6307c36 | note | 733.031
ea5430ee-75fd-525e-9b98-48e886e40820 | note | Refer Individual asset owners specifications
2aa91eab-cb3c-537b-9eca-74a2a7619c75 | note | - - - - - - - - -
b97d51b3-c102-5b28-8607-64374b56cd0c | note | Inspection / Test Method - Survey
4141367c-02e5-501e-8e63-b9279816d133 | note | - - - - - - - - -
9ca2980b-b8f1-5f2f-a259-4c4a24db1160 | note | Record of conformity - AS Builts
f54d930f-ff3c-5cbc-a869-8872fbfbd164 | note | - - - - - - - - -
950a630e-01ec-5eb0-a65a-c9de606bdb28 | note | SCP
bc8717b5-d6bd-5661-a004-0cb1e26c512e | note | - - - - - - - - -
b1d99370-6ab5-57d1-b83f-b0a62cc446f6 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
bc000201-763f-5dee-b536-918ab76bf096 | note | - - - - - - - - -
65e89a6b-f36a-513e-8198-3d1909460f6e | date | Date Completed:
| checkpoint | 3.3 - Backfilling
b9d57fc4-eb97-51f7-bbbd-f90c1ae64a06 | note | Frequency - Prior to backfilling conduits
7929dad2-1947-500e-9948-e6374f93c45c | note | - - - - - - - - -
31080601-d252-56ce-b602-fedf07560a54 | note | Acceptance Criteria - Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
6903fb91-ff84-5015-b829-818a570b15ce | note | For Vicroads assets only. Not applicable to Utility providers
2a932dc7-ac4c-51d2-b851-1a31a7ef4b17 | note | - - - - - - - - -
bee86efa-feeb-5dd9-b123-5537fa328b55 | note | Reference Documents - VR 733.06
4bd8e217-06fc-5b49-bb54-7dfae8722d3d | note | - - - - - - - - -
c37e7e2a-6bad-5d7f-bc8f-2a2b23ca3342 | note | Inspection / Test Method - Inspection
1ebc79ab-8ca7-520f-bf57-f5c6e21e89b4 | note | - - - - - - - - -
284a8453-54c5-57d0-b081-0340c56a57d6 | note | Record of conformity - This ITP
4f1d1d88-3509-5f7f-a13e-30a9f93d6d7f | note | - - - - - - - - -
3cd1e62f-9843-58cf-98ff-2e3e018ca7b1 | note | HP
820523c6-042b-5c62-aa82-cfe23e160a53 | note | - - - - - - - - -
aad57de7-2c1f-555c-a235-ed6c3c61bacf | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Superintendent or Representative
d64d645b-3387-5e8e-9286-1c363aa751d7 | note | - - - - - - - - -
c0a80673-01f0-5799-8db9-5d141809ffb7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Compaction Requirements
73ffdad8-43f1-56dc-8d2f-92e1d3ca1a4d | note | Frequency - During excavation
24bb9075-b851-5469-8bd0-e3ea2c0f9a6b | note | - - - - - - - - -
3367cfe5-382f-5d0e-be1e-d40b4133ae86 | note | Acceptance Criteria - Under Paved Areas - 98% Modified Compaction
be111cf2-30ee-56e8-933d-220c4d794c9e | note | Unless otherwise specified, pavement material shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified compactive effort.
e2281386-8bf3-5bd6-b362-267ad09c7745 | note | Bedding and Backfill (except pavement)
c18067ec-4471-5b9d-a3bd-dfd29b9ee95a | note | Backfilling beneath areas to be paved shall be assessed for compaction in lots as defined in Section 173. The number of tests per lot shall be three. Backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted to a mean value of density ratio of not less than 97%. The calculation of density ratio shall be based on Standard compactive effort. A lot shall consist of a single layer of work. A minimum of 20% of all lots constructed shall be tested.
3fde6a0a-a64f-5626-ad41-cc0f84c16b1b | note | - - - - - - - - -
ce8df9ed-9a10-5397-8f88-2da4a2b8bb5a | note | Reference Documents - Test Results
820dae3c-7a13-5699-b839-df0c338ece03 | note | - - - - - - - - -
7bafd51a-03e3-5aa0-be4f-d359dfc2d02f | note | Inspection / Test Method - Compaction Test
87de43e2-1b6c-5f21-bb03-ed533b898e04 | note | - - - - - - - - -
39a6c8be-0ed5-5966-8e32-ad6aab675f60 | note | Record of conformity - Test Result
623650b9-5d03-5ce4-b73e-dd1a22efd50c | note | - - - - - - - - -
953aa849-e3c8-5d17-8d08-254933682c77 | note | TP
4ddae27c-e154-5a21-9ef7-9f22698a93a8 | note | - - - - - - - - -
6eca88d3-c3cb-58d3-85e6-083c773a76da | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman -
a57cc047-d164-5a63-b16d-6e5bff011165 | note | - - - - - - - - -
0c810fd6-f3be-5736-a36c-18af7651eaa3 | date | Date Completed:
| checkpoint | 3.5 - Survey pick up / Bore Mark Out
68172a6d-1ebd-5985-9066-82dbacefea86 | note | Frequency - During Bore
9c889f62-f20e-5658-bf45-cb10a7734b82 | note | - - - - - - - - -
2c08cda6-b3f9-5094-a0d7-8c6165180c45 | note | Acceptance Criteria - Survey to pick up as record of conformity on top of laid conduit prior to backfill.
e249433b-2165-50be-b170-fe2a896831a1 | note | - - - - - - - - -
2a716089-0fc8-5efd-9155-6a1603a0a618 | note | Reference Documents - Survey
19a82845-e080-5eed-8e95-364742af7666 | note | - - - - - - - - -
ce827300-a2df-5a82-a562-a1dc025633de | note | Inspection / Test Method - Survey
341d63b2-4f84-5ac5-a016-b82a1e67bb29 | note | - - - - - - - - -
93d3e3be-71e0-5e4a-8211-6e75f71488af | note | Record of conformity - AS Builts.
209b4c5d-ff98-5eee-b68a-3384b90f6f7f | note | SCP
e2633fa5-4e82-5a05-a6e4-a82d4f489d65 | note | - - - - - - - - -
59cc5071-a40c-52e8-bfbe-67d753a0e130 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
b107f589-21ce-5a01-b019-2aa1fd972db4 | note | - - - - - - - - -
42fd5551-f69b-522b-aa6e-c1991da34ee0 | date | Date Completed:
| section | 4 - Completion
| checkpoint | 4.1 - Entry/ Exit Points
4c389474-e37a-5fe3-8992-4cc5f5bc153b | note | Frequency - On Completion
fe82a626-29fd-5153-867a-8c151b234efa | note | - - - - - - - - -
e5334ccd-5aa5-5365-b58d-659e0c6ec123 | note | Acceptance Criteria - Ensure clean fills is used to fill in Entry/ Exit points
95a541a4-7f5a-5a2d-91c6-e528081343c5 | note | - - - - - - - - -
013ecfe5-be2d-516d-ba8c-53e6429f3558 | note | Reference Documents -
b6cccf72-f80b-506f-82f1-eddc67dfbc63 | note | - - - - - - - - -
bf030900-c3f4-586e-af77-c422da21b0b1 | note | Inspection / Test Method - Review
38be73a4-16f9-59c9-a256-48609fd9040e | note | - - - - - - - - -
6ec49f1d-a783-5f8c-9a80-f77de87b6cd5 | note | Record of conformity - This ITP
c856313c-df79-5d84-a896-15346a5f6028 | note | - - - - - - - - -
1a68d3c6-2a77-5c54-9a68-0f72e6b09686 | note | IP
c4dbe53d-4b63-5642-9a45-4143242e554c | note | - - - - - - - - -
ce7f4330-471b-5d26-acc3-87ff9cb56e43 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
dbb4cde9-9c88-552d-9b4e-febf300ee6ef | note | - - - - - - - - -
d7b88314-7f9d-54a5-b7c2-35924d946d58 | date | Date Completed:
| checkpoint | 4.2 - Conduit Layout
cbfab4a7-d64c-54da-825c-5478c7a75978 | note | Frequency - Each Lot
fb2a5be3-38f7-51fb-bd0a-6ea128ad0e01 | note | - - - - - - - - -
a708ffe8-29a5-5001-ba44-155e8265912f | note | Acceptance Criteria - Conduit arrangement to suit trench detail;
b6ac4ec3-5fd6-518d-afe0-78a57ea60e3c | note | Conduit to slope towards pit for drainage purposes;
86ca988c-5ff9-59cf-9653-c11b6ed986ef | note | Quantity of conduits to be confirmed and entered w/ each lot.
559bfdfc-c511-55bc-bb28-a213e84d7fa9 | note | - - - - - - - - -
910c7e72-d4f1-544e-b6a7-103c79781c2c | note | Reference Documents - Utility Provider Drawings/ Project Plans
904cd85d-91a5-52b3-a7c7-881a84c6d077 | note | - - - - - - - - -
3ed14428-1cfb-5543-a195-10f3709bd1bf | note | Inspection / Test Method - Project Engineer
f9522652-9c06-551a-af0a-8000e45c9eed | note | - - - - - - - - -
7365baf2-e1d0-5d9b-89e8-3cf2a2f7a3ca | note | Record of conformity - Inspection
fdddea35-227c-599c-b4dc-60e4a1114e7c | note | - - - - - - - - -
0681350f-1190-58d2-b810-b25bb0a0a219 | note | IP
7a13eca0-2e6d-5395-9a54-f9e823c0556a | note | - - - - - - - - -
6b49a2fc-ee1c-5140-aaec-33068c125905 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
0b40f4a6-492e-50ba-859e-092577a5fd01 | note | - - - - - - - - -
f94fbcb0-b317-5bb8-8d82-b34efc138a12 | date | Date Completed:
| checkpoint | 4.3 - Draw Cord
e2a14e28-a836-59c4-94e4-e7f75bfad3c9 | note | Frequency - On Completion
631e826f-b971-5420-83f1-e03726b354a1 | note | - - - - - - - - -
a03c6ebf-7a00-59f8-a3fd-02616d2d7818 | note | Acceptance Criteria - Each conduit for electrical wiring an communications cables shall be provided one synthetic draw cord not less than 3mm diameter and a minimum breaking strain of 1.6kN
2b094b74-56f8-5d79-ba42-a5f1d412b94d | note | - - - - - - - - -
ebcff86d-fbf2-5b77-8127-22db83b47d5c | note | Reference Documents - VR SS
d1996381-6235-50c5-a0d6-084c879bc9f6 | note | 733.05
b660fdd6-e762-5c13-9c24-11f0f0f1eb6c | note | - - - - - - - - -
64cb7629-3327-5ce4-b1e1-512cb9e1d11c | note | Inspection / Test Method - Inspection
a5f87334-989f-55e3-8c06-dc80a78c8747 | note | - - - - - - - - -
40c21961-2d08-5638-a8cc-900f9b32b504 | note | Record of conformity - This ITP
0d44cdb4-b458-5bbc-8a70-4ad1e7b7522a | note | - - - - - - - - -
56b2d236-19bc-5f5a-b547-a1579f82f691 | note | IP
83f52dfa-105f-5b53-8be2-4f2a781289ea | note | - - - - - - - - -
e97ecee0-5551-5da1-94a0-536e338a9aac | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
0be40d70-4470-56bf-baea-522bb5e1da53 | note | - - - - - - - - -
3e767b45-cc21-5af2-8978-98afea7a5b59 | date | Date Completed:
| checkpoint | 4.4 - Site clean up
89ff9475-a015-58ef-b406-57a1dd7f6bff | note | Frequency - On Completion
cf50975a-3144-5e8b-b297-f94c5b6743ee | note | - - - - - - - - -
9684756e-7857-5fe4-9b71-7d7e1eb81fd1 | note | Acceptance Criteria - Ensure site is clean and all garbage has been removed
62a86219-834b-50e4-9189-2b5aa8506969 | note | - - - - - - - - -
05c105aa-fe7d-5db3-940a-8e680b7c50ed | note | Reference Documents - VR 733.09
d386d929-fb8a-5228-bb64-55360b2b8ab5 | note | - - - - - - - - -
672c20b5-a07a-5dd4-8a02-13f4636b9309 | note | Inspection / Test Method - Inspection
f8694096-b997-5e7b-8b12-297b3b193e40 | note | - - - - - - - - -
73356a16-1d26-58db-85d2-28e32a484eb1 | note | Record of conformity - This ITP
bee79ae0-f4f7-5660-9911-3cd5feea1e7e | note | - - - - - - - - -
2fa6c357-82e5-588b-bb9b-03a3bd66d3cd | note | IP
055a7ea9-1c91-599c-8fe3-977aea0aa778 | note | - - - - - - - - -
d3525125-5748-5c09-9bc2-334955b4b983 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
bab187e6-c1b5-59c0-8554-48a5e964b51e | note | - - - - - - - - -
1ae78df4-b53c-5a7a-a507-e27faf6bee01 | date | Date Completed:
| checkpoint | 4.5 - Maintenance of Pavement
964200bf-5b41-5dee-a5ab-18ada208b1b1 | note | Frequency - On Completion
0324547d-af30-51ab-abe9-7951a9bada85 | note | - - - - - - - - -
28a8fde7-b7d1-5c8f-8945-4925b774fffd | note | Acceptance Criteria - The reinstated surface shall be maintained in a trafficable condition after the completion of backfilling. Additional pavement material shall be placed in the trench and compacted as specified where in paved areas settlement or loss of material from the surface exceeds 20 mm measured from a straight edge laid across the top of the trench.
67905f50-0494-5efe-ad5b-5632a1474981 | note | - - - - - - - - -
4a1d83de-338e-59f3-b5a8-18f956b16c9c | note | Reference Documents - VR 706.11
353566c1-a4e4-59ed-a8b4-aed6c44920f0 | note | - - - - - - - - -
bb7cb7d4-7410-5c2d-923d-ca97f08d2a6f | note | Inspection / Test Method - Inspection
e15c04dc-0d5f-5203-bd3c-4c0fb534c82f | note | - - - - - - - - -
164ae65e-1790-5476-975e-fefd8d81fa16 | note | Record of conformity - This ITP
990bbf04-a11e-5ba2-b095-fa1816b6db1b | note | - - - - - - - - -
cc033f35-6151-5db8-bb5a-af6b1034667f | note | IP
8983b42c-c54e-505b-af6d-4d4111ec5886 | note | - - - - - - - - -
724f0e87-d1d2-50e9-a9fb-a83a87eeb306 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Foreman
2f0be1c6-2cf7-52f1-a2e9-60e53148fcc4 | note | - - - - - - - - -
3e649396-3e4d-5562-a54b-3026a295526e | date | Date Completed:
| checkpoint | 4.6 - Records
c3ef2df7-88c5-5f59-b890-047b2a0a569f | note | Frequency - On Completion
f260ba28-b219-54be-9c60-92678e1b2b50 | note | - - - - - - - - -
b13fdbcc-e8ee-50ae-b230-285a76353f71 | note | Acceptance Criteria - Bore Logs of the works to be supplied from subcontractor
b39209a1-6345-5b4e-8535-2c616dc84127 | note | - - - - - - - - -
697923c0-48ce-5885-b1dc-b5b010b12406 | note | Reference Documents - Bore Logs
72a4227d-1630-56be-b1e3-2ba2fd87e6da | note | - - - - - - - - -
a45f6451-27ee-50ae-8007-5bf73d7bfb8d | note | Inspection / Test Method - Document review
a486fbee-5dd7-5e56-9841-bb9ee4f26f89 | note | - - - - - - - - -
21ae63c9-6d5a-5008-b9b7-119c17146a14 | note | Record of conformity - This ITP
2881aa47-e5e1-54fb-9354-3b93a65017bb | note | - - - - - - - - -
d78fb87a-fc82-5645-b49f-229f718c1da0 | note | HP*
a5c73c81-a75f-5151-8398-d0e2187833e9 | note | - - - - - - - - -
614b3f87-e61d-54d8-8443-c5c81801ef76 | note | Project Engineer/Site Engineer/Superintendent/Surveyor Foreman - Project Engineer
4bcc92ca-b753-5a11-b857-774e6a7775d3 | note | - - - - - - - - -
ea7740a8-1c2d-5e85-ad98-61704605e765 | date | Date Completed:
| checkpoint | Final Inspection
1897ac67-c3c1-5519-a587-2a232191dd21 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
8f499b02-fb37-564b-956e-69713417acf8 | textbox | Print Name:
363b4956-b3e4-5915-aa71-96de60748d3b | textbox | Position:
96fffba3-d489-57a1-a837-5ffe39a8b300 | date | Date:
f0672d4e-1fae-5e28-892e-87b3eef296e1 | date | Work Completed On
| checklist | ITP 0078 - Insitu Pit Construction | itp | ITP-078-AX-LOT-XXX - Desc | be851287-66f1-4f8a-9ca3-a43cadd72550
| section | 1 - Preliminary Activities
| checkpoint | 1.1 Check for correct documentation
da4561b3-93b8-55a1-b566-9186a992c1c7 | note | Frequency: Prior to commencing any activity
e8910e2c-0cd8-5389-8234-c50b86964991 | note | - - - - - - - - -
349f50c3-fda3-5660-bb1a-30cc6342bded | note | Acceptance Criteria: Ensure that all employees and subcontractors are:
eb6888db-d91f-5d2b-bd7b-689885c1e64b | note | using the correct and complete set of drawings all drawings are the latest revision
72673838-7b92-5d36-8e76-0ceba07212ff | note | - - - - - - - - -
6f263a52-4f8f-5ca5-8650-116b298c0880 | note | Reference Documents: Drawings and drawing registers
8d4173ec-635c-5c18-ba5c-ce2e1937eede | note | - - - - - - - - -
dddd3163-9b27-5bef-89e1-1354f6c76dd8 | note | Inspection / Test Method: Visual inspection
71553964-030a-5561-9a7a-6c56ca11e956 | note | - - - - - - - - -
6e7bccaa-62fb-5407-be34-c085b2654a02 | note | Record of Conformity: ITP signed
360144cc-78ff-5398-a341-6b2a939577f6 | note | - - - - - - - - -
1eed8be1-0aa7-5002-83a0-f5b99559ab7d | note | HP*
228d1c07-2a5b-597f-bb93-987678416b18 | note | - - - - - - - - -
cbec7aff-e1aa-5514-a24f-fb09b1ac8780 | textbox | Responsibility: Site Engineer/ Supervisor
| checkpoint | 1.2 Implementation of all measures and controls
1219bcfc-3dac-53fa-b5f8-02da64c9bd56 | note | Frequency: Prior to commencing any activity
8455c975-dc9a-51b8-bc76-ebac9bd3adc3 | note | - - - - - - - - -
05e21734-8bdb-5cb6-a87e-8a9b9ae8e9b4 | note | Acceptance Criteria: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
4e29b9e6-b730-5157-8f3d-3ae3c32c9bd0 | note | - - - - - - - - -
3c87d162-5151-5563-ba11-c08a09ea7234 | note | Reference Documents: PSP, EMP, TMP, JSEA, SWMS, WP
7416a898-895f-569c-95b6-abea292f905e | note | - - - - - - - - -
452d8423-4a70-5b40-8559-4fa54eebb328 | note | Inspection / Test Method: Visual Inspection
2a2fe3d5-1d62-5668-9391-615351cc537d | note | - - - - - - - - -
96b22bcc-1956-528e-adf6-2f19b92ac47f | note | Record of Conformity: ITP signed
d4b7837a-e85b-5c56-8496-074a4e0b57dc | note | - - - - - - - - -
b8e573f3-67cc-51a1-b737-576eb9beb345 | note | HP*
0e45b82e-e6d1-5583-8b77-10b0d94a3c2e | note | - - - - - - - - -
0fdd45b8-4cce-5b68-909b-a9aba78d5ddc | textbox | Responsibility: Site Engineer/ Supervisor
| checkpoint | 1.3 Use of approved mix design
89e48fa3-7441-5a87-936a-64d5358f9308 | note | Frequency: Prior to commencing any activity
2d0489f2-1442-5f59-bf61-4221979f5fe1 | note | - - - - - - - - -
ea772bf3-373a-5a09-9b55-b5c5c222041c | note | Acceptance Criteria: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent, and allocated a registration number on the Register of VicRoads approved concrete mixes.
844ba840-1607-5a0b-808b-af7af70fe31c | note | - - - - - - - - -
5779e28e-7200-5933-94fe-9f7ba0999643 | note | Reference Documents: Cl 610.07
25ac793d-07f5-5eb3-b757-909308ff9ecc | note | - - - - - - - - -
018a5934-c061-5dd3-b282-9c405b7e668a | note | Inspection / Test Method: Verify
c2862fe6-ecb3-5518-a1a6-9fa9e54d3c3e | note | - - - - - - - - -
6b415eea-3e15-5159-acea-8f9906665516 | note | Record of Conformity: ITP signed
dbb0c830-9947-5cca-8122-cc2eb4d2f2ac | note | - - - - - - - - -
a0de4e72-89fe-58f7-8021-9ec0b8c26584 | note | HP
f17930f7-61d0-5bb6-97db-8136445a0756 | note | - - - - - - - - -
01ca96a3-b4a7-50b3-b1af-bfc9dd2a2799 | textbox | Responsibility: Site Engineer
| signoff | HOLD POINT
| checkpoint | 1.4 Correct materials are being used
3b8864b4-bca1-5dff-b118-bf4907c0018d | note | Frequency: Prior to commencing any activity
862b9cb2-5173-545a-90c3-9774263c03aa | note | - - - - - - - - -
7adb7342-f4de-50c8-a6f9-41c8b9288e10 | note | Acceptance Criteria: Falsework shall comply with the requirements of Section 613 and AS 3610 Formwork shall comply with the requirements of Section 614 and AS 3610 Void formers shall comply with the requirements of Cl 614.07 Reinforcement shall comply with the requirements of Section 611, contract drawings and standard drawings
8c7581f1-032f-581d-965a-0dd58114e260 | note | - - - - - - - - -
01c45d1f-b823-5ac9-9478-fe0a3816d0e4 | note | Reference Documents: VR Spec 611 VR Spec 613 VR Spec 614 Cl 614.07
9a19f05d-b405-51ba-af23-626b78271576 | note | - - - - - - - - -
f975efaa-c93d-5fc7-baab-b56fe2b30842 | note | Inspection / Test Method: Verify
5259f0fe-17a0-58c6-bd0d-ff4502d0323d | note | - - - - - - - - -
0e28cdb8-7a25-5944-be53-ab56e6c011a8 | note | Record of Conformity: ITP signed
b2798bf2-0105-5a22-8bc0-d4b039e75e03 | note | - - - - - - - - -
78b80836-f848-5afa-8a31-fba6bc7c5927 | note | IP
7cf579e7-a5ce-5c7c-8e4e-36c2f8c37854 | note | - - - - - - - - -
ed900e39-edd0-51a0-9dae-5fcb58c6ccfb | textbox | Responsibility: Site Engineer
| checkpoint | 1.5 Excavation Permit
6d41bdba-b2e1-5dd0-9b44-72d82a935d5f | note | Frequency: Each lot
c9975810-8fb7-57d4-8f93-89b58e0390c4 | note | - - - - - - - - -
7ebc6b64-cd8a-5c95-bcd4-41a626b07617 | note | Acceptance Criteria: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
2ed11c50-9803-5f45-b514-f6df490fbfed | note | - - - - - - - - -
99c25f99-7b00-5cb0-9285-0a9570cd1219 | note | Reference Documents: Excavation permit
4499864e-516a-5f2d-9115-83eba2221153 | note | - - - - - - - - -
b25f03a6-3525-55c0-96cf-0237dd4106ab | note | Inspection / Test Method: Verify
3062b51d-6287-5ac2-ad9d-fdcaf72aca9e | note | - - - - - - - - -
dda2ff5d-e740-552b-8986-38731044008c | note | Record of Conformity: This ITP Signed Off
1213998f-356f-51ac-89c7-099a47af9835 | note | - - - - - - - - -
884863ca-261c-5e1f-be65-cd7386ebe7cf | note | HP*
d314bf33-9c4d-5814-b2ec-d9bc09eaaf02 | note | - - - - - - - - -
efea2048-654a-56b9-9800-d10785bc472d | textbox | Responsibility: Site Engineer
| section | 2 - Excavation and erection of falsework/formwork
| checkpoint | 2.1 Excavation
f147a853-08ad-5671-b4c7-0cef43d7bf79 | note | Frequency: Prior to concrete pour
bb2caa7b-e5b5-5bc5-b26b-e900b6f3610a | note | - - - - - - - - -
23abb43f-af67-5ca5-93b8-50a7801246a2 | note | Acceptance Criteria: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
b60d4eaa-9b77-521f-8d01-9c3c8a847ea1 | note | - - - - - - - - -
143a0db8-b26e-50d0-a8a8-5b79d24bfc33 | note | Reference Documents: Cl 705.05
55a2c583-815c-5316-b74c-3deae4275208 | note | - - - - - - - - -
aff3ff37-72be-5a08-b97c-b15e8f61e91b | note | Inspection / Test Method: Visual inspection
4def822e-9579-58e6-aa67-84305b37a583 | note | - - - - - - - - -
d0b95ab9-06d0-521d-9e66-06fd8bfbf8c9 | note | Record of Conformity: ITP signed
6e2e7fa2-739a-5d88-bf4c-5a7bfbe8478d | note | - - - - - - - - -
d70b3dcd-b74f-553c-b0b9-8aa85cf40248 | note | IP
0b19f3da-33a2-5d8f-a292-ef15a0ac32a8 | note | - - - - - - - - -
fdd4d632-677d-5307-b13d-92ce0de31fb7 | textbox | Responsibility: Site Engineer/ Site Supervisor
| checkpoint | 2.2 Construction Methodology
c0e493fd-2e80-5878-ae7d-3b9e756a3fb5 | note | Frequency: Prior to erection
f8246b87-02b9-54c4-b8ef-fc751719a271 | note | - - - - - - - - -
0b0dcd9c-4b80-50ec-abb5-d5df7009c56f | note | Acceptance Criteria: Formwork shall be used in such a manner that it can be removed without damage to the concrete. Formwork shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to to confine freshly placed concrete and maintain position and shape during construction.
2966e664-8746-5a65-ba6f-c2cc06693957 | note | - - - - - - - - -
96466afc-ccec-5f15-a114-cf240f2fb9a5 | note | Reference Documents: Cl 614.04 Cl 614.06
ead50410-710a-5789-b018-bd8840623f80 | note | - - - - - - - - -
c0a9330e-a455-5787-ac3a-94a1f74d6d7f | note | Inspection / Test Method: Verify
2e08b15f-8dd6-539f-8c70-774d244566be | note | - - - - - - - - -
ef7836ff-d83d-5479-82e9-1d298734f235 | note | Record of Conformity: ITP signed
a04c50ba-9577-5b48-9ee0-42a1d5d747ab | note | - - - - - - - - -
4d8ba919-b2d0-5f3b-8b53-20be29d85743 | note | IP
33b649f8-3a35-584d-b71c-dd6cc4f695cb | note | - - - - - - - - -
122b690d-f705-5a82-901c-237d4b6d54ce | textbox | Responsibility: Site Engineer/ Site Supervisor
| checkpoint | 2.3 Formwork levels and position
37e2ab53-0cf7-5ddf-ae57-70772f98cee4 | note | Frequency: Prior to concrete pour
9e1f5ff4-f0d0-50d2-82bc-c975d785fb6c | note | - - - - - - - - -
40d20c1a-aa13-5836-8113-7169f5906748 | note | Acceptance Criteria: A pre-pour survey carried out by a surveyor. Surveyor report obtained prior to concrete pour. Erected formwork within the tolerance (as per Table 610.461 and Table 610.462). Any errors in the level or positioning of formwork is to be corrected prior to placing concrete
480704c0-8c15-52e3-bac9-de7d3b4481c6 | note | - - - - - - - - -
f1be7f87-4c9f-504c-8116-59d339c53b14 | note | Reference Documents: Cl 614.06 Table 610.461 Table 610.462
e18f58bb-aa45-51cd-850d-a1a45943b0cf | note | - - - - - - - - -
1b5db0a7-beec-510d-beed-ff6a8cc8dd70 | note | Inspection / Test Method: Visual inspection
a8ee9932-3661-5f76-9665-f43a52b341c3 | note | - - - - - - - - -
bfdb8170-927c-53fc-b466-6c68c25a70ec | note | Record of Conformity: ITP signed
7688466f-5826-5efd-b406-6d9e88d8ae1e | note | - - - - - - - - -
26c39169-9fd5-5c34-bc1d-e7ecb6438100 | note | SCP HP*
cd79c428-ec82-56db-8d7a-5e9e27894063 | note | - - - - - - - - -
689aacfd-4891-5a40-8d24-95b9c64ea066 | textbox | Responsibility: Site Engineer/ Surveyor
| section | 3 - Steel reinforcing
| checkpoint | 3.1 Placement methodology
7d1d352d-6d5e-56b0-8a9b-2320d86e121c | note | Frequency: At all times
80eacf55-c6e2-5e3a-9156-717eb962d072 | note | - - - - - - - - -
ac3b3615-82e3-5d3b-89d8-77b894e97c3e | note | Acceptance Criteria: All steel reinforcement to be securely held during placing and compacting of concrete Supports shall be of a material durable to impose loads without movement of the reinforcement The placement method shall not allow the reinforcement to become contaminated by contact with other steel
b62f2f1a-f522-53d1-8736-0d1c5509462b | note | - - - - - - - - -
5234924c-765f-5ffc-94e8-118d34d1ed38 | note | Reference Documents: Cl 611.10
50350abd-d55c-595d-98e6-4825dbb62e49 | note | - - - - - - - - -
a4f1e51c-59e5-53d4-b409-f2bb0dfda1eb | note | Inspection / Test Method: Verify
7a559f86-4527-58c6-be4d-f996f04fabb4 | note | - - - - - - - - -
bac3bfc7-c320-599d-acc6-11ffec3bbb33 | note | Record of Conformity: ITP signed
ec124365-f53c-565e-b8f4-d5f3a7ad74c1 | note | - - - - - - - - -
3c1f2cfa-c1ff-5340-92c5-c59862dbd10b | note | IP
04f3dd64-ddf7-515a-8bce-cf41011a3826 | note | - - - - - - - - -
1e35f7fb-fe27-50d0-a149-fc8b7dafa8be | textbox | Responsibility: Site Engineer/ Site Supervisor
| checkpoint | 3.2 Minimum Cover
c4e60fe1-3270-5e04-937e-34135a6406ea | note | Frequency: At all times
79c4bf62-ac3b-5683-9519-41b5c2d83796 | note | - - - - - - - - -
4e05c56d-eaf5-5d55-a615-4d5bae707eb3 | note | Acceptance Criteria: The specified minimum cover must be maintained at all tire wire positions. A tolerance of 0 to +5mm is allowed.
cb25120f-6f81-539e-8c8a-7b4e72262523 | note | - - - - - - - - -
3fe81cce-4822-5023-841a-52ecb0c6c574 | note | Reference Documents: Cl 611.10
ea951e75-7334-52c0-aa29-10af1794594d | note | - - - - - - - - -
b89f0015-e52f-520c-a75c-20982f86cb1e | note | Inspection / Test Method: Visual Inspection
ef122699-5219-56c5-bee7-9191f8794321 | note | - - - - - - - - -
e86ae757-62d7-594e-be85-3187b6913b40 | note | Record of Conformity: ITP signed
50b5274f-3786-5a67-87eb-c487ba3c8ca5 | note | - - - - - - - - -
d8975268-5bac-54b2-97c6-9a37a5ad411c | note | IP
a2c8eab5-240e-5e54-8d39-92a9f59bb248 | note | - - - - - - - - -
eb9d2960-59a2-5353-a53b-b78772243e29 | textbox | Responsibility: Site Engineer/ Site Supervisor
| section | 4 - Pre-pour Planning and Inspection
| checkpoint | 4.1 Pre-pour Checklist
0eb4ff55-dde6-5b62-a629-6e66f61a565e | note | Frequency: Prior to concrete pour
40c99853-b585-5db6-b683-b6c343e9afd5 | note | - - - - - - - - -
e35db7e0-8bc7-59f6-a329-ab68eaf43dae | note | Acceptance Criteria: Pre-pour Checklist (CLA) completed and signed.
3d0e84a0-d51f-5280-bc52-c0177870850b | note | - - - - - - - - -
01e1af31-a87c-537d-b256-a52f13d85b5e | note | Reference Documents: CLA
3f037b6f-92f0-57e9-80a6-9a228798c5f1 | note | - - - - - - - - -
de9cdb11-a6fd-53de-948a-396c0e809f15 | note | Inspection / Test Method: Verify
07f6cddc-fa04-536d-8fb3-2b221915e7d8 | note | - - - - - - - - -
10c2c73b-b9e9-5162-ac7b-bcfc149735bc | note | Record of Conformity: CLA
b1ad5c76-6793-5540-8fba-d1321750af0b | note | - - - - - - - - -
a0a1c6c0-2d31-51a9-8181-f8c153aacffe | note | HP*
147e4f6a-6989-5802-8ca7-62d7b71bdd7c | note | - - - - - - - - -
2821f6e5-49db-5cdd-9b4a-87a789c41622 | textbox | Responsibility: Site Engineer
| checkpoint | 4.2 Pre-pour inspection
3dcef586-00e2-5b8a-86cb-939d87c52663 | note | Frequency: Prior to concrete pour
4b4bd10d-2414-5772-9322-39bb79d05964 | note | - - - - - - - - -
a2bb86fe-12ab-57fa-8b58-e6c6e390fe59 | note | Acceptance Criteria: Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications. Hold Point released by the Superintendent.
ccac26ba-cbb2-506a-995e-30d2faed487f | note | - - - - - - - - -
094ad2c0-425d-5a72-8ca1-cde0b7ac9810 | note | Reference Documents: Cl 610.18 (a)
25ee1fce-76fa-5906-9fbc-be13bff228f5 | note | - - - - - - - - -
65a0dbf2-bbc3-508f-be1e-ed02bc306ad7 | note | Inspection / Test Method: Verify
56436b23-97a9-591b-a508-236e3dc3511e | note | - - - - - - - - -
490d2494-662e-5c39-9a03-a0ab121398b4 | note | Record of Conformity: ITP signed
87670014-b87d-5198-a30b-6d8c8bdc8b05 | note | - - - - - - - - -
4abe49cb-83c6-5c00-ab34-ca2789f1ebaa | note | HP
c7e009b0-974a-5e23-a5da-dd2eae7aaef1 | note | - - - - - - - - -
f7dec5c0-7f36-53fa-abc8-36fd4d317769 | textbox | Responsibility: Site Engineer/ Superintendent
| signoff | HOLD POINT
| checkpoint | 4.3 Temperature
63764210-d98b-52b0-abc3-631d087112a9 | note | Frequency: Prior to concrete pour
34d80346-3bf8-5edc-b91d-0ce2e9d37d27 | note | - - - - - - - - -
29a05ac5-2a19-5b67-a0f6-e60536fa7e90 | note | Acceptance Criteria: Concrete shall not be place when temperature is <5°C or > 35°C. All steel components that are in contact with the concrete shall be cooled to below 32°C before concrete is placed
7165d6c2-ce4b-5034-8d50-820c190f19a6 | note | - - - - - - - - -
c0f6450d-d3c9-58f1-989c-5fbbeb086c08 | note | Reference Documents: Cl 610.17 (b),( c), (d)
c3024c11-3483-5208-a944-99b86bb972b0 | note | - - - - - - - - -
bad33b4c-3249-5d1f-92fc-6a32444589ef | note | Inspection / Test Method: Verify
2b2142ed-9f51-52c3-aa72-6a64fe5147b7 | note | - - - - - - - - -
9e749198-4c15-5c33-a490-52a3464ccbe5 | note | Record of Conformity: ITP signed
7d0af27b-1476-5f2a-88b0-f5208bad7222 | note | - - - - - - - - -
d8929e63-2881-57a9-b229-b5b9e6000058 | note | IP
45d2f951-3c80-5da0-b9fe-38c88e197f60 | note | - - - - - - - - -
b913c7e2-ffca-5ad3-980d-075327c5356b | textbox | Responsibility: Site Engineer/ Site Supervisor
| section | 5 - Placing Concrete
| checkpoint | 5.1 Carry out sampling of concrete
c3303099-5800-5864-b264-b82f6fcc99f3 | note | Frequency: Each concrete pour
cba7c8b1-d813-5ca1-b99e-f7a94b69587c | note | - - - - - - - - -
82723d60-b2f7-5a37-bf29-9ed9e3f36cec | note | Acceptance Criteria: Compressive and slump sampled to be completed in accordance 610.16 No. of Samples: 0 to 10m3 - 1 No. 10 to 25m3 - 2 No 25m3 + refer to specification
05182662-75fa-550e-9c21-9bd027556d8e | note | - - - - - - - - -
cb1ad91b-cbfc-5e89-8761-27305752288f | note | Reference Documents: Cl 610.16 CL 001B CL 001C
90ac208c-b214-541e-8fb2-d38235cc9b14 | note | - - - - - - - - -
7d94b6db-ab5f-55b4-805a-539c2b29cd8a | note | Inspection / Test Method: Checklist
8d2c382f-8cf6-547a-8b01-c9fdd8168670 | note | - - - - - - - - -
dce1b94b-ae60-5b43-b3bd-22d2cd884d1a | note | Record of Conformity: CLB CLC
9d38b445-b09f-5005-8ba7-c8b08d50c738 | note | - - - - - - - - -
c49493ae-fff5-548f-bd3c-fbd298f57888 | note | TP
1390b934-29df-5f36-a58a-c37859d67394 | note | - - - - - - - - -
8891acc5-69f3-5045-b875-d580710f9ac3 | textbox | Responsibility: Site Engineer
| checkpoint | 5.2 Slump Testing
2c43e179-d882-5ccb-b49d-f83010d7bbea | note | Frequency: Each concrete pour as per 6.1
f5eefcc9-cee5-5e85-ad7c-4ac2dd2089e8 | note | - - - - - - - - -
7c6530d6-ae1f-59e8-a096-4f4bf8d1ffc3 | note | Acceptance Criteria: Slump testing to be within the tolerances specified in Table 610.162. <60mm = + or - 10mm 60mm to 80mm = + or - 15mm 81mm to 110mm = + or - 20mm 111mm to 150mm = + or - 30mm 151mm+ = + or - 40mm
38310d56-63ff-5038-9ec9-1e55840307a4 | note | - - - - - - - - -
ebf2e4a7-8ebb-53ed-8e7f-306400b8e263 | note | Reference Documents: Cl 610.16 Table 610.162
2ac6d363-bcdf-5044-9d52-b9ecd22bfbd9 | note | - - - - - - - - -
9118a81f-3083-5690-b441-f76a652ef469 | note | Inspection / Test Method: Verify
bc2b04ac-db77-5bcb-a9ed-20367573d9e5 | note | - - - - - - - - -
dd6a9293-74f8-59d7-80d9-c35d45610b4c | note | Record of Conformity: Concrete test records
6d20c279-42d7-56ae-b947-6e3b61777efe | note | - - - - - - - - -
8314e131-8845-5441-8211-e4cd09bbfb54 | note | TP
b3758d16-e5c1-5d99-9553-4fe2f26352c7 | note | - - - - - - - - -
d527ef1b-43d0-5de6-b514-6b7c1eaeaa4b | textbox | Responsibility: Site Engineer
| checkpoint | 5.3 Compressive testing
8c3f1ebb-569e-556d-86ee-9d452963d45e | note | Frequency: Each concrete pour as per 6.1
86ae3ead-8168-5e21-8999-b9f0ede94ba4 | note | - - - - - - - - -
6a6387ef-3d4b-5a8f-9eaf-4f9d5750ace6 | note | Acceptance Criteria: A minimum of one cylinder shall be tested at 7 days and a minimum of 2 cylinders at 28 days. The average compressive strength at 28 days shall not be lower than the specified minimum compressive strength. Additionally, the compressive strength of each individual cylinder shall be no less than 90% of that at 28 days.
4fd8b6db-3593-57a9-a40f-a28764616e33 | note | - - - - - - - - -
ef5ca710-443f-5e27-a00a-d800963422c7 | note | Reference Documents: Cl 610.16
049a4378-579e-542d-b829-96dd04061f02 | note | - - - - - - - - -
db3e0621-64b0-5b68-9e4f-04da5e46818b | note | Inspection / Test Method: Verify
8e43652d-cbae-531b-a8ea-b304be1faa16 | note | - - - - - - - - -
cbe7d77f-b193-5f8d-8f0b-5518148b981a | note | Record of Conformity: Concrete test records
810866b4-8b90-5ae5-b516-d52b95395d6d | note | - - - - - - - - -
7a393d99-edd4-51b1-8c9c-400c7aa1b2ea | note | TP
e6321a4f-e69a-5eeb-8354-7eb46eeed518 | note | - - - - - - - - -
2d5b1152-2b5c-5e10-979b-ce686272eb9e | textbox | Responsibility: Site Engineer
| checkpoint | 5.4 Cleaning formwork
509ece41-bc54-5fdc-8b83-69380bea6124 | note | Frequency: Each concrete pour
2e090620-19b6-5a29-8327-1d2bb4159288 | note | - - - - - - - - -
2fa06318-71ac-5b6d-841d-a123f2651be2 | note | Acceptance Criteria: Concrete shall not be placed until all foreign material has been completely removed from the forms
7f2b91b1-4a56-5f14-a16f-f75efc86d772 | note | - - - - - - - - -
ca3d4b45-20e0-5838-925a-573079c328e2 | note | Reference Documents: Cl 610.18 (a) (iii)
1de966d5-efe7-5ff8-b123-4070bf3e0022 | note | - - - - - - - - -
a68aaea3-0cd7-5aaf-b137-bbab92411701 | note | Inspection / Test Method: Verify
414e7692-cae9-55da-852d-03cd6896f5cd | note | - - - - - - - - -
d043cc49-8420-5f9c-af2f-2f744aef941e | note | Record of Conformity: ITP signed
c3e7834f-a581-56b1-b4d8-bb43043de1e0 | note | - - - - - - - - -
17836d7b-f36b-50a1-ad33-7672c3d03396 | note | HP
15cb02c3-67f9-5bde-854e-0989f16069a0 | note | - - - - - - - - -
d5825b1f-b9a3-53eb-9414-8164b0b716e9 | textbox | Responsibility: Site Engineer/ Superintendent
| signoff | HOLD POINT
| checkpoint | 5.5 Discharge time
dbe8e9b7-0f94-5928-b5ee-2f59f26fa465 | note | Frequency: Each concrete pour
faf53587-0a1c-5412-928d-5790d6458081 | note | - - - - - - - - -
edfe2ba8-1093-561d-ad77-456f55778689 | note | Acceptance Criteria: Discharge time (concrete placed and compacted) < 60 minutes from batch time unless approved otherwise.
f41fa240-1b26-55e4-b8f2-8aa40001889b | note | - - - - - - - - -
ce1931da-a7dc-59c4-85a7-7b9861d54c98 | note | Reference Documents: Cl 610.13(f) CLD
53c22cc2-1322-595d-88f5-3987cc20000f | note | - - - - - - - - -
e1bc90e1-13de-5abd-89ec-53973cc65d09 | note | Inspection / Test Method: Checklist
b93ac630-c2da-5b18-be64-d8bb14d56cae | note | - - - - - - - - -
f1c66d17-53ae-5f28-90ed-6d0f3318b326 | note | Record of Conformity: CLD
f68f9ec1-97a0-506b-9c02-6f5ffa52899a | note | - - - - - - - - -
efda79d0-d423-585b-ab65-1a27e55f81a4 | note | IP
cf582696-e27c-5f86-b1c8-cfb43b2aa19a | note | - - - - - - - - -
9609408d-cfee-5e93-b150-caa6e6ed647d | textbox | Responsibility: Site Engineer
| checkpoint | 5.6 Placement methodology
d484509b-c933-5703-85bc-c22b946b65da | note | Frequency: Each concrete pour
c79c220b-05b2-5331-a7c8-53de15d54236 | note | - - - - - - - - -
7a3d57e5-df0d-5255-85ed-3746867c8550 | note | Acceptance Criteria: Concrete shall be transported, handled and placed in a manner that will prevent segregation or loss of materials. Concrete shall not be freely dropped from height >2m. Concrete shall not be moved horizontally by vibrators
2a1d3d6b-06d0-5dc2-a3e6-1543ff6d02b7 | note | - - - - - - - - -
80df1af2-b8ff-567f-a15f-dc54899a0014 | note | Reference Documents: Cl 610.18 (a)
2accb996-3982-5784-96a7-e8d4bb1fa898 | note | - - - - - - - - -
16d30335-50a2-548c-b5ef-49f437570956 | note | Inspection / Test Method: Verify
45ca8c1a-99bf-514a-b3d5-3040f6c12cd0 | note | - - - - - - - - -
bbc70f59-c378-566f-a1f6-38396c477bb8 | note | Record of Conformity: ITP signed
e369c3a0-aa23-573d-825b-40233751fa89 | note | - - - - - - - - -
0224030a-e4e1-5826-9c6c-5eeaea8fd23f | note | IP
4eb5439b-962e-5631-8d04-79aba533bf80 | note | - - - - - - - - -
bf8f4df5-5669-501d-b26d-96267c2d9889 | textbox | Responsibility: Site Engineer/ Site Supervisor
| checkpoint | 5.7 Load Spacing
f1582dcb-d8fa-519e-92c7-d65a7c2de946 | note | Frequency: Each load
e2800fd3-4ef7-58eb-ab49-964d0d8f3494 | note | - - - - - - - - -
02efb41c-3d3f-57a4-a980-cd52d0259d0c | note | Acceptance Criteria: During continuous pours their shall be no more than 25 minutes lag time between truck loads (From Finish to Start)
1c8414bb-56c3-5d0b-9171-a817eea0c3fb | note | - - - - - - - - -
7ed6676c-0938-5b54-bfc5-70114207c2b3 | note | Reference Documents: Cl 610.18 (a)
2a33a8fb-f735-55af-b0ef-ee3a05f9b8eb | note | - - - - - - - - -
33fc1c4a-a1a8-5363-802d-a7b77f885b6e | note | Inspection / Test Method: Verify
31027459-df21-56e0-8b5e-99c2b19aefa3 | note | - - - - - - - - -
623e766f-79ad-52d9-a92e-0cc564330699 | note | Record of Conformity: ITP signed
00f2dbdb-06f7-5cc4-88d4-d2bfcd08858a | note | - - - - - - - - -
9105de8e-2b71-54a8-b149-6d7378380f19 | note | IP
252a61c2-a6ef-5652-9f67-cb9c1fc9c6d9 | note | - - - - - - - - -
8c15556e-f8ce-59d9-8768-bdc8afcd0fa1 | textbox | Responsibility: Site Engineer/ Site Supervisor
| checkpoint | 5.8 Compaction
d9697fc7-7fba-5fae-a378-a8ed71f7e00f | note | Frequency: Each concrete pour
030b7628-e430-5560-ad2e-8247021f917d | note | - - - - - - - - -
09b3a4e5-bcd1-523d-97db-e707eac3be39 | note | Acceptance Criteria: Vibration shall be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs.
157dbf88-80f1-5618-a7f6-fe298dc2e628 | note | - - - - - - - - -
e83029be-ed1f-598c-8d02-8778d0f2c915 | note | Reference Documents: Cl 610.18 (d)(i)
7da3f974-0d2d-50b2-aa7f-88c26f438f91 | note | - - - - - - - - -
c8bce364-a346-5f7b-b202-db186486fd7c | note | Inspection / Test Method: Verify
b489e632-dcf3-5dab-913a-ba4c595a8fd0 | note | - - - - - - - - -
3c0bf596-b68e-57aa-b9db-60b612f57fbc | note | Record of Conformity: ITP signed
dcf75f1a-0381-51d5-b61c-c54d90b010d1 | note | - - - - - - - - -
c687b235-7cba-53a2-8723-9c1800ed507b | note | IP
52f95276-2676-5a8c-aeca-03f37d6730c2 | note | - - - - - - - - -
f06ca4d1-864e-5224-8c6f-557fce841873 | textbox | Responsibility: Site Engineer/ Site Supervisor
| checkpoint | 5.9 Construction Joints
a79e1472-1c9a-5938-8ae4-402d290e5664 | note | Frequency: Each pour involving construction joint
809a2675-f211-534b-9270-3cf91cb0b3bd | note | - - - - - - - - -
fce8acad-9484-5256-978e-67bd67f29c93 | note | Acceptance Criteria: The location and details of construction joints shall be as shown on the drawings. The placing of concrete shall proceed continuously from joint to joint. Any point at which the placing of concrete has stopped and the concrete has taken its initial set shall be treated as a construction joint. Before placing new concrete against concrete which has set, the forms shall be re tightened.
0ea14356-0a57-5581-b4a8-44842d8f4541 | note | - - - - - - - - -
bfde2f98-4de3-5b3d-a83b-a88163823fcf | note | Reference Documents: Cl 610.20
63c207a0-4998-5de6-9798-338619088839 | note | - - - - - - - - -
5e644f60-92f2-54e4-87f1-aa5db7b74969 | note | Inspection / Test Method: Verify
1fded164-7afc-5b6c-897d-d074d7928825 | note | - - - - - - - - -
f3420e92-629b-56d6-9b33-815c789160f0 | note | Record of Conformity: ITP signed
3159a8a8-0dd2-5e15-89d2-e99aeb951cca | note | - - - - - - - - -
93c9da00-f168-5940-8322-ca0b7a2b66b3 | note | IP
aefe2be3-4192-5085-b45c-1e62d21a5558 | note | - - - - - - - - -
429defd6-c3f0-5585-b20e-e5aab788eb59 | textbox | Responsibility: Site Engineer/ Site Supervisor
| section | 6 - Post-pour Details and Inspection
| checkpoint | 6.1 Formwork removal
7007dcfd-f729-533c-a9ba-cb3d8561b8a0 | note | Frequency: Each concrete pour
6c821d3e-861a-5189-b8d7-7f01f7e37000 | note | - - - - - - - - -
6e2746d7-e06c-5bdf-9a06-4adeca3c6b34 | note | Acceptance Criteria: Formwork not removed/disturbed for the duration of the minimum removal time specified in the Table 610.251. Walls <2m = 2 Days Side of slabs and piles = 1 Day
4f819a1e-1c95-556a-96a3-d76465037eeb | note | - - - - - - - - -
f73a8eb3-51a1-5b6a-8897-faadb9b1ac65 | note | Reference Documents: 610.25 Table 610.251 CL 001F
4f651e55-028b-5139-a345-48a3b7aacb83 | note | - - - - - - - - -
9dceffa0-3c38-5607-bc8b-61df3b6abaca | note | Inspection / Test Method: Verify
0705b109-70d1-5261-bac7-5621f599102a | note | - - - - - - - - -
67ccdb57-4ed3-502b-9342-352f356642f0 | note | Record of Conformity: ITP signed
b8aba89f-14a2-5641-9806-e5e12d28b20f | note | - - - - - - - - -
fc1aa67a-3558-5528-b88a-08cbcfe0a773 | note | IP
04ef504b-664e-5179-a482-0bd2ee58b8ae | note | - - - - - - - - -
5dfebd3b-772f-5cfd-8654-9b9e33a5101e | textbox | Responsibility: Site Engineer
| checkpoint | 6.2 Post-pour Checklist
3e98bf4c-a1ec-59d0-9d64-b9144fe97651 | note | Frequency: Each concrete pour
12c351d3-2091-5294-9461-f6c0fb3d022c | note | - - - - - - - - -
1ff1690d-4d75-5249-94c1-4fe885091ed0 | note | Acceptance Criteria: CL 001F – Post-pour Checklist completed and signed.
a08f86b9-95db-5cb0-a398-e93ddbd862c6 | note | - - - - - - - - -
9eac6e64-245c-543a-bedc-f3a2c69eb834 | note | Reference Documents: CL 001F
f9d1e7b8-1faa-5bad-806d-f50637804b5e | note | - - - - - - - - -
5c5bb561-c520-559c-b11d-25124818c648 | note | Inspection / Test Method: Verify
ca2b1a57-a514-5508-89d0-8f0e75d310f3 | note | - - - - - - - - -
8fe06190-538d-5c7e-8366-bf32787df10a | note | Record of Conformity: CL 004F
7935c12c-946a-57c8-8877-b82b2f28e967 | note | - - - - - - - - -
875d3b26-3539-556c-842a-07115ec6b6c3 | note | HP*
8f5af7ae-cc69-5ca5-91d2-eb3e3786b082 | note | - - - - - - - - -
3d068369-a92c-583f-818a-5f7c55cf1788 | textbox | Responsibility: Site Engineer
| checkpoint | Final Inspection
e3d095d5-c315-582a-8e85-f90beb2cf941 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
056b37dc-3fbc-5396-a9f3-5f39b339750d | textbox | Print Name:
087bc97c-e809-52ea-afdc-ac969edeb93e | textbox | Position:
9b409934-5daf-5b59-b265-51db28aad275 | date | Date:
cc6e42eb-c499-57c7-a439-673aadbe35cc | date | Work Completed On
| checklist | ITP 0079 - Watermain Construction | itp | ITP-079-UT-LOT-XXX - Desc | 1ba60867-9f57-4091-b816-8b5de0e3acd9
| section | 1 - Preliminary Works
| checkpoint | 1 Issued for construction drawings
71ce61ed-bbd0-5678-b98e-dc77386b6ec4 | note | Frequency: Prior to commencement
ee0689c7-af5c-563c-a4b4-b1770cd0848b | note | - - - - - - - - -
7c779c0b-56a2-5295-b313-1a89b7071bda | note | Acceptance Criteria: Ensure the most current revision of drawings is used to conduct the works.
9e0fe188-c502-5df4-b917-1273b4c9a0be | note | - - - - - - - - -
05fe79d6-fc33-5686-a5ab-928313957ad3 | note | Reference Documents: IFC drawings
1a43333a-246a-5110-91c6-e66101da40c8 | note | - - - - - - - - -
e80d3a96-b3bc-5296-86f2-12c6a2d3a7f1 | note | Inspection / Test Method: Review
e450c126-f066-5258-b95e-934f7640cda5 | note | - - - - - - - - -
02fab799-aea3-54e0-911c-c7d664627353 | note | Record of Conformity: Compliance checklist - Daily Prestart Form
104befd8-3616-5798-b847-3e67b1a217dd | note | - - - - - - - - -
9b63e0ee-3ce1-5952-b5b6-28547afef91d | note | HP*
15ece9bc-0870-5b61-852e-6132a3398cd0 | note | - - - - - - - - -
75da4746-f00f-54e8-8721-8f20297fa5b9 | note | Responsibility: Project Manager/Engineer
| checkpoint | 2 Permits with relevant authorities
5e0ea6b8-c3a4-58b6-a070-276627b2a6cf | note | Frequency: Prior to commencement
4143ccdd-116b-5055-b492-3c5ee5f0514e | note | - - - - - - - - -
2c9ff944-1c13-5a91-8b58-5762d1fd2b65 | note | Acceptance Criteria: Permits to be obtained by relevant authorities
adb19514-be0a-56b2-9474-99d8fc48b449 | note | - - - - - - - - -
ac60abba-56ff-5dc9-9609-0e410671ad45 | note | Reference Documents: DBYD
8f7fcea3-ba79-5099-912a-cb29a0b42d8e | note | - - - - - - - - -
8118d3a1-0b1e-545a-89c1-390abce2dd6f | note | Inspection / Test Method: Review DBYD
3c4bda8d-9816-53fe-aa16-f2949f22e323 | note | - - - - - - - - -
2742ce32-dfba-5aaa-b997-06de6872c69c | note | Record of Conformity: Compliance checklist Excavation Permit
c8af969b-51c0-5ba9-93db-113d818cdd7e | note | - - - - - - - - -
508ebe92-e859-5d74-aa78-f6fa7849fff9 | note | HP*
be76e49c-62f6-5975-bc9a-a33c50e4709d | note | - - - - - - - - -
008f7e27-173d-5792-aceb-54a857c77696 | note | Responsibility: Project Manager/Engineer & Superintendent
| section | 2 - SURVEY, SETOUT & LOCATION OF EXISTING SERVICES
| checkpoint | 3 Survey set-out
3641fe8f-3e2a-5c2f-946c-31dfb5c75a61 | note | Frequency: Prior to commencement
abc59b6c-76e7-56eb-9903-64cfce918f3a | note | - - - - - - - - -
5cea5525-49ee-57bb-a345-361023492631 | note | Acceptance Criteria: Building line pegs to be installed prior to any excavation
d5840ddd-a670-510a-b2ba-30d6f7e321f1 | note | - - - - - - - - -
90a7f299-b6b2-57ec-9e87-92bc4212acc2 | note | Reference Documents: IFC drawings
d8cce7b9-b78f-5e03-ade7-654336198432 | note | - - - - - - - - -
f71605dd-f6a7-5f8c-b1bf-d7af8576ab2e | note | Inspection / Test Method: Visual check
4c3c2107-8529-5572-a455-372818b4b342 | note | - - - - - - - - -
fd33cba3-3b2c-5b77-bd03-1e00b6929d75 | note | Record of Conformity: Compliance checklist - Pipeline construction
b615ea00-b669-5256-a3df-2b9cdf74caa7 | note | - - - - - - - - -
a60d0226-ce37-5101-a108-fe88763ec0d0 | note | SCP
d495b59a-7cc3-5a1b-8930-388b2cfd7d6e | note | - - - - - - - - -
f1def94b-1289-5442-ac46-72ae2cd01906 | note | Responsibility: Surveyor
| checkpoint | 4 Service location
53fc9d33-93d2-52ad-abea-0efa2e5ba42b | note | Frequency: Prior to Excavations onsite
f7fd1676-58c5-56a7-b265-2326ce39174b | note | - - - - - - - - -
771de4c6-9dc2-510c-98c7-e70a6104d5c9 | note | Acceptance Criteria: All existing services to be located and protections in place
a699e081-43e4-5126-9743-f1e37149d161 | note | - - - - - - - - -
0ebb8d34-6d61-5ccf-a3d6-9602a459c286 | note | Reference Documents: DBYD
52d023f0-1c66-552a-abcd-57f74d4e01bf | note | - - - - - - - - -
8e181dcc-3718-5fac-835e-064373fcdc85 | note | Inspection / Test Method: Review drawings and DBYD
f4130936-cfc2-5c9e-8166-3126c354cd82 | note | - - - - - - - - -
c7a982db-2474-5469-8a86-bb18ab3998a3 | note | Record of Conformity: Compliance checklist Excavation Permit
2fd0fe3f-3974-5f59-bfdd-f0469cdcfba7 | note | - - - - - - - - -
a828dbce-5d07-54c4-8b0a-3539b252d1e8 | note | WP
98c293f2-3674-56cb-a9d7-0ec373f29b0e | note | - - - - - - - - -
eea2f853-11c1-57cf-a2a8-e92e1f71b93d | note | Responsibility: Site Manager/Engineer/Superintendent
| checkpoint | 4.1 Installation of property service conduits
9f5dc2ff-4b30-5215-b648-1380bceb0f6c | note | Frequency: Prior to commencement
31dc1be7-8a66-5929-ac60-5aea5ff4de0b | note | - - - - - - - - -
0a866673-110c-5d6f-af53-e1fec827fd17 | note | Acceptance Criteria: All service ducts required by road contractor to be installed prior to works to be inspected and ensure they meet MRWA standards
90ff4799-c0f4-5c33-91be-23b1a17bd207 | note | - - - - - - - - -
24fe0695-e193-51e1-8e89-5c50a77025a6 | note | Reference Documents: MRWA-W-110
18a45155-d478-569e-a0ac-406aba6cfa36 | note | - - - - - - - - -
b83b500a-4977-51d2-9c24-23aeb69dcc34 | note | Inspection / Test Method: Visual check
73e0a71e-20d5-50cf-b508-5af52a556a84 | note | - - - - - - - - -
b034c4e5-427d-5d1b-a5cc-a534eeb1df95 | note | Record of Conformity: Site Daily Diary Entry
8f347212-e032-5b9e-b077-90e2f163a644 | note | - - - - - - - - -
e78db91d-4272-5e72-b96a-2c826460a020 | note | HP*
a5d026aa-d631-5de1-82c4-a56501af9c93 | note | - - - - - - - - -
c03d5582-3c10-5a1b-9be7-d1caed91804e | note | Responsibility: Site Manager/Engineer
| section | 3 - MATERIAL CONFORMANCE
| checkpoint | 5 Correct pipe and fittings onsite
2044c14a-79d8-5423-9831-448cda6ae0dd | note | Frequency: When delivered
4db879f8-faab-5fdd-a8fa-48d6b9d3382a | note | - - - - - - - - -
fbb675d8-21e8-585e-957f-66d5fbad3bed | note | Acceptance Criteria: Inspect materials in delivery against order. Pipe size matches plans
0ed368aa-c8d1-5178-8276-7496181e4b5c | note | - - - - - - - - -
063d7457-ca24-5a74-ba32-ab344d1a9c93 | note | Reference Documents: Delivery docket/ IFC drawings
97988362-db32-50ad-a361-8ab2a8b3a826 | note | - - - - - - - - -
40b6e963-1c43-5530-acac-8821ab616be3 | note | Inspection / Test Method: Visual check
a126c118-ede0-5639-8540-e5d5aedf4a96 | note | - - - - - - - - -
94ff5875-3063-5c9a-a13f-9d0d02d1a633 | note | Record of Conformity: Compliance checklist - Pipeline construction
05f43226-3f59-5ffb-b527-40620408e78b | note | - - - - - - - - -
71c3ab1f-ff60-534e-8453-48b6ff95dbf8 | note | HP*
caaf1be7-bd12-56a5-bfda-66b85a147387 | note | - - - - - - - - -
30823e9a-0a7b-5167-aa10-f63ed3171124 | note | Responsibility: Site Manager/Engineer
| checkpoint | 6 Correct embedment / backfill materials onsite
d561db0b-d68d-5964-87a1-51219712ec11 | note | Frequency: When delivered
5c3046cc-f2b8-5ac9-949a-4315a580258a | note | - - - - - - - - -
e56a0323-bc4d-53d5-855d-25b9cdab8163 | note | Acceptance Criteria: Inspect bedding material to ensure suitability
4812d941-22dc-5fe4-ab7c-311604aa5c59 | note | - - - - - - - - -
997ab262-aac4-52e7-9962-f88c2423d650 | note | Reference Documents: MRWA-W-201 to 203
e805feb2-f0b5-58ba-922e-883fb45ed0eb | note | - - - - - - - - -
2de17da6-2461-594e-9b59-7189fd2fecb7 | note | Inspection / Test Method: Visual check
c01b5526-ddf5-5745-b356-5e095b8eec92 | note | - - - - - - - - -
c7cb2c2b-0c8b-5273-8b39-da67c76a955f | note | Record of Conformity: Compliance checklist - Pipeline construction
b7b40e50-0115-51f5-9273-09fa42f316fe | note | - - - - - - - - -
5383dde4-6204-53e8-b1c5-c46c494425a9 | note | HP*
b09475ca-e8a1-5b10-a12b-f02af01523d0 | note | - - - - - - - - -
ffa13d4d-2633-53b6-8239-cc0a99f4d1d1 | note | Responsibility: Site Manager/Engineer
| section | 4 - ENVIRONMENTAL & SAFETY
| checkpoint | 7 Environmental controls
65098306-7204-548d-a041-0c84b27f922a | note | Frequency: Daily
9f532d33-76dc-5fce-86d9-8e992d547355 | note | - - - - - - - - -
64a1ed90-43bb-5878-9ee0-951d490c979a | note | Acceptance Criteria: Ensure environmental controls in place and being maintained as per the site EMP (if the civil contractor is responsible for managing the site then as long as we do not distrust their controls this item can be ticked as N/A)
deefbfb2-0438-5ec3-a4d5-d1dd90b230a8 | note | - - - - - - - - -
fce295ad-0b2b-5b3c-9891-f1a892484949 | note | Reference Documents: EMP
47bac0ef-b138-54c1-8bea-656a3b1dd62e | note | - - - - - - - - -
2aca37d6-ea27-50d7-883a-eb7ed654cebd | note | Inspection / Test Method: Visual
0cdd9e6b-8be2-55e2-b114-cb2e52c629e4 | note | - - - - - - - - -
eb6e4670-c918-54e2-a1b8-1ce4e06f3e01 | note | Record of Conformity: Compliance checklist - Daily Prestart Form
36b401b5-9312-5d95-b911-a227951178cc | note | - - - - - - - - -
0f6acd3e-2767-5217-90be-f47b734acf12 | note | HP*
cb0a8088-e03d-52a1-88d6-5303d4a6e649 | note | - - - - - - - - -
6123005c-152c-555e-aa3b-6902513b2b0b | note | Responsibility: Site Manager/Engineer
| checkpoint | 8 Safety controls
75e87152-c09d-5ec6-a7bb-7290e66ecf54 | note | Frequency: Daily
3517eacf-c638-5430-b52e-b80debb6d321 | note | - - - - - - - - -
c2484e31-49db-53ee-9002-bbab162f499e | note | Acceptance Criteria: Ensure safety controls are in place as per the relevant safety instructions and SWMS
eaaab401-2c4f-599a-a4f0-bbfe249d6f64 | note | - - - - - - - - -
dcc5cbe3-cb51-5500-8d96-445b3b64c8e8 | note | Reference Documents: SMP
a64d6897-ee94-566e-b978-5fbb972488bd | note | - - - - - - - - -
6b9e1c8a-b426-5cb9-b5a2-597163f20d45 | note | Inspection / Test Method: Visual
7f759aba-59c5-5cc5-b675-730ca503d8a2 | note | - - - - - - - - -
4e0ae478-59e2-54d5-9e95-1c9694bb2f6d | note | Record of Conformity: Compliance checklist - Daily Prestart Form
2b5f8350-1cf5-5683-a328-7d17b772a5a7 | note | - - - - - - - - -
d6c1da69-891c-5870-b97f-8a3d3058d1d3 | note | HP*
48051d5c-f5ee-5ee5-b28d-285b67557264 | note | - - - - - - - - -
97f01bfd-9957-502c-b2c3-b027f02cebbe | note | Responsibility: Site Manager/Engineer
| section | 5 - TRENCHING & EXCAVATION
| checkpoint | 9 Trenching
637d656e-efed-5358-8351-d2441c27380e | note | Frequency: Prior to entry into open trench
55864416-d365-5e90-a074-e7caf931e37f | note | - - - - - - - - -
81ee81b5-2b82-5e7e-adfb-755eee005714 | note | Acceptance Criteria: Ensure trench width and depth are within tolerance
64b8de9f-40d8-55df-bccb-b45a4490d82c | note | - - - - - - - - -
ac3df8cd-8f03-5f47-ad24-ed5579ba10f1 | note | Reference Documents: IFC drawings / MRWA-W-202
27c4cf62-e238-5d67-b296-3c9a45cc3cc6 | note | - - - - - - - - -
c799c5b5-2554-5cfa-90ff-d60223d90133 | note | Inspection / Test Method: Visual
ec9a275a-64ae-5e03-8bfc-2c84f78afcac | note | - - - - - - - - -
a975f70f-861f-5805-b136-1dc69089c780 | note | Record of Conformity: Compliance checklist - Pipeline construction
db5d8acf-3585-59a6-9409-9fccb564c527 | note | - - - - - - - - -
a014c81a-c103-557a-b754-f9056e06ee8d | note | SCP
e2e2d251-9162-57a3-bfc9-41d4d4a5e100 | note | - - - - - - - - -
c12182eb-9c16-5dd3-a9dd-229cd5e0f90c | note | Responsibility: Site Manager/Engineer
| checkpoint | 10 Trenching
e1e15287-4b96-59dc-b8a5-2ecddb7875de | note | Frequency: Prior to entry into open trench
438d5fc6-eda7-5b92-ac5b-1edf019493be | note | - - - - - - - - -
a3a722e3-3b13-5ad0-ae6c-2675a84789e1 | note | Acceptance Criteria: Ensure trench foundation & wall firm, stiff & suitable
1cc98260-2b6f-5fe9-b769-d12112a145b8 | note | - - - - - - - - -
5e87becb-cfd5-55af-a5cd-a51ad30b5286 | note | Reference Documents: MRWA-W-202
8f7eeefd-66c5-552f-b1bd-8ff6b2245240 | note | - - - - - - - - -
f6d0ff0a-52c7-594c-9577-e2063ecd5e8d | note | Inspection / Test Method: Visual
b5fec29d-b79b-5731-8567-7eb9d8ad5296 | note | - - - - - - - - -
8053b1ab-9168-5c5b-b66f-fc1a90bcfb69 | note | Record of Conformity: Compliance checklist - Pipeline construction
28494b4e-0e9b-5d0d-b01c-f908e75d3f31 | note | - - - - - - - - -
f4e41a1d-2e3c-5084-ba14-7639ea0dc8bd | note | HP*
92d25a25-b480-5f6c-9746-02ef85a721cf | note | - - - - - - - - -
3ba32795-ad63-5a9d-9572-8402dcf8a0d3 | note | Responsibility: Site Manager/Engineer
| checkpoint | 11 Placement of embedment material
7220bdda-b5cc-5877-8f0f-64d534d34aa2 | note | Frequency: Prior to backfilling of specified area of trench
792a51da-7115-51b6-82e4-10e15e164445 | note | - - - - - - - - -
7768c6d6-bf38-51ea-b59b-5557b3d8bcdc | note | Acceptance Criteria: Ensure pipe bedding depth is acceptable
3b021843-3177-5929-9c31-4b346935297b | note | - - - - - - - - -
5439df03-e302-5802-93eb-7a2c090a91a8 | note | Reference Documents: MRWA-W-202
7dbda9c8-26a6-5506-9fba-d7a269c0ca7d | note | - - - - - - - - -
965d4cea-49b4-53bf-b764-8207a8ed6d6b | note | Inspection / Test Method: Visual
8af85bcb-bc5d-5b4a-b76c-1b0998da9382 | note | - - - - - - - - -
ad2b3c90-f87f-5809-aa84-6e78dcb1222d | note | Record of Conformity: Compliance checklist - Pipeline construction
c32143c0-ea12-5c63-b490-2c4c258a4238 | note | - - - - - - - - -
5bd812c4-e62d-5ff7-94d8-108ea75edf58 | note | HP*
9c029c85-a8e2-565b-8624-aafd3cea9c29 | note | - - - - - - - - -
ec958ad6-9f0e-5af5-ac88-20dca9560c16 | note | Responsibility: Site Manager/Engineer
| section | 6 - PIPE INSTALLATION
| checkpoint | 12 Pipe laying
cab76adb-f6e9-5e1e-865f-a2d6fd22242a | note | Frequency: Prior to backfilling of specified area of trench
d09fd656-129f-5a70-bed8-2e8bffd83b8d | note | - - - - - - - - -
8bf41397-6ec2-5418-aa9f-dcbcb1ac5e6f | note | Acceptance Criteria: Ensure pipe joint deflection is acceptable and witness marks are applied and visible
4e361f97-5ce5-5852-aaae-56f7a91696a3 | note | - - - - - - - - -
c051bc40-5016-585a-8112-deed06e920bf | note | Reference Documents: MRWA-W-103
fcb3c844-677f-53de-8083-41326f9a9786 | note | - - - - - - - - -
f8da28ad-3cb8-5dd4-801c-11a34fd26306 | note | Inspection / Test Method: Visual
59b60331-9436-5eb2-8a58-0ce3bba75519 | note | - - - - - - - - -
5332104c-8c52-5eea-9f14-15d30f5db732 | note | Record of Conformity: Compliance checklist - Pipeline construction
3b011eda-4246-5bcc-a0ff-6c1491d0ad8c | note | - - - - - - - - -
7550455b-cabb-5ce3-adb4-556d8e4be97e | note | HP*
831673e2-579a-5939-b311-0f4a2a69ba14 | note | - - - - - - - - -
13b2b34e-2c9b-59ba-860b-c70d85e9b572 | note | Responsibility: Site Manager/Engineer
| checkpoint | 13 Property services
298bf1cd-20d2-5e07-8e5b-42d5fcfa66c2 | note | Frequency: Prior to backfilling of specified area of trench
72955a6f-ea20-5cdb-827c-bfbd490a3ebc | note | - - - - - - - - -
d527befc-254c-5c94-861d-5f44cbf58de8 | note | Acceptance Criteria: Ensure tapping collars are installed as per measurements on plans
676e1c7b-2e72-563e-a499-f15c178f5a71 | note | - - - - - - - - -
a7e6b958-ae5e-56a0-ad42-3bb356f1bcf9 | note | Reference Documents: IFC drawings
6a4e8c19-6a26-56b3-a52d-e0a498a4265e | note | - - - - - - - - -
2b1b5ca9-004f-5ace-aeae-81ef54a6cbd3 | note | Inspection / Test Method: Visual
1c9e5389-3468-5a23-9c85-d3e5463859d1 | note | - - - - - - - - -
72322945-23e6-5b34-98c4-40cfc579ad4d | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
c515d233-454a-5914-ab8d-f535fdf21713 | note | - - - - - - - - -
ae2c7f85-84b4-506a-81fa-da5f82e3fb77 | note | SCP
72121894-801c-5820-bd06-1f2565020bcf | note | - - - - - - - - -
2b337e89-b53f-5cda-a254-3229860e1cc2 | note | Responsibility: Site Manager/Engineer
| checkpoint | 14 Dual water property services
124082dc-4e38-5b1c-8553-dea9453278a0 | note | Frequency: Prior to backfilling of specified area of trench
621ad254-902a-5d92-a702-2301bc755a71 | note | - - - - - - - - -
041680ef-bf89-5320-a0d5-86e930f61e78 | note | Acceptance Criteria: Ensure tapping collars are installed as per dual water specifications (to the left of the DW)
36929bb8-b97e-51ab-a945-cc5a9156fd96 | note | - - - - - - - - -
d21c2bd3-4f22-54e4-bd43-c181fbf5188c | note | Reference Documents: IFC drawings / MRWA-W110 & 111
7051f33f-ded2-502f-8969-46a5473dd9d4 | note | - - - - - - - - -
00f219ca-fb82-5b43-a460-2f8d1152240f | note | Inspection / Test Method: Visual
510c4d52-a55a-5d7c-bf97-eeed7fc572bf | note | - - - - - - - - -
abcc7586-93fb-52bd-92ae-aff59bafa762 | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
9943b6fc-b36c-53f6-8aae-187665f480f0 | note | - - - - - - - - -
a5234a4b-aafe-5727-900e-1d8c2649ab29 | note | WP
69f65e3a-a70f-5fa8-8111-16d24d5bdc9c | note | - - - - - - - - -
543883fd-514c-5009-bc37-c7e800a77a2c | note | Responsibility: Site Manager/Engineer/Superintendent
| checkpoint | 15 Valve installation
5a6a6395-d7d3-5379-a73f-577566d24b00 | note | Frequency: Prior to backfilling of specified area of trench
cc5a1cb2-0b87-548a-9df0-891af3e1e787 | note | - - - - - - - - -
ab149d07-1b67-5960-bb46-fa9d3f51673b | note | Acceptance Criteria: Ensure valves are installed correctly.
6afa7b40-5e2e-5c42-8c14-3bc241ff3eae | note | - - - - - - - - -
3383516a-ef3f-5be6-9fcf-c3a4aca693c5 | note | Reference Documents: IFC drawings / WSA page 233 15.4
f08b4bfe-9fb0-5167-83ad-4a3fae3593cc | note | - - - - - - - - -
968d51ab-3ce0-55b8-9464-4994ccdd428b | note | Inspection / Test Method: Visual
fc024d92-634e-53b5-89a4-ae0c4f4c6353 | note | - - - - - - - - -
860eb661-f3b8-5b3a-8328-04ddb6601300 | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
61c26649-6710-5f7c-9158-b1e143454ec0 | note | - - - - - - - - -
c0dd9b80-595f-5778-9563-42beb3ee4da2 | note | SCP
935576d1-40c7-5d4c-9f3a-088cb89d18a8 | note | - - - - - - - - -
8c439833-acb6-5c8f-a291-c0de78fa0a5e | note | Responsibility: Site Manager/Engineer
| checkpoint | 16 Hydrant installation
77466c97-a970-5fdc-b001-3fa14ab62b87 | note | Frequency: Prior to backfilling of specified area of trench
5a47b4a3-703c-5c42-a2cb-b83ac88d69dd | note | - - - - - - - - -
27b43153-9cc1-5774-ac9a-7567c0c25a1c | note | Acceptance Criteria: Ensure hydrants are installed correctly.
c265ca82-5703-5b15-b09e-122ae9841c83 | note | - - - - - - - - -
ff61f3d0-c46f-551d-9484-28f013b825dc | note | Reference Documents: IFC drawings / WSA page 233 15.4
d54fd15c-954d-5c0d-9b1c-4d6f8819ca9b | note | - - - - - - - - -
62612203-a123-5fb1-9df2-4401626737cf | note | Inspection / Test Method: Visual
91d29068-7af2-5028-9e8d-4fab22f9b3bd | note | - - - - - - - - -
6d5b62a2-8019-5fc4-82d8-994d7a6aa761 | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
47e0bf09-8692-5021-9e48-65b725f3fe5d | note | - - - - - - - - -
fad66766-75f7-5ef7-af3d-a0774abbf573 | note | SCP
c3081a56-7ee9-51c9-ab86-b995100f6818 | note | - - - - - - - - -
2c22bc67-281c-5b8d-85c7-617d1b154622 | note | Responsibility: Site Manager/Engineer
| checkpoint | 17 Washout installation
35f86488-b17c-59b5-9e70-f396b637e73b | note | Frequency: Prior to backfilling of specified area of trench
51d3ff25-1b05-564a-b0d4-ceef11b2f4b6 | note | - - - - - - - - -
8687e48e-e0f0-50be-8bd7-a429abb1051a | note | Acceptance Criteria: Ensure washouts are installed correctly.
887e388c-8700-5c8b-a6f9-cab3397dbeda | note | - - - - - - - - -
7aacd66d-5da7-56f9-b50b-34fb3cd099f0 | note | Reference Documents: IFC drawings / WSA page 233 15.4
16098f99-48e1-598b-85a8-d81420b884ec | note | - - - - - - - - -
074b84dd-cf83-54a3-befd-63acd25b12ce | note | Inspection / Test Method: Visual
1af390a4-4ba4-599c-a12a-519dda8dbd1b | note | - - - - - - - - -
53c0cc8f-6ae5-53d5-95e1-469f9b5ba871 | note | Record of Conformity: As constructed information / Compliance checklist - Pipeline construction
b20e60e7-bf63-54b5-8a13-6571fdc04fa6 | note | - - - - - - - - -
5e58eb1c-71ca-5499-b5e2-415d0c58b714 | note | SCP
8ef2943f-6c66-56f2-88aa-86a27e5d563d | note | - - - - - - - - -
dbcb158d-8d3b-5b62-bca5-e100bddabf22 | note | Responsibility: Site Manager/Engineer
| section | 7 - CONCRETE ANCHOR BLOCKS
| checkpoint | 18 Acceptance of concrete delivery
0126db76-d934-5061-a178-9f5dc6dcb36f | note | Frequency: When concrete is required
7b7aacad-fac3-5951-b222-cf2b58d46725 | note | - - - - - - - - -
f83ade12-5a5b-5a9f-8b84-9a5bcfffad28 | note | Acceptance Criteria: Concrete delivered to site to be acceptable. WIN 25 WSA approved mix (20Mpa, 20mm rock , 80 slump)
b8a29a2b-89ce-5a45-a1e3-9a93eb2aa2aa | note | - - - - - - - - -
16e17c5f-61d4-5a39-8c5b-f0414d4a58d1 | note | Reference Documents: Concrete delivery docket
2a44b5ba-362d-505c-a075-a614b9f235e9 | note | - - - - - - - - -
fd7744a2-0106-54d2-a2a3-131a362ff28d | note | Inspection / Test Method: Visual
3e401dba-d71c-5fb3-bcf3-8da0a3bd68ab | note | - - - - - - - - -
fae519f1-eae6-5808-bad6-9f66dae9cc4c | note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
acbc4205-84f0-5215-ab0b-80737527734f | note | - - - - - - - - -
64e18606-c4a8-58a7-b496-50bd30c36bc7 | note | HP*
ef3f1d60-00c4-5ad9-a733-cc2a65ac9cce | note | - - - - - - - - -
dee8341d-94ce-54e4-ae1f-db3f5c56431a | note | Responsibility: Site Manager
| checkpoint | 19 Installation of anchor blocks and thrust restraints
9ea0f5a6-fa1e-5616-a13e-4f4cb1e04f21 | note | Frequency: When concrete is required
f209600b-5014-5464-9cce-bc07a4102204 | note | - - - - - - - - -
f1d1f97c-affc-50f9-9bde-ecbc7d23fadc | note | Acceptance Criteria: Installed anchor blocks / thrust restraints are acceptable
66c724e6-2c98-536e-ae97-53005a5215ea | note | - - - - - - - - -
48a3bacd-0237-558f-acb6-0ea85bc268ca | note | Reference Documents: MRWA-W-204,205A & 205B
157d8cb9-8854-5d15-8281-230fe0bfb4b1 | note | - - - - - - - - -
1fa453f1-a1fd-5908-b36b-c8e0f775392b | note | Inspection / Test Method: Visual
595d4e00-4533-5a4f-9318-910a734cb672 | note | - - - - - - - - -
76979b51-0293-52a8-a272-2bee782dd9dc | note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
a9116201-bc22-5b75-9566-e10e996e372e | note | - - - - - - - - -
3d2a2ccd-1b30-562f-b1ef-7aa7a5f0df71 | note | WP
278c5de8-3abf-580c-bd74-dfcdc0a94d5a | note | - - - - - - - - -
34e8b4a1-8fc2-5df6-b434-945df6401fb1 | note | Responsibility: Site Manager/Engineer/Superintendent
| checkpoint | 19.1 Correct steel reinforcement used in restraint
0e8410da-0d9b-5f8b-b480-04f8b2eb09d5 | note | Frequency: Prior to anchor blocks being poured
3bd5c115-6c78-5e83-a8c1-33b2335d45f4 | note | - - - - - - - - -
ddb69537-e0f6-5da4-a353-2c4ce0d73008 | note | Acceptance Criteria: Reinforcement is as per MRWA 205-A, 205-B and according to thrust area as noted in face sheet of project plan
e9a6dd85-9cd4-5d51-93b1-ce9bb7772026 | note | - - - - - - - - -
5ed7c71c-a494-5bf3-8fd0-0465cde82120 | note | Reference Documents: MRWA W 205-A and 205-B
76e95805-e2d8-59a7-865a-8b28f7e5befa | note | - - - - - - - - -
7d3e5eb8-191b-5213-a4d3-f553bd5495da | note | Inspection / Test Method: Visual
6e3fb4c2-fad5-5f9c-b795-04ec1df1b917 | note | - - - - - - - - -
dba9b224-2e25-5196-9a45-a81d62df4536 | note | Record of Conformity: Watermain Anchor Block Checklist – Procedural Verification Checklist ITC-803
a4155bf1-29a8-52b3-9ece-e39e0d220fb7 | note | - - - - - - - - -
fd9ea5b5-b1bb-52d9-b3e8-5b70885a7008 | note | WP
4713806c-6df3-58a2-adc8-41649039e3fe | note | - - - - - - - - -
3de0a9ef-2516-531a-8b43-a4b19aa49974 | note | Responsibility: Site Manager/Engineer/Superintendent
| section | 8 - BACKFILL OF TRENCHES
| checkpoint | 20 Placement of embedment overlay
4ddd55f6-04fb-56b5-90cd-3d5d5a990ff7 | note | Frequency: Completion of pipelaying
7e77266d-d42d-502f-9a5c-a7d4b4a2ed24 | note | - - - - - - - - -
d228e336-660c-5a98-8d4d-97a4eb963c77 | note | Acceptance Criteria: Ensure overlay depth & installation is acceptable
b43165b1-8bbc-5415-8b2c-a89ee5b33cbd | note | - - - - - - - - -
dd8f70d5-0b13-5a68-a5c9-33e2b77ec226 | note | Reference Documents: MRWA-W-202
a4fa2ecf-f6a9-5270-88e4-8d00289fd2bb | note | - - - - - - - - -
7a8d0cb8-49a6-502e-9731-adda2e0c0d61 | note | Inspection / Test Method: Visual
9d6ba961-8552-5f97-9fb8-8b942f2e210b | note | - - - - - - - - -
88222bac-83f6-5cc2-b2b8-cf71cbfa0785 | note | Record of Conformity: Compliance checklist - Pipeline construction
ee36ac8c-b1be-5cf9-85a8-0e51c925fc4a | note | - - - - - - - - -
a40f8d76-b175-51e0-a5f4-aaab0497436b | note | HP*
9c75e8c3-8a03-559c-b049-7fe3ed530662 | note | - - - - - - - - -
4f707eba-de61-5fef-8a2c-4a698dfde611 | note | Responsibility: Site Manager
| checkpoint | 21 Installation of detectable marker tape
9e8fd6f3-3c2f-5f26-aeef-2bd64f6136fc | note | Frequency: Completion of pipelaying
5a85303a-dc6d-51d8-8c96-16423cfd3e46 | note | - - - - - - - - -
796437d7-2113-5c42-b891-514d01b50b37 | note | Acceptance Criteria: Detectable marker tape to be installed in first layer of backfill
61c80408-eed6-50cc-ac33-6a3376c7c138 | note | - - - - - - - - -
6a8a3cb7-123b-576e-9ae1-406d5926d87e | note | Reference Documents: MRWA-W-202
afa68cfc-f5da-545b-8844-6931d3039652 | note | - - - - - - - - -
e2ebf1a7-201f-50f9-a7dd-ba67644fd7f6 | note | Inspection / Test Method: Visual
6eb05367-172c-57a5-a24b-19b79b7182e5 | note | - - - - - - - - -
2569702e-98f0-57c2-93e5-dc0fda771931 | note | Record of Conformity: Compliance checklist - Pipeline construction
451661e5-6b9e-552b-9993-c548b92def26 | note | - - - - - - - - -
62a45931-adb8-5495-8458-d23c6604869f | note | HP*
68adc165-d676-5d10-aa8b-1fcb2c1717fd | note | - - - - - - - - -
3747812c-6a48-551f-ad27-68cde45e0b58 | note | Responsibility: Site Manager
| checkpoint | 22 Placement of compactable material in trafficable areas
152dad64-ac2b-5eb1-a1f7-b1807f9a89f9 | note | Frequency: Completion of pipelaying
527ff08e-4c9b-57fc-bad2-46680f80376f | note | - - - - - - - - -
8585b7db-f1ff-5ab9-ad4d-c057d0455bec | note | Acceptance Criteria: Backfill material to be acceptable & compaction of trench line completed
36b8e78f-21ad-5521-a433-87491921878f | note | - - - - - - - - -
caafe78c-1929-58f1-a5de-26b5084f943c | note | Reference Documents: MRWA-W-202,202
6aca51e2-2226-5091-b3bc-41c40ae62808 | note | - - - - - - - - -
3229be67-cafd-511b-99e4-3f74e0e8ec61 | note | Inspection / Test Method: Visual / NATA if required
334f41ee-995e-56fb-8c64-c57c79e9751a | note | - - - - - - - - -
198e0439-a5a1-5185-a590-39eb0ded012f | note | Record of Conformity: Compliance checklist - Pipeline construction
ef7aaa8c-2e6e-5c1b-9f4c-6c9ea7e8f6da | note | - - - - - - - - -
c9a0507e-d48a-5741-8f35-6c8dce10e95a | note | HP*
9c1a174e-0268-52c9-af8b-1e93db944177 | note | - - - - - - - - -
f930f1e9-092e-53dc-b17f-7711fa4ae778 | note | Responsibility: Site Manager
| checkpoint | 23 Monitoring of WC1 works
cbbdf052-963a-5aba-8a48-cbed9d8ff027 | note | Frequency: Once per week
dc87b9e4-bd5b-5639-8fcc-cfed25abe31c | note | - - - - - - - - -
f09dba1d-2fe9-536a-a711-ff3658fc27ec | note | Acceptance Criteria: Crews compliance with all Fulton Hogan Procedures and SWMS
6b743e12-0e84-561d-b942-560b0870e66d | note | - - - - - - - - -
ca75efa2-6349-56a5-bda2-436a0a003599 | note | Reference Documents: Pipelines SMP, SWMS, Trenching Procedure
1dec8705-8d33-503f-b95a-6a978f759ad2 | note | - - - - - - - - -
96c90eee-9246-59cf-a084-861ddb4a44a0 | note | Inspection / Test Method: Visual
d3017f7c-9322-54bd-9113-cffa97e5913d | note | - - - - - - - - -
9b7881c1-00d3-5edb-960a-bcac7e0cc7fb | note | Record of Conformity: Weekly Site Safety Inspection Checklist
792e5409-fdfe-5d3c-9bcc-63291af6f702 | note | - - - - - - - - -
50ca9850-a135-5b1c-a302-f77ecb1c1d63 | note | HP*
57337675-0c1b-52e0-ad88-7403663c9b60 | note | - - - - - - - - -
43718b8a-e5d0-594b-8f35-70e9ec18b6de | note | Responsibility: Project Manager/Engineer
| checkpoint | 24 Monitoring of WC2 works
0c0eb51e-4d06-59e7-9de3-c63c7b9687ea | note | Frequency: Twice per week
44e58e00-d184-554f-a13e-e5e5e573fbfc | note | - - - - - - - - -
ff116ab4-3af2-5f7f-acf4-6a206d6e64bd | note | Acceptance Criteria: Crews compliance with all Fulton Hogan Procedures and SWMS
76542155-0ccd-5819-a8a5-27ffde4887cf | note | - - - - - - - - -
e63a52cb-ad07-5c2d-8641-73d510c9c62c | note | Reference Documents: Pipelines SMP, SWMS, Trenching Procedure
4a5dea1d-3af4-5ee4-9633-58fd0535f2b2 | note | - - - - - - - - -
6aa9f761-0170-5b5e-bc50-42ecb7495e95 | note | Inspection / Test Method: Visual
b91e4acc-aa6f-5853-87c6-5d9c32846557 | note | - - - - - - - - -
e4ba16ce-2867-503d-bc67-2f84248eea54 | note | Record of Conformity: Weekly Site Safety Inspection Checklist
89b7b112-832e-59b4-8d05-23101e6653d6 | note | - - - - - - - - -
6fc38a85-18cd-5afd-a4fe-1a9c640f3931 | note | HP*
7a870caf-7234-5829-a97f-3bd1062d2cf7 | note | - - - - - - - - -
83ef9b4c-6d0a-5c6e-8f23-acf40773ff9b | note | Responsibility: Project Manager/Engineer
| section | 9 - QUALITY
| checkpoint | 25 Swabbing and flushing, Pressure test and Chlorination works
50fc12d4-f93b-52e7-b064-13f112815e48 | note | Frequency: Completion of pipelaying
1645676a-0385-53a1-9541-aeacec47e132 | note | - - - - - - - - -
330b076e-d64f-5d83-ac0c-9e5241a6ec07 | note | Acceptance Criteria: Pressure testing held for 5hr duration
56ef3403-868a-540e-9d21-20f8d9e567b6 | note | - - - - - - - - -
2f04b31a-f5db-5c4f-8734-451a1c985c7b | note | Reference Documents: WSA 03-2011 - 18.3, 19.2
a7e2d268-ebab-5144-ba00-3f47e91c5e9b | note | - - - - - - - - -
fcbf02f9-0783-573d-bc3b-0eb474f3c308 | note | Inspection / Test Method: Visual
7c9c05d5-e920-5494-aec4-32a239967c87 | note | - - - - - - - - -
36d7bbe1-66d4-5b0a-b393-802f3cd8d058 | note | Record of Conformity: Compliance checklist - Pipeline construction
fc3e3a05-78c6-579d-bc76-3014b0ec3fb5 | note | - - - - - - - - -
cd13ef2f-0b49-5e5e-bf47-d7ba11119c2b | note | HP*
0bc4cf87-897b-5b95-bfb9-3d11496fe7ea | note | - - - - - - - - -
56dfdc81-c4dd-563b-85ac-de31cd75a52a | note | Responsibility: Site Manager
| checkpoint | 26 Water quality testing.
c7ab7923-798c-5f92-a3f8-bc7655fd3e6c | note | Frequency: Completion of pipelaying
de7f2487-e26a-5d4d-9ad8-ae0179858d99 | note | - - - - - - - - -
0c8a5109-a9f0-5432-a47e-24c4d81c90ef | note | Acceptance Criteria: Conduct a bacteriological test on all new mains following satisfactory completion of swabbing/flushing and pressure testing of the water main
be1771d1-b35c-5574-af07-6b9d5ec84549 | note | - - - - - - - - -
bbb98c22-1a54-594a-841d-d5e56971bdde | note | Reference Documents: WSA 03-2011 19.7
b306f973-0de6-5c45-96f5-11efc9365268 | note | - - - - - - - - -
a7f382a6-560c-5f94-ad55-8274f630bc2f | note | Inspection / Test Method: Written
26835f58-082f-5538-baa9-f01ef205d395 | note | - - - - - - - - -
57e40b90-c9f9-582e-b84f-3b45d890b238 | note | Record of Conformity: The test results fall within the water quality parameter
721b7bea-ccb4-5853-b941-144094daabb6 | note | - - - - - - - - -
35e793a9-894f-5be3-81b5-600207db1f72 | note | HP*
749ad4c9-bbc7-5cb9-a79b-35bfac6b2b19 | note | - - - - - - - - -
e93b5a13-640f-500e-b184-d48862e87153 | note | Responsibility: Site Manager
| checkpoint | Final Inspection
5651da0c-d093-538e-8d77-82419fd71190 | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
83f02a91-2643-5324-9f6f-797f62cf3bf8 | textbox | Print Name:
189df685-5a01-5932-a925-e247422a973d | textbox | Position:
d4945c29-1185-5adb-b42e-7fc59faf471c | date | Date:
3900769b-ee99-5690-b1e8-b3f115ceb127 | date | Work Completed On
| checklist | ITP 0081 - Structural Crack Repair | itp | ITP-081-AX-LOT-XXX - Desc | 39c4a8ab-01fd-4c7b-afdd-1a521b2671f9
| section | Referenced Documentation
| checkpoint | Referenced Documentation
d0350451-e00d-5d8a-8b79-a817f77b7352 | note | Document Title: ITP-081-AX-LOT-XXX - Desc
378a2e13-82e6-5257-a380-bba85ffa91bd | note | ITP Description: Structural Crack Repair
68c7b7bf-42c0-50b2-a039-00f0c05b9295 | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0081
53b7f91b-e029-5fbf-be39-bfd9fde6477c | note | Revision Number: 00
92554cef-c8c0-55c6-8fde-a915294c51be | note | Revision Date: 04/05/2022
6767c3bb-a183-52ef-b58f-79138ddd4663 | note | 1.1 VicRoads Section 610 Feb 2020
78166a0d-3cd7-5596-a7ec-15fd53dc42f9 | note | 1.2 VicRoads Section 686 November 2018
2696f4b4-8556-548d-9cb4-6fc84cb7c824 | note | 1.3 VicRoads Section 687 August 2018
| section | 2 - Preliminaries - Procedures & Documentation
| checkpoint | 2.1 - Assessment of Crack
31fbc0d6-20e5-5735-861f-83a7eef1fd62 | note | Frequency: For each element, prior to Works commencing
58680cae-3a0b-5277-97da-dc120beb9d36 | note | - - - - - - - - -
f93058be-4e2b-53f4-85ec-06db6617de95 | note | Acceptance Criteria: Repair of cracks shall not be undertaken unless the cracked concrete structure has been assessed and the influence of cracks on load bearing capacity, serviceability and durability has been evaluated by the Contractor, and reviewed by the Superintendent.
23b91cce-8ae7-5338-b8b3-f69141701c7e | note | Cracks to be determined either as active or inactive.
5f0d4e23-5648-55c6-a7a4-10cba4e621db | note | Inactive Cracks:
1a1e35b4-b666-549c-acc5-77274838d075 | note | <0.2mm - May be coated by protective coating system provided they are not associated with earth or water retaining concrete components.
0a2152f1-7c92-5807-9088-bb4b71764132 | note | >0.2mm - shall be repaired via Resin Injection, Routing and Sealing or Gravity Feed method.
fa95137b-d076-5dfa-b7b1-1e39d1d72d25 | note | Active Cracks:
37a84f81-92f8-5dcf-a84a-fba806091c09 | note | >0.2mm - shall be repaired via Routing and Sealing.
2436c177-741d-514c-a563-f56ae09a747b | textbox | Teambinder Correspondence Approval number:
37e028a0-539c-541f-98d4-44b95fdfdbe2 | note | - - - - - - - - -
18c7e0d2-54ea-56a5-b56c-181b648b523a | note | Reference Documents: VicRoads Spec. Cl.687.01 Cl.610.24 (b)
17fe5a97-93c0-5709-9492-170bcbab9c28 | note | - - - - - - - - -
122ffb07-5f1f-5e21-93f5-f0ba99512ac3 | note | Inspection / Test Method: Visual Inspection
af7b1692-ccc4-506c-a465-e179b4f43a53 | note | - - - - - - - - -
c50251b3-f7ec-5588-ad06-7a8af550d5cc | note | Record of Conformity: Holdpoint released
d1d1681c-f560-54ca-ac27-c5e35482d6f3 | note | - - - - - - - - -
7936b1cc-5f62-56f9-93a7-3d921b120e30 | note | HP
85ebe7c0-e9cd-54b6-ab63-24c002f92191 | note | - - - - - - - - -
05fddbf5-ef74-5c5f-af10-73b4e89234ba | note | Responsibility: SE/PE and Superintendent
| signoff | HOLD POINT
| checkpoint | 2.2 - Work Procedure
7b128d95-bc85-5664-b181-009b3f643a98 | note | Frequency: For each repair methodology, 14 days prior to Works commencing
5f4e6503-2831-5494-9760-dafa6a516b35 | note | - - - - - - - - -
5cf69cbe-a077-5b01-ac39-3777ba82d0e4 | note | Acceptance Criteria: Crack repair procedure should be submitted prior to repairs being undertaken and must be approved by the Superintendent. Repair of cracks shall not be undertaken unless the cracked concrete structure has been assessed and the influence of cracks on load bearing capacity, serviceability and durability has been evaluated by FH and reviewed by the Superintendent.
cfd704d0-af74-583d-b46d-f5beb024afdb | textbox | Teambinder Material Approval number:
41c3d515-bef3-5a75-bddf-59aefa01e9e7 | note | - - - - - - - - -
bd63ec34-e532-5b3e-b023-f7c6af9106a4 | note | Reference Documents: VicRoads Spec. Cl.687.01 CI.687.09 (a) Cl.610.24 (b)
1dda63fa-d434-5acb-95ce-a40d29655fe4 | note | - - - - - - - - -
2480c1b8-c850-5012-ade2-c4fe99e1015b | note | Inspection / Test Method: Visual Inspection
4759e0f6-27e5-55f1-95ff-0dcb0fd00080 | note | - - - - - - - - -
85c523cf-123f-5c99-9ad9-bc55e15c8f62 | note | Record of Conformity: Holdpoint released
727e2259-e36f-57bd-bc88-a673e4a90abf | note | - - - - - - - - -
ae80bbf3-99e6-59f4-9f42-cbf9b345018e | note | HP
bf44ad9e-558a-5a3f-9e71-5bed2cd0dc65 | note | - - - - - - - - -
e1b69d81-b2a1-5801-9af8-5424c3d2552c | note | Responsibility: SE/PE and Superintendent
| signoff | HOLD POINT
| section | 3 - Preliminaries - Materials
| checkpoint | 3.1 - Resin Injection/Gravity Feed (Inactive): Epoxy or Polyurethane Resin Selection
4259e6cd-6ae5-548b-bba2-0f6f0d6c1414 | note | Frequency: For each product, prior to Works commencing
a3ddaeaf-bda8-52de-a4d3-658c8b4d17a9 | note | - - - - - - - - -
c48f9084-4082-58f3-9d52-b09e23f4c9ac | note | Acceptance Criteria: Product to be selected based on the following criteria:
fa0dbf60-3b92-5494-bb61-76e258103e8c | note | i. viscosity @ 20°C - 23°C 650cps max.
c2b907b3-53c5-5d67-ae7b-85018d2c9e91 | note | ii. compressive strength @ 7 days ≥60MPa;
953d2df3-a915-5d85-826a-a93ccdca9118 | note | iii. tensile strength @ 7 days ≥25MPa;
b47a9d26-16c0-59ef-b0c5-69f5db6405fb | note | iv. flexural strength @ 7 days ≥50MPa;
0d2fc045-7c54-5215-8cb5-ff4f27b7245c | note | v. adhesive strength at crack edges @ 7 days ≥2.5MPa (or concrete failure)
9fef23f9-c248-5ae2-80f1-1070d0614052 | note | Note: For the resin injection or gravity fed applications only.
1a6c4541-9432-5174-b325-31dcef8717e9 | textbox | Teambinder Material Approval number:
49577d74-eed7-5a8a-806e-d8b98a254621 | note | - - - - - - - - -
05cf5fd9-004e-524e-b5ee-eab6a73381dd | note | Reference Documents: VicRoads Spec. Cl.687.05 (a) Product TDS
e9461224-4f9c-584b-b76d-349bc4ec7f61 | note | - - - - - - - - -
77d2bcf3-83a6-5d79-91e1-c22d6db77a67 | note | Inspection / Test Method: Document Review
ad36e3d4-0320-5be2-9b92-ea6b867fd64c | note | - - - - - - - - -
89896374-b2ee-5239-a8fd-f20cf55df939 | note | Record of Conformity: Material Report
1a8a1f50-00ef-520f-bf9f-98d95c41bdf7 | note | - - - - - - - - -
9a984b6a-5c9e-55fe-a54f-b846e48b8fb2 | note | IP
2badafe3-9a9c-5ad6-82f9-288c1021b101 | note | - - - - - - - - -
f7cb1461-3041-5168-9af6-c666820ef5d0 | note | Responsibility: SE/PE
| checkpoint | 3.2 - Routing and Sealing (Active): Flexible Sealant Selection
1f0b9dac-8500-5ca0-b7db-e968a68a91ac | note | Frequency: For each product, prior to Works commencing
436e8393-cf4a-55b6-aaf5-c251d1c91f7b | note | - - - - - - - - -
870ca50e-71ad-5ffe-b274-71ad526aea79 | note | Acceptance Criteria: Product to be selected based on the following criteria:
4662d805-cbf4-5c33-adec-a525faac9587 | note | i. provide for a minimum expectant movement of ±25%;
d8bbd27b-cfb6-5a2b-b3b7-59cdb3808617 | note | ii. Whether or not the repair/sealant is subject to traffic (trafficable or non-trafficable)
0faccee6-d95f-5830-81c3-2118d85f60fe | textbox | Teambinder Material Approval number
e7aa7cf3-aea5-5874-8894-58f30eb62640 | note | - - - - - - - - -
7dd394b5-294d-575a-9769-1329cbda6cbe | note | Reference Documents: VicRoads Spec. Cl.687.05 (c) , Product TDS
15765d30-ccea-5cb6-a096-c7efcf879e00 | note | - - - - - - - - -
8d8cd405-ff39-56ac-a530-d31458405cdb | note | Inspection / Test Method: Document Review
1585677c-e358-557e-b615-02f30c77bb74 | note | - - - - - - - - -
772d740a-9b6a-5f12-aae3-0558e881c0ab | note | Record of Conformity: Material Report
c66a64d4-1355-56a9-8077-52856a3bc567 | note | - - - - - - - - -
f43c9bae-b578-5f3e-bdf5-24f31795e80f | note | IP
bcbe3c90-c739-5804-ab4a-33d19841788c | note | - - - - - - - - -
000d5883-b8e3-5580-a2f4-6f6efd500866 | note | Responsibility: SE/PE
| checkpoint | 3.3 - Routing and Sealing (Inactive): Epoxy Mortar or Paste Selection
ed717c91-cf30-563e-bd7b-29c85a5b88ef | note | Frequency: For each product, prior to Works commencing
64b3b79f-e6cd-5016-8b82-e1343e76aca0 | note | - - - - - - - - -
1ef6a9a6-ee73-51c2-b300-3a228f64f7ae | note | Acceptance Criteria: Product to be selected based on the following criteria:
48df0755-3485-5762-b4c0-8971661a4a39 | note | i. compressive strength @ 7 days ≥60MPa;
ab878c55-f581-5059-bca3-3eaa273b68f8 | note | ii. tensile strength @ 7 days ≥25MPa;
87772d8f-22c5-5f0c-964c-47aac03b2ac6 | note | iii. flexural strength @ 7 days ≥30MPa;
de16ee26-3e45-55f1-b949-7232eeaca30a | note | Note: For the routing and sealing, injection nipple/entry port placement and surface sealing applications only.
8b2a2f0a-78b8-58dd-8c11-401321487059 | textbox | Teambinder Material Approval number
f56399f1-5bcd-5553-9270-aecc5907389c | note | - - - - - - - - -
660686cd-7fc8-56ae-b2e3-6b90f304417f | note | Reference Documents: VicRoads Spec. Cl.687.05 (b) , Product TDS
75b60e14-e2cb-5386-af42-01a7ad4f2134 | note | - - - - - - - - -
06fae678-1e8f-5858-b702-9af6663d8254 | note | Inspection / Test Method: Document Review
5553d37a-9246-5a10-9552-08bd818a296a | note | - - - - - - - - -
901865d3-99d2-507f-9252-f8ecbb42f44d | note | Record of Conformity: Material Report
e24fa0f8-8946-58c3-bb98-a136436647fc | note | - - - - - - - - -
e9099de3-d4ee-5f80-949b-e1927bc797e8 | note | IP
bb406f03-c282-5e10-b753-147cff099132 | note | - - - - - - - - -
fde16194-608c-5b99-b559-a37310827445 | note | Responsibility: SE/PE
| checkpoint | 3.4 - Protective Coating: Silane Selection - Inactive Cracks <0.2mm Width
7b774ec9-91ba-5016-9c9a-284a2d7d4b6f | note | Frequency: For each product, prior to Works commencing
e237f960-85ca-5a04-b772-6fae7b8ebd9b | note | - - - - - - - - -
159422b8-3645-578d-a204-b985d4bfc6cc | note | Acceptance Criteria: Product to be selected based on the following criteria:
94b44775-bb33-59bb-9745-7902691dd7a7 | note | i. active ingredient: ≥95% (penetrant) ≥80% (solid silane) ≥80% (silane crème)
8dcca035-e4d7-51b1-873d-8d4d5477b6ac | note | ii. penetration depth: 5mm min.
6b00452e-7b34-5956-9320-096353ecda9c | note | iii. contain a fugitive dye to enable coated areas;
32c3c1ee-5799-5cf5-ba81-b6af88ce0082 | note | iv. be compatible with a film-forming top coat;
8e473b2d-5f30-54c4-beba-056a71d3928b | note | Note: For the protective coating of inactive cracks ≤0.2mm in pre-stressed elements and exposure classifications B2, C & U only - 0.2mm cracks are acceptable in other precast elements and exposure classifications.
ffecc039-5bec-5ae7-b21d-71f093fdf76f | textbox | Teambinder Material Approval number:
969fbc6f-7086-53dc-ae50-ed6dfe097bc6 | note | - - - - - - - - -
3d8cfb06-7300-5a5b-9783-df293baeab06 | note | Reference Documents: VicRoads Spec. Cl.687.12 Cl.687.05 (c) Cl.687.05 (h) , Product TDS
8c42ae43-a0ed-5333-a5f5-16aab6832538 | note | - - - - - - - - -
060f472e-24ab-5489-bd43-7a6af510d91f | note | Inspection / Test Method: Document Review
6041154a-873f-54a2-b363-04a18ae34625 | note | - - - - - - - - -
97ba8fca-3689-5100-9e1b-9b55c5de602b | note | Record of Conformity: Material Report
92a75bc6-d0f7-5b51-b391-b560ee4f0fc6 | note | - - - - - - - - -
b3f8223a-150e-5b2d-80a1-5a8f02368355 | note | IP
d4b8e3cc-437a-55cb-8ce2-4a67780c9eba | note | - - - - - - - - -
c4231623-39f3-5226-9b45-170d2adec820 | note | Responsibility: SE/PE
| section | 4 - Pre-construction activities
| checkpoint | 4.1 - Contractor Competency
2d94f058-7d17-55b0-a1cb-1a5c7113929d | note | Frequency: Once, for each personnel, prior to starting Works
5de7a891-3adf-55e2-8306-a04478c33e5c | note | - - - - - - - - -
4a111943-9e93-53f5-bf20-54aa977448fe | note | Acceptance Criteria: Personnel undertaking the concrete repair works shall have a minimum of 5 years experience in application. Documented evidence to be available.
d646abcc-f08d-5c69-bf2c-c8ab0a33f069 | note | - - - - - - - - -
31413474-eab2-5ce2-8d58-305a4e2fedd0 | note | Reference Documents: VicRoads Spec. Cl.687.04
89532020-9e33-5b79-af64-48145ddb8175 | note | - - - - - - - - -
61ddcf2d-e940-58e8-a7fe-f4ddbc0dca6b | note | Inspection / Test Method: Document Review
9d584172-b5fc-523c-a620-15bd7f8bae00 | note | - - - - - - - - -
e71a309e-fac6-5d6e-a009-4d917182c08d | note | Record of Conformity: Document evidence of adequate experience
1e672104-4533-567d-841e-c01e268de779 | note | - - - - - - - - -
f4a7401d-e0ed-5ec6-a88b-a9dda355070a | note | IP
3dd8f745-f430-5374-957d-2b654fab4faf | note | - - - - - - - - -
3857e381-f299-5c88-b24f-f78d1b0716ef | note | Responsibility: SE/PE
| checkpoint | 4.2 - Injection Equipment
04f6ca95-2c34-531e-af6f-48af073e8aa2 | note | Frequency: Once, prior to starting the Works
77777b9b-2d3f-574c-bd80-ca2cf293929c | note | - - - - - - - - -
d2284902-5137-560f-9d84-47520f3c037d | note | Acceptance Criteria: Injection equipment to be simple, easy to handle guns with pressure regulation or limitations in the operating range and be simple to clean and maintain.
077603b8-9105-5e95-a63a-1e9ecfbc0e7c | note | Nipples/entry ports to have shut off valves or at least the ability to be capped to prevent leaks or air travelling back into the crack. Resin adhesive injection shall be performed continuously until cracks are completely filled. If port to port travel of resin adhesive is not indicated, the work shall cease immediately and the Superintendent notified.
e336af7a-3ea9-50ee-8358-c33564aca521 | note | Note: This ITP does not cover special purpose, multi-component injection pumps.
839a0acf-4c1d-56c9-adea-0e81c9088a43 | note | - - - - - - - - -
320ed45f-7834-5afc-9c81-1e6e7a788534 | note | Reference Documents: VicRoads Spec. Cl.687.06 (a) CI.687.09 (c) (iii)
27e8271f-62c1-5b72-ae44-cef5ce700f2f | note | - - - - - - - - -
43cb3494-7f89-51bc-9c6d-188466b76cb5 | note | Inspection / Test Method: Visual
14dd5df0-0b73-5376-b744-350c350f4341 | note | - - - - - - - - -
e303c082-019c-5c91-b122-7ac70bc9453e | note | Record of Conformity: Signed ITP
8f4672da-9fab-50f1-b687-d79d77dffd7a | note | - - - - - - - - -
ac71b232-e138-5632-bb75-92ff5fbb988e | note | IP
03269220-e248-5eb8-abe6-c624c6a64409 | note | - - - - - - - - -
f62503c0-5505-5e4c-bef7-00145ffca7d3 | note | Responsibility: SE/PE
| checkpoint | 4.3 - Weather Conditions
bc9b5aae-8d76-5c7a-85c8-0b3be362a821 | note | Frequency: Prior to each repair
ad5e3816-9d3c-5ddb-80f2-8934cf4ccb49 | note | - - - - - - - - -
9984b987-66b8-53f0-bc9c-2f4d545db26e | note | Acceptance Criteria: Repairs are not to be undertaken when the ambient temperature is below 5°C or 5°C on a falling thermometer, or above 35°C.
aacbc3b4-b9a0-5642-a86b-8aaf839430c0 | note | Cooling the materials is allowed should the need arise if temperatures inadvertently rise during the repairs.
d85494ea-07ad-5374-9423-c0c0965d6195 | note | Where re-injection is required, this shall be carried out within the temperature-dependent period of the crack filling material given in the directions for use by the manufacturer. At high ambient temperatures, the use of cooling to influence the workability time of materials in containers is permissible.
97a6bd4c-74fe-5ede-8005-44babc3ce868 | note | - - - - - - - - -
4a01de9a-97ce-5ed6-a915-827bf983191e | note | Reference Documents: VicRoads Spec. Cl.687.05 CI.687.09 (c) (i)
96f14414-40ca-5d05-94ea-fe76cc12ee2a | note | - - - - - - - - -
89dc25f2-f9f3-582e-adee-7540e0844cba | note | Inspection / Test Method: Visual/ Measure
c68fe9eb-a17e-5787-a891-54f683ec7f6b | note | - - - - - - - - -
be482b11-e66b-5f38-b03b-06ab8a1b169c | note | Record of Conformity: Signed ITP
5fd40c57-a4a9-5893-8057-30cf024059fd | note | - - - - - - - - -
d473b096-c078-5097-9e5b-5fca56d741a8 | note | IP
d72a1eac-d1e2-5cb9-94f0-6e56d836f141 | note | - - - - - - - - -
f752c1f0-11f3-51ca-aa77-a51b2db5d0dd | note | Responsibility: SE/PE
| section | 5 - Construction Activities
| checkpoint | 5.1 - Surface Preparation
ab4178bb-080b-5f51-9456-7222d8df454c | note | Frequency: Each crack
883e2239-6070-5e65-a0cb-69b7eb30dac6 | note | - - - - - - - - -
ad67c6f8-1fbe-5048-a3e8-a59e6bcddf3a | note | Acceptance Criteria: Cracks and surfaces located within 50mm each side of the crack to be cleaned of all loose particles, dirt, dust, curing compounds, grease or efflorescence by appropriate means (i.e. oil-free compressed air, industrial vacuum cleaners or flushing with high pressure water). Impurities, which inhibit wetting and adhesion or penetration by the crack filling material, shall be removed.
f2320494-55f8-55e7-bbd8-f6f8e765bfd6 | note | Where cracks and surrounding areas have been moistened during the cleaning process, sufficient time or accelerated drying-out needs to occur unless the crack repair materials are water tolerant
0cd3e2ca-c6ce-5386-9071-f1aa4a5bb4fa | note | - - - - - - - - -
300644d0-5004-5df8-9224-274e2ed6d021 | note | Reference Documents: VicRoads Spec. Cl.687.08
7f0fbf0c-2ae4-5c85-9852-a13761f6264e | note | - - - - - - - - -
597fb638-0dfe-5238-af04-9365411d580e | note | Inspection / Test Method: Visual
980180b5-0ac1-51eb-b3ac-5613436fd00f | note | - - - - - - - - -
dd3c5931-d633-59e3-a257-5bcce122d427 | note | Record of Conformity: Signed ITP
c0097b8f-e09c-5acb-aff5-4a7c4f9b2a28 | note | - - - - - - - - -
e2a0b2f8-c632-5781-b99a-873e35294c0f | note | IP
cfa18793-5f22-509a-a690-7ba4338d9fd6 | note | - - - - - - - - -
81dce741-d342-591c-a160-34e78afdad97 | note | Responsibility: SE/PE
| checkpoint | 5.2 - Resin Injection: Inactive Crack Repairs
4a5c8ac2-e285-5d5a-8d03-31303e1284a3 | note | Frequency: Each active crack
be62bf80-2fd1-5682-af85-8d5382d4b5ff | note | - - - - - - - - -
f858a76e-cc44-5622-8514-6500914a1a33 | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
3f81ca93-3782-5498-a14b-395cf852bc77 | note | i. All materials in date and mixed as per the Product TDS;
43953c9c-4fea-5d91-aad7-486774c75907 | note | ii. Each nipple/entry port coated in epoxy mortar or paste to create a water-tight seal to the entire perimeter;
a812d621-6ebe-5ed0-87cb-d76ea2b38eb4 | note | iii. Nipple/entry port placement central over the cracks at 200mm spacings maximum (where cracks are through the full section, nipple/entry port placement shall stagger);
a006e429-816c-5d7e-9ffa-fd788c5ecb91 | note | iv. Epoxy mortar or paste applied to the surface of the crack in between nipples/entry ports and the full height of the crack if within tolerance to eliminate resin leakage);
49afc31b-e6ae-5525-8fbc-a13c3ecea1c0 | note | v. Once the epoxy mortar or paste has fully set, connect the injection gun to the lowest nipple/entry port (for vertical cracks) or at one end of the crack (for horizontal cracks);
97acbfec-c5dc-5ae3-bfef-e28028ce5066 | note | vi. Initiate the injection, applying pressure until resin can be witnessed entering the next nipple/entry port;
e3db8922-7c64-549e-883c-04918f2dbadd | note | vii. Stop pressure and close the valve of the engaged nipple/entry port and connect to the nipple/entry port where the resin appeared, working either upwards (for vertical cracks) or along the crack (for horizontal cracks) until all nipples/entry ports have been filled;
ca8645e1-82e0-5774-9761-6b50d57618a7 | note | iix. Repair to be protected from damage or adverse weather while curing;
ff9b8ac7-818e-5bf4-a0ee-25eebb90b1ec | note | - - - - - - - - -
ad5ef80f-0c41-59d9-97e8-967851c274db | note | Reference Documents: VicRoads Spec. Cl.687.09 CI.687.14 (a) CI.687.15 Product TDS
5ce58b51-88c4-5ce6-8a00-6f33159d9ed2 | note | - - - - - - - - -
9380c2bd-5b30-5e66-9ac6-70923630f4a8 | note | Inspection / Test Method: Visual
c24584cf-ba0e-534b-b1b9-4775ec8dfb8e | note | - - - - - - - - -
a2b93e2f-afbf-5527-8773-ae169b6eaabc | note | Record of Conformity: Signed ITP
36008d09-b86b-58cc-960f-be1094678a31 | note | - - - - - - - - -
4a397f77-dc64-56c6-9697-3d380ba677c3 | note | IP
9ad05614-5399-510d-9d8f-e63ac3220f62 | note | - - - - - - - - -
11992c72-2c2f-56d3-b5d7-749c5e61869a | note | Responsibility: SE/PE
| checkpoint | 5.2 - Routing & Sealing: Active Crack Repairs
522e07c3-d582-5bb5-b336-f03ce47c972c | note | Frequency: Each active crack
502104f0-fbc8-556a-bd3d-9fe1e07fbedb | note | - - - - - - - - -
98ffafe9-d27c-5cf9-915b-7c9c16e3f3cc | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
bc8be5af-1e79-58e4-a561-76b920e90262 | note | i. All materials in date and mixed as per the Product TDS;
a30457ad-8983-52a5-bf6e-64d74843ef26 | note | ii. Saw cuts to be at a width to depth ratio of 2:1 and rectangular in section;
3a2e0463-6e3b-56af-8c5d-00dddde80f2a | note | iii Surface dust to be removed;
47754e77-6a66-58bf-afc7-faa1abbb823c | note | iv. Bond-breaking tape to be placed at the base of the chase/reservoir to limit sealant interface to 2 no. faces;
e9774f7e-326d-54a2-a01c-c919a5ad8c58 | note | v. Where required, masking tape to sides of the adjacent surface to create a neat finish;
31beff94-20c0-5ec8-bffc-8c275e246b80 | note | vi. Sealant gunned or tooled into the saw cut to completely fill the void;
7a3160de-1afd-5d50-886c-4030d4a9dea8 | note | vii. Product shaped with a suitable tool to recommended profile;
80e86a88-2611-5762-bd38-4f141b00735d | note | iix. Repair to be protected from damage or adverse weather while curing;
d4cb4ee5-5491-5add-816f-0dcfc5e7b5b7 | note | - - - - - - - - -
a88ee68e-7f4f-5590-9b55-881edeeaaec3 | note | Reference Documents: VicRoads Spec. Cl.687.10 (b) (ii) CI.687.15 Product TDS
81cffffc-d000-5cc0-a378-bfa411c0695a | note | - - - - - - - - -
9dd66077-ee1a-5d38-a558-f763ad1e0436 | note | Inspection / Test Method: Visual
c0ca500f-2790-5198-a440-474e5306dee1 | note | - - - - - - - - -
b3bf1127-3591-52aa-9868-61d9f063023e | note | Record of Conformity: Signed ITP
1ab39d44-9197-57b6-a464-c197b4398b59 | note | - - - - - - - - -
bd70e94d-0b3a-58d5-a960-9daa55c3f2f6 | note | WP
cc21fed7-c324-5bc3-a47f-efb656e784d5 | note | - - - - - - - - -
796bcbe3-6361-54b1-aa81-295ab4b23cc7 | note | Responsibility: SE/PE
| checkpoint | 5.3 - Routing and Sealing: Inactive Crack Repairs
aa0df729-bdbe-54bd-8c15-9ff57f61459c | note | Frequency: Each active crack
5d554c43-a552-5b9a-b808-db46a0f894d8 | note | - - - - - - - - -
00c4ecd8-5f1c-5769-8622-c7a2548e6daa | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
05b3cd35-bab0-50b9-88dc-1e62fb9c4531 | note | i. All materials in date and mixed as per the Product TDS;
594637b7-1a37-5628-933f-cadeb04d1e69 | note | ii. Saw cuts to be at a minimum width and depth of 10mm and V-shaped in section;
393e0e1c-87a9-5443-adce-8d17e3ee4349 | note | iii. Surface dust to be removed;
beb72d50-3aa2-5a2d-9389-f71f484bc116 | note | iv. Epoxy mortar / paste placed into the saw cut to completely fill the void;
c4bf6ac4-47b0-53f3-b341-fbbb4b312ac2 | note | v. Product finished flush with the surrounding surface;
4696cff1-aae4-5fa1-a54f-9b3ab46a313a | note | vi. Repair to be protected from damage or adverse weather while curing;
9b2933db-7668-58f8-bebe-34e321e4fdc4 | note | - - - - - - - - -
5f65c104-140b-5b44-948a-54f47d11ae8c | note | Reference Documents: VicRoads Spec. Cl.687.10 (b) (i) CI.687.15 Product TDS
30348e51-1e43-5156-8346-497691949afd | note | - - - - - - - - -
7809b5b3-35a1-5fe3-939d-a7d58371d8a2 | note | Inspection / Test Method: Visual
ce3066bd-4ea6-5100-b9ad-fbabd35ae0b9 | note | - - - - - - - - -
d94c90bc-1c6a-515e-91b1-602b3de68738 | note | Record of Conformity: Signed ITP
501cadef-02cc-5a3d-bb86-b722a0d37988 | note | - - - - - - - - -
bce6159f-478f-5f67-867c-b9c0c6bc0414 | note | IP
ede936e8-b823-5bb0-aa53-67080972be39 | note | - - - - - - - - -
97930195-c8e9-5c8f-a4f9-bcb50d6bc1b7 | note | Responsibility: SE/PE
| checkpoint | 5.4 - Gravity Feed: Inactive Crack Repairs
01625f8e-2a5f-513c-aa57-bdecb1d46b96 | note | Frequency: Each active crack
196d0b70-98a1-593f-9d43-d8726db2ed12 | note | - - - - - - - - -
e3add9b5-ec44-599d-b0ed-7f99a9d2427d | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
b99f1ec6-98f6-5d93-b1ab-2bb2d2adc195 | note | i. All materials in date and mixed as per the Product TDS;
c4006f10-0ff5-551e-90a8-9cdd2e8de996 | note | ii. Where required, a water-tight reservoir, to be created with silicone or polyurethane sealant;
d736769d-ce83-573c-9510-64cb17a74fe1 | note | iii. Epoxy resin to be poured onto the crack and either sufficient amount contained in the reservoir (if used) or worked back and forth by suitable means (such as a broom) until no more material can be absorbed;
6b811510-57d4-5606-925a-3f12a69bad48 | note | iv. Excess material and reservoir can be removed as the epoxy resin gels;
790a2181-e9f5-52be-9f52-3068d440746c | note | v. Repair to be protected from damage or adverse weather while curing;
dafc7e44-7bdc-5c93-944a-4dfe748b5b73 | note | vi. Repair to be protected from damage or adverse weather while curing;
210470de-be3b-5c4f-896b-05cae03f0018 | note | - - - - - - - - -
748b3e61-14b9-59e1-a197-aebd38574d94 | note | Reference Documents: VicRoads Spec. Cl.687.11 (b) CI.687.15 Product TDS
35fbb7d1-24d6-56b1-b480-dd569dcd6c23 | note | - - - - - - - - -
2ccdcb27-74c6-52e4-864c-78fa75b2515c | note | Inspection / Test Method: Visual
681d9cb0-5493-55e0-801f-d3fba482f2f0 | note | - - - - - - - - -
b16fef82-4d90-5308-8994-632886dcbe9a | note | Record of Conformity: Signed ITP
11238b31-7b18-5ef1-a77d-b313eb65aa99 | note | - - - - - - - - -
46cf8c2b-b707-51c9-b263-9477c4215eaa | note | IP
13b85f51-c720-5a30-87f2-ff05bee6cae4 | note | - - - - - - - - -
1ec70b98-6b4e-5e82-a830-f2f7cdd00241 | note | Responsibility: SE/PE
| checkpoint | 5.6 - Penetrant Coating Method: Inactive Cracks <0.2mm Width Repairs
1cab4ae4-4805-5566-aa8d-edcbf3d3f712 | note | Frequency: Each active crack
ceea2b00-15e0-53ce-9ad8-3279cd814f74 | note | - - - - - - - - -
e3374cf5-4545-5db7-b45c-d09e9b204a9f | note | Acceptance Criteria: Approved procedure to be followed, steps to witness:
7f725786-96e1-5adf-bc91-040ea734ef12 | note | i. All materials in date and mixed as per the Product TDS;
9e13cfde-ce7c-5394-94b4-075ee15e3dca | note | ii. Silane to be applied with an airless sprayer (for penetrant) or brush (for Solid Silane or Silane Crème) , working from low to high areas and approximately 150mm beyond the extent of the crack;
64b4b55b-1c93-5881-985d-e7bf1513ca14 | note | iii. Application rates to be as per the TDS for each type of product ensuring wet appearance;
31095e65-81b3-5f2f-ac1c-e35d25315f00 | note | iv. Re-coating if required;
519bf71a-7bea-5047-9b71-eb802ac9fc0c | note | v. Repair to be protected from damage or adverse weather while curing
d854822e-5d1d-5870-bb72-65fcd2c64a15 | note | - - - - - - - - -
665d5d82-5b25-527d-a035-6fc01466b6b2 | note | Reference Documents: VicRoads Spec. CI.687.15 Product TDS
95134f1b-f633-5046-9e6d-a3da985e92b9 | note | - - - - - - - - -
d3239843-1a5e-5c47-8f71-840560c6c288 | note | Inspection / Test Method: Visual
f0042c09-ac64-5845-8539-e96dfcf06ef0 | note | - - - - - - - - -
18e2787c-7477-588f-99a0-6d8dbbbee496 | note | Record of Conformity: Signed ITP
f651fe4f-91e5-5091-af3a-4bbe166a3f02 | note | - - - - - - - - -
790df409-5c1e-57a6-893c-da7ecfc4c34e | note | IP
662b2668-5808-51bd-ad4d-3e39048340df | note | - - - - - - - - -
9788d57d-59fb-5464-9693-235a5c9338b1 | note | Responsibility: SE/PE
| section | 6 - Post-Construction Activities
| checkpoint | 6.1 - Curing & Finishing
b8a1b361-638a-5725-abd1-890c37f39075 | note | Frequency: Each crack
e4f10dc8-6497-52ee-b858-bf9545226163 | note | - - - - - - - - -
df66dae4-79c9-516e-964a-5adeeaab8dec | note | Acceptance Criteria: After the repair materials have cured in accordance with the manufacturer's recommendations, any surface seal, nipples/entry ports and repair materials can be removed by suitable means.
62e6b7ea-8842-563b-b72b-c8cc9658a968 | note | The surface shall be ground smooth, leaving no traces (indentations or protrusions) of a repair and if the repair location remains exposed, a fairing coat can be applied where not being coated with a pigmented coating system.
272d4641-8adf-5165-ada7-9718d1f032ba | note | - - - - - - - - -
189e9e9c-c452-561b-915b-d38ee7c8c06c | note | Reference Documents: VicRoads Spec. CI.687.15 Product TDS
810b3efe-f6fb-5980-b402-4a7cd017de0a | note | - - - - - - - - -
84aa744c-8495-52fe-9b66-fcdab8031bc9 | note | Inspection / Test Method: Visual
5f5834c5-968e-54c0-be42-90748e8c1e65 | note | - - - - - - - - -
27660ebe-d854-5c6e-aa4c-737c25b02760 | note | Record of Conformity: Signed ITP
e04b0414-f772-5cdb-ad0e-bb21ac56203b | note | - - - - - - - - -
6c6021c2-b91e-59e3-9de8-095f7edc6c71 | note | IP
13cbdde8-5b36-5b13-9872-1cf099b6df92 | note | - - - - - - - - -
addd4ed2-0ecd-5d64-991f-85d589dd021a | note | Responsibility: SE/PE
| checkpoint | 6.2 - Repair Verification
d5b5627c-5a90-5fda-9de6-41cccf8b2a56 | note | Frequency: Each crack
62c6cc90-cd29-55f6-b2b5-dc523a4eab20 | note | - - - - - - - - -
e0a3a04c-32af-51ef-890b-48d364e3a971 | note | Acceptance Criteria: After 7 days minimum, 75mmØ core samples shall be taken to verify cracks are fully sealed.
0a3feee4-c616-5d8c-accb-569b5a9297a0 | note | Cores to be located in conjunction with a covermeter to avoid reinforcement and approved by the Nominated Authority.
522c5a57-c71d-59ed-b20c-3639a9a52e8b | note | 2 no. cores for the first 25m of crack and an additional 1 no. core sample for each 50m of crack or part thereof.
e83233b2-1fb9-5142-84c1-0bb8909f6929 | note | Core holes to be filled as per the cementitious repair ITP.
f4a7c232-18ae-5361-8b9c-53cb940a54d9 | note | Attach: Photographs of Core Samples
e016bfe1-4535-58ae-9d7e-837cb825204f | note | Complete: Structural Concrete Cementitious Repair ITP
23c73a56-2131-5b50-a73f-64441dc45a47 | note | - - - - - - - - -
d5f5b193-e19c-5b72-9d3f-e3debcd60227 | note | Reference Documents: VicRoads Spec. CI.687.16
7420b103-f385-554d-8e64-f82aedc0f686 | note | - - - - - - - - -
c13bab74-f9af-5d18-b92c-c9d0b98c804c | note | Inspection / Test Method: Visual
9a7e3f2f-2785-5f53-a6ed-a2042337d2fa | note | - - - - - - - - -
bc52591f-8320-5c7b-858d-c6e1ab51c9ba | note | Record of Conformity: Signed ITP
7f5f7a64-522d-55d8-8722-4c42e1bd59fe | note | - - - - - - - - -
b6b96691-2d7a-534a-afea-6719f6103632 | note | WP
1177e4ca-371e-5a20-b394-95df6344300a | note | - - - - - - - - -
0c4eedac-e5ba-5358-8454-adc9f11e3ef5 | note | Responsibility: SE/PE and Superintendent
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
432d53ca-9e64-5817-bafa-55fb9256c1f4 | note | Frequency: Once, prior to closure of this lot / element / Work area
e7feed32-47f5-5908-8749-1d890e65838d | note | - - - - - - - - -
d6afd402-c62d-5b85-b305-db163ed35ff2 | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
e38feaf7-8b8b-5f45-9bec-098f1b1fb716 | note | - - - - - - - - -
e2743d6f-22a5-5c0e-b52c-b713713ca747 | note | Reference Documents: FH Quality Management Plan
dd3edbec-dec5-53ad-a7c4-c62ff96b4663 | note | - - - - - - - - -
90d5d9ca-2c53-5621-8ae4-2037f1db5365 | note | Inspection / Test Method: Document Review
70ddf1b8-6654-5f2c-8d4a-5eaea8dacd61 | note | - - - - - - - - -
80c3e47e-5dd4-5d56-be7c-16a3f88ca92c | note | Record of Conformity: Signed ITP
5ec8ba80-92e4-5ea5-9b0e-ff1c733999f9 | note | - - - - - - - - -
dcd528f3-a07f-55bb-954e-0e37aa6333eb | note | HP*
a9d11939-34a6-5c16-881b-c9fd07455df4 | note | - - - - - - - - -
75c74614-49a5-5b4f-9379-6d04d496355d | note | Responsibility: SE/PE
| checkpoint | Final Inspection
491a9a47-5f7f-57d9-9b6b-b50b7156bd9a | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
d5f7cdc9-f466-5e54-8b00-07bd5ef9a77f | textbox | Print Name:
beedb7d8-63d3-5627-8f0d-6869d95feccb | textbox | Position:
dbb8bab7-b700-5cd5-a411-268e28298c42 | date | Date:
fbe4d0b5-75af-5e9d-825c-61ce1fd6a0d6 | date | Work Completed On
| checklist | ITP 0082 - Structural Patch Repair | itp | ITP-082-AX-LOT-XXX - Desc | d71c343f-e523-4e3a-8a98-3116a55cd569
| section | Referenced Documentation
| checkpoint | Referenced Documentation
00c397ca-b117-585a-9418-16059c7cddb6 | note | Document Title: ITP-082-AX-LOT-XXX - Description
41761891-4650-5f6c-8151-61e077c83f7d | note | ITP Description: Structural Patch Repair
36824288-5536-5459-8a18-b9c927f99918 | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0082
e2084857-067a-5b77-ad06-fa2ef0b9d6e5 | note | Revision Number: 00
90640134-67e1-58e2-9bfa-6fcc1d42b8ce | note | Revision Date: 09/05/2022
307a0ae5-3c9f-5ed5-8ac0-5623f24545ef | note | ITP created by: Omar El-Khub
3beedde7-2ef2-53b7-94c5-a74e9c9cde56 | note | ITP approved for use by: Babak Rudd
4827feb8-6836-5168-82e7-7ee3d5f85457 | note | 1.1 VicRoads Section 689 (Dec 2017)
3ab25ba2-17a1-52f9-b7b9-9f3dc3974e71 | note | 1.2 AS1012
| section | 2 - Preliminaries - Procedures & Documentation
| checkpoint | 2.1 - Assessment of Affected Concrete
c4e225ff-1dd3-56be-893c-86f6e0b08d7d | note | Frequency: For each element, prior to Works commencing
725c55ac-7dc3-528d-882d-4209ed15fd40 | note | - - - - - - - - -
4b8e8f48-66ca-563c-b162-df5b8f50159b | note | Acceptance Criteria: Contractor shall assess the affected concrete to determine influence of spalling, deterioration, and honeycombing on the load bearing capacity, serviceability and durability of the structure.
a5646d73-2f88-5c71-a6e3-b596240abab1 | note | - - - - - - - - -
1750b062-0e3c-582b-af58-39d91f50ddd5 | note | Reference Documents: VicRoads Spec. Cl.689.02
84cf7d92-cb25-54bf-8d30-e89d1608a4c7 | note | - - - - - - - - -
72fc3cfa-1fba-5362-8544-d3194990e386 | note | Inspection / Test Method: Visual Inspection
5291f6b8-f316-5f06-8c55-6559e254d2bb | note | - - - - - - - - -
4e59b39c-be55-5ec0-a1c3-5a975e5192d0 | note | Record of Conformity: Hold point released
f881dd99-b715-58c8-8ed6-783ab251c0ef | note | - - - - - - - - -
98b601d4-d1d5-5ebf-958c-c5b5a024e1a1 | note | HP
b3a8f3a7-33fb-571b-acba-8a5db2c29a2f | note | - - - - - - - - -
26de7a39-a6c4-53a0-932b-491f507b2429 | note | Responsibility: SE/PE and Superintendent
| signoff | HOLD POINT
| checkpoint | 2.2 - Deviations from Manufacturer's TDS and/or Specification
835a1137-480c-511b-ac22-f156b6e7ea10 | note | Frequency: For each element, prior to Works commencing
92254b42-3a26-5081-bd26-cd1d26d8712f | note | - - - - - - - - -
d9e2ce12-8024-5fcf-b14b-6687d8787e8e | note | Acceptance Criteria: The contractor shall perform concrete repair work in conformity with the manufacturers specifications. Any deviations from manufacturers specification must be submitted for approval as an updated WMS and/or ITP.
fdf0dcca-8d48-581f-b168-a8a35aecfdc2 | note | - - - - - - - - -
8a1eac11-109a-58d7-b092-64ac678b30a2 | note | Reference Documents: VicRoads Spec. Cl.689.08 Product TDS
d933c7c3-c89b-52f6-a8fb-e66db0926180 | note | - - - - - - - - -
755c6f09-1a09-5cd2-9259-431d129de9ba | note | Inspection / Test Method: Visual Inspection
064e58c4-7c03-54ff-b066-214144ffca95 | note | - - - - - - - - -
8fc4dab9-2a2e-5f3a-b631-7b672b9b74cd | note | Record of Conformity: Hold point released
90ad157f-52fa-5437-9f16-8dcb2c55e355 | note | - - - - - - - - -
9b34d773-9f29-581d-9791-442b3eb1ad6e | note | HP
ac118c67-841b-5aac-ba61-2213f3fd1ce4 | note | - - - - - - - - -
e2c45bb6-43db-521e-9614-9353b9f05770 | note | Responsibility: SE/PE and Superintendent
| signoff | HOLD POINT
| checkpoint | 2.3 - Work Method Statement and Inspection and Test Plans
baeb1e1f-52b5-5655-9e13-ba745e95326c | note | Frequency: Prior to commencing repair
74ec7761-cc7e-593f-800b-3c1797fbfdcc | note | - - - - - - - - -
5468294a-181c-57ce-8432-4009a997184f | note | Acceptance Criteria: WMS and ITPs completed by FH should be reviewed and approved by the Superintendent
ed311e93-f2c0-550a-bd9e-ffbc77f03214 | note | - - - - - - - - -
16c713a4-a387-54b1-b6c2-b5974b1d0809 | note | Reference Documents: VicRoads Spec. Cl.689.13
34d4a833-03fb-5f5c-a5ad-f399f77af37a | note | - - - - - - - - -
838d9607-9573-533b-b571-948085af2e0d | note | Inspection / Test Method: Document Review
dacbb8d4-01d0-5876-ae2f-82e226422ee6 | note | - - - - - - - - -
9792db99-072c-55cb-97c3-dfb98d25e5cf | note | Record of Conformity: Hold point released
5b612aae-1e61-5574-bca5-c39fea50ce7b | note | - - - - - - - - -
3596630a-830a-5b9f-95b5-3d47aa180c0e | note | HP
44b62041-cea3-59cc-bc98-32ded36fb82d | note | - - - - - - - - -
b65e3eb4-b310-575b-8f20-2d3197dba72b | note | Responsibility: SE/PE and Superintendent
| signoff | HOLD POINT
| section | 3 - Preliminaries - Materials
| checkpoint | 3.1 - Material approval and Reference
65ce6e79-0bfa-56da-b864-92ffbc0481bd | note | Frequency: For each product, prior to Works commencing
ece3c4a4-682a-5976-81ac-24a4cbd3f40a | note | - - - - - - - - -
ea390678-c204-51a4-9107-aa105e766598 | note | Acceptance Criteria: Is the selected repair mortar material capable of:
57c28646-1b8b-5747-9274-ad7aa11e3dc1 | note | being hand applied in vertical and overhead sections up to 30 mm thick in one application with no slumping;
750c34a5-c333-5cd5-8852-763ddeebad53 | note | achieving a drying shrinkage ≤600 microstrain;
47b2f89c-e05d-510f-9a69-8b2fc9ac7ef1 | note | achieving a minimum wet density of 1600kg/m³;
bb01630c-e9c3-5aa0-af88-198c3cdc6d2b | note | achieving the strengths and bonds conforming to the requirements in Table 689.061.
72af5fe5-845c-585f-98fd-03e059694db3 | note | Is the selected fairing coat material capable of:
12c7ed76-2e29-5b08-a9d3-2041142fe36b | note | application to 0-3mm thick;
0213b3f6-0c2d-5ddf-bdae-959d38eebadf | note | covering a large area without shrinkage cracking.
6d867d83-9709-5cbd-a407-f88ee1f0772b | note | The following information shall be provided with each batch:
81a5ec39-94a8-5daa-a694-dc2ddf7537db | note | Manufacturer's name and address
0b79dcc0-a185-5e50-9244-a38c827be6e5 | note | Product reference
2eea2df6-b4f7-5b56-a42b-bb12d46278f2 | note | Batch number of identification
6a839731-f6e2-58e1-9af2-791dc1164e37 | note | Quantity manufactured in the batch
522891f1-2cbb-5006-9231-d8cba59149d7 | note | Certificate of date of manufacture
0364299a-d777-583c-9aad-5b8b2cd3f151 | textbox | TeamBinder Material Approval Number:
89e37b5a-4d07-5f0f-b4cb-a999c47610b0 | note | - - - - - - - - -
5cada697-c60b-57f8-b53f-d2c676c85f17 | note | Reference Documents: VicRoads Spec. Cl.689.08 (a)
6e2aa6e8-612d-5ba8-9176-69c6322a58be | note | - - - - - - - - -
70f8867f-e8c4-576c-9549-9f339049da32 | note | Inspection / Test Method: Document Review
daa19242-99cb-596e-aa96-db26a39e1de9 | note | - - - - - - - - -
437236f7-c743-5adc-b37a-5459f76c30a0 | note | Record of Conformity: Attach repair mortar product TDS, Attach fairing coat product TDS, Signed ITP
e96b1945-3997-5e1f-af67-4bbcc3be7d47 | note | - - - - - - - - -
51dab150-4520-5b04-8d3c-16fb39bea959 | note | IP
aa277bbe-e56f-5264-9010-36bc58783c6e | note | - - - - - - - - -
779b705c-e609-5069-b361-ecff7ac6ebed | note | Responsibility: SE/PE
| section | 4 - Structural Concrete - Cementitious Patch Repair - Application
| checkpoint | 4.1 - Surface Preparation
a279ee33-3899-5b6e-aa8c-a8010648020f | note | Frequency: Each element
3a50a311-ce9f-55c5-9052-5d162f36ea44 | note | - - - - - - - - -
32aa3ca6-4545-5989-bec6-8486aec64af1 | note | Acceptance Criteria: For all types of patch repair all defective and delaminated concrete and existing repair materials shall be broken back to a sound and dense concrete surface. Defective concrete shall be removed using light hand held percussive equipment or high pressure water jetting
68cab0ea-1e61-527f-86df-f8439749d520 | note | Resulting cover allowance:
7311d360-6ee4-5245-bfc6-f4f6be3e3d95 | note | Exposure classification A and B1 = 20mm minimum
605998d2-1903-5e03-b18d-7fa1f99980bb | note | Exposure classification B2, C1 and C2 = 50mm minimum
e392abd6-87fc-5347-8b36-57ee082217f5 | note | All concrete surfaces and mortar substrates shall be sound, clean and free from dust, oils, and grease and surface contaminants. All loose and unsound materials and surface laitance shall be removed
4eac9847-e6c7-5b6c-a7a9-bd52f27fbf12 | note | The concrete substrate and any exposed steel reinforcement shall be cleaned by a final wash down or by blowing down with oil free compressed air to ensure removal of all residual contamination. The prepared concrete substrate shall be thoroughly pre-wetted with clean fresh water and shall be surface dry prior to application of repair material
64f537dd-f974-57bb-9b98-eeff6007bdee | note | - - - - - - - - -
d186c296-487b-5e34-9e7d-88cacbb628a4 | note | Reference Documents: VicRoads Spec. Cl.689.08 (b) and (c)
48825f0f-92d8-5ace-bdbe-8f5ff48cbad9 | note | - - - - - - - - -
c3392059-a4c5-5b25-9aaf-9a910e24cc7f | note | Inspection / Test Method: Visual Inspection
b7d0f548-56e8-5a6a-9b41-d29753e35ab9 | note | - - - - - - - - -
00b472e3-2b10-581b-b98b-6e63f41a7c1f | note | Record of Conformity: Hold point released Signed ITP
0a0bfbe5-e04d-5a7e-96ff-eef37a20d936 | note | - - - - - - - - -
6e858867-065c-5a58-b4d1-fa4990f0bff7 | note | HP
c4ef4d14-ac09-5295-99cd-15172affc304 | note | - - - - - - - - -
f5f53ee6-d276-5673-ad54-a6e6e840f557 | note | Responsibility: SE/PE
| signoff | HOLD POINT
| checkpoint | 4.2 - Pre Application of Repair Mortar
4ae9cee8-8c63-59a8-82bc-c1c48150ce43 | note | Frequency: Prior to each repair
1143e5d6-651a-55c7-beb5-df1c04279a18 | note | - - - - - - - - -
d681c27c-089d-5c3c-a66b-70f85a9ed0c5 | note | Acceptance Criteria: Reinstatement of prepared areas shall not commence until:
1d0d8346-4a31-5955-9c80-561806c9d514 | note | (i) a joint measurement of the repair area by superintendent and Contractor
39a91894-4176-5b2c-9bbd-5237abdee70d | note | (ii) evidence the area conforms with specifications
eb136af2-5282-5730-912e-14fe81d09fc7 | note | (iii) Contractors quality procedures have been sighted by superintendent
e347d272-4f67-517b-985d-04274d8954c8 | note | The repair mortar shall be thoroughly mixed in whole bags with potable water prior to commencement of application.
e027fab0-152b-59d9-aab6-e7e5f0f5607a | note | All materials shall be applied in accordance with the manufacturer’s specifications or instructions for use in a continuous process.
9050a67f-038a-5c34-9774-fa71153b7aa7 | note | - - - - - - - - -
2374a9cf-0dae-5497-a3d8-1ff05a644a9e | note | Reference Documents: VicRoads Spec. Cl.689.08 (e)
1d72f71c-2455-5342-baff-447eb2642770 | note | - - - - - - - - -
dc424bc2-506a-581f-8648-a46742c8f011 | note | Inspection / Test Method: Visual/ Measure
f4b81d5f-f619-529d-b005-9363e2d338a4 | note | - - - - - - - - -
6ed1970f-ccac-50dc-8621-7c9322686fcf | note | Record of Conformity: Hold point released
f3289cd6-c9bb-5ee6-aede-1aad702ee033 | note | - - - - - - - - -
67d1386f-7a45-5c43-8549-b2cae6b0bc1e | note | HP
f195cd9c-2e12-5500-9fe4-7406a806bcde | note | - - - - - - - - -
4ff59b32-f6db-5a53-a827-100827f60a4b | note | Responsibility: SE/PE
| signoff | HOLD POINT
| checkpoint | 4.3 - Application of Repair Mortar
4e0ae27e-6b34-52ae-9add-b9a7fb4bfa59 | note | Frequency: Each Repair
8dbd8b49-4683-5f07-a8a5-bc6e7e9338b9 | note | - - - - - - - - -
4326493b-4754-5c7e-b3e0-0135e4f7bd1b | note | Acceptance Criteria: Temperature at time of application:
4c0f22a0-fa17-5cda-b66c-31880c6c6e65 | note | below 5°C or above 35°C
415e49f1-eba6-544a-bde0-be51ab0b3f91 | note | Repair material shall be applied while the substrate bonding coat is still tacky
9bfb13ff-c796-5aba-a38b-2b7e7f501538 | note | Where formwork is used to facilitate the patch repair, it shall be pre-treated such that it prevents moisture absorption from the repair mortar and positioned such that it does not inhibit effective compaction of the repair material.
c24c6ecd-6ef6-59af-aa11-daa50bb0b300 | note | Concrete shall be rebuilt to the original surface profile using a cementitious repair material. Where the existing concrete cover to the steel reinforcement is less than the design requirements, the new repair shall be profiled as required to ensure that a minimum cover of polymer modified repair material to the steel reinforcement is achieved as specified in clause 689.08(b).
53543066-1c0c-50eb-bb8b-9a8b698de23f | note | - - - - - - - - -
1c0c6369-c951-5262-a7c7-0db6056e3b4e | note | Reference Documents: VicRoads Spec. Cl.689.08 (e)
34f10dfe-9302-51ca-b63d-daef5de0f75b | note | - - - - - - - - -
7c5672cb-c143-5793-9b4d-3f6aef7ff067 | note | Inspection / Test Method: Visual
56cc2207-ae19-54ca-b922-57b492ee4e10 | note | - - - - - - - - -
a9c638a0-ad27-50e6-b15b-e72a2047134e | note | Record of Conformity: Signed ITP
b2c0851c-ef38-5a1d-89fa-0cc782c9a1fc | note | - - - - - - - - -
d7009457-d1cc-5ab5-9b25-8528d3e2ec00 | note | IP
002b3780-2e26-5219-9ffd-e53b91646df0 | note | - - - - - - - - -
a60a39bc-8e28-5263-ba3f-259778a15821 | note | Responsibility: SE/PE
| checkpoint | 4.4 - Measuring Tolerances
0b0bce7f-578d-5c2c-82f5-6d1b9a5ae013 | note | Frequency: Each Repair
f0717e0c-d5d5-5216-87ca-4d47e2389d21 | note | - - - - - - - - -
396b6c11-bb57-5b40-902b-03eeb9bb9b94 | note | Acceptance Criteria: Tolerances applicable are:
599a6e24-020b-5c51-a230-1f152e65d050 | note | Edges and Surfaces: ±3mm
0ac6655d-5797-517c-a3bb-68f1e5a58af5 | note | Maximum allowance for irregularities: 3 mm with a 2 m straightedge
71e44aad-32f8-53c7-92d4-b3dce7de8c4d | note | Maximum allowance for unevenness: 1 mm with a 300 mm straightedge
c9cc49cb-9fa3-5455-b1ab-178c5d505055 | note | - - - - - - - - -
2034a10c-3dcd-50f1-99d6-52ce450bb0e4 | note | Reference Documents: VicRoads Spec. Cl.689.11
bc3864ac-fd03-55f2-ba52-f4fadad9a3bc | note | - - - - - - - - -
52da5db3-2a57-5514-8394-728cd81e3fb1 | note | Inspection / Test Method: Visual/ Measure
d3a56ff4-9c8a-5703-98ce-320d1d0eeb2c | note | - - - - - - - - -
b54f5c30-72d5-512f-ba4a-b876170c89c5 | note | Record of Conformity: Signed ITP
6b20d70d-542e-5f4e-8515-c7532d458f99 | note | - - - - - - - - -
16674a7b-728f-5fa8-b99e-d0a668787a10 | note | WP
3b223433-85e3-5b6e-9ed1-ce77c36b1712 | note | - - - - - - - - -
4d3b0f98-338e-5ddb-acd0-6e3f34238ea7 | note | Responsibility: SE/PE
| checkpoint | 4.5 - Cementitious Repair Mortar Test Cubes
389ede12-21c9-55a6-a0b3-d8c82ee7dd70 | note | Frequency: Test Specimens
959fdf92-44ec-5f29-8be5-c5bec69a8cbc | note | - - - - - - - - -
57746050-5f14-54a7-9ebf-6cc9938fbc53 | note | Acceptance Criteria: Three 75 mm test cubes shall be taken from the first batch of material mixed, then three 75 mm cubes for every 100 kg of material used thereafter to test for compressive strength. Test cubes shall be made of steel or polystyrene and shall be fully sealed.
7b8ae619-681f-54cb-aea4-67378dd6c73c | note | Cubes:
03a71fc6-79b3-55b2-ae4d-df67322de4b0 | note | 2 specimens tested at 7 day strength
86c347b5-f325-51eb-b24c-6cb7fdf62a76 | note | 1 specimen tested at 28 day strength
bc7a60f7-68df-517e-ad94-5cc25ff7ff30 | note | - - - - - - - - -
56191b92-0b57-5f26-a3d2-8be5a7ec17d4 | note | Reference Documents: VicRoads Spec. Cl.689.12 (a) Table 689.061 AS1012.8.3 AS1012.9
69ad23dd-da0c-57d7-bfb5-27ea75f29f8d | note | - - - - - - - - -
b5573200-da0e-5512-9853-574f24a3ef86 | note | Inspection / Test Method: Test
03d02fb1-209b-5088-8c4a-726ba7e29b34 | note | - - - - - - - - -
477c4641-3875-573a-b4b1-2d4d6921d4a2 | note | Record of Conformity: Test Results Signed ITP
8cea5c59-2deb-5f59-987d-aca2e604de8c | note | - - - - - - - - -
40c915dd-7732-5e28-b749-48a9b805cd56 | note | TP
1886666c-528c-542e-b474-df2f1efb0ccd | note | - - - - - - - - -
d33ebbc9-b92e-5492-b804-430aa283d38d | note | Responsibility: SE/PE
| checkpoint | Final Inspection
d36d167c-2eb5-5582-891c-cf4f89c96f1c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
a2dd93d5-bb9e-5b3f-be92-469c4197adae | textbox | Print Name:
7a05fc52-f359-5773-b144-98f4343d3c06 | textbox | Position:
7a71f668-9f01-5d2d-8bc9-00a7aa81946d | date | Date:
911f687e-b2dc-5bdf-ab03-779e90af4646 | date | Work Completed On
| signoff | Sign ITP
| checklist | ITP 0083 - Precast Concrete Install | itp | ITP-083-AX-LOT-XXX - Desc | a83efb4c-2072-41e7-82b8-aa612fb0496b
| section | 1 - Referenced Documentation
| checkpoint | Referenced Documentation
55dda094-fcef-5969-81c5-089d14a04272 | note | Document Title: ITP-083-AX-LOT-XXX - Description
52a08e27-461d-5278-b64f-519ace4027ab | note | ITP Description: Precast Concrete Install
6dc2de25-19c9-5d23-b862-0bff9b31aaf7 | note | Document Number (in Teambinder): 1145-C200-FUL-QAC-ITP-0083
e024f0f2-192d-5099-ae59-a148ca8f0be8 | note | Revision Number: 00
2b7f92ad-d668-5dee-9600-116d27718141 | note | Revision Date: 03/06/2022
e451f99e-0188-5a60-9843-4b5810bbf224 | note | ITP created by: Omar El-Khub
b5c80c5d-d8fa-5bf0-94d8-007e40d63c0c | note | ITP approved for use by: Babak Rudd
bbe674f6-e076-5f5c-8fd7-7241092fbd88 | note | 1.1 VicRoads Section 610 Feb 2020
5a75eb5f-e0db-5203-8717-7847e109c955 | note | 1.2 VicRoads Section 620 May 2009
fdd62128-e20f-5bc3-82ee-664301b786fc | note | 1.3 VicRoads Section 630 Oct 2013
4b8bb21a-a5d4-5489-8b2f-3b94f51e4325 | note | 1.4 VicRoads Section 671 Oct 2013
21c499df-45fc-5203-914b-6518124070b3 | note | 1.5 AS5131
| section | 2 - Preliminaries - Materials
| checkpoint | 2.1 - Precast Elements
d7d5fb0f-4247-5c95-9e98-10d71db443f8 | note | Frequency - Each element
e2a862ff-98be-5e61-b16a-ac302801938b | note | - - - - - - - - -
27bc8f22-50ee-585e-bce5-f7bce7c5b6d3 | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
a0caa089-f6af-508e-a94f-23295c9aaa38 | note | i. Certificate of Compliance / Birth Certificate
c86bb90b-6674-5f47-a860-c4d7234347bc | note | ii. Compressive strength test results
177937b7-38bb-5d77-adcf-738907580981 | note | iii. Precast Lifting Design
bfde8633-f5f6-5a92-ab9f-dad95b5b408e | note | iv. Pre-pour check sheet / ITP
a250c60f-a850-5c2a-b140-723a396090a4 | note | v. Post-pour check sheet / ITP
2d5c2a82-b367-519f-a4a7-27dc6069d0d4 | note | vi. Covermeter check record
a6156925-413b-5f82-9461-f50967d53f60 | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown in Cl.610.47
4b0cedca-bd02-578f-a514-531948f559ae | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
b5eac316-a59b-5538-8ff5-dd6c809b794f | note | - - - - - - - - -
2827428a-3ff0-51c1-982b-703f5b92b361 | note | Reference Documents - VicRoads Spec.
444d4725-c009-5b5b-b005-680325a039dd | note | Cl.610.47
79016eb3-7600-56c4-b02c-397357827624 | note | - - - - - - - - -
f26c470e-4af7-52df-abb3-821b73d5fad8 | note | Inspection / Test Method - Document Review
0bd6055b-69bc-5f2d-a8ec-257b4f406ed4 | note | - - - - - - - - -
32d3aa49-321f-5a91-9d87-dcec028866a7 | note | Record of conformity - Material Report
fa79bd58-29a0-5bff-8301-8f38b39aa015 | note | Signed ITP
3aa1189f-d515-57b1-a2a6-b868e7935047 | note | - - - - - - - - -
37cdabdd-9d9a-5159-87bc-636c6f347aca | note | IP
06b827ac-f069-5e13-9e34-f97f532df218 | note | - - - - - - - - -
1f0217f5-8d1f-5754-9042-44df39a4ff58 | note | Responsibility - SE/PE
754d303b-d596-591c-8630-c1e834d5cb7f | note | - - - - - - - - -
e982d5ac-365a-5007-b6ab-7421ceb119e7 | date | Date Completed:
| checkpoint | 2.2 - Joint Sealant
7b88c251-5aa2-51c8-a074-d61d780fc2a3 | note | Frequency - Once, for each product
1c98ab92-b42c-5543-b601-50a96b2cfad8 | note | - - - - - - - - -
9a57e2d2-d503-51a2-b83c-c2d8290544fe | note | Acceptance Criteria - Details of the joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
e5bdb79d-3a43-5349-9dd7-ef6aae050266 | textbox | Teambinder Material Approval number:
e24720dc-ee74-5d8d-a8ae-8ec09d97e02b | note | - - - - - - - - -
5e7745ab-d165-5c3e-b320-174c3d33c14b | note | Reference Documents - FH Quality Management Plan
96b0ea76-8da1-5dce-aaf5-ad3a597d94b1 | note | - - - - - - - - -
3d8fb2f7-0eaf-50ca-809c-75cf59393271 | note | Inspection / Test Method - Document Review
12373875-b922-5390-a3ec-98ccc71e8b5d | note | - - - - - - - - -
8e45f693-2f1f-5c21-bd25-3243cbc03b4d | note | Record of conformity - Signed ITP
771c6c8e-4189-5cb5-afb5-8614beda3ad2 | note | - - - - - - - - -
b1439bf0-1b08-5543-a9b0-83af81eff17b | note | IP
5c959b56-9e19-5d9b-987f-156f5e2c07bf | note | - - - - - - - - -
7cef14b8-de8b-57e8-b78c-e470442bcf08 | note | Responsibility - SE/PE and Superintendent
d60f0f07-aba0-544f-b6ca-b35a0443f024 | note | - - - - - - - - -
fa716069-0db7-541b-a2c5-253dfadf9cea | date | Date Completed:
| section | 3 - Preinstallation Activities
| checkpoint | 3.1 - Survey Set-out of Precast Elements
ec0eb7a4-25f2-598a-bd26-2633adb60d6d | note | Frequency - Each element
df4a02ac-a612-524b-9499-6e445cc40b93 | note | - - - - - - - - -
2f7fce6a-6cf3-5b96-b686-fd9a49d568dd | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per Cl.610.47 as applicable to the element.
60aa70ee-52b4-5530-9389-c48c2be77366 | note | If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
82257c5d-079a-5049-a460-c28eb463e8cf | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
a65c0cd1-11ea-57cd-adf3-af55219dfccd | note | - - - - - - - - -
9e663a26-28dd-5dfa-adc6-62196a5a080b | note | Reference Documents - VicRoads Spec.
d16121f7-62aa-5872-88c1-62f8ad9ed4bd | note | Cl.610.47
cf167637-8303-590f-98ca-b4916529d34f | note | - - - - - - - - -
b244d0cc-4aa2-51de-8527-e25eaaff4e37 | note | Inspection / Test Method - Visual/ Measure
596013c5-30b9-58c0-861d-9e8154f4bee4 | note | - - - - - - - - -
a1e58570-7ce3-5660-9f7c-d97544ce51ff | note | Record of conformity - Signed ITP
6b3d2fc4-2267-59da-98ec-331d7c1862c0 | note | - - - - - - - - -
3da0a5c5-728e-5ade-9c04-31e14a66a750 | note | SCP
923433da-d88c-5e64-b037-9b2cfe4567f2 | note | - - - - - - - - -
2fb901a5-7133-532f-8cf0-8f320ccb31c1 | note | Responsibility - SE/PE
a5c6be89-4318-5df3-b5f0-3616842dc5fb | note | Surveyor
6b60b94d-2be4-5ad2-b69f-43b3cf21bc7e | note | - - - - - - - - -
3b0083cb-4b7f-5c09-b594-674cc4a809be | date | Date Completed:
| checkpoint | 3.2 - Sealing Strips, Backing Rod & Bitumen Board
39b8e5d1-bb25-5bde-b458-b36da3ef1bf5 | note | Frequency - Where applicable, each installation location
5c1da474-c815-5d25-a313-c0c40079e76a | note | - - - - - - - - -
c774cc23-e4b7-5bb2-bb2e-8f5a94fd89d1 | note | Acceptance Criteria - Adhere any sealing strips, backing rod or bitumen impregnated fibre-board into the positions shown on the IFC Drawings or where grout or concrete ingress will affect the end use (such as around conduits).
fc98e219-2e7c-51f7-a5a8-14388596155a | note | Backing rod should be compressed enough to prevent movement during the concrete or grout pouring activities.
24a7bea2-8252-5bcf-b61b-aa8fae8534ff | note | - - - - - - - - -
08c00c8f-50bc-55f4-be3f-20aad48b5557 | note | Reference Documents - IFC Drawings
c3755117-b159-5708-9c1c-a01bc3c01078 | note | - - - - - - - - -
c5eed545-2b19-544e-bc5b-21cb4e248467 | note | Inspection / Test Method - Visual/ Measure
a8be7bb7-a6b0-5cf7-881a-eed6f1e493dd | note | - - - - - - - - -
3200cae3-e584-529d-b707-fbd5ba7d8804 | note | Record of conformity - Signed ITP
b2af78f2-88e0-559d-ad56-784c206736a8 | note | - - - - - - - - -
199feaa4-545d-5708-ae0b-9871aa23bbc5 | note | IP
49ec6f2a-2157-59d9-ab3e-6b04409e96d6 | note | - - - - - - - - -
9ee807cf-3afd-56c0-8de8-47f7af94f4cc | note | Responsibility - SE/PE
24fcede6-4469-5ecd-b788-f890a98d2352 | note | Surveyor
f1a5a696-2423-58e0-b356-83d9f52b470a | note | - - - - - - - - -
f74209fc-cf2f-55fb-a13b-c6b987351b6a | date | Date Completed:
| checkpoint | 3.3 - Materials Inspection Checklist
894b3f72-09d0-52d8-8542-72c443efc77b | note | Frequency - Each element
906ec2e8-2446-5772-bb40-bc57d7d14edd | note | - - - - - - - - -
ca25cb51-662c-5d71-adb0-84c45b2fa87e | note | Acceptance Criteria - General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
2aef64ce-8c8c-5d03-acb4-66235969d671 | note | Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
250c838e-704f-5599-8406-5756f2d9613f | note | Elements shall have unique identification and orientation marked (if applicable).
d9c7bd86-76e4-5816-9aaa-069862596ecb | note | Complete: Materials Inspection Checklist in ConQA
2c31e08e-f66d-5b1f-ae47-611a323e4e13 | note | - - - - - - - - -
6eaea873-6f5e-5552-a4df-5e0f3c8c90f0 | note | Reference Documents - VicRoads Spec
3f2c6e2e-f1b9-5680-965a-cb5653df871a | note | Cl.620.06
26aeff6b-7cc7-5dda-827d-f927d1187006 | note | 620.07
2ca8dc55-ab02-5816-b64e-6a3bc5e56e62 | note | FH Quality Management Plan
927c8b5d-20a5-59a1-9734-8a01d9bd5a45 | note | - - - - - - - - -
c83e0392-9a92-52d1-ad0c-f5f63c94882e | note | Inspection / Test Method - Visual Inspection
41b1471f-8f5d-5405-bf4f-ea088177f4ff | note | - - - - - - - - -
2de58b79-dfb7-5640-8b6f-0f682fff60e3 | note | Record of conformity - Signed ITP
e37d46b6-8cca-5a8e-83c7-a40c75210892 | note | Material Inspection Checklist
38fc0080-8eec-5eb2-87f2-a0c1cbd77d9c | note | - - - - - - - - -
fc087edd-2772-5842-9bb3-e7609c9cc052 | note | IP
7f2c9854-b396-58ba-b27c-f4bb584107b9 | note | - - - - - - - - -
39f323ab-9380-598e-ae1d-d6dad6ac19ef | note | Responsibility - SE/PE
d621c8d2-8381-5a1a-b85a-6459d3ee8900 | note | - - - - - - - - -
0ab750fd-8e18-52eb-8cc9-62467984036e | date | Date Completed:
| section | 4 - Installation activities
| checkpoint | 4.1 - Precast Handling
4c6bba73-10b3-5645-9c14-2270bbcc0a89 | note | Frequency - Each element
98f7f159-93d2-5a5b-86e4-7cd251dd693c | note | - - - - - - - - -
fb4e22de-f68f-5bfa-addd-270f5d10e587 | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
8186e099-9d9c-5b1b-9b4c-ebb305b3077b | note | - - - - - - - - -
761eb029-9b6b-55c5-bf19-55bff0c2f8a4 | note | Reference Documents - VicRoads Spec.
856f77a5-b927-560d-9c33-25201761a905 | note | Cl.620.07
35403cb0-4254-5934-800a-4aad0ee9d1c9 | note | Crane Lift Study
abff1d3c-8505-56c9-b62f-cf1393f2367e | note | - - - - - - - - -
d3bc3e64-2c9e-5694-8a8f-b856b00e82c0 | note | Inspection / Test Method - Visual
ce346a88-d975-5793-b7cb-89486cf7465b | note | - - - - - - - - -
d28b0ba8-fa3b-56b3-b1d3-4a188217f2d3 | note | Record of conformity - Signed ITP
cc6bab31-d90d-5933-a609-cc0f5e16fff2 | note | - - - - - - - - -
1a955380-d36f-5a42-aee4-f95a3f1fb882 | note | IP
de777b92-0ffd-575c-ad98-4b00a6301794 | note | - - - - - - - - -
c0ece1dc-36f6-5f58-887c-f4c10d4326d3 | note | Responsibility - SE/PE
0a36cdf1-d302-5cc0-ad0a-d1cf9e4e3ba9 | note | - - - - - - - - -
54272968-ab31-5264-91b5-3c421414bff7 | date | Date Completed:
| checkpoint | 4.2 - Precast Placement
af50f8c1-5a68-525a-b18a-0980f8a148ee | note | Frequency - Each element
3afa88b0-683f-561c-bd6a-1a6eb6aee477 | note | - - - - - - - - -
4e4d033b-791a-5d03-a5ed-2e4300e8aa22 | note | Acceptance Criteria - Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
dc9ee135-7b7c-55a0-9b82-a172a9ab0953 | note | Make any adjustments necessary by lifting the unit and adding/removing shims or adjusting the levelling bolts so that alignment between units, overall height and position remains in tolerance.
5b4330f8-6c2a-541e-aa29-426f4ccf1e63 | note | The nominal gap between elements is as per the IFC Drawings.
8f5100d6-f0c5-54f4-90f1-54ec7bac7765 | note | - - - - - - - - -
59395b19-233b-5c74-a32a-95b8d85d3ac2 | note | Reference Documents - VicRoads Spec.
38ae6843-0c33-507b-ab9a-539d8c9e985f | note | Cl.610.27
4e970e96-8233-5558-bdbd-9f040b3635c7 | note | IFC Drawings
0ffd2d5b-b178-5a3e-8c6c-aa88991b1d5b | note | - - - - - - - - -
6caeea5a-bf64-5441-a497-2847f1f10058 | note | Inspection / Test Method - Visual
0904239e-ddad-5bb6-b039-c71a2628b971 | note | - - - - - - - - -
608c4f95-428d-54f6-aecc-2a9fa1c8a529 | note | Record of conformity - Signed ITP
8fb98454-4ef9-55f5-9533-149db9224ad1 | note | - - - - - - - - -
90f7b6ea-ed13-536f-ba84-f95abbccf4a7 | note | IP
96ac8c8d-0cf4-5d06-af97-90faef2dba4d | note | - - - - - - - - -
7b658ff8-6025-519e-a626-fa9c226a50c9 | note | Responsibility - SE/PE
a3315998-d812-5ac4-86d0-ca75ac5efb94 | note | Surveyor
53c55854-4122-5a84-bf9f-dc8f8171b4d0 | note | - - - - - - - - -
9aa8e997-3f1f-5996-aa51-5999b18209e2 | date | Date Completed:
| checkpoint | 4.3 - Draw-string in Service Ducts
7430a0c5-ad9f-55b2-89ac-3e69f095a532 | note | Frequency - Where applicable, each element
5520ed4d-5fd6-5b08-8abd-a5ada39ff692 | note | - - - - - - - - -
abaa466b-231e-5d90-b3d3-9f05f29d4d44 | note | Acceptance Criteria - Place a continuous length of 3mm galvanised wire or high-strength nylon draw string so that it can be terminated at any junction boxes.
f7ba4910-0e80-529f-b1bc-f8c8d17346af | note | - - - - - - - - -
53889f12-50e8-57bc-97a2-51a695cfa7d1 | note | Reference Documents - VicRoads Spec.
b403a672-0928-5f46-a33a-1b449406392c | note | Cl.671.03
b9d4da93-369b-57f8-93f1-ad72bd6b6c6f | note | IFC Drawings
d5a2d498-717f-5246-aaff-5bac92eecaf2 | note | - - - - - - - - -
e050458d-db78-5e9a-a288-74b94a15b650 | note | Inspection / Test Method - Visual
ad372034-cdb3-5cce-8b1f-b631617a86be | note | - - - - - - - - -
3c78113b-4ab7-5dcb-b585-3f1c892087c7 | note | Record of conformity - Signed ITP
6e939a6a-36f6-56a8-a770-f1312e646877 | note | - - - - - - - - -
c222b9e0-e0ab-5640-902a-eaf1a43ebbf9 | note | IP
8c215eaa-79d5-5dd1-a390-ef8cf3447edd | note | - - - - - - - - -
b4b4f8ae-df16-52e2-b0cb-85ffc9429757 | note | Responsibility - SE/PE
c90fde95-c1df-5945-a8f9-fea698cfeb42 | note | - - - - - - - - -
eb738bf9-1628-52b7-9d71-07eb0418812e | date | Date Completed:
| checkpoint | 4.4 - Precast Traceability
5f0eee63-8c09-559d-b53f-b57ab79443a0 | note | Frequency - Each element
a8261571-cde3-5720-8aa7-a1b2843c93cf | note | - - - - - - - - -
e27c8623-b3d2-5f3a-ac6c-e8de474abf6d | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
97972ae7-1817-52b5-b49f-3b140e7d9c05 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
2477f850-8137-5222-9508-21b3c18e5e65 | note | - - - - - - - - -
3c6cc57e-2b88-52bc-a2c1-7878796c89ed | note | Reference Documents - VicRoads Spec.
3a5d0d85-f3cb-573f-bed0-52bb42bdc9ff | note | Cl.620.09
3f23dc8b-d25e-5ced-a46c-f19d134a0499 | note | - - - - - - - - -
a9c61e3a-0bcb-5a16-bc1d-5e2082530822 | note | Inspection / Test Method - Visual
e27364eb-3bd4-5c43-ac50-1eaa30b691db | note | - - - - - - - - -
44b04ec2-bce1-57d0-8ffc-476c9638282c | note | Record of conformity - Signed ITP
68e64dea-9024-5b55-81a3-f3c62a0b62aa | note | - - - - - - - - -
9e676d5b-9753-52b3-b7b8-ee7a425df73c | note | IP
79048376-b6e0-5226-96e9-35bf2d2c26c3 | note | - - - - - - - - -
720a2a1f-790f-5575-8d6b-f026ccd6a5d5 | note | Responsibility - SE/PE
56e42b42-f49f-59d8-935b-bb41a43a8663 | note | - - - - - - - - -
44826238-9d21-5c4d-a88d-e9be7aa439bc | date | Date Completed:
| section | 5 - Post-installation activities
| checkpoint | 5.1 - Joint Sealant Application
458d6eda-bfe6-57d4-8ac1-dda319a79488 | note | Frequency - Where applicable
78e48ef9-9834-588c-8ee0-ab956a0d8249 | note | - - - - - - - - -
bf49f74d-92cb-53d2-9247-830ab0621045 | note | Acceptance Criteria - The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
aa2df3be-1c17-557c-ac51-8d7bef2fc0fb | note | - - - - - - - - -
73b705f2-945f-56e2-988d-5dd0ef8fe323 | note | Reference Documents - IFC Drawings
7371c1fa-0197-5c4d-addd-1463a254e02a | note | - - - - - - - - -
edc470cb-155c-52bf-bb75-a69991407de3 | note | Inspection / Test Method - Visual
a2203aee-8be7-59a5-bada-0261298dd649 | note | - - - - - - - - -
89fb53ff-66cf-54ea-802d-dc9002a0f0e1 | note | Record of conformity - Grout Pedestals & Bearings ITP
6f27a63c-84ae-5f0b-be5c-9912470441f2 | note | - - - - - - - - -
9b36dcf7-5d35-5dd6-967e-137a5d3ad0ba | note | IP
3bbb95ae-4fe6-5b74-9b21-c2a37697bfd7 | note | - - - - - - - - -
f0468e6c-9416-52e5-8201-8db2cbef744f | note | Responsibility - SE/PE
f276e039-e1a8-502f-8f80-e8c368e6bed3 | note | Surveyor
ae55d600-8eed-5d19-87af-97a80462b30a | note | - - - - - - - - -
ad82653b-5c7b-5ed9-aacf-03cfc6f59a30 | date | Date Completed:
| checkpoint | 5.2 - Flowable Grout Pour
175d9776-ebbb-53d7-954b-52039b4764a0 | note | Frequency - Where applicable
42660d96-65f5-5bf5-988a-fdecc14eef4d | note | - - - - - - - - -
8130dcf6-eb8f-5fa9-ab53-edaed80144e3 | note | Acceptance Criteria - Grout shall be poured at connections between elements and/or in the gap between the bottom of the precast element and top of the bridge deck/foundation following full sealant application.
c2263a51-43c1-54d2-96f3-51afaf7f090f | note | Complete: Grout Pedestals & Bearings ITP
ba744b7c-8b36-58ad-9cfb-7b1407ba1d9d | note | - - - - - - - - -
bf8c73c8-deb5-525a-aeed-42e10c2736e5 | note | Reference Documents - IFC Drawings
117e023a-2ae7-5d4e-9069-28769ccb2ed2 | note | - - - - - - - - -
b067277a-7946-5e7b-82e1-64d8d8cd2f71 | note | Inspection / Test Method - Visual
f88d3020-5b57-5dce-aad4-91f8f9b448f5 | note | - - - - - - - - -
650338a0-6e5b-522d-a404-25ab61d545e2 | note | Record of conformity - Grout Pedestals & Bearings ITP
62e6687a-0859-59d1-aece-8b53ba8be131 | note | - - - - - - - - -
c7350c7d-0c0f-545f-adef-76ff7363795a | note | IP
cfab6dea-532a-59d3-8bcc-1d912a63cd1f | note | - - - - - - - - -
903030bd-2ed4-513c-9534-73863a178f44 | note | Responsibility - SE/PE
3a84c1ca-004e-5a6e-a6fc-988b9a014148 | note | Surveyor
9b8cd3ca-c2f8-50fd-b19c-4dfcc860cad8 | note | - - - - - - - - -
61e690f9-369f-5ed7-be69-a6fdce826e58 | date | Date Completed:
| checkpoint | 5.3 - Barrier fencing
5563616f-b32e-5ba3-a200-3315c2bddffb | note | Frequency - Where applicable
e9231cea-8f1b-5d50-a184-eff897a799de | note | - - - - - - - - -
a67e16ca-9ad9-587d-b3d7-1027e7e9dbb8 | note | Acceptance Criteria - Where applicable.
fc4c739a-e3e4-5711-9db2-138605b268f3 | note | Complete: Steel Barrier Fencing (Supply & Installation) ITP.
29f41fbd-274f-5fd8-b029-5e9f85782ef4 | note | - - - - - - - - -
bb109321-d34a-5234-8e3f-30b058599ae1 | note | Reference Documents - IFC Drawings
82985c24-537b-505b-a398-e47ce292e783 | note | - - - - - - - - -
a031165b-6bcf-5b5e-bcc8-1e2222747b8d | note | Inspection / Test Method - Document Review
fa8de290-d1cf-5d53-9d13-f582705885b0 | note | - - - - - - - - -
f5d89cc5-844d-5eca-ade5-265c0a3dc3ca | note | Record of conformity - Structural Steel Barrier Rail (Supply & Installation) ITP
480189d0-1f4f-5dac-8328-b7e7ac310b62 | note | - - - - - - - - -
53841263-002d-57dc-a78c-ca3e02d8b1c5 | note | IP
cfd756f8-5862-5d50-94f5-bd7f28de3121 | note | - - - - - - - - -
e3924801-65c2-525f-9291-8e279e262b43 | note | Responsibility - SE/PE
1bcbd3fd-b67a-572e-af58-44a1bb62a002 | note | Surveyor
adb69e0d-31c0-51d3-944f-eec431d762a6 | note | - - - - - - - - -
d965d180-1605-5d4d-8a0b-533fc24c261a | date | Date Completed:
| checkpoint | 5.4 - As-built Survey
497a7fb4-8521-5aff-bc10-46428285fee7 | note | Frequency - Each element
ced52d15-de9f-5989-93c2-f2edad9e0084 | note | - - - - - - - - -
817ff4a7-9dd2-582a-8859-6c9de9bee672 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances in Cl.610.47
2275339e-07b7-5e44-858e-689f53024d00 | note | Attach: Survey As-builts / Survey Report
4de31b99-a071-5e8b-8fc9-57ec62828c45 | note | - - - - - - - - -
6f9ef60b-3290-517e-844d-a5875cbe22fc | note | Reference Documents - VicRoads Spec.
cc608786-7ed3-5989-af79-52be9f049e76 | note | Cl.610.47
65e4d4f6-6804-5dad-8ad1-10f5c078de8c | note | IFC Drawings
cd68885b-2472-5164-9785-29ff5b58113d | note | - - - - - - - - -
a8aa3dd3-8c31-593a-a387-798eabf3d4b8 | note | Inspection / Test Method - Document Review
a8b3085d-d990-5b2c-a923-e5d5ac23fff2 | note | - - - - - - - - -
6e3b27d6-0e93-56d9-a403-4c3581d2d725 | note | Record of conformity - Signed ITP
bcca2746-33d2-5649-b261-a8beccd60a03 | note | - - - - - - - - -
fb6f8301-f055-5d12-b13e-0e754de6be1b | note | IP
4b29c789-7c3a-567e-b084-56b48c040e17 | note | - - - - - - - - -
6d8a67a2-3cf0-599e-aca2-d40308759a2b | note | Responsibility - SE/PE
ee50563b-1962-5616-a81e-ff25a3fc88b8 | note | Surveyor
a9ac3baf-04ee-5874-b3d9-3b710b78b685 | note | - - - - - - - - -
535c50ca-c888-58a1-841b-b61809d4585f | date | Date Completed:
| checkpoint | 5.5 - Non-conformance Report (NCR) Closure
a976a1af-1f31-58c9-81ed-ec4b497cc5f8 | note | Frequency - Once, prior to closure of this lot / element / Work area
c55ef204-e466-57ed-ba23-a801115aaffa | note | - - - - - - - - -
ae073dba-3186-5e52-a140-a38fcddfca54 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
8dd09611-3be4-5535-83c0-d0194281c2fe | note | - - - - - - - - -
ed77e5c2-519d-5b73-8c3e-0b9a8baf0656 | note | Reference Documents - FH Quality Management Plan
c3d0b0f6-86b0-5a4e-a316-6d2eb3100c29 | note | - - - - - - - - -
13473713-7332-53e0-b69d-143ba5b8bff2 | note | Inspection / Test Method - Document Review
fe35efb0-af08-593f-bcfb-e7aa6c791fe0 | note | - - - - - - - - -
a08ca9b2-4cf1-5374-844a-59666795c765 | note | Record of conformity - Signed ITP
ee31b202-b601-5904-b451-b667a2d983c4 | note | - - - - - - - - -
3eeaaa11-750b-582c-b25f-34422eae6654 | note | IP
8abf7bfe-d939-5237-9ebb-5a3cfb76502c | note | - - - - - - - - -
b16d672b-ecd1-5384-a210-706f357a55e5 | note | Responsibility - SE/PE
99536755-dd7e-572f-a352-1b673f0a6a34 | note | - - - - - - - - -
dac40f6c-99a8-537b-b6ba-17f7c1f74ec5 | date | Date Completed:
| checkpoint | Final Inspection
1f8657d2-54e7-5923-8c0b-99ef273af93c | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan's Quality system Procedures and verifies lot compliance with specifications.
941946e5-41d4-56da-91ed-f78130dced46 | textbox | Print Name:
dc149d26-1f8e-5789-aba1-e7770985b24f | textbox | Position:
7b3790cc-4f5c-505f-a44e-78a02a807e74 | date | Date:
211ff6cc-cf81-5273-9ecc-15970dcb79f8 | date | Work Completed On
| checklist | ITP 0084 - LIME STABILISATION OF EARTHWORK MATERIALS | itp | ITP-084-AX-LOT-XXX - Desc | 431e7191-c7f2-4c74-89c2-1cbc95610a98
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
5a0f5dcf-59be-529c-a67a-e87bfddd20fa | note | Frequency: Prior to Commencing
7f42cd1d-1739-5690-8172-61d52a04efd3 | note | - - - - - - - - -
7fd16195-5240-56a4-9f54-ebc52b1a9551 | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
12423cb7-40bf-54b6-aff6-77ff2b7991bc | note | - - - - - - - - -
45500dc0-b0f6-5f48-96d2-35cfa4317ef7 | note | Reference Documents: PMP Inductions Register
e2fa9367-888e-553c-bb30-83704739d0e4 | note | - - - - - - - - -
55540eb7-7502-5b66-8853-dbd9c5ea6b27 | note | Inspection / Test Method: Document review
6370ecd1-8bac-5a7d-bf0d-79efc455616f | note | - - - - - - - - -
db3db14c-a21e-5b2c-b3c2-05b91881912e | note | Record of conformity: Site induction signed.
63e1340d-52ea-5206-86fc-9b0ef0109bda | note | - - - - - - - - -
d0f39cf9-7c93-5ab7-9ffd-780c37900418 | note | AP
9e463341-c479-5619-a441-bae3f584fcbe | note | - - - - - - - - -
8ea7489e-e2b9-5299-b44b-66c6ca33342f | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Check that current revision drawings are being used
17fcc206-f560-5e6f-8ee1-1d5f9d73cfcd | note | Frequency: Prior to Commencing
76d9a278-73f7-5fc7-895c-92bc7b3172ab | note | - - - - - - - - -
5e8bb86d-8341-5858-9a3f-acc75f880643 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
8721f58e-cdef-5ffe-9fac-d31b7416188f | note | - - - - - - - - -
2176f2ab-a4db-593f-b011-f8a69a0ea646 | note | Reference Documents: Project Drawings / Drawing Register
bc8f159f-f32b-5a46-870b-dd5efc70259c | note | - - - - - - - - -
5a45e87f-1175-50ab-91eb-a23c7ef192fd | note | Inspection / Test Method: Document review
c7bebc0e-1378-549a-b8f9-fb49d6e52ed8 | note | - - - - - - - - -
c2640d1d-6489-5a0c-807b-e49c14b49e7a | note | Record of conformity: Latest Revision Drawings
6ab11c5f-16e8-5761-a6d2-952fbc32eba6 | note | - - - - - - - - -
ae5af7c6-af94-52de-a710-fb1ec9629b37 | note | AP
9dd089eb-641a-5bd2-836f-328abb68f2b6 | note | - - - - - - - - -
23a00e67-6626-5c4d-b3fd-645bd548ee48 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.3 - Confirm understanding of current Construction Environment Management Plan (CEMP) and Environmental Control Plan (ECP) related to the work area and that all prescribed environmental controls are in place
d4dcbd42-3c9b-5d11-b2ee-2d33462cc9ad | note | Frequency: Prior to Commencing
c82d81f9-489a-5845-ab26-c5b9ccd2d8fd | note | - - - - - - - - -
a0ceb18c-18a5-5ace-ace2-d4361a95d4f2 | note | Acceptance Criteria:
63c5bbf4-17d8-519c-99ed-6d19b3553457 | note | • All environmental measures to be implemented as per current CEMP, ECP and local authorities.
81fc6b46-2670-50b7-8d3e-d0fa22212c7c | note | • Sediment control measures to be installed and protected; sensitive vegetation to be clearly identified.
89d5bff3-5ce0-505e-9cfa-9bbe3fa10fbd | note | • CEMP to be provided to Melbourne Water, incl. details for all water quality/ turbidity monitoring both upstream and downstream of works site.
9b6553bb-2ee2-51ed-a625-de97cf3976b2 | note | • Provision to MW of a ‘Groundwater Management Plan’, including a dewatering methodology and where the water removed from the creek will be discharged.
9e08791e-f7ae-5533-af14-deb047465030 | note | - - - - - - - - -
c9e069b2-83fd-589f-9906-76b271d8549b | note | Reference Documents: CEMP, ECP, Site induction, Project Specification Cl. 1200.03
fb3d65e5-a962-5aea-a51c-0d0b46ef68ef | note | - - - - - - - - -
77348d55-b429-5c2b-b417-05d2857dcbdc | note | Inspection / Test Method: Document review & Site inspection
b2b79a5b-4f70-5293-81ee-b05320869e43 | note | - - - - - - - - -
d328d90c-2680-5d20-b8e6-2bfa47209ab5 | note | Record of conformity: Signed ITP
89d2c688-6ef2-5564-8d92-371230643c74 | note | - - - - - - - - -
6e15054b-f5bc-5d64-ad61-3b6b4dc57a27 | note | HP*
42f036cd-867b-567e-9b86-357909ab1d6c | note | - - - - - - - - -
ba0e9731-571f-5d16-9a1a-7471df66e3ec | note | Responsibility: Site Engineer
| checkpoint | 1.4 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
711cc2a0-a575-5d0a-836d-861ea217aee7 | note | Frequency: Prior to commencing
c81bedef-1877-5a3c-af45-33afe0c1e66b | note | - - - - - - - - -
63485170-4011-595a-a44e-5f8bb154f814 | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
3a33e42a-0781-5ead-9133-4b38a674d48e | note | - - - - - - - - -
d5b707df-0fd2-554e-9cf9-d9195bd1d5fe | note | Reference Documents: Project Specs. Cl.1125.02 Cl.1125.07 Health and Safety Co-Ordination Plan
56cd17f7-62c3-5db3-8df3-fa7abc0277a0 | note | - - - - - - - - -
7b4166e5-1c9a-51c1-a037-ac7461b3851e | note | Inspection / Test Method: Document Review
4d78c863-ebff-5307-a11e-0fd3021bc232 | note | - - - - - - - - -
e9cebd8e-04da-52fb-9d2e-bdaf86cd4eaa | note | Record of conformity: SWMS(s) signed
50b9c6ba-3f7b-53a5-9902-9d69b0410457 | note | - - - - - - - - -
3d3cf3c6-c150-576b-9edd-aa8b10cf729c | note | HP*
4de898e5-ea7a-50ed-a831-ec655c67082c | note | - - - - - - - - -
14c740c8-f84f-5f37-9049-94aa74789127 | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Excavation Permit issued (if required)
42a965cf-2e64-5e28-a2ce-e577e3074039 | note | Frequency: Prior to Commencing
493daf0f-191e-5438-a1f7-5b40a6dc94dc | note | - - - - - - - - -
d87444d2-b8a9-57f6-891c-02da240f4f2a | note | Acceptance Criteria: Current Excavation Permit signed and specific for the area where works will be executed.
e334ee7d-2797-5aa3-8a1c-fe7a22f77c59 | note | - - - - - - - - -
05316a9e-8504-50a2-823c-49878ba2eee4 | note | Reference Documents: Excavation Permit
159ac5d5-eeaf-5516-8fc3-b932b17608a2 | note | - - - - - - - - -
cce2813f-d771-56f2-9b98-d1661c6a46d4 | note | Inspection / Test Method: Document review
581379ea-8ff6-53b4-92b7-a71457152365 | note | - - - - - - - - -
f9026cb8-6d28-5770-924e-c4d11771bd59 | note | Record of conformity: Excavation Permit #
02fe09d6-f20a-5032-9ba9-ff4f16e38fcd | note | - - - - - - - - -
50cea333-2b49-5a1c-aab9-914f97933cb1 | note | HP*
dec74a71-5bb0-5d73-a2d5-a66aa77c22cc | note | - - - - - - - - -
f6ff0e25-b8d3-518d-97be-979282310f50 | note | Responsibility: Site Engineer
| section | 2 - Subgrade Stabilisation Preliminary Documentation
| checkpoint | 2.1 - Stabilised Subgrade
392ecbbc-58ed-5d7d-be15-83ac774645ca | note | Frequency: Prior to Commencing Works
1df63cc9-43a6-5afd-a671-5e1b85837cce | note | - - - - - - - - -
dc601914-c7a0-568a-885f-36271d103269 | note | Acceptance Criteria:
6a76648d-943e-5525-9699-678635a834d6 | note | • Methodology & scope agreed with Principal’s Representative prior to works commencement, outlined in Work Procedure and design drawings.
f39e0856-10ce-50f8-afad-aca2da7bbe4e | note | • The Contractor must submit to the Superintendent for approval in accordance with the Review Procedures, a detailed procedure for lime or cementitious stabilisation not less than 10 Business Days before commencing any lime stabilisation work.
c1735d6b-7494-591a-a3dc-3a05b57cddcd | note | - - - - - - - - -
559dfe24-9ed9-589d-ba9a-0b1f8a13d3f9 | note | Reference Documents: PS3020.07 (j) VicRoads section 290
55a34426-0461-509a-9fa4-f9e2f992ca0d | note | - - - - - - - - -
3918e8f7-9407-5820-bf62-d1e4f130f31e | note | Inspection / Test Method: Testing
f5a54e38-71a6-57f4-bb8b-7a2190004f83 | note | - - - - - - - - -
f4b746a8-3afa-57fc-a87c-9cac5ca420c5 | note | Record of conformity: This signed ITP
9da3cefc-b3d4-57a7-9782-21a37e8c9ce3 | note | - - - - - - - - -
919d9320-df60-564b-a268-a468e40427c1 | note | AP
d5158921-efb5-533a-a19d-428e03d42e49 | note | - - - - - - - - -
6f05e7de-c7c0-5316-afc8-0fcb8da643ba | note | Responsibility: Site Engineer
| checkpoint | 2.2 - Investigation and determination of design lime spreading rate
25cd6062-280a-5104-8e53-3d2f1b1e6819 | note | Frequency: Each Lot
42e6293a-e0de-51e7-95ba-4cd1c8e5bb82 | note | - - - - - - - - -
880e289b-0d11-53ef-b9ae-2269c13fb2af | note | Acceptance Criteria:
fdc9d810-ed45-5f2a-885b-fdf09b95480f | note | • The Contractor shall not commence work until all mix design details including the stabilising binder spreading rates have been presented to the Superintendent for review.
982fefd7-e110-56cb-9827-2737ad6d3100 | note | • If the Contractor is required to determine the Design Distribution Rate of the stabilised binder(s), evidence shall be produced to show that the material properties specified in clause 290.07(a) or clause 290.17(a) as appropriate have been met.
92963212-f485-5dc2-8915-e4c86b3ddd2c | note | - - - - - - - - -
d3e9365f-73b3-5265-bcdb-5fc3bcb079a8 | note | Reference Documents: VicRoads section 290 CL 290.08
f5c3bac4-2b93-5669-a91c-967113fc5137 | note | - - - - - - - - -
357741bb-00aa-5904-8e8f-ef8eefb32ff0 | note | Inspection / Test Method: Verify
9a281f09-f973-5ac0-90a5-0a9419e1abec | note | - - - - - - - - -
9bfeb81c-8f11-5520-9635-ce6aaa552056 | note | Record of conformity: Subcontractor Quality Docs
622fc143-c9a0-5faf-88ed-e9d072613480 | note | - - - - - - - - -
cdeb755f-b9df-5b5e-be62-95a2d81f0397 | note | HP
7f9e9632-5066-5826-8637-6c0f2586d9a3 | note | - - - - - - - - -
3b8a7828-f266-52c1-ad23-a3d2772f3e7e | note | Responsibility: Site Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Material Selection
e791b3a1-a8c1-58fc-986c-c407088960da | note | Frequency: Prior to
ba4aafac-75c0-5099-a37e-a2a64f930b53 | note | - - - - - - - - -
2c78951e-0e1d-5d92-bae9-1df40e3eda98 | note | Acceptance Criteria:
622aac63-a9ab-5bb3-bffc-c5d413b89402 | note | • If Type GP is proposed, the Superintendent shall be first notified and evidence provided to show that the earthworks material can be mixed and compacted to the specified density within the Maximum Allowable Working Time for Type GP Cement.
aec93ed3-5f7e-583f-9950-aaf707136a19 | note | • Quicklime and hydrated lime shall meet the requirements of AS 1672.1
e7eff0af-97bd-5b94-93bc-f52bb937c620 | note | • The stabilising binder shall be selected in accordance with Table 290.061
1ea17fd9-ee7f-5ead-8379-6347fd92767c | note | - - - - - - - - -
f3802f5c-79f9-50cf-81c6-e51bacc09a4c | note | Reference Documents: VicRoads section 290 CL 290.10
853c54f2-85d9-5f2a-b30b-c212c74a57bc | note | - - - - - - - - -
916e1644-da7c-5b04-8e50-93e90bb4548d | note | Inspection / Test Method: Verify
a603fe49-0cb4-56be-9b38-e7a0f583574e | note | - - - - - - - - -
47db01e0-16f6-5e17-adf9-7e6aa061a55a | note | Record of conformity: Subcontractor Quality Docs
e847cdeb-6105-51ba-ac5c-76c1fde37ef3 | note | - - - - - - - - -
b7588ea8-3ae6-5a62-909f-0b9be7989417 | note | HP
1722fbcd-abfa-57a6-9f9e-dfa146cdae60 | note | - - - - - - - - -
295d8410-9fa0-5bcb-9aa3-3d0b8e91caa1 | note | Responsibility: Site Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Preliminary trial
eb1a364e-2f42-5e96-bd9c-90cc09d04d68 | note | Frequency: Each Lot
0fb5b60a-5a13-5ff3-b23d-77ed3498c6fb | note | - - - - - - - - -
c9c89940-309a-5cc2-9b2a-4fc14a6d5d52 | note | Acceptance Criteria:
9b2d15c8-256a-557f-b501-7dff59957401 | note | • Preliminary trial to be undertaken of the proposed stabilisation operation. Trial to determine:
b750cfae-28ae-5e04-b885-afbfabcd450f | note | – Effectiveness of plant
c88b858a-6c94-5f47-9668-72153394e4dc | note | – Number of passes required by the stabilisation to achieve uniform pulverisation and mixing
45233f37-e126-5cbd-a1b1-c2b0b10978a5 | note | – Field moisture required to achieve specified compaction requirements.
1c1a67e4-1ac8-55d1-91ac-6d6eae7f30a3 | note | – Rolling routine required to achieve specified compaction requirements
dbff7428-63da-5533-9568-7b2a14ff5309 | note | – uniformity of mixing of six random test holes.
77dedb26-5a1f-585b-a04d-ab262aba8722 | note | – Lime stabilisation not to proceed until reviewed by the Principal’s Representative, with an outcome received within three working days.
616d7e77-c989-567b-8007-51ef7ae10f18 | note | • Stabilisation shall not proceed outside the trial sections until the Superintendent has reviewed all aspects of the work. If the Specification requirements are not met for the trial, the Superintendent may direct that another trial be undertaken or that the work be re stabilised and presented for re assessment.
04a71cb8-2acf-5e69-b0ff-56e3c8a25a3c | note | - - - - - - - - -
99bec649-fdfa-5ce9-b7d8-06c069faf991 | note | Reference Documents: VicRoads section 290 CL. 290.11 CL 290.17c
1011908e-d93f-5a51-bdcc-18ca38b3142c | note | - - - - - - - - -
547bda7b-2667-5369-b4e5-490a1904e7db | note | Inspection / Test Method: Visual Inspection
f2c75ed2-8e98-5ea4-88bc-8d27c977f6d5 | note | - - - - - - - - -
5cc9ecb8-e151-521b-a761-c5987eef5019 | note | Record of conformity: Subcontractor Quality Docs
5ae58188-1cfe-5fd3-a29a-2f7cdf5d0da3 | note | - - - - - - - - -
30456e04-76d0-5120-8cb8-ab9163bdc41f | note | HP
abe468fb-37f6-5b8d-a0ef-3380653a250a | note | - - - - - - - - -
1706558c-06e6-54a6-87b9-bbe02d69dbde | note | Responsibility: Site Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Construction process - Lime Stabilisation
| checkpoint | 3.2 - Preparation of Subgrade
6406baeb-1bca-5520-a6c3-b928f8841243 | note | Frequency: Prior to construction of subgrade layer
5fc9ab85-bec3-52b6-b6cd-a98fc0fdfaef | note | - - - - - - - - -
7b3b6072-3c25-5e93-96b3-c83fc2f6c7fc | note | Acceptance Criteria: The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water)
13e107b0-88de-5841-a2be-609b30962969 | note | - - - - - - - - -
4d444380-6262-5c18-8443-36a54e930b2f | note | Reference Documents: VicRoads Spec. Cl. 204.15Cl. 204.03
10096ce7-c5fd-546c-a26a-02f683dc1319 | note | - - - - - - - - -
ee371fe8-a484-5cef-8131-a1ede844b21a | note | Inspection / Test Method: Site Inspection
f7aa514c-5600-5c35-8f84-ec1e4dfdb70a | note | - - - - - - - - -
45d58ad9-0505-57db-8e02-46637420c1e8 | note | Record of conformity: Signed ITP
593e9241-fcc3-5e21-9d66-3d1b75416eb2 | note | - - - - - - - - -
d4582125-825e-5363-8e75-2010aeb1acf8 | note | IP
04fe3d3a-6b4d-5f21-b87e-106bb472be38 | note | - - - - - - - - -
88fb4935-fc39-5090-b57a-b6fd3289632c | note | Responsibility: Site Engineer
| checkpoint | 3.3 - Proof Roll
1dbf8f33-f50d-5665-bbca-ae3ff12ffb59 | note | Frequency: Prior to Placing fill
00bc343c-e2a4-5ea3-ac44-f54768a15f72 | note | - - - - - - - - -
de833126-c2e7-519b-953c-ab00d6eec285 | note | Acceptance Criteria:
34dcd12f-f109-5c40-ba99-ac9abda909cf | note | • Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
64d4b44a-4309-51f6-9f14-71821c57889d | note | • Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
89578ced-b77f-51cc-aa78-9bfb0c95731a | note | • No fill is to be placed on the prepared areas until the area has been reviewed by the Superintendent. Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review. Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent
638e76b9-cfe5-5d28-8b76-9a302bafeadf | note | - - - - - - - - -
02f72f88-6f6a-5098-b3f4-0da36e555f03 | note | Reference Documents: VicRoads Spec. Cl. 204.12 Cl.173.03 CL.204.13(b) Cl. 204.10(b) Cl. 204.07(d) Cl 290.12
4911029a-dbc3-5f43-b730-83031d64b758 | note | - - - - - - - - -
d9b35677-7981-5154-9c86-3e1177aef3b9 | note | Inspection / Test Method: Site Inspection
bc9d2b72-e178-552e-bed5-6144adedcf80 | note | - - - - - - - - -
f3252c84-85e5-525a-9a5e-d0769477c981 | note | Record of conformity: Area visually reviewed by Superintendent Signed ITP
4d8c3e50-b33d-5c6c-b068-2739c265d55f | note | - - - - - - - - -
9d6e6416-9d8f-59a7-b227-d38de7b0be51 | note | HP
e5e6132f-eac0-5b58-b63d-3611c34249e8 | note | - - - - - - - - -
149c538d-281d-5dfa-82d3-4f20276c0b8d | note | Responsibility: Site Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Pre-treatment of earthworks
a1139730-f1b8-57df-9ba2-c4012c57a5ed | note | Frequency: Each Lot
2d023294-9a09-5a54-9a28-130192de4114 | note | - - - - - - - - -
af25ed00-ea54-51e6-9de6-427155de5875 | note | Acceptance Criteria:
784df25b-3999-554f-a49c-7619c1ea92d4 | note | • The area being stabilised by lime will need to be scarified/pulverised to the specified depth. Any rock particles greater than 75mm to be removed from the soil.
054c179a-cb03-5b09-8bf3-732b698ee3ed | note | • The maximum compacted layer thickness for any stabilised material shall not exceed 250 mm, unless otherwise approved by the Superintendent
1f8390e3-4514-55c4-9cdd-20350729306a | note | - - - - - - - - -
47901521-cec8-5562-b5d1-8fcad4aec0f2 | note | Reference Documents: VicRoads section 290 CL.290.10 (b)
afd8f405-553a-57b3-87a7-c4aae2905fd0 | note | - - - - - - - - -
9a4ffb86-1f81-5e13-a154-cce2deaf2d64 | note | Inspection / Test Method: Verify
6ca7bd6d-7d6e-5099-b1ab-50940d0e1458 | note | - - - - - - - - -
05668678-8262-5fa4-97c6-47f4cee0c5d0 | note | Record of conformity: This signed ITP
e9ce9f98-10dd-5fa2-bbfe-89281508d1d1 | note | - - - - - - - - -
cf6e104b-9344-5c00-bd4d-d8638c8ff876 | note | IP
| checkpoint | 3.5 - Spreading of Lime
35755468-a57c-5074-b909-5dffd821b7e3 | note | Frequency: Each Lot
bfa3764f-3364-54a6-900d-f47376d15390 | note | - - - - - - - - -
72f59e72-28f2-5fed-be07-59440b85e987 | note | Acceptance Criteria: Lime to be spread uniformly over the prepared surface at the Lime spreading rate calculated.
deaa9796-5578-5551-acb8-0996eee1bcb1 | note | - - - - - - - - -
d63d024a-49e0-5ede-b552-454ce0670d62 | note | Reference Documents: VicRoads section 290 CL.290.10 (d)
fb1c7eb4-9796-5e43-a81b-be484d9c04ca | note | - - - - - - - - -
175fdb01-a363-5142-8113-ff8f9511d6a8 | note | Inspection / Test Method: Verify
eb821e1c-f5c8-535e-bcb3-aa630e881cf5 | note | - - - - - - - - -
c29658c7-9c1e-5e3f-8f7a-6d9ad96ed847 | note | Record of conformity: This signed ITP
90617317-761e-52f6-b8c5-5e8e4729e8ea | note | - - - - - - - - -
e74af931-c1da-5238-9042-d818a105fcbc | note | IP
| checkpoint | 3.6 - Slaking of Quicklime
d8493b83-2c80-5d75-8f5d-38ec55ec3d69 | note | Frequency: Each Lot
aac8821f-0136-56c1-b827-8cbe676de99f | note | - - - - - - - - -
3f4c8a34-7379-5433-be53-309bcac3dce4 | note | Acceptance Criteria: Quicklime shall be slaked with sufficient water to allow full hydration to take place.
ecc7af09-191c-5768-8ed2-4e546d6083a1 | note | - - - - - - - - -
dcb951d7-ead3-548b-b41d-ce7490b9d272 | note | Reference Documents: VicRoads section 290 CL.290.10 (e)
8475f56c-4fad-5515-88ec-e2916446262b | note | - - - - - - - - -
6b3a6b60-281d-5302-ae7b-11654b6da1d7 | note | Inspection / Test Method: Verify
0d6e4d21-b7a6-5020-861b-e08f62aaa3e1 | note | - - - - - - - - -
3b25ae9d-61f5-5d81-ae68-09cc3f3e25d1 | note | Record of conformity: This signed ITP
f4220970-2fe7-51e6-ad9e-c8241f6c9653 | note | - - - - - - - - -
dcb6ccf9-75cb-57bf-a639-cbc577aef57e | note | IP
| checkpoint | 3.7 - Mixing
0a90bc2c-0ce9-5f3d-8f72-f78f54f5c41d | note | Frequency: Each Lot
05c2d1d6-53bb-56ce-bbe1-fc14b74aeacc | note | - - - - - - - - -
6b4d4697-e040-53ef-9bb1-5406dfed0f83 | note | Acceptance Criteria: All lime to be mixed to the specified depth within 6 hours of spreading. The stabilised material shall be visibly inspected for uniform mixing by excavating test holes to the full depth of the loose material at six random locations within each lot.
5d92e172-a87a-5a42-b4bb-72325b7654fd | note | - - - - - - - - -
bb160c50-6c21-59ac-b555-44f216b2f6b9 | note | Reference Documents: VicRoads section 290 CL.290.10 (f)
42a2a6ed-5d13-5ffb-8955-a5ca3b785815 | note | - - - - - - - - -
f4d4e47c-9bb4-5dc3-ba06-8db4d7f81cb3 | note | Inspection / Test Method: Verify
f1d10183-3bab-51ce-923b-4ea38f6c6535 | note | - - - - - - - - -
eb78a492-4a66-521c-a912-b1c2f1c4ea8f | note | Record of conformity: This signed ITP
afc0ea41-b3eb-57d0-b5e6-11469289a97d | note | - - - - - - - - -
61a93a76-434d-57c8-a850-bd482b3c4850 | note | IP
| checkpoint | 3.8 - Compaction
3480077c-8705-5050-a0f1-3add4331e2f0 | note | Frequency: Each Lot
0f1e80d6-e141-5389-bf75-7db46385c8f8 | note | - - - - - - - - -
56735bca-ce04-583f-b2ad-0bb62ffb9dfe | note | Acceptance Criteria:
9ff6aa2e-72b1-5b23-bd5c-a14250da9480 | note | • Compaction of the stabilised layer shall commence immediately after mixing, but only after the requirements of clause 209.10(f) or (g) or (h), as appropriate, have been met
57255a00-8339-5f00-b7b2-115b12fbf2b4 | note | • All compaction shall be completed within the times specified in Table 290.101 after addition of the stabilising binder.
fe31880c-dd4c-5a49-84f3-183f428fb739 | note | • If necessary during compaction, the Contractor shall water the material to maintain the moisture content within 80% to 100% of the stabilised materials optimum moisture content.
40d2367a-ce4e-51b5-9c09-04b3b9eb3015 | note | - - - - - - - - -
5b53700c-b28e-5952-8a7d-7da8bb3e1845 | note | Reference Documents: VicRoads section 290.10.(i)
c0a44cdf-9223-5036-ae90-18beccd305a5 | note | - - - - - - - - -
4eaf5e55-7446-5b77-bfcd-83fc04784302 | note | Inspection / Test Method: Verify
323bfac2-fbcb-512c-8946-2c77b87137ca | note | - - - - - - - - -
cb649592-6990-5a38-af17-8138d24d0748 | note | Record of conformity: This signed ITP
6c64df86-3d42-545f-b4af-523ee3ded1ac | note | - - - - - - - - -
f844d952-eed4-52ea-8db9-5a943cf40ce1 | note | IP
| checkpoint | 3.9 - Trimming
e8a0fd2f-1601-59e2-af3f-4acca09d4f70 | note | Frequency: Each Lot
695ca475-d4e2-599a-8591-5a1fc9babdb2 | note | - - - - - - - - -
47e53a19-1a65-5347-8960-abd1b78e1409 | note | Acceptance Criteria: Surface may be trimmed before or during compaction to conform to surface level tolerances.
17367bd9-37d0-5286-9e0f-5e171c9c34d8 | note | - - - - - - - - -
9935fec6-d47a-5c6f-b044-c561b83b7468 | note | Reference Documents: VicRoads section 290 CL.290.10 (k)
e02265c1-eaf6-5ba3-abe4-2c362b249fc2 | note | - - - - - - - - -
0cfb93d0-f889-5535-91fa-eeacda70c8b8 | note | Inspection / Test Method: Verify
882f45cd-6e37-5db8-92e6-c05ac4197f86 | note | - - - - - - - - -
7e80ddfa-0677-57aa-be1d-e845c9f6d883 | note | Record of conformity: This signed ITP
f9a5995d-988c-5833-a271-98677fe12366 | note | - - - - - - - - -
ab117209-19fc-551b-a119-e1f8965e6cf0 | note | IP
| checkpoint | 3.10 - Curing and protection of compacted layers
afb9737d-6104-5ccb-84a3-5a907eed467c | note | Frequency: Each Lot
fa9d5a58-33ac-55c6-a5ef-7a5ed2ab8465 | note | - - - - - - - - -
fb9a3a2b-44d8-57ed-94be-023a9edfa9e9 | note | Acceptance Criteria:
b882a876-341c-5469-9cb3-81b2da581c3c | note | • The surface of the compacted layer shall be kept continually moist, and free from contamination until the succeeding layer is placed.
e8d2a6f1-0e60-5f47-8bbc-a853ec86fa16 | note | • If the stabilised material overlies an expansive material with a percentage swell exceeding 2.5%, the stabilised material shall be maintained at a minimum characteristic moisture ratio of 90%
0162a35a-2d3e-5515-b28b-f3ac978942c9 | note | - - - - - - - - -
aedb328d-362c-5fb9-a110-23619dcbae0a | note | Reference Documents: VicRoads section 290 CL.290.16
142f39ed-875a-5163-ae04-05d452a17cf3 | note | - - - - - - - - -
64fe05d5-3aa7-5ca0-a54d-6bd42bd08c55 | note | Inspection / Test Method: Verify
5d4882a9-53fc-5571-b180-8091a25de0f2 | note | - - - - - - - - -
f67f8dba-8d78-5be2-87f3-4fb09e5171ca | note | Record of conformity: This signed ITP
04bbc471-90b4-5c2c-a6c2-8da3e7587d79 | note | - - - - - - - - -
2932b16b-0315-586c-bd49-6ce13425b22d | note | IP
| section | 4 - Acceptance - Pavements
| checkpoint | 4.1 - Requirements and Acceptance of Lime Spreading Rate
61093d8d-870b-56e8-9901-e87ad4a8fd64 | note | Frequency: Each Lot
fe29a1ac-9a28-506f-a262-f0005ca56684 | note | - - - - - - - - -
fa3dcd91-d536-5325-a0c7-928c442dee6a | note | Acceptance Criteria:
0d792b46-83b0-54ee-aa08-a10bab99c8fc | note | • The Average Lime Spreading Rate and Uniformity of Lime Spreading Rate are to be determined by either the Mat/Tray System or the Continuous Weighing System, as described in VicRoads Clause 290.13.
e98cab4e-75eb-574e-bb1e-36d8a14385fe | note | • Evidence of results to be presented to the Principal’s Representative upon request.
683c0f60-ffe5-5347-8bc0-d2ba702c7793 | note | - - - - - - - - -
951e12c5-e668-5280-abb8-22618494ed66 | note | Reference Documents: VicRoads section 290 CL 290.13
e03287f7-ae65-5f81-9525-0ca604dfb619 | note | - - - - - - - - -
edd5b10e-0369-531d-9fb6-5f042d2e2e53 | note | Inspection / Test Method: Verify
eaad7275-5ccf-53ea-9194-bef22e58feeb | note | - - - - - - - - -
b254043b-72c3-5c8c-9df4-9148f5afe244 | note | Record of conformity: This signed ITP & Test Results
8bac6c3e-bb15-533b-a82c-f514965e2a09 | note | - - - - - - - - -
e01c7a65-13c6-5b03-a3c6-e4d643fd2b13 | note | TP
d1cd65e9-fac1-5b7d-a294-77d630eb885c | note | - - - - - - - - -
ccfb7e34-7508-5926-9637-c89ccb2134bb | note | Responsibility: Site Engineer
| checkpoint | 4.2 - Subgrade Testing
7edc2756-39af-5db7-9544-efc4cca7802c | note | Frequency: Each Lot
3f2c9d20-8810-5389-b59b-0f87b0edcac8 | note | - - - - - - - - -
1350212d-5da0-5f84-aecc-c98823daa5f9 | note | Acceptance Criteria:
1e1b1080-8ecd-5b91-ae84-44ad0470efdd | note | – Average dry density ratio of not less than 99% MDD (standard) for lime stabilised subgrade material.
a8599d68-ee52-54bb-bc32-dead0c2d72b6 | note | – Field dry density at three random locations throughout each uniform section, per scale A requirements.
217f6977-f186-5caa-a3f3-d1746e4c2f36 | note | – Where the subgrade has been replaced with 200mm of Class 1 Crushed Rock, the field dry density is to be compacted to 99% (standard compactive effort).
128f7289-e6ee-55e8-a130-f5be85c08227 | note | ○ Characteristic Density Ratio ≥ 99%
f8d13b40-c0de-5d35-ba65-1d7037909618 | note | • CBR ≥ 6%
8b480b4d-419c-5eb0-bd19-291dccf22dc9 | note | • Swell ≤ 1.5%
7e674f59-e39f-5cf7-b341-526a4bdf60a1 | note | • Permeability ≤ 5e-9
e0eab66d-2dfc-569f-83bc-3a898ecefb35 | note | • PI (LL) = 6 - 25
61eb6248-a453-5175-a94c-bde15b3d12f3 | note | • PI x 0.425 passing ≤ 1000
40ce64d2-b3a6-54d9-884a-4c734a065aec | note | ○ Grading:
46fa9e35-1a41-5a89-80b8-41b04ef7b837 | note | • % passing 75.0mm sieve = 100
a7da44bf-f3d4-5b14-9e3b-bf8695f11e45 | note | • % passing 4.75mm sieve = 40 - 80
220a3656-298e-5814-9911-f26f607d1734 | note | • % passing 0.075mm = 10 - 40
e06979fc-8c75-5845-bb91-e9309924d4aa | note | - - - - - - - - -
f05be061-7f9e-5611-a88a-72873e998cfc | note | Reference Documents: VicRoads section 290 CL 290.14, Table 290.141 for compaction requirement and Table 290.15 for the frequency of Testing
0118129b-0d2c-531c-8f3d-c6aaf96f58a6 | note | - - - - - - - - -
d28fa21b-8340-5a38-8867-e59ff40f8a78 | note | Inspection / Test Method: Verify
f6dfa506-6446-5dc5-bc1b-e253a0b56f25 | note | - - - - - - - - -
967b6fcb-d184-50a1-9346-a018f5fe81ce | note | Record of conformity: This signed ITP / Test Results
c9527e2a-64ed-59b6-bd1e-1b375463cfe6 | note | - - - - - - - - -
9d01ffc1-1da6-5be7-bca3-18870cf9a0f8 | note | TP
c9e572f0-0cc0-5b01-b9f3-eeeed2e3e4ff | note | - - - - - - - - -
e3f9b49b-c2ef-5a25-aa6a-0f3e7cd573cb | note | Responsibility: Site Engineer
| checkpoint | Test Requisition
f41284b4-8973-5b4f-a762-c7972fc7afd3 | textbox | Test Requested on
4e1c38d8-5457-5e6c-885f-fe568d743523 | textbox | Location
77a94740-5367-5769-8498-99edacef672c | dropdown | Material Type | Type A,Type B,See comments
e9e20409-567e-5eb2-9083-0f1f915c13e7 | dropdown | Material Source | Holcim,Boral,See comments
9a454284-cd2c-5f0d-b2eb-ca46db4d7619 | tickbox | Compaction Test (Standard)
14f55b24-d80e-5210-8dc1-8e5172c85c35 | tickbox | Compaction Test (Modified)
d5ec320e-2e60-5c24-aad3-7c38975b5417 | tickbox | Maximum Particle Test
b386597d-9de4-5143-8db9-fd169979395d | tickbox | CBR/Swell Test
9dfada47-d744-5b82-b866-b919189fb984 | tickbox | PI Test
3b9ae2e9-b69f-5757-b471-92c9006ae48e | tickbox | Permeability Test
3ed91647-6b81-51a0-9aa1-b9ae16f2430d | tickbox | Grading
be2ce7aa-3e0f-5c88-94f1-e2e6855ad997 | tickbox | Moisture
4b032538-8bbb-53b5-b202-4f858f0d2e1b | tickbox | See comments
4544bbb4-8b4e-5bb7-9558-77ed16178ae1 | textbox | Test Level/ Layer
| signoff | Test Requisition
| checkpoint | Final Inspection
0f9b6bda-0398-54ea-ab8f-a04f7817bfd1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
c536519a-7683-526f-95f1-b99b83fa37ab | textbox | Print Name:
2fbeaff3-cdd3-5f41-81c7-ca2e73e42108 | textbox | Position:
385faa9f-6fff-5a0d-8cb0-a5a67402e9f8 | date | Date:
eb5fc7a6-91ca-5b1f-90ba-8158144f77eb | date | Work Completed On
| checklist | ITP 0085 - SUP INSTALLATION (HCC) | itp | ITP-085-AX-LOT-XXX - Desc | ed7cffb0-19d5-497c-84b5-1359ac943fbf
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check that current revision drawings are being used
03ba854b-b32a-5c0b-a053-cc7e39b82987 | note | Frequency: Prior to Commencing
47ee0802-6b91-5ac5-93de-232b3e34548d | note | - - - - - - - - -
a218be83-ea64-5b4b-9383-1a18181153b4 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
a3f3449a-8a82-5a7d-95a1-860d96056389 | note | - - - - - - - - -
ad1b6bc5-bbc0-5b8c-8a3e-d828a731a920 | note | Reference Documents: Project Drawings / Drawing Register
9567aab5-175c-56c2-8678-d1511d6f3dee | note | - - - - - - - - -
c6f44a6e-c9c1-5668-8834-79ddbd9f63a1 | note | Inspection / Test Method: Document review
d007f70b-f3c1-5cd0-8bdb-1f075f3cc1c0 | note | - - - - - - - - -
8b8dc6c4-bb64-51ed-bf13-6107d85e88f8 | note | Record of conformity: Latest Revision Drawings
41ec0ccd-ba91-58e6-88c4-365ce08153ae | note | - - - - - - - - -
4737f95a-cac4-5aa7-b8bf-1bbfbbdc33c7 | note | AP
cd8fd411-bf35-56fd-9836-11d57d9c6a29 | note | - - - - - - - - -
eda3a119-53c6-56e6-b3a9-ea4308f7353b | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Bedding Material / Base Layer
d7a15792-a48a-5b18-b9d5-68c7f47d0133 | note | Frequency: Once, for each mix design, prior to placement of material
ffdecb39-3427-5063-8bb4-3b1424d529e9 | note | - - - - - - - - -
6a7980d8-eb97-5eb5-81d8-e630a96663e5 | note | Acceptance Criteria: 20mm Class 3 bedding material conforms to specified requirements applicable to the class of product as detailed on the drawings.
c9a7c89a-134c-5dfc-ab54-8219b2d0bebc | note | • Material is registered with VicRoads in accordance with Code of Practice RC500.02.
477ad267-e765-52c9-96cd-812d885f3d56 | textbox | Enter: Teambinder Material Approval number
22ee4344-ffba-5228-b826-41c01afc9a0e | note | - - - - - - - - -
7c5b5029-93b6-5f41-9cc7-f85365bd2037 | note | Reference Documents: IFC Drawings 703.21 812.04
bc656808-5c3e-5df5-b018-19b90a582312 | note | - - - - - - - - -
1eb0c545-0904-5b3d-a2c4-b6b61045d68a | note | Inspection / Test Method: Document Review
8b8b0713-b4ee-5146-a1cd-8cca3a96334b | note | - - - - - - - - -
b1a0e9db-b0b2-5115-8787-cc497249296b | note | Record of conformity: Teambinder reference number
ce416f03-ee4e-5e98-8eeb-cf9a6d1d9b78 | note | - - - - - - - - -
0ff38acf-f232-5b89-903b-c0c1e8ac277a | note | IP
30357104-658a-5215-91a3-6bfd4e4e66f4 | note | - - - - - - - - -
8f407237-8144-5354-a9b2-666727d74bc3 | note | Responsibility: Site Engineer Superintendent
| checkpoint | 1.3 - Concrete Mix
da06a36d-d3b8-588c-90da-747127492591 | note | Frequency: Once, for each mix design, prior to placement of concrete
71a03480-8fff-5bf7-905b-1e99875d09b3 | note | - - - - - - - - -
9a8eb31c-c5d7-5411-9245-e5a7ab1d1a62 | note | Acceptance Criteria: Concrete mix meets strength, grade, and maximum aggregate size as detailed on the drawings.
0277912c-3d52-5789-bd76-2b3906d5e4e2 | note | • Paving concrete mix conforms to AS1379. SUP concrete mix is registered with VicRoads.
79606b8c-0a6d-5938-a972-274ccb9a3659 | note | • No air entraining chemical admixtures shall be used without approval from the Nominated Authority.
022a1a03-dd8f-5c89-90de-850cd1ed47bd | note | • Concrete mix designs shall remain valid for 12 months from the date of registration, unless constituent materials and material proportions cease to comply with the specified requirements.
5c75723a-37bd-5515-9177-ee98240e37c2 | textbox | Enter: Teambinder Material Approval number
9116eeaf-701b-5aaa-880b-5cd158aba87e | note | - - - - - - - - -
d9106ef7-f1fa-536b-bc02-98e6cf214c7a | note | Reference Documents: IFC Drawings 703.05 (a) 703.07
e77803af-2a87-5cd1-8d99-2898ebcb4c32 | note | - - - - - - - - -
a65fe421-1113-5abc-b3de-91d21aafc04c | note | Inspection / Test Method: Document Review
b5d3de90-ea03-5907-a4ec-5bcd24d9a785 | note | - - - - - - - - -
5ad3f1d4-a0ef-576f-9d67-1461c01acd19 | note | Record of conformity: Teambinder reference number
75ee7403-9c29-5fe4-96be-d1b64994b213 | note | - - - - - - - - -
ef2f99f7-9def-5ad3-a617-347f2777fabf | note | IP
77fd491a-d9cb-55d6-8690-32c605c234f8 | note | - - - - - - - - -
850c6cca-b84c-52bd-84dd-25363af4d9e0 | note | Responsibility: Site Engineer
| checkpoint | 1.4 - Evaporative Retardant
d9f3b64e-d607-5c7d-bbd9-6c2595dbde77 | note | Frequency: Once, for each product, prior to placement of concrete
07b515af-115f-5ee3-982c-84a6a022a68d | note | - - - - - - - - -
ea97d5af-bd02-5ba6-bb27-b64b5d57a61d | note | Acceptance Criteria: Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
01587371-86e1-5287-a8b3-78a818b657f0 | textbox | Enter: Teambinder Material Approval number
7b6c002f-3e35-59d5-b01c-3d4c25913173 | note | - - - - - - - - -
6a96cb4a-7f6b-52cd-858f-17b6333a2e3d | note | Reference Documents: 703.09
78ea67fb-422f-5dea-8a6f-82c6c357e2e4 | note | - - - - - - - - -
0b2a7192-f246-53b4-8d03-9abe064bce9c | note | Inspection / Test Method: Document Review
be8da57c-1885-5114-bf05-3d89eb92ad56 | note | - - - - - - - - -
c8f2d46b-6d90-5d93-b980-ff3b43b181a3 | note | Record of conformity: Teambinder reference number
81c0ad6e-0806-5f23-ac93-cdbd19f0f9d7 | note | - - - - - - - - -
f65c2ac1-020a-5805-92aa-25d1976f1f8b | note | IP
7bbc87a8-bdc4-55f2-b8a1-1d310407128c | note | - - - - - - - - -
48b08975-edca-52ef-9ef1-2463ddec3f13 | note | Responsibility: Site Engineer
| checkpoint | 1.5 - Curing Compound
1de96a0f-06bf-5de3-8e0c-dc283b92d9f6 | note | Frequency: Once, for each product, prior to placement of concrete
e8f09c26-fccf-5e6c-9aa9-deb30c226394 | note | - - - - - - - - -
3916b31a-341d-585d-9539-81888c4c1552 | note | Acceptance Criteria: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
5b13f73c-eed5-5f11-9265-b1fda4da6d1d | textbox | Enter: Teambinder Material Approval number
a23e027a-3f71-587a-89e8-6e1128725482 | note | - - - - - - - - -
6e15d972-851e-504b-9278-92ee00620943 | note | Reference Documents: 703.10 (a)
0b44f637-8a2c-5c7c-86c4-e970e72a8361 | note | - - - - - - - - -
1cc5b3ee-8093-54c9-aa4c-7c4f56e698e4 | note | Inspection / Test Method: Document Review
97588777-32a5-5da4-849b-5e516b9ae987 | note | - - - - - - - - -
f3c53191-3e2b-5d4d-8f83-7fffb2634b94 | note | Record of conformity: Teambinder reference number
7c01548a-0fa1-55d7-96ee-6931298f881b | note | - - - - - - - - -
bbae6927-b4dd-5a20-a493-493c9de5b41e | note | IP
61b3e519-d6e2-50d5-b7c4-180879855c36 | note | - - - - - - - - -
65a5c324-15af-5a3b-8fc8-da33d04ed22c | note | Responsibility: Site Engineer
| section | 2 - Construction Works
| checkpoint | 2.1 - Temporary Drainage Provisions (if required)
d417ac57-e860-5e34-96b3-9a1896509f2a | note | Frequency: Prior to Commencing
bd1b96eb-1eb7-538b-bf88-f9a79302460b | note | - - - - - - - - -
8ae64aeb-d2f0-533c-a5da-69046d0d043f | note | Acceptance Criteria: Before obstructing any waterway, channel or culvert, the Contractor shall make appropriate provision for its temporary diversion, and obtain prior written approval from the relevant waterway authority.
825d2e34-802f-5cc0-83a2-3f0902b95093 | note | • The Contractor shall make provision for the safe discharge of drainage and stormwater at all times during construction.
cb4c477b-635f-54a3-bdbf-5451dfdd5844 | note | - - - - - - - - -
a111c4bd-70a3-5ecf-a8db-b7cb67665471 | note | Reference Documents: IFC Drawings, VicRoads Spec Cl.703.18
be520e0a-c6c2-55c0-83a7-6240136bb292 | note | - - - - - - - - -
cf243149-5c57-52bb-9472-4f2b4474ad29 | note | Inspection / Test Method: Site Inspection
72fd8e00-2b81-5912-ad8e-d14b687935a7 | note | - - - - - - - - -
e23289b6-f8bf-579e-812b-33bd6039c095 | note | Record of conformity: Written approval from relevant waterway authority, ITP Signed
b523b06b-e005-53ca-b553-f1d892452abb | note | - - - - - - - - -
7ed8032c-775d-52ee-9644-82165d515c3b | note | AP
96f9af6b-404d-567b-8dba-d3a76fa25220 | note | - - - - - - - - -
5008eb22-9294-503f-b0cb-0fa455d92eb5 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.2 - Pavement Thickness Increases for Crossings
43a8ca59-5bd5-533f-8e3f-b8c7be0b8818 | note | Frequency: Prior to Commencing
2de765d8-c46f-5dec-8176-b4f634de8810 | note | - - - - - - - - -
36ba0123-857b-52b3-94aa-0609afc072ff | note | Acceptance Criteria: Where applicable, excavation to allow for increase in the bedding and slab thicknesses at:
9036ad8c-c582-58f7-8358-b384fbdd134e | note | i. Pram crossings
cde8086d-82a4-577b-afc1-1c10234e8a6f | note | ii. Vehicle crossings (residential and/or commercial)
1559ac49-1bc2-5a28-976e-52d009034bab | note | iii. Established / existing mature trees
9b9f562a-071c-516c-9dc5-651b34672142 | note | • Consult the Relevant Council drawings for dimensional tolerances for thicknesses, grades and ramp lengths.
54db333a-02d2-5051-81b6-9f39065d74e3 | note | - - - - - - - - -
2e61c20c-4baa-5363-99ae-adbcc5b216e4 | note | Reference Documents: IFC Drawings
b37c639d-91d4-5f05-8885-bcc961d9b03f | note | • VicRoads Spec 703.16 703.24 EDCM 401
bb4ddcaf-1822-5bf4-92dc-bf74b6544069 | note | - - - - - - - - -
ee33397e-677f-5d1e-af6c-ec2657a2d601 | note | Inspection / Test Method: Site Inspection
e78aba38-5652-5ecf-8622-a7ff22199fd4 | note | - - - - - - - - -
cd3b5de0-f55a-52b1-bd7f-4f6de83c9c4f | note | Record of conformity: ITP Signed
446050c9-da3b-5d76-80af-b793fd3ecdba | note | - - - - - - - - -
3b6c2b03-268a-5571-a123-1046eac86982 | note | IP
78161c5a-30f5-527a-89f4-f7abdf712ec3 | note | - - - - - - - - -
8fea581a-8a8e-5478-8020-782e659b5bb2 | note | Responsibility: Superintendent/ Supervisor / Site Engineer
| checkpoint | 2.3 - Bedding Preparation
797a6674-0891-5f84-8551-a8dc769e3152 | note | Frequency: Each Lot
e1dbcee8-9447-55e3-af52-62d51cc743e1 | note | - - - - - - - - -
9f4aef2c-4a2a-5366-a641-ccfe9324a085 | note | Acceptance Criteria: All bedding material shall be as specified on design drawings. Where not specified, bedding material used for cast in place concrete paving works shall be compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
c20c5a68-46ce-5d36-ae16-f6d14bb0f31f | note | • Bedding to be mechanically compacted. Immediately before concrete is placed, the bedding shall be moist but shall have no free water on the surface.
8de39cbc-5818-57b5-9e05-e710c37060e2 | note | - - - - - - - - -
ee33a454-6a35-5849-addf-66c86bf70e9e | note | Reference Documents: VicRoads Spec Cl.703.21 812, 820 IFC Drawings
9932223b-4da2-53ad-9901-586955e06eda | note | - - - - - - - - -
40fce6a7-0408-525f-9f02-7879542c673c | note | Inspection / Test Method: Site Inspection
32b8172e-ba90-5819-8176-803557cc77c7 | note | - - - - - - - - -
4e9ea9e1-ba13-544e-9246-dc0d60db8cc9 | note | Record of conformity: ITP Signed
3630a1e3-f55d-5a10-b978-eb56a124927e | note | - - - - - - - - -
c9432e25-67c0-564b-b6e7-330397016dfa | note | IP
6947c32c-bf7a-5e7d-afcd-5beee32f7d87 | note | - - - - - - - - -
dbe3aed5-9505-5ed8-88eb-1fdac88ac71e | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.4 - Formwork
720db574-d1fa-5ef1-8f96-104014d42558 | note | Frequency: Prior to Commencing
68ffc86f-2454-5658-925a-7ad086c6bca6 | note | - - - - - - - - -
ccc8d395-6e6d-569b-80b1-d43a1f5653b4 | note | Acceptance Criteria: Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
09b173fd-475d-58b1-9fe6-6e76c12a0d47 | note | - - - - - - - - -
14a6daaf-539a-567b-a62a-39ba37a95ab4 | note | Reference Documents: VicRoads Spec Cl.703.12
9911084b-2f15-56c1-a547-7419025f20f6 | note | - - - - - - - - -
aaa3946f-4153-5af9-a69a-acc484a30efc | note | Inspection / Test Method: Site Inspection
be9e9181-d9f6-5d25-a14b-88e89c5a658e | note | - - - - - - - - -
d4acbd00-60d6-5e0e-95f0-b978e2ae7be7 | note | Record of conformity: ITP Signed
d9301a4f-4e25-56ef-b997-adf709f9161d | note | - - - - - - - - -
aee9a29e-1fa8-5ba6-b36b-ec76bfa5ef6b | note | IP
65b007dd-a158-5461-b50f-db10291367ac | note | - - - - - - - - -
ae46a071-5bec-5cbc-81bd-8055c13f0756 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.5 - Steel Reinforcement
a19484f8-58ac-5cda-967f-4542cb5c898f | note | Frequency: Prior to Commencing
0e02a311-5206-5ffb-83f7-52200d0431f7 | note | - - - - - - - - -
1bc23a12-a99e-5b1b-989f-8d59f024875b | note | Acceptance Criteria: Steel reinforcement shall be placed in accordance with drawings and AS/NZS 4671. If not specified, mesh shall be placed as per VicRoads Spec Cl. 703.16.
4d69c18d-7812-5a71-9954-6ed1c571b104 | note | • The minimum cover of any steel reinforcement to the nearest concrete surface shall be 50 mm unless shown on the drawings.
f0d21b07-9369-5a28-a153-17be6c86bd0d | note | • Reinforcement shall be supported using either concrete or plastic chairs.
9841d848-dd26-580c-b817-1882693ea8ed | note | - - - - - - - - -
7b760cb7-dba8-5dba-a23f-84c6da11501f | note | Reference Documents: VicRoads Spec Cl.703.13 & Cl.703.13 AS/NZS 4671
2c65f66d-2f33-53b2-a7dd-fc327ddca017 | note | - - - - - - - - -
dd1ee7f1-3028-5419-a20e-703506bbebf8 | note | Inspection / Test Method: Site Inspection
00a202f6-fb21-5165-bd0f-0c44963558fa | note | - - - - - - - - -
accbfdd0-cf3e-5497-bc77-ab0078d665d8 | note | Record of conformity: ITP Signed
13548bc3-b98d-5fad-95ff-9bd5174526a3 | note | - - - - - - - - -
61f43437-ca20-546a-9eb0-833e74fa4e9b | note | IP
4282b0c4-a5ea-5876-80ec-7c5e69450eef | note | - - - - - - - - -
8cc0b8fb-4841-545a-92fd-64f94e097058 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.6 - Pre-pour inspection
d77832c5-55d9-5b97-8f87-7cee6ebf6271 | note | Frequency: Each Lot
ae031f47-c9b8-56de-ace8-300ffcc26897 | note | - - - - - - - - -
71d7391e-bbc8-55fd-857b-dac9e47ba582 | note | Acceptance Criteria: Inspection to ensure that forms, reinforcement dowels and other embedments conform to the requirements of the specifications and drawings. The Superintendent will review and confirm the set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
fe104258-9f40-5765-a45a-443ba8cf50cd | note | - - - - - - - - -
3a988b75-6e56-55a5-b59f-ffdcdc5fb193 | note | Reference Documents: VicRoads Spec Cl.703.05, Cl.703.09, Cl.610.17 (a)(b) (c)(d) 703.17, AS 1379
e3964374-c89f-5dc5-b869-121c81588669 | note | - - - - - - - - -
a26539f6-29e7-5e98-95f5-f385c51c3937 | note | Inspection / Test Method: Site Inspection
fd6fea9e-4ebf-5ae4-9ec3-410f00b1acd1 | note | - - - - - - - - -
44728309-138c-57be-ad98-5a1edc1f49f8 | note | Record of conformity: ITP Signed
52d4b115-9a58-5aab-839f-3ae7fb56d19b | note | - - - - - - - - -
78051ad9-5b9a-5fcb-a962-1ccd430f3447 | note | HP
02f6ced4-3726-5699-8c68-1ff123d17027 | note | - - - - - - - - -
d9ea4fef-6f8a-5023-8709-6183d9e05fda | note | Responsibility: Project Engineer, Superintendent/Council & Surveyor
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Concrete Testing
75adc7ba-bb70-56c6-920d-7c9ff50ed4c2 | note | Frequency: Each Lot
694a0728-8c96-598a-9721-61bd455f3ef9 | note | - - - - - - - - -
7212d104-0425-55c5-870f-3a8e4ad0c7eb | note | Acceptance Criteria:
e9e44750-a172-5db2-9303-206f473534b7 | note | ○ Concrete Testing Frequency:
23973c37-6173-5bf8-897d-f62c3600227d | note | • 0m³ to 50m³ = 1 sample
70bd7ebe-d691-5497-815e-cd45bef38927 | note | • Each sample shall consist of 1 no. slump test and 2 no. compressive strength cylinders minimum.
a00fd68d-ef8e-51ce-a5cf-74121d682a71 | note | • Compressive strength cylinders = 2 no. 28 day strength.
45f32bb3-bc04-55be-bece-86e86b919894 | note | ○ Slump Testing Tolerances:
9bf9121e-e24c-58f7-a5dd-323e6d73f6aa | note | • <60mm = ±10mm
62f7fb59-93f5-5c21-82ee-b3ad7acebb63 | note | • ≥60mm to ≤80mm = ±15mm
b3f2f322-c7bf-511d-9120-5064c37ea97a | note | • >80mm to ≤110mm = ±20mm
9a464dd2-66fc-5150-9428-0040771e712e | note | • >110mm to ≤150mm = ±30mm
5ecc9baf-41eb-565e-949b-671a13bebf72 | note | • >150mm = ±40mm
7016646f-9793-56b3-8375-6d518691faed | note | - - - - - - - - -
7500100d-518a-5388-81ee-a1d5f7740264 | note | Reference Documents: VicRoads Spec 703.11
0c9a26bc-7994-5109-be83-192059450c46 | note | - - - - - - - - -
e6bb22c3-35aa-54ff-922b-1967645a1ef8 | note | Inspection / Test Method: Site Inspection
a94ff21b-3484-55a7-9736-59b421aecd4d | note | - - - - - - - - -
bff58cc1-0ca0-56d5-9b93-5f1b4514988d | note | Record of conformity: Concrete Pour Record, ITP Signed
4cb43fe9-671f-5158-8c4c-fe473875aa83 | note | - - - - - - - - -
7540bb29-8d83-5eaa-9c43-78773331c80b | note | IP
e315771f-76d2-5411-a693-ab6160695049 | note | - - - - - - - - -
e5587377-54f3-5d16-9a86-ef0f3108fb32 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.8 - Curing
855f6610-543e-54a6-9dd7-b3a15eb27a1a | note | Frequency: Each Lot
a62314cb-297a-52b0-b6c4-4d85f5918a2a | note | - - - - - - - - -
c7bec2df-5b60-5c8b-b68c-2a44717f7ecc | note | Acceptance Criteria: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete
4a35ed38-f179-5b23-a3fe-96ee2bae4c20 | note | • Concrete shall be cured either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these
ac55d0c1-1653-5d14-be85-9bdbee911a37 | note | - - - - - - - - -
76c36c46-7bf6-592c-a755-768dbec5ae49 | note | Reference Documents: VicRoads Spec Cl. 703.10
671fce9f-1ee5-5bac-873e-cbdf54923834 | note | - - - - - - - - -
29321499-9552-5827-b0a6-4dd8af9cf632 | note | Inspection / Test Method: Site Inspection
efbfa684-de87-5cfb-b779-4b90bbff7d9d | note | - - - - - - - - -
1d7e76f5-2528-53c4-ab92-2bab88490823 | note | Record of conformity: ITP Signed
88b6f185-a8c2-5529-b567-ab5208eccf22 | note | - - - - - - - - -
59e5ebb2-4a42-5079-bd10-7eae5d25a731 | note | IP
be3fd892-47bf-5c7d-b666-058dbf1a8602 | note | - - - - - - - - -
ef2ecad0-26d0-5b71-aef8-0a686233df62 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.9 - Tolerances
c366887a-2e05-5c2d-89c3-d711531351c9 | note | Frequency: Each Lot
b671cd5d-3f7b-5b97-9c14-8544dc4af575 | note | - - - - - - - - -
79cf5380-cdca-55ec-93a6-6f31f49e386f | note | Acceptance Criteria: Concrete paving to match existing fixtures (e.g. pit covers, edgings and vehicle crossings) within 5mm.
1d2055e7-9291-5506-a076-51a0bd518c98 | note | • Deviation of finished work shall not exceed; 10mm from line or level; or 5mm from a 3m straightedge for curves and shaped areas.
31c4fba5-c796-58e3-9a62-c09d66b146c2 | note | • Deviation of section dimensions shall not exceed 5mm (except for overall width); 25mm for the overall width; and +/- 3mm for dimensions less than 25mm.
4d9cef40-554b-504e-9d69-b5c04d03c008 | note | - - - - - - - - -
a0233f58-4dda-50bd-b2d8-7774b754219e | note | Reference Documents: VicRoads Spec. Cl 703.15
bb4033ef-5327-5821-af06-c1afa1228504 | note | - - - - - - - - -
4392b5ef-9cca-5b5a-b38f-bc63b2a5b596 | note | Inspection / Test Method: Site Inspection
dd2655cc-cc56-5f5f-a5cc-fa02458090a5 | note | - - - - - - - - -
ac6c00a8-c118-5043-9a24-51ecd6d6fc21 | note | Record of conformity: ITP Signed
aee03a08-7ab3-5431-986a-e61d70edf531 | note | - - - - - - - - -
1371d305-96d1-5acf-a8c8-2b59630e1094 | note | IP
614740e6-1516-5643-a8b4-0c054e01e82b | note | - - - - - - - - -
bf381db7-acbd-5dc6-a463-d33a927ffdc5 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.10 - Joints
311fad84-98d2-598c-983f-e4feee1f560a | note | Frequency: Each Lot
34cf4ab9-8409-5ac4-9961-9483cc84aa8d | note | - - - - - - - - -
9e8c7f23-a312-5a20-a861-4f62d8667692 | note | Acceptance Criteria: Expansion Joints: shall be placed at intervals as specified by the drawings.
0bc675b7-ff69-5a9a-b5b2-ec79bf368b2d | note | • Control Joints: at least 25% of the paving thickness deep and 5 mm wide shall be formed with a cutting tool at 2.5 m intervals along the full width of footpaths, other surfacings and shared use paths.
3cbfb09f-fa91-5ae9-ab24-384b3e0630b1 | note | • Between Concrete Paving and Shared Use Path: Except for medians <2.0m wide, bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt (ableflex).
9cbf7f9c-2ffa-5d52-be55-3e79876581b5 | note | - - - - - - - - -
d11a5f9b-18bb-53f6-8a46-ba0b649af821 | note | Reference Documents: VicRoads Spec Cl. 703.26 (b) EDCM 401 IFC Drawings
35f19ae0-6129-54d4-b8b8-e7cba5e2ffd4 | note | - - - - - - - - -
1e3f27e6-d7fb-536b-b6fe-8a5f0f503a02 | note | Inspection / Test Method: Site Inspection
91e58e28-d2a2-59f8-819b-c770ff9acbea | note | - - - - - - - - -
b4db6cea-0074-55da-8be3-467fb5c2ae61 | note | Record of conformity: ITP Signed
033b4157-48db-5f99-b87f-82322d64fe20 | note | - - - - - - - - -
7e876d85-c786-52d6-acec-81a15967a7e4 | note | IP
bb4ba5d6-737b-5b4e-bf74-90e8c1af6851 | note | - - - - - - - - -
9838584d-e82a-5891-8eb8-650e9d7098be | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.11 - Stripping Formwork
1d61756b-940f-547a-8388-dafa2febca6b | note | Frequency: Each Lot
85fef905-2687-57d7-98b0-370cb00b7ec1 | note | - - - - - - - - -
0a733d20-7673-55bb-ae65-046511399041 | note | Acceptance Criteria: Formwork shall not be stripped until the minimum times have elapsed from the time of completion of the placing of concrete:
dee02d83-1166-5408-92b4-dcaaafbaefa4 | note | i. 2 days for vertical formwork on external surfaces; and
23d4bc26-e258-5188-b0f6-86f59a791d01 | note | ii. 1 day for vertical forms on permanently hidden surfaces
a6652543-003b-59bd-b27e-10831489c387 | note | - - - - - - - - -
b52adc98-5e8e-5ef9-81fa-4381b677bf55 | note | Reference Documents: VicRoads Spec 703.12, AS3610 Table C2
e5badc1c-d953-5c17-ba1d-016a52d36435 | note | - - - - - - - - -
6520901c-5d12-5c84-be7f-76bc223d80b6 | note | Inspection / Test Method: Site Inspection
b205bdb5-59b2-56d4-9ba6-8bc395fa55a5 | note | - - - - - - - - -
81f7e58d-cdbb-5a48-bc36-db490a7815a3 | note | Record of conformity: ITP Signed
40454dcf-c358-5041-b04a-39bd82fcb04f | note | - - - - - - - - -
acc6f36e-cbb7-5c20-ba98-3b76d5d6f1c6 | note | IP
02b95ad8-8942-5d7c-8c18-0a6ce363d03d | note | - - - - - - - - -
8b1b670d-0081-54ed-9917-057686da4d25 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 2.12 - Protection of Newly Poured Concrete
3c66bc04-7450-5c5d-803c-8bd750ded3d5 | note | Frequency: Each Lot
634172b8-eaaf-517f-ac07-d0bd5cf1e8bd | note | - - - - - - - - -
515df587-dd1e-544a-aaa7-64e1b7b7b21c | note | Acceptance Criteria: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
38c0d659-96f4-5b3f-8df4-a0dd7bfc43c8 | note | • Suitable flagging, signage or bunding shall be erected to prevent vehicles from crossing over residential and/or commercial vehicle crossings a minimum of four days after completion of casting of the concrete. Vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
097ccfa4-7b54-562b-af70-f7934ac360ce | note | - - - - - - - - -
ce50c730-e35d-5759-8c02-d80290a439d3 | note | Reference Documents: VicRoads Spec 703.27
3edbe754-6596-5b4b-978d-0e55705f2db5 | note | - - - - - - - - -
626eaeba-6741-5de3-83c7-a5b27af6e832 | note | Inspection / Test Method: Site Inspection
b6259f68-b48e-5a0e-937d-e3a26d56ca19 | note | - - - - - - - - -
f3ac16de-88a4-5357-99e7-30a9e9e14dcd | note | Record of conformity: ITP Signed
9c31e9e3-6b91-5f1d-8528-802815f61f4c | note | - - - - - - - - -
fe2f345f-bbb5-5935-9ffe-85f7f512505b | note | IP
3ad24805-bf2c-5e24-a0f0-b393a50c8ec8 | note | - - - - - - - - -
62321f86-07a1-55a7-bb09-276c2ecbc486 | note | Responsibility: Supervisor / Site Engineer
| section | 3 - Post-Construction
| checkpoint | 3.1 - Survey data captured for as-built purposes
27052ef7-6ed0-59a4-80ef-2fb5eb3aef5f | note | Frequency: Completion of each lot
603d23ad-8e52-5670-9159-d7da91e68bf5 | note | - - - - - - - - -
1d5bd2d3-9fca-5c73-86a8-3da68d1575dc | note | Acceptance Criteria: Survey to ensure and validate that all works meet level and location requirements.
487aa9fe-7639-5235-ace5-553cb92862fa | note | • Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
e1d6623d-cefe-549b-bc53-4fb7cd928807 | note | • As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
724443b0-34d7-5064-8c69-c3f1da4e3ff2 | note | - - - - - - - - -
12b619b8-a78d-52a5-a415-1c66cd396182 | note | Reference Documents: IFC Drawings / survey records
c24e033b-bea9-599f-beb4-17084bfeab33 | note | - - - - - - - - -
ca853635-4ea2-54cd-a770-c6a3a35a9e76 | note | Inspection / Test Method: Document review
397e293f-af65-5c79-a0aa-26027c04f2c8 | note | - - - - - - - - -
38a2c532-83e4-58bf-8849-405ebce661e7 | note | Record of conformity: As-built survey records
63cf10ee-383a-54e3-9614-5a40f8c5145d | note | - - - - - - - - -
a4bffba9-7714-531a-9154-87392fbd6a27 | note | SCP
3b3119d7-f9b0-5db4-bae8-e51f8fa410f0 | note | - - - - - - - - -
822e1dda-60ef-5e27-ad43-a55d55913543 | note | Responsibility: Project Engineer
| checkpoint | 3.2 - Cracking of Concrete
d90ecc67-f4c1-5ff5-8d0f-3b37da3eb7b4 | note | Frequency: Each Lot
78806adb-1cb6-597b-b0e2-5a076834efc2 | note | - - - - - - - - -
34181c44-6dbb-548d-98ad-41c3224318ce | note | Acceptance Criteria: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
a5a67ae3-04c9-5a02-9d87-16c0f5471760 | note | • Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
4e1e77c7-5944-54b8-add6-689f528505e3 | note | - - - - - - - - -
5465394a-fc06-5d3b-b95c-0e9a9483c901 | note | Reference Documents: VicRoads Spec. Cl. 703.30 687
bcda19e5-3e03-5f0d-8656-87b717c26ebd | note | - - - - - - - - -
eb740f0f-a8d9-5d10-9364-95fa3c62bf5d | note | Inspection / Test Method: Site Inspection
79eba09b-140b-5cff-b380-a9402be46d24 | note | - - - - - - - - -
253d0431-745a-5d47-ada0-c9b554d3bf80 | note | Record of conformity: ITP Signed
341ba66d-fa69-51b8-b93c-6a3aef9fd1d2 | note | - - - - - - - - -
f8119a01-fbad-567c-b2a7-1cc708d353a4 | note | IP
06ede263-5026-5f78-8e34-9f8cf070f1da | note | - - - - - - - - -
a8a97725-7308-5bab-a943-5a270791e03b | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 3.2 - Compressive Strength Test Results
590fc6b9-1789-55a1-a24f-d9ed68c23f0b | note | Frequency: Completion of each lot
ce95fabf-3846-54bf-af02-ddf0400a5c92 | note | - - - - - - - - -
395b87eb-a092-525d-90cf-996be51805c0 | note | Acceptance Criteria: 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
5576493a-8004-51b0-93c5-02fae38f99ee | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
3b3dfc5c-a997-5388-9abd-0edd3ba0bae8 | note | - - - - - - - - -
ea857fc7-80a3-59db-9917-5bc31bac9c40 | note | Reference Documents: IFC Drawings, Relevant Council Drawings 703.11, Table 703.111
d2769744-2b10-5c6b-9a6f-b9e7a7d2a5a4 | note | - - - - - - - - -
57da2188-21e6-5b25-a621-8200acad75e8 | note | Inspection / Test Method: Site Inspection
e0a13b38-f4d1-5eaa-bc80-ba6bc6b05012 | note | - - - - - - - - -
bf426bb7-3d34-5eaa-b9fc-554ea98a669b | note | Record of conformity: Attach: Compressive Strength Test Results
c980960b-8ed7-5dd6-bd6d-765c11c5d364 | note | - - - - - - - - -
0941626f-42d6-56dc-9f88-141bf10c75e1 | note | IP
3fb343f8-1876-5090-afd5-da891fd48c11 | note | - - - - - - - - -
18820e57-455c-593e-9082-ad4606c79af9 | note | Responsibility: Supervisor / Site Engineer
| checkpoint | 3.3 - Backfilling
e4b9dbad-9577-5a02-95c9-3d80830df664 | note | Frequency: Completion of each lot
4d228298-322f-5995-99af-2b2226d0c293 | note | - - - - - - - - -
37dfdafe-34d0-56a7-ad6d-c2367adb9c84 | note | Acceptance Criteria: Where required, as soon as concrete has cured sufficiently and not earlier than three days after placing, topsoil shall be placed and firmly compacted in layers not exceeding 150mm and to a width not less than 300mm behind the edging to the top of the edging.
27cac322-cc4c-57c2-a889-c2ad11b2e464 | note | - - - - - - - - -
86f37c64-9e07-56b7-b5c3-9c636a62a6c8 | note | Reference Documents: VicRoads Spec. Cl 703.29
78f7973e-fc41-50fd-bfff-e2516b940613 | note | - - - - - - - - -
71356e09-63e4-55e1-ae54-f9d1620f3f40 | note | Inspection / Test Method: Site Inspection
79db8794-b43f-5943-aac0-3a37a219e1fc | note | - - - - - - - - -
ba6f7120-d309-589f-8550-b1fcaa56fd2c | note | Record of conformity: ITP Signed
7ec71a18-632f-57d3-8677-f2471898af79 | note | - - - - - - - - -
703b6938-0ea4-5959-903d-1e8b4d6e974f | note | IP
b35ac524-520c-5f54-9240-b8e43123680c | note | - - - - - - - - -
1e10b170-b54e-5ffb-860d-23e28a0a8ffc | note | Responsibility: Supervisor / Site Engineer
| section | 4 - Completion
| checkpoint | 4.1 - As-built Survey
6e95023a-b2e6-5d71-83dd-8ff5abad8767 | note | Frequency: Completion of each lot
936c1ff6-8bfb-5c99-8a09-929cd05e2327 | note | - - - - - - - - -
508ffa0b-f46b-5972-92e2-80550900c99b | note | Acceptance Criteria: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
3018657e-50bc-57aa-bf8e-44e3703f4b76 | note | • Departure from RL = ±10mm
8c487d4d-0ec9-528d-aae8-974c410d9138 | note | • Departure from alignment = ±10mm
18cd95f2-5932-54c4-b315-528b08653b18 | note | • Rate of change of deviation from RL or alignment = 10mm in 10m
3feabb21-6029-5203-a648-d004bb3458be | note | • Irregularities in alignment = 5mm in 3m
b91c80a8-4413-5f5d-aa7a-ad03ce59db59 | note | • Section dimensions = ±5mm
63bd660f-1ce7-5e80-8d3e-6cd31a37646a | note | • Section dimensions (less than 25mm) = ±3mm
0ecf98e6-3fc9-5f46-a28f-972ee3997576 | note | • Width of pavement = -5mm, +15mm
57f8beaa-55f3-5492-a10f-b741d4c6d0e5 | note | • Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
fe3a9a69-863e-5ec5-9069-f110777dd555 | note | Attach: Survey As-builts / Survey Report
4b176fb4-429e-5998-ae0f-b71c79b4457c | note | - - - - - - - - -
57a161f1-35ce-5a57-9b01-07e08083302c | note | Reference Documents: IFC Drawings, VicRoads Spec 703.15
f7cfccb1-227f-5b44-ae66-40b1a2af0579 | note | - - - - - - - - -
1a6e2f0e-b6f7-56b7-8338-e6970ae54780 | note | Inspection / Test Method: Document Review
251a41c5-a272-5557-b8aa-6b9897073756 | note | - - - - - - - - -
4ef3d4d9-f70b-554a-8f5b-b1065de5d905 | note | Record of conformity: ITP Signed
9bd1cd65-bce1-5340-a120-d0c529128fc2 | note | - - - - - - - - -
d6f07da4-0972-500b-a216-4c19804f172d | note | IP
8575fd9d-2e30-5e23-a8e0-d9f83058edbc | note | - - - - - - - - -
aa8b75c9-d015-569d-87ce-4b36f29325ff | note | Responsibility: Site Engineer
| checkpoint | 4.2 - Red-Line Markup
a2236011-65fc-55cf-a3f8-e61eed4beb8f | note | Frequency: Completion of each lot
66764df0-e996-5ee9-be66-115ab0db0edf | note | - - - - - - - - -
e1b9319e-1396-5a0b-825e-3395d96c304c | note | Acceptance Criteria: Capture any changes in design or RFI's as per approved red-line markup procedure
3b1a9e0a-c379-50b4-ab1c-2f5cb7d67895 | note | - - - - - - - - -
af1cdd70-752c-5847-ac9c-0156868f13c4 | note | Reference Documents: Quality Management Plan
f121c69e-9a43-5c7f-8442-7c7996529832 | note | - - - - - - - - -
63a618fd-b845-5f78-b932-d95b05b64d8f | note | Inspection / Test Method: Document Review
7d7ba3be-79fb-59aa-a496-1a3544caece9 | note | - - - - - - - - -
b6a349c4-5012-58da-90f6-79eb71e59308 | note | Record of conformity: ITP Signed
9f9a2261-a1c5-53dc-8a5e-73228bea2c5a | note | - - - - - - - - -
34c579c8-9151-59f4-aede-3554ee5da675 | note | IP
32a0908e-cc56-582a-96fe-370ade1b3bcb | note | - - - - - - - - -
c9012f92-1693-5010-808d-4cb9f782f262 | note | Responsibility: Site Engineer
| checkpoint | 4.3 - Non-conformance Report (NCR) Closure
f2e73706-27f8-548f-9f9d-dfe66ce16df6 | note | Frequency: Completion of each lot
ae102f42-43a2-58cf-b50a-1bbd42648e67 | note | - - - - - - - - -
328d5e9a-b766-545f-9149-460a5fb8c66c | note | Acceptance Criteria: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
2f4422c8-06fa-5b8f-ac5c-88622433cad3 | note | - - - - - - - - -
f77214bf-495f-5a70-a6d5-fcfe1c7264bd | note | Reference Documents: Quality Management Plan
f4b253d9-6515-5236-b0b7-eb8865b90a7e | note | - - - - - - - - -
a87f6fdc-86cc-5d59-84a5-f5e94e079220 | note | Inspection / Test Method: Document Review
2779e04e-b5d2-5693-ba14-de350c25beec | note | - - - - - - - - -
9ecb401a-78fe-585a-a938-e8bf8a968709 | note | Record of conformity: ITP Signed
2bfe4b42-6b66-5725-acb5-abff25031941 | note | - - - - - - - - -
bbe6e287-5a91-5a47-9277-719522c48763 | note | IP
cc99dbe1-b2ff-5619-a62b-7a12b3890d01 | note | - - - - - - - - -
4699245a-206a-5eb2-91e4-2e48568a0f7d | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
a90a4b3b-7a67-58e9-97dd-51cdb1f08e83 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a6b5f8ad-f262-563e-bae4-49f3fd31fdc5 | textbox | Name:
1bd4fe32-6509-54de-b24a-da4947a2da7e | textbox | Position:
7357d833-089d-53c6-a24e-e6dc8f6f24bb | date | Date:
dece111a-2149-5168-9aa4-da46e1dc8815 | date | Work Completed On
| signoff | Add Signature
| checklist | ITP 0086 - WELDING CARBON REINFORCEMENT | itp | ITP-086-AX-LOT-XXX - Desc | d310740b-eb65-4974-8ccd-4ebb0ae11172
| section | 1 - Preliminaries - Permits
| checkpoint | 1.1 - Induction
5c6a7777-a85d-56e6-afe5-d22b803c237f | note | Frequency: Prior to Commencing
ed25a299-d7cc-5ec5-a3f7-feeafce0bf4b | note | - - - - - - - - -
0f8ea686-1182-54f0-b73a-a4c69eda7be7 | note | Acceptance Criteria: All personnel on site have been inducted to the CRG site
de18049b-27cd-5a5e-bf20-3a1fd2c77667 | note | - - - - - - - - -
1a24e628-ab1c-5b9f-a568-a6fcfb8ef2df | note | Reference Documents: PMP Inductions Register
799cb019-77d8-5a7d-b917-29817b8dba1b | note | - - - - - - - - -
34f61721-1ebc-51a7-8221-b65d880dbe82 | note | Inspection / Test Method: Document review
bac30f01-e851-5986-ad65-fba326499538 | note | - - - - - - - - -
087cfa11-4cb1-525e-adc8-d89ccd27eb89 | note | Record of conformity: Site induction signed.
8c9f2380-6923-5117-bd89-fb72d49b14cb | note | - - - - - - - - -
e7616030-52f3-5f28-9254-22d8fdd250b7 | note | AP
40e27565-4ab7-5634-9ee3-2176454804ee | note | - - - - - - - - -
c1fc6fdf-ceb3-5ae3-a688-fa8d49345332 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.2 - Check that current revision drawings are being used
f4dfafad-fd79-508f-8063-db3b73707dbb | note | Frequency: Prior to Commencing
b049ebb0-590d-5038-a483-9175557dd032 | note | - - - - - - - - -
8ff1fe59-d51a-58b8-89d3-123a5957d768 | note | Acceptance Criteria: Issued For Construction (IFC) and latest available revision used
60d413ce-d5d5-548b-94b5-a631b7b07f19 | note | - - - - - - - - -
3f327730-6243-5b99-bef1-7cf404c5d166 | note | Reference Documents: Project Drawings / Drawing Register
652e222e-a634-5e29-87c3-db0b5c0c0462 | note | - - - - - - - - -
20e86d11-ea5f-59dc-9eef-57725ea83c72 | note | Inspection / Test Method: Document review
f96c21ff-b312-511d-a07d-baba717a81ae | note | - - - - - - - - -
68ccbcbf-f9ad-5947-82e5-dd027618b5e0 | note | Record of conformity: Latest Revision Drawings
098439b8-890c-5a78-bf8c-eefa37b79b39 | note | - - - - - - - - -
4b30358c-e994-583e-8bdd-d233c2910f1f | note | AP
184c3392-2555-5db2-98e1-821dac94c903 | note | - - - - - - - - -
7f7b1952-4dbe-5535-9d84-9696bd8f47d0 | note | Responsibility: Site Engineer / Site Foreman
| checkpoint | 1.3 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
b95cdad2-1281-59b9-a10c-d459bdf7843a | note | Frequency: Prior to commencing
51e311c0-c54a-567c-91bc-37a6fe325fdd | note | - - - - - - - - -
d0b7df0a-9c2f-58da-bb9e-1fdd8da0b914 | note | Acceptance Criteria: As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work.
e95c92ca-ab54-53ff-8101-3a3cf57cb230 | note | - - - - - - - - -
407f27a5-16d1-53ce-95b4-192c9169e214 | note | Reference Documents:
e2d06647-fae4-5149-b201-0e8c81d755c3 | note | Project Specs. Cl.1125.02 Cl.1125.07
2fd15f93-065b-5ecc-b5e1-7e29bb84cd64 | note | Health and Safety Co-Ordination Plan
4e24ccff-f8bf-5fc4-a42f-9b6b245ef20a | note | - - - - - - - - -
41215b31-a1b7-56d5-b78b-b955d68e5294 | note | Inspection / Test Method: Document Review
713120e1-c40c-59c4-8547-c72cdaf12372 | note | - - - - - - - - -
fc49e317-8e0c-52b5-8443-a8e01bf80ed3 | note | Record of conformity: SWMS(s) signed
1a92273d-4fc2-5150-b44c-5950def10ec5 | note | - - - - - - - - -
00f741da-d3f0-5d44-8df5-4dbbfcfe58d3 | note | HP*
6a11ba5e-ec7e-52eb-9edf-4a709dd5924a | note | - - - - - - - - -
88562653-22b9-594d-af7d-7c42b4a936d0 | note | Responsibility: Site Engineer
| section | 2 - Preliminary Works
| checkpoint | 2.1 - Welding Procedure Qualification
c5b261b3-196d-53e5-9c59-ff17102b9a95 | note | Frequency: Prior to commencing
1ccdc6a4-6ccf-5b32-8a08-ddd20301d265 | note | - - - - - - - - -
478b6cee-a159-5981-b127-eea92cf4312c | note | Acceptance Criteria:
439eace4-337e-518c-8d74-8da40ab0abb7 | note | Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding procedure has been qualified and reviewed by the Superintendent.
79c33943-ab9c-5d9d-909e-724053f9918a | note | Submit the following documents:
7697cdcf-18b8-56be-9940-c19f00c01836 | note | • Qualified welding procedure
3cc7bb6b-4984-5a05-af84-464c428076fe | note | • Qualified welders record
9a22f0e1-510e-51e2-b546-919aedf07084 | note | • Welding supervisor qualifications
bce0ffc8-6eac-5e21-acb2-611a163b7e21 | note | • Welding Test Plan
8b7c93e2-ae0f-51d7-bb77-f52dbb296c68 | note | • Welding test certificates
6e65bebc-eef4-578a-a06c-a9045e872b1e | note | - - - - - - - - -
018ed06f-7ad3-5ec3-8026-1e93950db88e | note | Reference Documents: VicRoads CL611.14 AS1554.3 Section 4
9684978c-b74e-5795-ab9b-262814089d21 | note | - - - - - - - - -
2d67e604-f476-5904-acdc-2208c4cab6d8 | note | Inspection / Test Method: Document Review
c5636a77-62d7-5eee-9e9a-e0bd312b9f5e | note | - - - - - - - - -
139aafd4-9367-58ad-8cfe-17dd469a6a05 | note | Record of conformity: Signed ITP
5f99db47-221b-5534-90b0-756fe29e4996 | note | - - - - - - - - -
3b305e34-22b3-5f16-81b6-cab434c89fdf | note | HP
b012662c-0c4b-5a0f-ba57-19f85f7abb68 | note | - - - - - - - - -
be6c28ff-7de6-5db1-a2c2-b6a6b957e0ba | note | Responsibility: Site Engineer & Superintendent
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Construction Activities
| checkpoint | 3.1 - Surface Preparation
1d8e3166-bba9-5263-8bec-dbb6b8adc2fc | note | Frequency: Prior to Welding
8a16486b-3c1e-555a-b614-68ce70756782 | note | - - - - - - - - -
882f49ff-33a3-54f7-9c52-fb0f5105792e | note | Acceptance Criteria: Surfaces to be welded are free of corrosion & paint or any other foreign material that may affect the quality of the weld
ed9f49dc-9c67-5a19-8f84-2d564092683e | note | - - - - - - - - -
126b39b1-73a9-549c-81bf-c9d0937beb44 | note | Reference Documents: AS1554.3 CL5.1
51e69a8b-dd39-541e-ac2f-94db9e030da3 | note | - - - - - - - - -
f1028ff1-cfc2-5471-9549-59517451f9bd | note | Inspection / Test Method: Onsite Inspection
89b75d1f-5b36-5c12-be85-cc0d6b00a81f | note | - - - - - - - - -
3cc6f9c2-a067-5b25-bbb3-67b01952b291 | note | Record of conformity: Signed ITP
94429516-ff35-56b3-a4be-c2801f8cedb9 | note | - - - - - - - - -
8ba1790d-36b2-5a31-8f50-b8801bdee5b8 | note | IP
2a9f0332-d203-5d4b-91bf-a7a7c5cec1f4 | note | - - - - - - - - -
6c0210e5-2ebb-53e3-bc5a-406e0d82eef6 | note | Responsibility: Site Engineer
| checkpoint | 3.2 - Assembly
de31d9b4-e2b4-5f56-b63f-eb1fcb01c588 | note | Frequency: Ongoing
f7053806-9a1a-50b1-8ca9-987217648dba | note | - - - - - - - - -
59504494-c329-5a6a-a325-65dc1c328846 | note | Acceptance Criteria:
58f83325-11b0-5863-91eb-020f884cc1fb | note | Where reinforcing steel is to be assembled prior to welding, it shall
2d0f6ac0-5a11-5c86-94cb-5226c29ffff8 | note | a) Bars are to be in the correct location
4791e4e7-e44f-5530-9b44-a45d5a8968ff | note | b) Before welding a butt splice, bars shall be not out of alignment by more than 0.1 times the diameter up to a max misalignment of 3mm
bd004619-71a1-51d5-9645-ce82da24135f | note | c) Parts to be spliced shall be into as close a contact as practical but not more than 0.25 times the diameter of the smaller bar but not more than 3mm
e80f8972-0c12-5493-b15f-dd4ea95a60e3 | note | d) Tack weld, shall be subject to the same initial treatment (preheating). Tack weld that will be consumed in the final weld shall be cleaned. Defective tac weld shall be removed before final weld
e0fcbbb1-e82c-513c-863d-317f6614efff | note | - - - - - - - - -
798c2792-7388-5c4b-a4ef-a1d26fa09d4a | note | Reference Documents: AS1554.3 CL5.2
266c14e7-62ae-56b1-9f7f-6950c8a6e188 | note | - - - - - - - - -
4c462f2e-36f4-5f2a-b894-c1ef592363e7 | note | Inspection / Test Method: Onsite Inspection
d2d27a32-71a2-5874-8a62-8c4f1ce04820 | note | - - - - - - - - -
c9082733-7631-5bdf-bae9-96bc0e3978c3 | note | Record of conformity: Signed ITP
efa356c5-590b-57b8-b0d1-c5c223f6c809 | note | - - - - - - - - -
cee32148-d54c-52eb-8677-58ef3c0ac7b5 | note | IP
fc593338-798c-572d-8f35-1caf0cdf8414 | note | - - - - - - - - -
b4a3138c-b050-510f-9400-7efc333d5436 | note | Responsibility: Site Engineer
| checkpoint | 3.3 - Preheating
94806dde-2388-5151-99a9-6bfdd553b621 | note | Frequency: Ongoing
65ee1dc4-8125-5883-80c7-bb41bf4c0be9 | note | - - - - - - - - -
682f0fad-34c8-5fd8-93ee-a4cf077a3f05 | note | Acceptance Criteria:
f435c8b2-238a-5a4d-84fc-9527a7f79f35 | note | Please refer to table 5.3 to determine if preheating is required
34b5f033-a0d3-533d-b8bf-f81aee90eeb3 | note | Grade 500N, bar size less than 40mm pre heating is NOT required
f64707f5-55c2-5acc-a2fd-b3084b2e3701 | note | - - - - - - - - -
dba33ff6-31b9-5cb5-97da-601b2ae5f78e | note | Reference Documents: AS1554.3 CL5.3 Table 5.3
d2d15eb3-d36c-57d7-9369-4938c9c50645 | note | - - - - - - - - -
3d6c18a8-78a9-518e-b74e-04152ee70960 | note | Inspection / Test Method: Onsite Inspection
3c155d27-fe45-5713-8dbb-b9527b03c3d6 | note | - - - - - - - - -
72092f03-7b63-5b35-8abc-5f06eb042c4f | note | Record of conformity: Signed ITP
946a2adc-d1da-51a9-b938-0fb6340df635 | note | - - - - - - - - -
aea1d238-028a-5016-ab67-c3d227ccf8fb | note | IP
a7c89f36-c339-5a20-97a7-f7015dd18b8a | note | - - - - - - - - -
1a163e37-6aa7-5701-ad2a-74cc9a368ca3 | note | Responsibility: Site Engineer
| checkpoint | 3.4 - Weather Conditions
d3584d8a-3eca-57ec-9c24-daf1d7d0d8c2 | note | Frequency: Ongoing
650be565-fbb3-5549-83f4-25dda23921f3 | note | - - - - - - - - -
5e67bbd0-6fb0-5892-b478-b8d48f48b491 | note | Acceptance Criteria:
8f551892-c6ac-5b7b-a304-7ffcec2ca074 | note | Welds shall not happen when:
22188c59-bf0a-51b2-b6c9-a607b281e3d2 | note | a) Temperature of the metal is colder than 0 degrees
edd47938-331d-51ee-b219-3d6cbb244e4b | note | b) Surfaces are wet. If surface can be dried pre heating is required to 20 degrees
ffba5e07-6187-5f11-a790-8ba06390d39b | note | c) During periods of high winds
4e17e553-8771-5226-9cfb-e29c81ebf6f3 | note | - - - - - - - - -
b8731209-fea4-5517-9bb3-bf10d6916910 | note | Reference Documents: AS1554.3 CL5.5
5fde583a-c98a-59ed-bedc-e6c86cfe6354 | note | - - - - - - - - -
78265d05-4fd5-50da-b8c7-0fe3ae56e7c2 | note | Inspection / Test Method: Onsite Inspection
f85ed06a-d0ea-52b0-82ec-ecbc651f64c3 | note | - - - - - - - - -
c2197cc7-67e8-5808-a6a0-e88b60e6ed0b | note | Record of conformity: Signed ITP
42602167-31bb-5964-82af-1def4c85ea9c | note | - - - - - - - - -
ccc9b0be-0280-54b3-9457-f74df08ebd0b | note | IP
b0d3fa7b-2595-5d12-8fad-6e7a59623512 | note | - - - - - - - - -
0f394a8a-9dd1-595d-8391-06014864f02c | note | Responsibility: Site Engineer
| section | 4 - Testing
| checkpoint | 4.1 - Inspection and Quality of Welds
e2a3f6f0-68f8-539a-addd-899bdb553896 | note | Frequency: As per table 611.141
1c0ec940-b9f9-5424-bc34-0c84e6c26903 | note | - - - - - - - - -
22893580-711f-58d8-9a2f-991344b30ff2 | note | Acceptance Criteria: Testing shall not be less than what is shown in Table 611.141
a4a6ff4c-40f9-594f-b1d3-9eaa0cefcbef | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
b207fbf4-bf7e-5efa-911c-9114b8ef0e8b | note | Table 611.141 Inspection and Quality of Direct Butt Splice Welds
23fbd8a7-a7a0-5d37-87e8-5ecc5cb2d7a0 | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
b263cf13-7e74-539a-b0f5-00c2bda8af20 | note | Inspection Process ¦¦ Minimum extent of inspection (% of welds, as no.) ¦¦ Detail of inspection of direct butt splice welds ¦¦ Quality requirements
f405dd0f-976c-5e68-a855-5c6fd31b8d02 | note | Visual inspection ¦¦ 100 ¦¦ Each full weld circumference ¦¦ AS/NSZ 1554.3, Table 6.2
65bf6977-607a-5867-ad2a-0ff70e42cf5f | note | Non-destructive internal inspection by Radiography ¦¦ First two inspection lots :: 20 ¦¦ with a minimum of 12 bars inspected per lot, and at least 6 of these 12 bars to be examined at two directions, at least 60 degrees apart ¦¦ AS/NZS 1554.1, Table 6.2.1
0e5cbef0-b6fa-567a-ab9e-38c134512427 | note | Non-destructive internal inspection by Radiography ¦¦ Subsequent inspection lots after first two :: 10 ¦¦ If more than one weld in an inspection lot does not comply with the quality requirements, revert to extent of inspection as for the first two inspection lots ¦¦ AS/NZS 1554.1, Table 6.2.1
1e189ceb-eb88-5c12-842f-abc95a14ae4e | note | Non-destructive surface inspection by Magnetic particle, or Liquid penetrant ¦¦ 5 ¦¦ Each full weld circumference ¦¦ AS/NZS 1554.3, Table 6.2
3cd2ed55-6de4-566c-a635-beea37baf3b4 | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
9ad93c50-616f-5230-aa62-d87f5124b87c | note | - - - - - - - - -
88d7fdf8-00e7-5122-bae8-f5e8120f9f6d | note | Reference Documents: VicRoads 611.14 AS1554.3
c614f815-b27d-5bbe-8479-e2d17ebb042f | note | - - - - - - - - -
3d4c051b-ad32-58ce-ad3a-fa1c32cde051 | note | Inspection / Test Method: Test Reports
2cd822ad-b107-54e0-9957-e0ad26cf1106 | note | - - - - - - - - -
9b4aeb1b-5376-5102-8ae8-565a1145eedb | note | Record of conformity: Signed ITP, Test Reports
55aa86c0-837f-5588-87a1-0300b9890c71 | note | - - - - - - - - -
8da4a912-9566-59a0-802b-00be881ba614 | note | IP
510b7e28-1039-5f21-a209-ca90389cf406 | note | - - - - - - - - -
af7c74f4-250f-52ea-b2b9-22014e6e3c8b | note | Responsibility: Site Engineer
| checkpoint | Final Inspection
17636bf7-9129-5ff6-89d3-b1d2a27d3ec1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
091b60b2-909c-5ad2-8081-313cf3df84c3 | textbox | Print Name:
2890f111-051f-523d-adf5-e35526daf37b | textbox | Position:
587950a8-a2e6-5396-b72a-cfc65b6b2c51 | date | Date:
66f1ac2e-8fdd-5bbd-893d-300dbf557031 | date | Work Completed On
| checklist | Order Acceptance Certificate |  | Order Acceptance Certificate - Lot: | 4cd71ef6-21ed-4ca1-ba68-80946fb10a5e
| section | Details
| checkpoint | Order Acceptance Certificate - Details:
58065ea3-8612-5c56-8432-47ef64d09904 | textbox | Subcontractor (full name of Subcontractor, ABN, Subcontractor's ACN and ABN)
4d194c4f-397d-5a14-8033-3e9354c956f0 | textbox | Order No.:
9ce93add-9e77-5a87-a9ae-2781efaf8566 | textbox | Delivery Site:
ebf2fe43-c7e8-505c-8ea2-4b89e51bfd2e | date | Date on which materials delivered:
d59ead29-7e72-530c-a037-cbb30c1badd2 | textbox | Inspecting Engineer:
a9648dd6-9bd3-565a-8a5f-dce3ad077364 | textbox | Delivery vehicle (registration number):
0314a84c-559a-5af5-a302-78b78e87924a | textbox | Subcontractor's delivery personnel (full name)
| checkpoint | The Subcontractor has checked all Materials included in this delivery and is satisfied that all of the Materials comply with the Subcontract.
| section | Packaging Inspection
| checkpoint-no-value | Fault ID:
57862648-3160-5744-bf2b-6247b38359bc | note | OK = Meets all criteria
7896bcff-57a1-5495-afda-0ebcd18e628c | note | QI = Quantity incorrect
6991022e-3bf7-5646-96fd-ec9a67af7a51 | note | IN = Item incomplete
0a338a64-9c7d-5426-9fd6-582c89ed60fd | note | MI = Make or type incorrect
eebf7b66-fc59-5f63-bdf6-9b9915e3596b | note | TD = Damaged in transit
042ce3f9-c548-5b05-96ce-f9c6a16998dd | note | NI = Not properly Identified
| checkpoint | 1)
f57d3e45-df6b-54c9-8ba8-379a7c64116f | textbox | Item ID:
2390d8d8-289d-5d16-99e2-0ff808abe8af | textbox | Item description:
540cf9f0-4d2d-57d8-aa39-bae42a33f7d5 | textbox | Units ordered:
93ebf95c-5f9c-54d0-b45e-994e74e37a2e | textbox | Units delivered:
42cebd35-3343-5e8f-9170-330a49359f76 | textbox | Special Storage/ Handling Requirements?
922aadd7-e14c-5287-8851-1359876c5e2a | note | The following is for completion by Fulton Hogan
0b20ffa1-6f8b-5bd3-a7e6-fdec98ab26e2 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
9fccd442-0f74-50dc-8305-78893ed9a389 | textbox | QA Docs Delivered?
0787c437-9982-5e0e-86d9-b97ee6c91e8d | textbox | Defective?
51a88e12-95f8-5fff-b453-10b4b03401cb | textbox | Number Accepted / Number Rejected?
b945f327-803d-5d15-902b-1c85575b722b | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 2)
ec7199bf-feb9-5e90-97be-684d328a1cd1 | textbox | Item ID:
f9e4cb3c-9473-5e40-a2c2-e70923d63daf | textbox | Item description:
c3daa8d9-c7c4-5179-9336-0899396e8ede | textbox | Units ordered:
4742fa20-0438-5d7e-898c-6c595a21b3c5 | textbox | Units delivered:
f107de2d-a5c8-5149-b1f5-90e8e8d3d6cd | textbox | Special Storage/ Handling Requirements?
839ed013-5b7e-5ade-ae97-03b8618b4ae3 | note | The following is for completion by Fulton Hogan
4720806d-c381-5bf8-a2d2-16c9a437e685 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
4e451557-c45f-569d-8540-cb6e26878f3e | textbox | QA Docs Delivered?
d369c722-6feb-5aee-9cc2-8b829b3cd656 | textbox | Defective?
f9fdd534-8a63-5527-9c6d-050c34dd1a39 | textbox | Number Accepted / Number Rejected?
8e3829d2-87cc-58e2-96c8-680ea4ae5400 | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 3)
491892da-7787-5cb6-8bac-cad0f93324b3 | textbox | Item ID:
58d86e4a-8e72-5545-b9a2-aedf65b284cb | textbox | Item description:
d1833c87-0323-5e16-a70f-b32f13eb0b8b | textbox | Units ordered:
fba80f19-9e21-5453-8c5d-979bf182b596 | textbox | Units delivered:
696b9b56-866e-5fa0-b395-afee5b48523d | textbox | Special Storage/ Handling Requirements?
7d575334-ae0e-51db-b640-f2e74aa6ebe4 | note | The following is for completion by Fulton Hogan
40617772-828a-53d8-b55e-ce2799b7a792 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
90070218-1a01-583e-9077-cdb334de195d | textbox | QA Docs Delivered?
9020b992-289a-57fe-94ef-df0168da81fc | textbox | Defective?
5cbec1b5-4071-5d18-a5e4-23a376e467e7 | textbox | Number Accepted / Number Rejected?
f92324d2-54f7-5df5-9bcb-51b743135c8a | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 4)
21e44a53-1a62-5bf5-b683-d93007c45b7a | textbox | Item ID:
d4f74ff5-5cc2-5526-b59d-d60a0de27263 | textbox | Item description:
a9eb79da-7b7d-530a-af05-0907303ea8f5 | textbox | Units ordered:
18e72d79-3869-5c0b-aafd-7f959a41fcbf | textbox | Units delivered:
974704c5-f543-55fa-927f-61f68b9f1ed4 | textbox | Special Storage/ Handling Requirements?
33ae5019-3337-5961-93bd-ff22ae186f4b | note | The following is for completion by Fulton Hogan
c1f538eb-ce82-54d2-88ba-9e2ca42624f9 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
fe63a6f7-8be7-5cd6-97bd-ef7ea50efd9e | textbox | QA Docs Delivered?
c09b6883-d150-5284-9eac-0d7707f6da50 | textbox | Defective?
9080b640-51d0-50d3-982a-c2b236006c9b | textbox | Number Accepted / Number Rejected?
fb3d9619-861f-5106-aa68-4540d0b26dc1 | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 5)
284b1a53-60d9-576c-8955-22893d9b10e2 | textbox | Item ID:
46baa942-57db-5499-b75d-deb12146093c | textbox | Item description:
606e0602-a544-5e5e-a027-60f3aa3022f9 | textbox | Units ordered:
535b7214-36d5-54b9-9a6f-c5eac24e56ec | textbox | Units delivered:
db12f34d-c190-5a92-adf4-37d13a45e19e | textbox | Special Storage/ Handling Requirements?
2f68fd67-8bad-5ac1-9d8e-a906b7cc7fe1 | note | The following is for completion by Fulton Hogan
183b55a7-abf0-52a0-a8e9-604a9e237f03 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
73055674-b944-56df-8af5-bf8a37e1c586 | textbox | QA Docs Delivered?
73898e67-9d5a-5277-a1a8-5c5ca1e9b326 | textbox | Defective?
3589e069-3367-5262-a3a9-f98f1fa849f5 | textbox | Number Accepted / Number Rejected?
499749d4-a2a5-5ef8-8a2e-3bd17dad96c5 | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 6)
84621ab1-6e37-5cc0-a6ee-642bc17d9207 | textbox | Item ID:
f293b402-5f42-515c-aad1-11d1806c2f7b | textbox | Item description:
ab742d3c-4d92-571e-b208-ef8970747f47 | textbox | Units ordered:
6a069697-dd78-5e2b-bd2e-301e2660d647 | textbox | Units delivered:
bb3ee157-5cd3-5720-a59c-a7f87a1567f9 | textbox | Special Storage/ Handling Requirements?
3b73ef1c-5e99-5193-92a0-b3ba427ab37a | note | The following is for completion by Fulton Hogan
c05580b7-d35e-5440-abca-41cf61335ea8 | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
cd987fb8-f909-5b3a-ab43-73594f16c9d2 | textbox | QA Docs Delivered?
042fce15-dcc8-537e-a1ea-e29c374cd98f | textbox | Defective?
30e6ddd2-bd86-5795-8e63-283e2e4231df | textbox | Number Accepted / Number Rejected?
6d18a629-0b72-589a-94ab-6e9a82433e41 | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 7)
fce2ecd1-66b6-5503-a5f2-a22d76b389af | textbox | Item ID:
a6c4a5f9-0cc5-568e-8327-b920f7aa3d10 | textbox | Item description:
e2383807-a597-5bd0-9087-62dc1a8dac3a | textbox | Units ordered:
b195dac2-1945-54bc-8c23-29f98d6d6480 | textbox | Units delivered:
85861d29-5a3d-5efe-ac08-ee9df461a5ea | textbox | Special Storage/ Handling Requirements?
26d2b5a3-069d-56e1-b656-4e8521c929f2 | note | The following is for completion by Fulton Hogan
2b4baba7-d1be-56d9-9b73-2dc23787057d | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
5117d8a3-704d-5691-9064-ff1c2fca63bb | textbox | QA Docs Delivered?
4eb7dc5d-1867-5a45-abf4-dc8dc030de74 | textbox | Defective?
9cc9900f-3365-5b4e-a202-8e48ab3a022d | textbox | Number Accepted / Number Rejected?
3e76d77a-7a29-5a20-a4ed-e80a5da40182 | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 8)
3d4f15fa-bc39-5fc9-b523-533471dd952f | textbox | Item ID:
ae29e9cf-6241-5de0-9bef-57795adc1eaf | textbox | Item description:
2e5dbd6f-dca9-5072-aa9f-64a5b74276a9 | textbox | Units ordered:
a5feaad5-873c-5b8d-8972-bbcef66695b0 | textbox | Units delivered:
ec51fda0-8c16-5713-bc1c-544a68faf128 | textbox | Special Storage/ Handling Requirements?
a12788d2-11c9-5224-84d3-4bb0894397bb | note | The following is for completion by Fulton Hogan
76adcd53-0909-54ae-98ff-eff1fe221baf | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
5c5d5c2c-4dee-5db8-8c3b-879a69b93f71 | textbox | QA Docs Delivered?
2785ef75-b47a-55a1-af7f-0ac99aeb5287 | textbox | Defective?
795410cc-670b-5ef6-8df1-f17f97d0dbe3 | textbox | Number Accepted / Number Rejected?
20f305b9-aa8a-5e13-a2bd-0c64c6ee8687 | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 9)
d5d733fc-e7d2-5caf-934b-35450dd54b77 | textbox | Item ID:
5ec59114-c110-5b73-8e1e-1f37cb22a1b7 | textbox | Item description:
ddcf35cb-d185-5c48-8c69-0c699ba6f235 | textbox | Units ordered:
dcfad476-f6eb-57e9-b1e8-d54c553a6b27 | textbox | Units delivered:
67e282e9-2c35-56ac-b966-99ac6a5bc06a | textbox | Special Storage/ Handling Requirements?
90806342-9ce5-572b-b7a0-f9a77be2bc98 | note | The following is for completion by Fulton Hogan
ae18d54d-c524-55e9-8ba1-7b69b1dcfd9c | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
1c5f90aa-2ed4-5cab-ad0b-bd45d9401fe6 | textbox | QA Docs Delivered?
2a20e620-e90b-5b06-b14c-d67b876346f8 | textbox | Defective?
8d56e232-2131-515f-b3af-91d14d823e64 | textbox | Number Accepted / Number Rejected?
d4400f5e-f834-5ec5-815c-2190cde90c93 | button | Fault ID: | IN, MI, NI, QI, TD,OK
| checkpoint | 10)
b18f50e4-ecbd-5027-95a5-0a9ccb81a5aa | textbox | Item ID:
1ca9d127-a953-5936-99c4-e1be8829050d | textbox | Item description:
66b8afdb-f9a3-54d0-a6c8-762119445d73 | textbox | Units ordered:
4c6eead5-64aa-565f-89e6-5f2e7353fd63 | textbox | Units delivered:
d261439f-bf67-56af-bbd2-ffde140a1058 | textbox | Special Storage/ Handling Requirements?
c4400991-5478-5ac1-8e57-a327c6dcea63 | note | The following is for completion by Fulton Hogan
28e00e90-ec11-5a89-bd92-26b938250a7f | textbox | Confirmation of receipt of Units delivered. [Subcontractor does not complete. Contractor will initial on receipt.]
98feb4b2-ea3b-596b-8662-037d526213a2 | textbox | QA Docs Delivered?
3130dac8-c315-5395-aa51-da5421b62443 | textbox | Defective?
f4642255-ef5d-5e7c-b989-2b75a11fd02a | textbox | Number Accepted / Number Rejected?
5a4f09a2-358f-505e-8c1e-c671aecc940a | button | Fault ID: | IN, MI, NI, QI, TD,OK
| section | Sign Off
| checkpoint | Accepted by Fulton Hogan
| signoff | Sign Off