## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP 0087 - High Friction and Coloured Surface Treatments | itp | ITP-087-AX-LOT-XXX - Desc |  | 3a120435-3cf8-498d-9216-c384aa5da4c5
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check that current revision drawings are being used
1f03c3ae-eb10-5238-b171-70ebe96c8e3a | note | Frequency: Prior to commencing works
69262882-e277-5f4d-936f-e97219e3f513 | note | - - - - - - - - -
fff9722f-a580-581a-96ab-e67f32cf35de | note | Acceptance Criteria: Issued For Construction (IFC) drawings, & latest available revision used.
c1c4ff69-f5f4-5584-8264-07024af4e0e7 | note | - - - - - - - - -
75f92bec-de06-5977-9834-f8dcdfbf4f2c | note | Reference Documents: IFC Project Drawings, PS3070.07
c35deee4-b5ec-5d5d-8672-02bc5f4ff694 | note | - - - - - - - - -
96275861-671a-521b-a68a-096e5d6ef6ef | note | Inspection / Test Method: Document review
ebce02d9-84de-59a5-9eb7-50671c7992ee | note | - - - - - - - - -
dec0914b-75a9-5df4-b913-ff5d729d1d31 | note | Record of conformity: ITP signed, Latest revision IFC drawings
c7404e51-2a6c-50c1-a47c-80be8caffff4 | note | - - - - - - - - -
9c5501dd-8c46-5831-bad7-0012a152c9fc | note | IP
971b136e-f316-5cb0-ba1a-4da617ec96b2 | note | - - - - - - - - -
1d395255-3e86-5395-b602-8fd043bc3327 | note | Responsibility: Site Engineer / Site Foreman
| section | 2 - Preliminaries - Materials
| checkpoint | 2.1 - Material approval - Binder
16218b56-32d6-50c1-a8a4-704acb5a9a9a | note | Frequency: Prior to commencing site preparation
a9630add-5fd1-5850-91ab-488c912d3519 | note | - - - - - - - - -
4a4354fc-3ec9-5dfe-a02e-a2c38e7d105d | note | Acceptance Criteria: The following primer and binder details shall be provided to the Superintendent at least 14 days prior to the start of works:
40941651-258d-53bd-9ccd-283beab4ed39 | note | (i) priming materials type and source
04b6f190-fb64-50bf-bc8e-749cb8c6ec99 | note | (ii) binder type and source
ce5b4c8c-431d-5779-8d2f-1be1f12b5a3a | note | (iii) manufacturer's recommendations/instructions for priming material supply and placement
7ba4caf7-e9cc-5a65-8cd9-6a1662de9163 | note | (iv) manufacturer's recommendations/instructions for binder mix quantities and tolerances on mixing components
25ea0774-844d-5f04-873e-d2dc3a92453d | note | (v) manufacturer's recommendations/instructions for mixing of binder and components
08f12460-3aae-5ba8-b419-93163ddcafc2 | note | (vi) manufacturer's recommendations/instructions for pot life of binder, i.e. time of mixing to time of spreading
3ed0c2b5-5d5e-50df-8c47-3a7f16188460 | note | (vii) manufacturer's recommendations/instructions for placement of binder including application rates and tolerances and placement temperatures
697a8448-bb24-5952-8f4c-e70650577ae5 | note | (viii) manufacturer's recommendations/instructions for curing
8dc6e536-cfe3-532c-9b39-f65622d86b60 | note | (ix) manufacturer's recommendations/instructions for accelerants (if applicable)
6b227aa5-d71c-5d75-b60e-171348941143 | note | (x) manufacturer's recommendations/instructions for supply and placement of protective sealers
f7294507-d562-5ac6-967a-e96702e32d0a | note | (xi) type of coloured pigment.
ec3b0756-a479-5c97-a82f-570d56d0a4ec | note | - - - - - - - - -
b78bd22f-742e-5526-92fa-1709dd7e5e89 | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.03
a38b9267-8e54-58e4-8535-9ce7da37b07d | note | - - - - - - - - -
f8073321-87ea-5095-8c73-1b587a0fb058 | note | Inspection / Test Method: Document review
d34f69d9-4a69-568d-9420-aec1ca8cbbc5 | note | - - - - - - - - -
d2bb8782-04e4-5bd7-a6bd-1f8bd6199ade | note | Record of conformity: ITP signed, Latest revision IFC drawings
6f5af9b5-bdca-5eb1-a78f-b229347886de | note | - - - - - - - - -
8dfd8dee-bdfc-5a44-9ad9-3ea7f84727de | note | WP
52f5fb8a-ea63-5035-8489-7739d083f45f | note | - - - - - - - - -
e1742401-a74c-53ff-9825-f993f7f4c0a8 | note | Responsibility: Site Engineer/ Superintendent
| checkpoint | 2.2 - Material approval - Aggregate
7e1f5004-b53a-520b-b116-ea57e4521202 | note | Frequency: Prior to commencing site preparation
70e19fed-3c24-5cf5-8e1b-a694d1613e64 | note | - - - - - - - - -
4e921e42-5612-520f-ac92-423c2ddb4531 | note | Acceptance Criteria: The aggregate shall be clean, free from dirt, clay and organic matter, of uniform shape and quality, resistant to fuel and oils spills from traffic, able to withstand traffic stresses without damage, and able to be swept using a mechanical broom and cleaned with high pressure water equipment without damage. The aggregate may be pigmented to provide a colour match of the final product.
76f2993b-e0cf-5ff5-9b37-d14b26e898a2 | note | The following aggregate details shall be provided to the Superintendent at least 14 days prior to the start of works:
bf0292d5-c450-5345-bd29-2bfc25e542f3 | note | (i) aggregate type, source and gradation
6feba2d3-524f-5a1f-bf5f-9c1015effd55 | note | (ii) manufacturer's or Contractor’s recommendations/instructions for placement of aggregate including spread rate
ddaeb815-e849-59fe-8ebf-ea14545d4d4b | note | (iii) Polished Stone Value (PSV) – aggregates shall have a minimum PSV of 54
71fe41cc-6246-51bf-8ff6-165bd8f9685b | note | - - - - - - - - -
b37ab66b-10f0-50f4-8c8b-e3543906789c | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.03
4b028ebf-f41c-518d-ae1c-92668e58a0f2 | note | - - - - - - - - -
847fcfc8-7fd2-519c-8364-94c48a7866fa | note | Inspection / Test Method: Document review
b8ea096f-8e2f-5fef-810e-26b1d382e1b5 | note | - - - - - - - - -
4c623333-783b-54d1-8fb6-482daae40c31 | note | Record of conformity: ITP signed, Latest revision IFC drawings
c46a4975-63a0-55ad-af10-3fb1841d9f55 | note | - - - - - - - - -
353ebc88-92f1-5554-a7ca-00c3f40fe5dd | note | WP
4f7bc645-7401-5e9e-9c42-ec15383624e3 | note | - - - - - - - - -
92be3ddd-b9a9-58d3-a554-245029bc7002 | note | Responsibility: Site Engineer/ Superintendent
| checkpoint | 2.3 - Material - Material safety data sheets
983b3814-7d69-5cc5-bbe4-3ee9ff8fed08 | note | Frequency: Prior to commencing site preparation
59ce7bca-fbe5-52ac-8321-4681e5031119 | note | - - - - - - - - -
ceb0897f-c0f1-52cf-b22d-67ed0599d045 | note | Acceptance Criteria: Copies of Material Safety Data Sheets (MSDS) for priming materials, binders, aggregate coatings, protective sealers and any other work materials shall be provided to the Superintendent prior to the start of works. Any requirements for environmental protection measures as recommended by the material manufacturer shall be undertaken. All materials shall be used and stored in accordance with the manufacturer’s instructions, and MSDSs.
4f50ea48-0fe1-5bfd-9897-65d24ead2d27 | note | - - - - - - - - -
e5bfe9af-7c3a-5455-8b91-735ade3588ea | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.06
c0acbdd0-9ea6-58e5-97a6-20da8f19af48 | note | - - - - - - - - -
cc0abe7e-2f75-50f7-902b-1fc360e22034 | note | Inspection / Test Method: Document review
0218b06a-1f4c-5491-860b-5ace6070a5cd | note | - - - - - - - - -
452078ba-0554-5d04-b694-77628556271c | note | Record of conformity: ITP signed, Latest revision IFC drawings
70b0d14f-458a-5df4-9b3e-6b1acd85c12f | note | - - - - - - - - -
c8894634-93cc-5f90-834b-f209d7394971 | note | WP
1cc60ac1-414b-5d19-8c30-2e1d6b293fe6 | note | - - - - - - - - -
be4453e8-826a-5209-967a-d6b194f0f3f0 | note | Responsibility: Site Engineer/ Superintendent
| section | 3 - Coloured Surface Treatment - Application
| checkpoint | 3.1 - Site preparation
03cdaf9c-421b-56b1-975a-0d3e02671b7f | note | Frequency: Per lot
5753a104-5b79-5391-8b5c-4393a2056904 | note | - - - - - - - - -
7cc7e5ae-803e-5609-b105-b292a53c89fd | note | Acceptance Criteria: All loose material, grit, stones, vegetative matter, and rubbish shall be removed from the area of works prior to placement of the coloured surface treatment. The site may be further cleaned and prepared as required. Cleaning and preparation shall not cause structural damage to the pavement. All cleaning agents and collected material shall be removed from site and disposed in accordance with Environment Protection Authority (EPA) Victoria requirements for the type of waste generated.
24906b64-4eb7-5f3d-b505-f6373a93bbd9 | note | Existing pavement markings shall be masked to ensure the coloured surface treatment is not applied to the markings. All Raised Reflective Pavement Markers (RRPMs) shall be removed from the area of works prior to any coloured surface treatment being placed. New RRPMs shall be reinstated after the application of the coloured surface treatment.
bfc80436-7fab-502b-b1aa-1df6a0540b3c | note | - - - - - - - - -
b1ff4347-1cac-548f-b401-05a0fef0e5ef | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.07
84d7910c-00ea-5f48-96c8-42fc910a5668 | note | - - - - - - - - -
a30a5270-f634-5d51-acec-c6476941a075 | note | Inspection / Test Method: Document review & Site inspection
30c27515-dd1e-53e0-90c9-6cc3011b91bc | note | - - - - - - - - -
4227c6e9-d6e3-527e-8ff3-56f4373a02cc | note | Record of conformity: ITP signed
05b34c78-e007-5f42-929a-09861ba28e4b | note | - - - - - - - - -
9a5dcf3b-3750-5d04-98b5-28ba69ae4b4e | note | IP
46638917-8aae-5f68-b163-0809b90c0a72 | note | - - - - - - - - -
5a5072d0-b05a-5b30-9a22-0a77f345a880 | note | Responsibility: Site Engineer/Foreman
| checkpoint | 3.2 - Site preparation - Service pits, valve covers
e3c0a9ac-c5c0-54ec-9258-97f86d972c9d | note | Frequency: Per lot
e8f14ee0-ff50-525f-81df-fd196ba48e3c | note | - - - - - - - - -
f1a040ef-7e4a-5b24-b752-48086efb5715 | note | Acceptance Criteria: Service pits and valve covers less than 0.03 m2, and drainage grates and frames shall also be masked. Larger pit and valve covers shall be covered with the coloured surface treatment. All lifting mechanisms and joins between the lid and frame shall be masked and protected such that the coloured surface treatment does not impede lifting and replacing lids.
8d76097c-ed0f-539e-9f10-ea476b613387 | note | - - - - - - - - -
2446d0d0-005c-5a06-a327-a5859c873161 | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.07
5cd2fe0a-42e2-5dda-af8e-3380a6c113d3 | note | - - - - - - - - -
8710266e-255b-56dd-b133-81b6f37358fa | note | Inspection / Test Method: Document review & Site inspection
78e8f55e-7578-5f91-97ca-942381f5c107 | note | - - - - - - - - -
a0f7da40-f98a-5ed6-a872-8326072e0e06 | note | Record of conformity: ITP signed
27539d6f-bb9f-54f7-a2ac-42e0443a1ab6 | note | - - - - - - - - -
c4452400-30a9-5828-9fbd-21148d9f5ef5 | note | IP
03e2e89b-4995-5316-aa21-65428ec40a32 | note | - - - - - - - - -
44d3ec8f-3721-5651-8268-a1d29711972f | note | Responsibility: Site Engineer/Foreman
| checkpoint | 3.3 - Site preparation
264ea435-175a-53f0-8e54-5620f7adea36 | note | Frequency: Per lot
1a3eb5d5-9c46-5a6c-8555-3d5cdb3c3a86 | note | - - - - - - - - -
ca9dae38-94e1-53b8-b901-165cdc6a8d68 | note | Acceptance Criteria: The Superintendent shall agree to the method of removal and any pavement repairs for pavement markings and raised refelctive markers (RRPMs) prior to these works occurring.
8248c1d3-9dee-5cdd-953b-2c73ff9fbc6e | note | - - - - - - - - -
87d588da-c9a9-5ec1-9927-0e53873b1ee7 | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.07
4213cd3a-9433-50b1-aad4-f3eaec3f8820 | note | - - - - - - - - -
451a295f-47bc-5f36-aae8-c099f7476153 | note | Inspection / Test Method: Document review & Site inspection
6f5afaed-9d5d-5020-a337-5e6f903f59b4 | note | - - - - - - - - -
3e555779-402d-5d40-b82b-39acfc5a74c5 | note | Record of conformity: ITP signed
1755e3e4-17d3-5695-91aa-39e10f4ea941 | note | - - - - - - - - -
9ec87411-1450-5f62-a608-cbdccd5513a2 | note | HP
93baec7e-5bfb-5f61-98d2-e7346bcc97d2 | note | - - - - - - - - -
8ffadf9b-1c62-5f51-bed1-31688aedcf25 | note | Responsibility: Superintendent
| signoff | HOLD POINT
| checkpoint | 3.4 - Placement - Coloured surface treatments
63461f8b-3f78-55c3-8d2e-36bd7ed9e734 | note | Frequency: Per lot
e08c25bc-f8cf-58b3-94cf-fbc409a79fdd | note | - - - - - - - - -
9d180299-9705-5998-8828-6e9e658073ee | note | Acceptance Criteria: Coloured surface treatments shall not be placed until the Superintendent agrees that the prepared road surface is ready for surfacing.
83b2b7e1-2da7-5eef-b200-8b94c21b654e | note | - - - - - - - - -
44cad2bf-5abb-5781-99b1-65420ee060ab | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.08
be8889ef-1299-55bd-aef8-3095410d010f | note | - - - - - - - - -
812f39ae-51fc-58d5-badf-41fd9aaa1d63 | note | Inspection / Test Method: Document review & Site inspection
988efcad-8a94-598f-8428-3e0d68e9721f | note | - - - - - - - - -
6543893f-559b-54d5-be48-144a42bd4723 | note | Record of conformity: ITP signed
9e0afb8a-4e9f-52ed-88cb-de57557f8c24 | note | - - - - - - - - -
33a626c3-ccfd-581d-9e43-f34652e533ec | note | HP
9797a1eb-45f8-5539-a0cd-e95347f08e5a | note | - - - - - - - - -
74a0f3b6-c0a1-5bbb-ab8f-e353ce6c2b43 | note | Responsibility: Superintendent
| signoff | HOLD POINT
| checkpoint | 3.5 - Placement - Coloured surface treatments
ac713811-f530-5cd9-b958-71c97231b631 | note | Frequency: Per lot
e0c7a76d-aa09-5aa9-8429-e12302a065f7 | note | - - - - - - - - -
1477d4f8-da8f-5fda-a718-aa067d7a993a | note | Acceptance Criteria: Coloured surface treatments shall be applied to produce a visually uniform coloured and textured surface. The edges of the work shall provide a neat and clean line onto the adjacent surface.
7cb10a30-5426-5f80-a3e2-a252588f4e80 | note | - - - - - - - - -
1bc44f6b-8d60-5c37-b0e2-39dd26b51a89 | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.08
0e072deb-03c2-5d64-9d6f-6aa76bf80928 | note | - - - - - - - - -
09692e60-036f-59b2-97d5-7c3fd9d85aeb | note | Inspection / Test Method: Document review & Site inspection
8c4ed13e-a32d-503a-b841-1687d1ec174e | note | - - - - - - - - -
ecfca976-339f-5ef7-a7d6-83c158e5a271 | note | Record of conformity: ITP signed
37435864-f979-5191-a2e3-f60772a4ea71 | note | - - - - - - - - -
f95dc781-60b9-5afb-abb0-7095417465db | note | IP
1beb6d0a-e24c-55dd-91a3-d5b0ea2dfb03 | note | - - - - - - - - -
cd41024b-0fb2-5842-b835-e3de344fc5c6 | note | Responsibility: Site Engineer/Foreman
| checkpoint | 3.6 - Placement - Application rate
b9f34584-08cc-589b-b0cc-d1d82776d428 | note | Frequency: Per lot
b97c0b2a-4052-5d95-8687-ee22feb66a65 | note | - - - - - - - - -
d8722f7d-fdae-5f6c-a5a3-4c667f862a73 | note | Acceptance Criteria: All application rates for the work involving placement of priming materials, binder, aggregates and accelerants shall be provided to the Superintendent.
d7e4034c-18c8-50fe-ac2f-0d33be44e214 | note | - - - - - - - - -
a951558f-1c55-5eef-951b-5760d20c8f85 | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.08
9fb3a048-dd28-59d6-a231-ad922ab1a303 | note | - - - - - - - - -
6c615edc-21ad-5752-b81a-485ad65f510c | note | Inspection / Test Method: Document review & Site inspection
f698b56b-a8d4-5347-a72f-b61ed03be46b | note | - - - - - - - - -
001675f2-b2e3-5cb3-ab40-1b2129ec3edd | note | Record of conformity: ITP signed
933265fa-4f7f-5cbd-84da-764a15135e5f | note | - - - - - - - - -
4b719bb9-ad89-55e5-b092-efdf2cae1bb0 | note | AP
82899055-2155-514e-ad3d-af057763a364 | note | - - - - - - - - -
036a1770-acca-593d-b8f2-ad6ed908dca4 | note | Responsibility: Site Engineer/ Superintendent/FH's Sub-contractor
| checkpoint | 3.7 - Placement - Temperature
443e501d-10ff-5500-90a4-f7a4721b3d5f | note | Frequency: Per lot
a296e072-8e74-5208-97e7-7ff42abfe75d | note | - - - - - - - - -
57520933-38fb-54e8-a98a-2b1e9a52f71f | note | Acceptance Criteria: The pavement temperature of the site shall be measured and recorded at least every 2 hours during the works. The temperature shall be measured using an infrared temperature gauge accurate to +/‑2˚C. The temperature results shall be provided to the Superintendent. All materials shall be placed within any temperature limits recommended by the manufacturer.
10d6731e-bab4-5918-9391-0a8e38cb3428 | note | - - - - - - - - -
9c45fb71-09c9-5279-a8ad-df391eaf9a15 | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.08
8f7123e9-f2b8-554e-8385-3e7dc846684a | note | - - - - - - - - -
d38b7289-0b2d-5f8a-a409-d929744d8267 | note | Inspection / Test Method: Document review & Site inspection
d0f3ab12-7b1d-5b9e-9146-2ee7457c1b0d | note | - - - - - - - - -
4ef3b6cb-8bd4-55a6-877f-3da762099035 | note | Record of conformity: ITP signed
dec1983b-351f-5623-9b57-acc3ee1dfb98 | note | - - - - - - - - -
feba04e6-1496-55d9-ab97-1ec4479e8091 | note | AP
d0c21251-e74d-572c-9543-7d5d736e1cf7 | note | - - - - - - - - -
325c3e86-1a32-5464-9544-e0a86726023f | note | Responsibility: Site Engineer/ Superintendent
| checkpoint | 3.8 - Clean up
782d10b8-6934-5ee1-9a6d-8280fefe1385 | note | Frequency: Per lot
c5bd0bd3-9338-54e6-adcc-423c30317590 | note | - - - - - - - - -
2f5865b6-2246-58a8-b91f-aefe501f4354 | note | Acceptance Criteria: The Superintendent shall agree the site is neat, tidy and free of excess aggregate prior to opening to traffic.
65b65bf5-c1f3-58b6-8293-17ff009305ee | note | - - - - - - - - -
90ae7e6a-502f-5993-902c-7d6c1b6dcb73 | note | Reference Documents: IFC Project Drawings, PS3070.07 VR431.10
3ad7239e-d6eb-5959-a6e0-67b487b2a351 | note | - - - - - - - - -
cbd36203-6614-5181-b63a-3d6382bed158 | note | Inspection / Test Method: Site inspection
4ceb9c5a-625e-5691-949c-6c2b1afedf6b | note | - - - - - - - - -
d92f8990-cf4d-5272-a78c-6a0d3a977ba5 | note | Record of conformity: ITP signed
2520930d-af7e-5206-96db-a6475c65d47a | note | - - - - - - - - -
6efcef38-34cd-54fd-90d2-c4b6e530389f | note | HP
cdd0e8f3-0063-5a00-8540-854c5f2871c9 | note | - - - - - - - - -
263f64d8-f28d-5caf-b110-9d83fc7d4f96 | note | Responsibility: Superintendent
| signoff | HOLD POINT
| checkpoint | 3.9 - Protection of works
502c0fce-770c-575e-9174-fc0b1b909625 | note | Frequency: Per lot
0d4b8cc8-adfa-54e1-895a-417da4e7c92e | note | - - - - - - - - -
527f59a4-0219-5df7-8e9c-ac21c9035151 | note | Acceptance Criteria: Work to be protected by appropriate means until it is trafficable.
672f3650-645a-52a3-b7a7-b30ffc4954c4 | note | - - - - - - - - -
775ab7b6-475a-56e8-84de-d48fe508ec39 | note | Reference Documents: VR721.A11
f43576bb-5ca5-56f2-8313-a5bbd164dd7f | note | - - - - - - - - -
801dfbce-1473-5d64-ab78-57fd557b4c0c | note | Inspection / Test Method: Site inspection
b8683301-065f-53a1-a0f5-84e8394fa173 | note | - - - - - - - - -
36ebeccb-b8a1-5b00-b343-2cfad4d5e0b7 | note | Record of conformity: ITP signed
ca9fc85f-9279-58fa-a2d1-0fb22400f8da | note | - - - - - - - - -
e4901d53-471e-5dc9-927c-1973284703f2 | note | IP
a3557a42-d953-5007-b503-f76b55dcd096 | note | - - - - - - - - -
2d86d3c3-4590-56c2-85d7-01dc7b0a20f8 | note | Responsibility: Site Engineer/Foreman
| section | 4 - Acceptance of works
| checkpoint | 4.1 - Acceptance of works - Surface texture & Testing
2b4d90ee-18e9-56d3-9b82-40fbd61b7dad | note | Frequency: Per lot
9c9a34cc-31dd-51e1-877f-c8fced6cd894 | note | - - - - - - - - -
646fca5f-e5c4-5831-a6fe-bde7872e1227 | note | Acceptance Criteria: Coloured surface treatments shall provide a visually uniform surface with uniform aggregate retention, and be free from delamination, stripping and areas of wear/scuffing. Any work that fails to meet the minimum requirements shall be rectified.
abefa615-aa14-56f9-a53b-66e943051aac | note | Acceptance of work for surface texture shall be based on visual assessment, however in marginal cases the Superintendent may request that nominated areas be tested in accordance with the test method for assessment of surface texture testing as listed in Section 175.
6d50fae0-167f-5724-9645-d9b684b66ae9 | note | A lot will consist of a single batch or area of like work which has been constructed under uniform conditions and is essentially homogeneous with respect to material and appearance. A lot shall be the lesser of one day’s production or each 500 m2.
b0013325-eace-571c-8a82-f46e43995294 | note | The surface texture of each test site within the lot shall be a minimum of 0.6 mm.
56477d41-d350-532d-96b4-4b9336d6c419 | note | Discrete portions of a lot which are non-homogeneous with respect to material and appearance shall be excluded from the lot and either treated as separate lots, or replaced. Where the areas excluded from a lot as non-homogeneous exceed 20% of the total lot area, the whole of the lot shall be rejected.
2bea2a53-4942-5ac4-800d-6e44d51c041e | note | - - - - - - - - -
b52c85fb-05c2-5bea-a7b9-1debe007a0b0 | note | Reference Documents: VR431.11
bf567beb-f148-5e57-a8de-0e9e930712e9 | note | - - - - - - - - -
481b03e5-95ef-57d0-b8ce-bed3ba6e7ec0 | note | Inspection / Test Method: Site inspection
1391edfb-1072-53e8-a051-209a27dd83fa | note | - - - - - - - - -
d7b9035b-d870-5fc7-b2e7-51dd6ba273e7 | note | Record of conformity: ITP signed, Test report
ab8686cb-7d28-56bd-9c67-16a1e3ef0153 | note | - - - - - - - - -
aff213b9-a569-51fa-bf5f-8ceb9d92730e | note | IP
851d67ee-c330-5249-9523-ed9b7ffee3c9 | note | - - - - - - - - -
92e65200-f1e6-53b9-b354-b72c2c1a8449 | note | Responsibility: Site Engineer/Foreman
| checkpoint | 4.2 - Acceptance of colour
e3739aaf-f543-50b7-ada1-cd7aa09c1ae5 | note | Frequency: Per lot
a8159c63-a3e8-55c5-9b30-fed9f3d122e0 | note | - - - - - - - - -
23c09913-46cc-5e1f-a2a7-162cf579be57 | note | Acceptance Criteria: SUP Pram Crossings to be installed as per RDN 03-07 with Golden Yellow (AS colour Y14).
f90c915c-6be2-59e0-9eba-212e77053864 | note | Bus Lanes to be installed as per AS 1742.12 Signal Red R13
001f2d50-8307-5fc3-b7a7-eefae5809057 | note | Bicycle Lanes to be installed as per Table 4311.111 Emerald Green G13
52578996-3bfb-5462-83ec-16933d6f46c1 | note | - - - - - - - - -
cd0c99b3-6018-521a-b8cc-62ab045991a6 | note | Reference Documents: PS3070.07, VR RDN 03-07 VR431.11
04bc9945-735b-57d6-83ba-62577346f5db | note | - - - - - - - - -
73aa2977-079d-56fe-bc60-9d7be622e5b9 | note | Inspection / Test Method: Document review & Site inspection
0d80478b-ed0b-52d1-a706-2d0c2ceb5537 | note | - - - - - - - - -
027c1b1e-37cd-50f4-a56e-8040110f0502 | note | Record of conformity: ITP signed
d9848918-5974-5cea-9f67-17daa2b02b46 | note | - - - - - - - - -
add76e02-8de9-5563-9cb7-d739d3f1e5a7 | note | TP
282997df-f590-5aea-b5f5-dbe9858ef57a | note | - - - - - - - - -
be09ebdc-6075-5c33-a24e-c5f826f40236 | note | Responsibility: Site Engineer
| checkpoint | 4.3 - Testing of Colour
95fdfac8-cad8-5f4a-b037-c4353ce2289a | note | Frequency: Per lot
4a08a9a1-dc51-5886-8bb6-9da0e2a2f308 | note | - - - - - - - - -
71338743-9974-5842-b5e1-76cd10eb6f4a | note | Acceptance Criteria: The colour of the finished surface shall be a Rating 3 Approximate Match (or better) with the approved colour as per item 4.2.
3cc7eb55-58f2-5ccc-a80e-e8fa84c4d21e | note | The initial colour shall be measured in accordance with Australian Standard 1580.601.1:1995. Each lot of material shall be tested within 2 days of placement. Testing shall be undertaken onsite and under daylight conditions only. Each lot of coloured surface treatment shall provide a Rating 3 Approximate Match (or better) with adjacent lots.
db5333cc-4bd6-54bd-b27a-5b71f729b673 | note | - - - - - - - - -
01d4aadb-6ebe-5fc6-a5c5-e5e77df3ede7 | note | Reference Documents: VR431.11
2426e060-5a0b-51bd-b9e7-7e3793366038 | note | - - - - - - - - -
1dc3e746-ef17-51ec-8c08-d34709af4333 | note | Inspection / Test Method: Document review & Site inspection
3e1f4b97-839e-5b73-a493-ced6aa6196a3 | note | - - - - - - - - -
12b3764e-abf1-5930-b508-327ff40d1ed9 | note | Record of conformity: ITP signed
71b208af-ab09-5bf2-9df2-e3fad9a72cae | note | - - - - - - - - -
625af44f-ee71-52b0-bd29-8b4b0fe4549f | note | TP
18a971e5-d016-5d1d-8144-e5a874b132f7 | note | - - - - - - - - -
6b0115d5-4f96-588b-a53b-266e08b55e68 | note | Responsibility: Site Engineer
| section | 5 - Maintenance and repairs
| checkpoint | 5.1 - Repairs - Coloured surface treatment
e91b1db8-07da-528a-8514-9cd52cda40b2 | note | Frequency: Per lot
36180931-2394-5a9c-a490-9265b4320ed9 | note | - - - - - - - - -
0571bdce-302f-5cd4-b9db-8d9d9542d568 | note | Acceptance Criteria: The Contractor shall be responsible for monitoring and maintenance of the coloured surface treatment from the time of placement, until the end of the defects liability period.
6941f3ed-81bb-525f-9916-8e044f98b896 | note | The Contractor shall advise the Superintendent in writing of the proposed treatment for any repairs before undertaking the work.
5f7d2834-ab04-56e1-8e2b-1103b7ba4589 | note | - - - - - - - - -
6efdd876-fac3-5a91-aec5-92b233269832 | note | Reference Documents: VR431.12
f2c7ec50-0695-5cff-a7cc-32990ad06bc7 | note | - - - - - - - - -
20a5d02e-2d40-5f9e-88fc-1f375e7a416b | note | Inspection / Test Method: Site inspection
53760706-e8b1-511a-9889-6dbf714f15cd | note | - - - - - - - - -
a627c7eb-880b-5721-bd8a-92cc1ed252f9 | note | Record of conformity: ITP signed
c1b95761-6a17-5696-8833-d0aacadce120 | note | - - - - - - - - -
62de511e-0e02-523b-9bbd-9ae705dcf6b7 | note | HP
c59ebb3e-74ec-584c-9c35-42c9e670e7f1 | note | - - - - - - - - -
13e43225-eed2-5717-bcad-6a229c4757b7 | note | Responsibility: Superintendent
| signoff | HOLD POINT
| checkpoint | Final Inspection
ccad7d87-43e1-5ee6-9768-6e119d0c0b96 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
6b16ce3f-5df2-54c5-bc08-b5016c8bf759 | textbox | Print Name:
07fd468f-d617-5ba7-b005-3b5ec1a67b46 | textbox | Position:
0bbfd3bb-dae9-5b52-a17d-828d133a4bfd | date | Date:
d5ec86b9-787a-5db1-b5d9-a185e253ca9e | date | Work Completed On