## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-163-CIV-SSB-Rail Delineation Fencing-Permanent
ITP Number |  | 163
ITP Description: |  | SSB-Rail Delineation Fencing-Permanent
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 1
Revision Date: |  | 2024-09-20
ITP created by: |  | Diana Delac
ITP approved for use by: |  | Victor Mira
Special Notes to ConQA Team : |  | ITP for Station Street, Beaconsfield
Inspection & Test Plan - Rail Delineation Fencing-Permanent
[9 empty] | Revision: | 1
[9 empty] | Date: | 2024-09-20
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings L1-CHE-STD-005 L1-CHE-STD-025 VicRoads Section 610 VicRoads Section 630 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Materials
2.1 | Concrete | IFC Drawings Section 610.07 Table 610.071 | Concrete Mix is Registered with VicRoads. 32MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP | SE/Site Supervisor | Supplier Certificate of Compliance
2.2 | Steel Columns, Cladding, Handrails, etc | IFC Drawings AS41000 AS1163 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Supplier Certificate of Compliance
3 | Pre-construction / Pre-installation Activities
3.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. | Measure Visual | Each element | IP | Surveyor SE/PE | This ITP
4 | Construction / Installation Activities
4.1 | Excavation works | IFC Drawings L1-CHE-STD-005 | Excavation for post foundation must not undermine footing of existing structures. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in the rail corridor | Visual |  | IP | SE/Site Supervisor | This ITP
4.2 | Ground Conditions | IFC Drawings | All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required. | Visual | Each post | IP | SE/Site Supervisor | This ITP
4.3 | MTM OHW Structures | IFC Drawings L1-CHE-STD-005 | Fencing must be a minimum 2m away from OHW Structures. Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level. | Measure | Each Overhead | IP | SE/Site Supervisor | This ITP
4.4 | Fence Post Foundation | IFC Drawings L1-CHE-STD-005 | 32MPa concrete. Footing to be a min. 1m clear from proposed TTC footing Typical Footing: Footing dimension 900mm deep, cross section 300mm X 300mm DN80 MS Pipe (88.9 X 4CHS) to be installed full depth. Alternative Strip Footing: 800x800x300mm thick 101.6 x 4.0 CHS sleeve to be cast into footing. 150x150x5 thick base plate welded to sleeve. Refer to IFC drawing for reinforcement details. | Measure | Each footing | IP | SE/Site Supervisor | Post and concrete dockets
4.5 | Fence Post Installation | IFC Drawings L1-CHE-STD-005 | Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays. An individual fence space may be increased to Max. 3100mm locally to avois clashes with services. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line. | Measure | Each post | IP | SE/Site Supervisor | This ITP Concrete Dockets
4.6 | Chain Wire Mesh Installation | IFC Drawings | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire. 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN. | Visual | Each element | IP | SE/Site Supervisor | This ITP Delivery dockets
4.7 | Bracing | IFC Drawings | 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners. | Visual | Each element | IP | SE/Site Supervisor | This ITP Steel delivery dockts
4.8 | Refuge Installation | IFC Drawings | Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located every 20m max. along the fence. 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. | Visual/Measure | Every 20m Max. | IP | SE/Site Supervisor | This ITP
4.9 | Gate Post Foundation | IFC Drawings | 350mm DIA. PILE 1300mm DEPTH 1200mm POST EMBEDMENT 101.6 x 4 CHS GATE POST. 1200 EMBEDMENT 32MPa Concrete | Visual/Measure | Each footing | IP | SE/Site Supervisor | Post and Concrete Dockets
4.10 | Gate Installation - Post | IFC Drawings | 3000mm nominal clear between the gate posts. Minimum offsets from centre of the rail to the fence: 3000mm Alignment tolerance: +20mm to -0 (- being closer to the track) Max. post height 1800mm above ground level. Vertical Tolerance (Hight Risk Areas): ±20mm from the design line. | Measure | Each Post | IP | SE/Site Supervisor | Delivery Dockets
4.11 | Gate Installation - Gate | IFC Drawings | 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED. | Measure | Each Gate | IP | SE/Site Supervisor | Delivery Dockets
5 | Post-construction / Post-installation Activities
5.1 | Fence Height and Track Clearance | IFC Drawings | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | Measure | Each lot | IP | SE/Site Supervisor | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /