## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing | itp |  |  |  |  | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing Rev 1 | aa2068ed-2461-4feb-8e4f-a110771b75e0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-163-CIV-SSB-Rail Delineation Fencing-Permanent
label | ITP Number: 163
label | ITP Description: SSB-Rail Delineation Fencing-Permanent
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 1
label | Revision Date: 20/09/2024
label | ITP created by: Diana Delac
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: IFC Drawings L1-CHE-STD-005, L1-CHE-STD-025, VicRoads Section 610, VicRoads Section 630
section | Materials
checkpoint | 2.1 Concrete
label | REFERENCE: IFC Drawings Section 610.07, Table 610.071
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete Mix is Registered with VicRoads.
label | ○ 32MPa concrete to be used as per IFC drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Mix
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Steel Columns, Cladding, Handrails, etc
label | REFERENCE: IFC Drawings AS41000, AS1163
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | ○ Steel posts to be CHS with a grade of C250
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual and Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: All elements
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 3.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | ○ Offset checked against the running edge prior to installation of posts.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Excavation works
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavation for post foundation must not undermine footing of existing structures.
label | ○ Follow asset owners guidelines for work around their service.
label | ○ Excavation must use Non Distructive Digging in the rail corridor
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY:
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Ground Conditions
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All post (fence and gate) foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 MTM OHW Structures
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fencing must be a minimum 2m away from OHW Structures.
label | ○ Where temporary fence is in proximity of the OHW Structure, the OHW Structure is to be cladded with timber for a minimum height of 2.4m from ground level.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Overhead
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Fence Post Foundation
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 32MPa concrete.
label | ○ Footing to be a min. 1m clear from proposed TTC footing
label | ○ Typical Footing:
label | – Footing dimension 900mm deep, cross section 300mm X 300mm
label | – DN80 MS Pipe (88.9 X 4CHS) to be installed full depth.
label | ○ Alternative Strip Footing:
label | – 800x800x300mm thick
label | – 101.6 x 4.0 CHS sleeve to be cast into footing.
label | – 150x150x5 thick base plate welded to sleeve.
label | – Refer to IFC drawing for reinforcement details.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each footing
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Post and concrete dockets
date | Date Completed:
checkpoint | 4.5 Fence Post Installation
label | REFERENCE: IFC Drawings L1-CHE-STD-005
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Maximum post spacing to be 2.7m ± 250mm, two spans at 1350CTRS at gates, at the ends and at Refuge bays.
label | ○ An individual fence space may be increased to Max. 3100mm locally to avois clashes with services.
label | ○ Minimum offsets from centre of the rail to the fence: 3000mm
label | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
label | ○ Max. post height 1800mm above ground level.
label | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Concrete Dockets
date | Date Completed:
checkpoint | 4.6 Chain Wire Mesh Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Chain-wire mesh 1800x50x2.50 to be fixed to fence post with 1.57mm tie wire.
label | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
label | ○ 3 NO. W10Z TWIN-STRAND 3.15mm DIA. WIRES TWISTED BETWEEN POSTS. TENSIONED TO 1kN.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Delivery dockets
date | Date Completed:
checkpoint | 4.7 Bracing
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | ○ Bracing to be installed on both sides of the fence at the fence corners.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP, Steel delivery dockts
date | Date Completed:
checkpoint | 4.8 Refuge Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Refuge Access to only open from track side.
label | ○ No chain wire mesh to be installed at refuge access.
label | ○ Refuge Access to be located every 20m max. along the fence.
label | ○ 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual/Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Every 20m Max.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.9 Gate Post Foundation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 350mm DIA. PILE
label | ○ 1300mm DEPTH
label | ○ 1200mm POST EMBEDMENT
label | ○ 101.6 x 4 CHS GATE POST.
label | ○ 1200 EMBEDMENT
label | ○ 32MPa Concrete
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual/Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each footing
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Post and Concrete Dockets
date | Date Completed:
checkpoint | 4.10 Gate Installation - Post
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 3000mm nominal clear between the gate posts.
label | ○ Minimum offsets from centre of the rail to the fence: 3000mm
label | ○ Alignment tolerance: +20mm to -0 (- being closer to the track)
label | ○ Max. post height 1800mm above ground level.
label | ○ Vertical Tolerance (Hight Risk Areas): ±20mm from the design line.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Post
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Delivery Dockets
date | Date Completed:
checkpoint | 4.11 Gate Installation - Gate
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 2 NO. 1800mm (H) x 1500mm (W) ROUND TOP GATE
label | ○ MINIMUM 2 NO. FENCE BAYS MUST BE PRESENT EITHER SIDE OF GATE TO ALLOW BRACING TO BE INSTALLED.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Gate
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Delivery Dockets
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 5.1 Fence Height and Track Clearance
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP