## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
8dc3ae88-3f32-5437-9a16-ef8987538cd1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 0 | Level 0 Window No. A0-15 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
5d4dc608-0ce2-5864-8de4-4221d75b1df5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 0 | Level 0 Window No. A0-17 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
c76cf45f-c866-5802-9056-0e99531ad143 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 0 | Level 0 Window No. A0-16 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
4e7428d6-cf3f-5d6c-ab49-76496fb0e224 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B5-05 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
694b4204-d61f-583e-a1d3-d2d1201942b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. A1-16 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
e59e2d6a-8620-5144-9493-129154c04fbd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. A1-26 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
c39b4279-0f88-5ae2-9871-a729027b52d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. A1-15 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
61e59304-6fb8-581e-a451-82d49820c907 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. A1-06 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
c598e64f-ae16-55c8-85ee-ed018c603d29 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. A1-34 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
8bd12243-fdd5-588b-bf2b-f3f6a4647618 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-10 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
10a01a9a-aece-505c-ba61-18bc00c002c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-18 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
ee6ecbe2-63a1-5d1e-921f-9411fe0729ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-05 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
70a803d8-45f0-5b03-88c5-460e6fab31c8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-06 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
81ff0bc4-596c-5c75-bb7a-9af1eac46f47 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
d3523e70-ecd9-51f0-bf12-e744f2faca9d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-27 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
28618a75-4c21-59a1-9a39-11e825d2ccdf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-03 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
a76ff7d4-ec48-5c72-8726-5d90aa38f395 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 1 | Level 1 Window No. B1-02 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
1288aad5-492b-5cdc-a24b-7339afaa96f3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-15 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
beace7a4-22a6-5dbd-89ba-b3647e7562e2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-33 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
594e8915-cc7f-5bab-bd86-e9e4292a6808 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-24 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
67450509-122e-5a8e-a6e8-cd001afb2c90 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-07 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
2ff03c55-8eb4-5146-a5fb-bc687eda2426 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-11 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
40958bfc-fb17-5d3d-b102-f268d87cd74c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-10 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
8a49bcaf-3550-5a68-8e28-7ef060aaee5d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-25 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
fd550d12-7a6e-50b5-a862-98a3ede0db53 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
41f9a1e1-8560-599d-846c-8ca6b9fcdcc0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-31 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
cb486f6c-ab66-53e1-8ca2-abbdcbb08353 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. A2-01 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
db5543fb-204d-59ac-a7e0-4cf44eab4000 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-06 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
fa994b2c-0115-5741-b5d6-f2f359051348 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-01 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
35666fc4-1cf5-5bee-b7c6-363138678076 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-03 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
f18e7f55-6eac-533c-acb5-f9100b7fa350 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-02 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
0334590c-8faf-5f4a-a16f-2414b805d7c9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-19 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
032ec7bb-8a2d-53ea-8db3-7455076fe7ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-05 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
7de79b52-d231-5d78-b7d8-2166df2fb06f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-28 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
0c1a11ae-f667-5fef-8430-5d385032bef3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-29 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
5fb074da-d632-5fef-b639-a5e55b992736 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-34 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
1b5d4ce3-e051-580e-881e-65a78420908d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-20 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
8f64b032-d53e-574f-aa8c-8981d68ad9bf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-05 (H) | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
ac7e3663-c318-54fe-8427-5a7f636e2dad |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-07 (H) | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
402a5f7e-a454-5317-b177-7df781ac7f97 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 2 | Level 2 Window No. B2-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
96c67cad-305c-5980-af35-f8ce8ec00e78 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Skylights | SK-01, SK-02, SK-03, SK-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
e8e3a3ab-b611-5876-9894-c236f0d22491 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-36 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
b801962f-1777-51c2-b92c-f2d6690ec41f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-23 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
2e3c10d8-a6af-5281-b2d8-ab11052881b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-37 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
87a06314-be20-59d0-8206-0963bb8d896b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-27 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
ed390240-a194-522b-81a5-7542cd563fc0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-28 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
ea706ecb-fd57-5090-9286-8585eb8c2e3b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-15 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
1518aea9-8c0c-5da9-b608-df91cbca2be3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-16 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
fa60455e-38b6-50f3-9994-c7e0b3c8c987 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-22 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
bc4c2ed6-b71a-51b8-b85a-abe33eedad80 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-29 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
3e87d8c1-26bb-582a-bbfe-a9d3312097e4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-30 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
c8ef2e0e-cebb-5fdf-bf99-8ed0eeecc05d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-26 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
bbf7ac85-7d92-5c76-b315-f30c36cb278a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 3 | Level 3 Window No. A3-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
258437d6-7cdb-5c44-833a-7ef208970156 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B5-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
33874a11-d282-5c3b-8a50-e5ac3446a6ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B5-03 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
d9333081-ad9e-5078-97c6-ee78995aac32 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B5-11 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
08ecc202-e2df-55c8-a60d-4f96eecd399b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B5-02 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
c0f2c97f-1ccb-5296-9513-0adacfc68016 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B5-08 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
6c3c6f62-1ed0-50ed-bf00-ca0ac556567d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B5-09 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
c781f014-5632-52a5-8288-24deda2ccacb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B5-07, Window Type Z8 15no. In Total | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
df171671-a98a-5313-b383-0c418cc8843b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-03 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
aeb51773-d8ee-59cc-8cea-9670b698188e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-09 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
e8cbc8f6-b070-571e-ba25-790255b4e4ea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-32 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
108f5198-347b-5787-bd70-08c56e9b3e9a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-17 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
34d68a66-e07b-5844-ba47-19e8730e907b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-19 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
31f46b3b-eb13-5cea-bd30-b61cc86a343f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-05 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
00dd8791-2345-5aff-85e4-55132d1205af |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-29 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
47214359-38fd-58bd-875b-b01be18456d2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-33 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
40ffd350-48cf-584c-8023-e607c1693f53 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-27 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
e01ad64a-cf0e-565d-b779-b6932c730707 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-23 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
135d6038-5cd6-5456-88f3-4808c69e5317 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-26 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
85657535-b649-5955-9446-952e13bdc151 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-15 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
01ca9234-2fbf-5413-a4f6-b52d6a2e47db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-18 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
bd95ae7e-681e-5583-bf1e-00f0765c6717 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-02 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
3333468a-8c3f-58f2-ab62-4ba7282eb644 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-06 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
5f39e01a-f5e5-599e-ae99-f3bb40cba1c4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-12 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
72109bc4-5794-5cb7-b78c-b583b77d4c6d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-13 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
50f09e44-425c-5e31-911c-6db46c5153a3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-14 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
ad03c3bc-1f11-5f64-8b36-e9255e834603 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-16 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
81f61252-437e-5687-a238-14793a351ac0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-22 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
6b27c6a8-2c5c-540a-8bbb-ae1f8054dffb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-08 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
4809b02d-05b2-5cbe-96f3-da88f58a7228 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-30 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
90670841-7da1-5941-9655-becf13cf5ffb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-07 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
b0949474-536d-59f5-8eaf-9b66f60f73ef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-20 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
f7417b40-40b4-543e-8aba-5c379d755451 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-25 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
076a23b6-2d63-5aff-9eac-6a13cb34c632 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-11 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
616ca225-4098-5066-ae6b-979cd53c46fa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-10 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
c47bec69-d145-5f79-8bbf-17a7badc8348 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
9ecc55c7-9ad1-541a-ad89-b54dd1b3a38e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-31 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
2797dbf2-b6c9-544c-9b27-ba852817719c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-21 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
9ee3f7f9-7edf-5eb0-bfcf-674acba47809 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-24 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
cb8545e2-c71d-5eee-aead-09770f1f062f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. A4-01 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
e05aed8b-3714-5758-b425-2a142e8b8041 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-04 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
2b664d6d-4e1c-5cc2-a6f6-246bc3a23e0a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-05 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
5995245a-ebc3-51a4-970c-0c27f0c8ce4b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-14 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
a64770ef-2e43-5ec8-9a8a-b1f04f4de51d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-05 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
223bdd1f-29b6-5257-8849-bcf897ab01f5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-12 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
d7c062f8-7d56-520e-ad26-6b82b1447389 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-03 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
0601e0c5-97a4-5a31-91e1-cc88e9274428 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-03 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
9aea6bb7-56f0-542e-8b4c-961eb0d6395c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-07 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
37892939-1bf1-525d-a544-daf7ad4f546b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Level 4 | Level 4 Window No. B4-02 | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.