## Master List Templates
Id | Type | Name | Values | Prompting Name
ddd17450-011e-50d0-b56e-6cf334a3bd57 | checklist | QA - Balustrades |  | - (Item number)
b8669220-f05c-5c4b-b7d8-53f474c050b4 | checkpoint | Glass free from defects as per standards AS/NZS4667:2000
ed58fc66-01ed-5023-9595-f87672c9407e | checkpoint | All stickers, glue and writing removed from glass. Trade clean
4a50d3da-62e8-5c4b-8e7c-6c88d123192d | checkpoint | Installation matches council consented drawings, specification and PS1.
e4a89b08-50b4-53fa-b6c6-0a1100e68af3 | checkpoint | Lagscrews and or bolts have minimum penetration achieved as per PS1 and are at the correct spacings.
9e65a28c-0035-5919-84cb-a7e7a751c0f6 | checkpoint | Threaded rods anchored in concrete have minimum required embedment as per PS1 along with dust removed from holes prior to using the specified chemset. And are at the required spacings.
d9884a22-433b-57ee-80e6-557ef8c866aa | checkpoint | Fixings to steel are the correct size as per the PS1 and at the required spacings.
d3e41dd1-0d84-5940-bdcd-df0cfefadd02 | checkpoint | EPDM washers have been used between different materials.
4dedbbb2-e752-54be-bb95-b6201f2e34b5 | checkpoint | There is no direct contact between metal and glass.
d86aa3aa-c471-59a4-84de-ede67e2d361e | checkpoint | Interlinking panel clamps are fitted and at the same height.
89f16931-988c-59bd-a393-da9797b7982c | checkpoint | Handrail brackets are securely fitted to the glass and handrail fixed back to the building structure.
e94c71c5-01de-54b8-972b-ead61a5a0ca5 | checkpoint | Interlinking rail is correctly fitted and adhered to the glass and fixed back to the building structure.
e71d1884-f722-55b9-90ba-32c12c56c885 | checkpoint | All cover plates are correctly fitted and secure.
4b1e3611-f97a-58c6-ac20-171020f0d18a | checkpoint | Glass in semi frameless posts have the correct amount of edge cover as per the PS1.
28718c23-f47f-5304-a493-95e82b75ecc0 | checkpoint | Semi frameless post are installed at the required spacings and correct fixings used as per the PS1.
6c31c826-2033-5ded-9c27-2b7111b2be4f | checkpoint | Glass panes meet the minimum requirement for both width and height.
9936e838-7962-5590-9aee-3c963b390f63 | checkpoint | Compliance (Toughened, sizing and specification/film inside)
2a76a1d7-5303-5256-b3e3-82a12a0b3b9f | checklist | QA - Frameless Pivot Doors |  | - (Item number)
b8669220-f05c-5c4b-b7d8-53f474c050b4 | checkpoint | Glass free from defects as per standards AS/NZS4667:2000
ed58fc66-01ed-5023-9595-f87672c9407e | checkpoint | All stickers, glue and writing removed from glass. Trade clean
12691482-b677-5500-a8cd-e2fdd9c28c2d | checkpoint | Manually opening and closing properly.
ed9222e2-b4ad-5889-819f-6b81a652ea5e | checkpoint | Floor Spring as specified HO or NHO
081b5af6-0c2d-5633-867f-55c256a06f35 | checkpoint | Floor Spring closing & latching speeds adjusted.
7704d197-0ddc-5e8f-842d-8346ee7fcae2 | checkpoint | Gaps between doors / sidelights, consistent.
f68b2249-198f-5436-b13f-7f99f466f595 | checkpoint | All patch fittings/handles secured tightly and free from damage.
e171dadd-6d0f-5f21-82c4-279c8bdd64d7 | checkpoint | Door rails secured tightly and free from damage.
a2f7d54d-7bfb-5b9f-9661-8a1dcf4eb08e | checkpoint | Lock function not sticking and securing door.
0d054f8e-fed6-5bfd-b31c-7f89b040a2ee | checkpoint | Compliance – Toughened, sizing and specification etc. as per NZS4223 and or Specific Design Statement.
75ede2f7-3446-5b40-bd09-96126c2b728e | checklist | QA - Shopfront/Partition Glazing |  | - (Item number)
714b5f0d-214e-58bd-b4ae-d7b8d5cc1e5a | checkpoint | Glass free from defects as per standards AS/NZS4667:2000.
e8bdfc31-29c5-5d88-bd45-db7da09c0886 | checkpoint | All stickers, glue and writing removed from glass – Trade Clean
2a7f3eb7-7245-5e6c-8dd1-683b48c171e3 | checkpoint | Wedging Finish – no lumps, neat and tidy
db458b7f-5e5a-5925-bbeb-bea3b78e389a | checkpoint | Backing rubber neat and tidy
0f7016ff-cc66-59e8-9c58-77467b4f3729 | checkpoint | Silicon joints neat and tidy. Excess residue removed.
1f557497-6c23-5f25-908c-8787b9c1a5a2 | checkpoint | Heel & Toe Doors.
1c6a3064-9d76-5754-894f-2e59cc8285a0 | checkpoint | Auto Doors operational & commissioned, glass hanging plum / level with clearance.
a06db337-e7e8-576d-aaac-440fc7b34ee9 | checkpoint | Compliance – Toughened, Laminate sizing and specification et. As per NZS4223.
9207cb49-5f9b-5481-a216-df741dc28618 | checklist | QA - Shower/Mirrors |  | - (Item number)
bb8842d3-f4f4-5aed-9469-2d50bd8737f1 | checkpoint | Glass free from defects as per AS/NZS4667:2000. Frame free from defects (Silicon, scratches etc.)
5f80ba35-d7a9-51bc-a96f-d3b0b3c82a3b | checkpoint | Internal channel corners dammed up with silicon to prevent leaking.
ac598f63-6040-56c4-bb14-a4cb320a37b2 | checkpoint | All stickers, glue and writing removed from glass-Trade clean
548737d1-8fec-5e7f-af73-3e09e1d4d276 | checkpoint | Silicon neat and Tidy and no residue left on glass or channel.
8c5ac5e1-1d2c-5168-9407-92935ce735fa | checkpoint | Overpanel installed and secured in place
b08c34b7-9b03-5c59-8097-956aad91cf28 | checkpoint | Doors – Open / close / alignment
070c577c-6081-5cee-8ec5-ce4e7fbc081e | checkpoint | Hinges – Fitted tightly and no loud Squeaking
16119d42-7a13-5c3f-8297-98acfc7c116c | checkpoint | Handle – fit Tightly
e4694f8d-00cb-503d-b3d8-1c3dc15a6ef4 | checkpoint | Compliance (Toughened, sizing and specification)
feca1297-f65b-5e8c-be7d-1bfdbbceac61 | checkpoint | Water test –No water coming out between tiles and channel
fc3a7308-9ae2-599f-91c1-27a1118a561e | checkpoint | Mirror – Installed, endcaps done, free from scratches and or fully adhered to finished wall.
cb850fdb-f3e9-51de-9cfc-c3eea19da385 | checklist | QA - Windows/Doors/Facades |  | - (Item number)
e3b51a1d-8ead-4a69-b125-1f4b76890eeb | section | Details
f695c6e1-b823-53df-b1c1-73cd32636df4 | checkpoint | Glass free from defects as per standards AS/NZS4667:2000 AS/NZS4666:2012
158a86f2-bc7b-51c1-a5c6-c208cacbb24c | checkpoint | All stickers, glue and writing removed from glass -Trade clean.
32ffd941-6526-5d07-9138-d35f39e95a47 | checkpoint | Beads correctly installed.
c4a59bd8-7493-56ed-9e99-ea43654b6f23 | checkpoint | Wedging – Neat and tidy. Not over stretched or cut short.
9b702d1f-8770-518a-b1d1-4a522f8a6900 | checkpoint | Hinge Door fitment with Toe & Heel setting blocks x 4 (Seal in)
fbdfb755-cef9-5ef6-9952-6b02ff0ba352 | checkpoint | Gap – around door is consistent. open/ close freely
f5d5f28d-b3e5-52b1-9827-5c6428928f4c | checkpoint | Sashes fitment & open close.
6cf4287c-8b74-5afb-8db5-c1b2eb44a903 | checkpoint | Slider doors – setting block glue in left/Right
0890116a-e093-57ee-9fb5-599c8241910e | checkpoint | Backing rubber uniform. No creasing
ae78ee3b-94dc-59f4-93a9-c9366a9099fc | checkpoint | Compliance - Toughened, sizing and specification etc. as per NZS4223 and or Specific Design Statement.
84e5124f-24bd-5f59-ab37-083efeede9df | checkpoint | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
152be9e7-7094-4b5c-82fa-3a1d34f52c61 | signoff | Request signoff from Epic
c041c517-f03b-52f3-b734-28fb685d5431 | checklist | Structural Glazing |  | Structural Glazing
ae49d216-ff3e-5787-bc64-b9362ab568fb | checkpoint | Glass free from defects (scratches etc)
b3281b80-93c3-5251-bd08-a97ff3f9584c | checkpoint | All sticker, glue and writing removed from glass - Trade clean
bbc5f7c7-0bd0-506d-9a00-434ec89508d7 | checkpoint | Structural silicon neat and tidy, no blemishes
93a060c2-e27d-5016-932c-e9fef1c1a48d | checkpoint | Step units’ silicon application outside and inside cavity
38563d99-56f7-52a7-96a6-a388d93d71c0 | checkpoint | Silicon applied to the inside of bottom sill if no back painted application
ccdd8b6d-0a37-54f3-8768-8e1936b00e1a | checkpoint | Frames free of Silicon or contamination
7ae2fe7f-438c-507b-92b4-c6cbc7dcc921 | checkpoint | Compliance(Toughened, sizing and specification/film inside