## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
cb850fdb-f3e9-51de-9cfc-c3eea19da385 | checklist | QA - Windows/Doors/Facades |  | - (Item number)
| section | Details
f695c6e1-b823-53df-b1c1-73cd32636df4 | checkpoint | Glass free from defects as per standards AS/NZS4667:2000 AS/NZS4666:2012
158a86f2-bc7b-51c1-a5c6-c208cacbb24c | checkpoint | All stickers, glue and writing removed from glass -Trade clean.
32ffd941-6526-5d07-9138-d35f39e95a47 | checkpoint | Beads correctly installed.
c4a59bd8-7493-56ed-9e99-ea43654b6f23 | checkpoint | Wedging – Neat and tidy. Not over stretched or cut short.
9b702d1f-8770-518a-b1d1-4a522f8a6900 | checkpoint | Hinge Door fitment with Toe & Heel setting blocks x 4 (Seal in)
fbdfb755-cef9-5ef6-9952-6b02ff0ba352 | checkpoint | Gap – around door is consistent. open/ close freely
f5d5f28d-b3e5-52b1-9827-5c6428928f4c | checkpoint | Sashes fitment & open close.
6cf4287c-8b74-5afb-8db5-c1b2eb44a903 | checkpoint | Slider doors – setting block glue in left/Right
0890116a-e093-57ee-9fb5-599c8241910e | checkpoint | Backing rubber uniform. No creasing
ae78ee3b-94dc-59f4-93a9-c9366a9099fc | checkpoint | Compliance - Toughened, sizing and specification etc. as per NZS4223 and or Specific Design Statement.
84e5124f-24bd-5f59-ab37-083efeede9df | checkpoint | Two-sided structural glazing on site (Mullions / Transoms) Cavity free form dust / dirt, Perimeter seal completed. No visible cavities between silicone and tape. Silicone joints are neat & tidy.
| signoff | Request signoff from Epic