## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 003 - Structural Steel | itp |  |  |  |  | ITP 003 - Structural Steel
section | 1.0 Documentation
checkpoint | 1a Construction Drawings
label | Type of inspect / Test and Frequency - All drawings are for construction and latest revision.
label | Acceptance Criteria - IFC Drawings
label | Inspection Responsibility: BCL - I
label | Inspection Responsibility: Client - S
label | Verification Records of Inspection(s) / Test(s) - Drawing Register
checkpoint | 1b Shop Drawings
label | Type of inspect / Test and Frequency - All drawings are for construction and latest revision. (hold Point)
label | Acceptance Criteria - AISC Detailing for Steel Construction
label | Inspection Responsibility: BCL - H
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - Drawing Register
holdpoint | HOLD POINT
section | 2.0 Manufacturing
checkpoint | 2a Structural Steel
label | Type of inspect / Test and Frequency - Confirm structural steel grade is correct
label | Acceptance Criteria - Sec. 19 4.15.1.1 Table 1. Materials
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Manufacturers Mill Certificates
checkpoint | 2b Nuts, Bolts, & Washers
label | Type of inspect / Test and Frequency - Confirm nuts, bolt and washer materials are hot dip galvanised
label | ○ Approved stainless steel components must be Grade A4 (Austenitic 316) strength 70
label | Acceptance Criteria - AS 1214 IFC Shop Drawings Bill of Materials
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Manufacturers Mill Certificates
section | 3.0 Delivery, Storage & Handling
checkpoint | 3a Delivery
label | Type of inspect / Test and Frequency - Check structural steel is undamaged; not misshapen, no surface damage, free from contaminants etc. on delivery
label | Acceptance Criteria - NZS 3404
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Delivery Dockets Photos
section | 4.0 Welding
checkpoint | 4a Nominate Inspector
label | Type of inspect / Test and Frequency - Employ approved independent Welding Inspector.
label | ○ Submit two weeks before fabrication
label | Acceptance Criteria - CBIP
label | Inspection Responsibility: BCL - S
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - N/A
checkpoint | 4b Welder Qualifications
label | Type of inspect / Test and Frequency - Ensure welders are competent and accredited to carry out welding activity prior to construction.
label | Acceptance Criteria - ASME IX
label | Inspection Responsibility: BCL - I
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Welder Qualification Records
checkpoint | 4c Weld Procedure
label | Type of inspect / Test and Frequency - Ensure procedure is Code compliant to weld specification of applicable work being done
label | ○ All welds to be category GP unless category SP nominated
label | Acceptance Criteria - ASME IX
label | Inspection Responsibility: BCL - A
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Welding Procedure
checkpoint | 4d Weld Inspection (Visual)
label | Type of inspect / Test and Frequency - The extent of Non-Destructive examination listed in Sec. 19 4.15.2.4
label | Acceptance Criteria - ASME IX
label | Inspection Responsibility: BCL - I
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Inspector report
section | 5.0 Corrosion Protection
checkpoint | 5a Nominate Inspector
label | Type of inspect / Test and Frequency - Employ approved independent Painting Inspector
label | Acceptance Criteria - CBIP
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - N/A
checkpoint | 5b Preparation
label | Type of inspect / Test and Frequency - Thoroughly clean all surfaces of oil and grease with turpentine, not kerosene.
label | ○ Visual Inspection
label | Acceptance Criteria - Sa 21/2 in S1S 055900
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Galvanising QA Package
checkpoint | 5c Galvanising
label | Type of inspect / Test and Frequency - Apply Zinc coating by hot dip process to give coating weight of not less than 600g/m2
label | Acceptance Criteria - AS/NZS 4680
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Galvanising QA Package
checkpoint | 5d Galvanising Inspection
label | Type of inspect / Test and Frequency - Inspect for defects, misses, etc.
label | ○ Dry film thickness measurements and demonstration that film build up has been achieved
label | Acceptance Criteria - AS3894
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Galvanising QA Package Painting Inspector Report
section | 6.0 Grouting
checkpoint | 6a Grouting Mix
label | Type of inspect / Test and Frequency - 50MPa grout to be used, mixing as per the manufacturer spec
label | Acceptance Criteria - NZS 3404
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Delivery docket
section | 7.0 As-builts
checkpoint | 7a Redline Drawings
label | Type of inspect / Test and Frequency - Redline Structural Drawings Sets post construction
label | Acceptance Criteria - N/A
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - As-Builts