## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
79775255-fe71-4f66-859f-c277be0c1b5e | checklist | Commissioning Workbook |  | Commissioning Workbook
d471eca2-a912-4cd0-b31f-c69b36625174 | checkpoint | Commissioning Workbook
08bd0dee-31ba-5448-96ad-e64f29272d1c | note | Photo or PDF upload of Workbook required
f070204f-76a6-416a-9b5e-7c68c3b7bc5c | checklist | Equipment/System Commissioning Workbook |  | Equipment Commissioning
9d811228-72d7-433a-b8b1-de6056a4ef3c | checkpoint | Completion of all workbook Pre Commissioning Sheets (PCS)
739a398e-2883-5e38-b11c-9f8acc03503a | note | Workbook portion completed
2753729c-5269-5961-a4a5-e628780a0fda | dropdown | Percentage Completed | 0%,25%,50%,75%,100%
636b1654-9ec0-5484-853b-45b8e4aecbd6 | note | Photo or PDF upload of Workbook
deeb00d3-2e81-4ee5-8b79-8e3727a9ed65 | checkpoint | Completion of all workbook Commissioning Sheets (CRS)
b1ef1814-ef55-567b-b4c5-f4d726cf90a9 | note | Workbook portion completed
dc67c195-8cf3-5049-8005-c26f3a53204f | dropdown | Percentage Completed | 0%,25%,50%,75%,100%
6c2d8e2f-099e-589b-b81f-f64bf5a76595 | note | Photo or PDF upload of Workbook
0f36128e-5dbd-438d-96bc-b37e7e2c8429 | checklist | FD Drop test |  | FD Drop test
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e9418188-7474-4efc-afe0-0b12f5847416 | checkpoint | Confirm drop test of F/Ds as per relevant schedule
53e4ea8e-4770-5f76-be9d-cc6f53357483 | note | Photo or PDF upload of relevant schedule required
93374815-0a50-4b30-b816-276134130bc4 | checklist | Fire Damper Drop Test |  | Fire Damper Drop Test
9fc07955-47b4-4775-aaf4-7a62fde80eee | section | Details
4c8b1541-45bb-4e66-ac97-935b104cdfb7 | checkpoint-no-value | Enter Fire Damper designation
a87064b9-a027-582d-a8e5-ff85076dcc2e | textbox | Fire Damper designation
a386689e-7168-4dcb-bb93-ce7836bb72e9 | checkpoint | Photo of ceiling access
effb9543-3ec8-4966-a056-64452a146c97 | checkpoint | Photo of duct access
ea268f05-773e-4a27-928b-cf7defcfe4d5 | checkpoint | Photo of hand touching linkage
642bbfc5-9421-44db-b6b1-19bcfa414b70 | checkpoint | Photo of Fire Damper blades dropped
8d685500-379c-4535-bbc2-08b0351f1fb7 | checklist | NFH-ITP-01 - Mechanical Installation Rough In & Fit Off |  | NFH-ITP-01 - Mechanical Installation Rough In & Fit Off
22e1ebd4-4131-451c-8152-36b512e053f8 | section | Rough In
0e0e449c-51bb-4801-b592-c226cf39ddec | checkpoint | Ductwork/Pipework
fd734c87-4335-5a0f-9a48-ad667768ba0c | note | Ductwork and Pipework installed in accordance with approved IFC Drawings
0e054bdf-1dd2-4006-81d6-06af933d2ede | checkpoint | Ductwork delivered and stored with protective plastic to ensure duct cleanliness.
3d1c8e81-7598-5f54-87de-8bb9f1873804 | note | Photos of all title block/(s) required
f699a951-630b-4908-abec-caaabddc8b34 | checkpoint | Equipment Installed
1b71c90c-9f91-53fe-9bb8-789ebe5a639f | note | Photo of equipment schedule on drawing required
c1af3fb3-8e50-477d-95de-109f88ad187f | checkpoint | Fire Damper Installed
1bc538fb-750b-50f3-bca6-7cdbcf779248 | note | Fire Dampers installed in accordance with manufactures literature and TruSeal advised certification can be undertaken
57293d1e-171f-4e21-9b9d-3b34913f7e0f | checkpoint | Pipework Pressure Tested
ce65aa0c-c939-528f-a44c-a10759edaecc | note | Photo or PDF upload of NFH-ITP-04 required
66af4142-f3bc-41f7-8ff0-0dda6061ea90 | section | Fit Off
85d39323-17f9-4e8f-9ac9-882b343df295 | checkpoint | Registers installed in accordance with approved IFC drawings
7e119d75-3fd1-515a-abb0-f1d1410a2886 | note | Photos of all title block(s) required
1767c746-1fbc-41da-b35f-5d9e11e93728 | checkpoint | Ductwork installed with no open ends and system is internally clean.
bd6fbf23-eabc-4cc3-af81-ee1b916ca4ad | section | Drain Inspected: Sighted and Tested
d0d415b5-79d1-42ec-8f09-7757beb7be3c | checkpoint | Confirm 0.2 L of watter was applied and drained within 1 minute
74e3b49a-6b16-42e8-a7eb-f366274dbc95 | checkpoint | Confirm water drains freely
0a890bc9-7cb2-4902-b1c9-e12a2a37eff6 | checkpoint | Confirm water visibly drains through sight glass
9413005b-5a20-4a2a-ae52-a3f46ea5ac56 | checkpoint-no-value | Add Tested unit Name
8eee6e5f-f3df-50e8-a23a-cf8d60964ab0 | textbox
3626b8d2-66ae-44b8-bfe9-11961c8fa4c0 | checklist | NFH-ITP-02 - Piping Pressure Test |  | Piping Pressure Test
19679366-04c1-4428-ac62-344bb3e1d1e8 | checkpoint | Copper pipe used meets AS1432
5e8b45aa-2a38-5fba-8ba1-155fc18b1b5c | note | (Type A, B and C Copper Tube from DN15 to DN100)
31871b8f-641c-46a6-b844-6cd2237e41e4 | checkpoint | All Viega Press fittings have been marked and crimped
c4910c04-68a3-430a-a22c-efd145b4236b | checkpoint | All welded/brazed joints [steel or copper] have been visually inspected
6074649f-76c6-47a4-aa85-54ba0d14f832 | checkpoint | Details
7813ef98-d57b-5391-82af-f3c62dc50fe8 | textbox | Test Date
18d012ad-ec44-5707-a616-c6577861be80 | textbox | Test No.
9fe521b0-98c7-5d1e-9121-1acc24bcb4ef | textbox | Pipe system under test
fee766ed-ab4f-5e80-89d2-9c9a788c8360 | textbox | Area/Section under test
47dd69ce-c2b6-51c4-b50a-e39e942c1470 | textbox | From
cc7cec26-a3f5-521c-b92f-6b292d10dc36 | textbox | To
be7a13e4-94eb-5165-82dc-d441b623a226 | textbox | System Working Pressure
eff25227-b369-5f69-980f-2f87c03beb08 | textbox | System Test pressure (as per Specifications)
1b260b3f-8ae3-44b9-b6f5-7c30c6b3f7d9 | checkpoint | First Reading
7d3ddc14-5dfd-5ffb-a71a-13697ab9b323 | textbox | Pressure (KPa)
c8bc9f3a-30fa-5b0e-929b-a09d8316dffe | textbox | Time
436b53c8-785a-5428-a6da-913c798a8d6b | textbox | Ambient Temp (Deg Cels.)
4f9f9206-a10d-4f2b-b86c-8b92db3acbeb | checkpoint | Second Reading
247deb09-34ca-56cc-b00a-4f94aaa33831 | textbox | Pressure (KPa)
5ed58343-2e40-5cfa-a191-2e4634f8f97b | textbox | Time
3b9e22a4-1481-5b91-8e7c-cc8edb9c08a5 | textbox | Ambient Temp (Deg Cels.)
2cb1f0e6-8192-4706-b8aa-f7eb7e46c5c5 | checklist | NFH-ITP-04 - Pipe Flushing & Cleaning - Floors, Plant, Risers |  | Pipe Flushing & Cleaning - Floors, Plant, Risers
b473b844-a5ac-46bf-8855-8b4f4a94ebfc | checkpoint | Paper ITP Uploaded below
d2438498-c5c1-471e-ac27-0856e024a4d4 | checklist | NFH-ITP-05 - HVCA DW143/DW144 Duct Leakage Test |  | HVCA DW143/DW144 Duct Leakage Test
a6cca7ee-93b1-4e23-bd67-378e6d1c1599 | checkpoint | Paper ITP Uploaded below
4e30540a-13df-4c3e-a4e9-1816047d5a1b | checklist | Paper Based ITP Uploaded |  | Paper Based ITP Uploaded
60fb82e0-17bd-47c7-9bc5-65ef2c1fe9ad | section | Details
861f4178-3ae6-4c3f-b165-c574ed620693 | checkpoint | Paper Based ITP Uploaded
1afc033b-6cc0-48c1-ab09-77b7d0e9f188 | checklist | Photo / Document Upload |  | Photo / Document Upload
d323b4f4-c1b6-4581-beb1-3e20fd7adc44 | checkpoint | Photo / Document uploaded below
8e0779fd-4328-4404-b577-09aaee3e38a7 | checklist | Subcontractors |  | Subcontractors
5fa57d8b-0026-40af-b532-a98ac4f11faa | checkpoint | Mech Elec ITPs
262d5a17-0c1c-5a1e-b827-9a0e4173cb87 | note | Photo or PDF upload of ITP required
e78cc93c-c694-494a-8371-a49f7a4ecb23 | checkpoint | Fire Certification ITPs
5fbdc195-543c-528f-9335-ca3ea05142bc | note | Photo or PDF upload of ITP required