## ITP-001
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-001
[11 empty] | Revision : 1 | Date :
Client: |  | DTP |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | DMLR Ch. 13.63km Landslide Site |  | Reconstruct Fill |  | Name: | Jack Kay | Name: | Jarrod Rodrigues |  | Name: | Jarrod Rodrigues
Contract No: |  | VRMC |  | Specifications: Nil
|  |  |  | Structure / Component: Roadway & Fill Batter |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Deans Marsh-Lorne Road Ch. 13.63km |  | Date : | 2023-10-26 | Date : | 2023-10-27 |  | Date : | 2023-10-27
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - Using the correct and complete set of drawings - All drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Site Engineer/ Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PMP, EMP, ECP, TMP, SWMS. | PMP, EMP, ECP, TMP, SWMS | Visual Inspection | This ITP signed | HP* | Site Engineer/ Site Foreman | N/A |  | N/A
1.3 | Dilapidation |  | Prior to start | Dilapidation report has been completed prior to establishment of site. | N/A | Verify | This ITP signed | HP* | Site Engineer/ Site Foreman | N/A |  | N/A
1.4 | Installation of sediment and environmental controls |  | Per layer | Adequate sediment and environmental controls have been implemented as per the site EMP & ECP | EMP, ECP | Visual inspection | This ITP signed | IP | Site Engineer/ Site Foreman | N/A |  | N/A
1.5 | Service Identification |  | Prior to start | All services are located and the relevant service authorities have been consulted and permits obtained | DBYD | Verify | This ITP signed | HP* | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Site Setout Survey |  | At Commencement | Setout of excavation and works to be done by DTP Geotechnical Engineer | Design IFC Drawings | Visual Inspection | This ITP signed | HP | Superintendent/ Site Engineer |  |  | N/A
2.1 | Saw cutting |  | Where required | An excavation permit must be issued prior to any saw cutting commencing. Extent and location of cuts to be clearly set out and checked prior to saw cutting | Design IFC Drawings | Visual Inspection | This ITP signed | IP | Site Engineer | N/A |  | N/A
2.2 | Excavation Works |  | During excavation | An excavation permit must be issued prior to any excavation commencing. Excavation operations shall not disturb areas outside the limit of excavation and always remain within the parameters of the Native Vegetation permit. | Exc Permit Native Veg Permit Design Dwg | Visual Inspection | This ITP signed | HP* | Site Engineer | N/A |  | N/A
2.3 | Inspection of the Base of the Fill |  | Post-Excavation | Floor of layers to be free draining towards face (0.5%) or sub-soil drain installed taken to ends of site outletting below toe of works. The Superintendent and Works Supervisor shall inspect sub-grade material prior to placement of rock in accordance with clause 204.04 | 204.06 Vicroads Technical advice | Visual Inspection | This ITP signed | HP | Project Surperviser Geo-Technical engineer |  |  | N/A
2.4 | Benching |  | Each lot | Benches to be cut at widths of 0.7m. Maximum overall excavation angle must not exceed 60 degrees (0.6h:1v). | Design IFC Drawings | Visual Inspection | This ITP signed | IP | Site Engineer/ Site Foreman | N/A |  | N/A
2.5 | Disposal of Material |  | All times | Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible. | Conctract Specification 402.03 | Visual Inspection | This ITP signed | IP | Site Engineer/ Site Foreman | N/A |  | N/A
2.6 | Placement of Rock Fill & Geotextile |  | Per layer | Machinery must be approved weights and only used in staging as detailed for the impact & load assessment. Un-approved machinery cannot be used. Ensure extents of rock fill is wrapped in approved Geotextile layer. | Work Methodology | Visual Inspection | This ITP signed | HP* | Site Engineer/ Site Foreman | N/A |  | N/A
2.7 | Test Rolling |  | Each lot | Base of excavation prepared and test rolled in accordance with Section 173 & 204 prior to placement of geotextile and geogrid. | Section 173 & 204 | Proof Roll | This ITP signed | HP |  |  |  | N/A
2.8 | Placement of 40mm Class 3 Crushed Rock Layers and Geogrid |  | Per layer | Density testing each layer as per section 304 at compaction standard C (not less than 98%). Density Test Results for first to layers to be provided to DTP Prior to placement of remaining layors. Placement of approved non-woven geogrid shall be roller out perpendicular to the centreline with no joints parallel to the centreline. The Geogrid shall wrap around each layer as per drawing (refer section 210 and placed at the base of excavation in conjunction with Geotextile fabric. | Section 173, 204 & 210 | Density Testing/ Visual Inspection | This ITP signed & Test Reports | TP | Site Engineer/ Site Foreman/DPT Geo-Technical Engineer |  |  | N/A
2.9 | Placement of Subase layer 20mm Class 3 Crushed Rock Placed in two equal layers |  | Per layer | Density testing each layer as per section 304 at compaction standard C (not less than 98%) | Section 304 | Density Testing | This ITP signed & Test Reports | TP | Site Engineer/ Site Foreman | N/A |  | N/A
2.1 | Placement of Jute Matting |  | Each lot | Place local topsoil 50mm minimum thickness along the batter of the works and place jute matting over extent of works ensuring jute mat is pinned in place. | Design IFC Drawings | Visual Inspection | This ITP Signed | IP |  | N/A |  | N/A
2.11 | Kerbing |  | During Installation | As Per Kerb & Channel ITP_002 | ITP 002 | Review | This ITP signed & Kerb & Channel ITP | IP | Site Engineer/ Site Foreman | N/A |  | N/A
2.23 | Guardrail |  | During Installation | As Per Guardrail ITP_003 | ITP 003 | Review | This ITP signed & Guardrail ITP | IP | Site Engineer/ Site Foreman | N/A |  | N/A
2.13 | Asphalt |  | During Installation | As Per Asphalt ITP_004 | ITP 004 | Review | This ITP Signed & Asphalt ITP | IP | Site Engineer/ Site Foreman | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.