## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Reconstruct Fill | itp |  |  |  |  | ITP-001 - Reconstruct Fill
section | Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — Using the correct and complete set of drawings
label | — All drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, ECP, TMP, SWMS.
label | REFERENCE DOCUMENTS: PMP, EMP, ECP, TMP, SWMS
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.3 - Dilapidation
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Dilapidation report has been completed prior to establishment of site.
label | REFERENCE DOCUMENTS: N/A
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.4 - Installation of sediment and environmental controls
label | FREQUENCY: Per layer
label | ACCEPTANCE CRITERIA: Adequate sediment and environmental controls have been implemented as per the site EMP & ECP
label | REFERENCE DOCUMENTS: EMP, ECP
label | INSPECTION / TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.5 - Service Identification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: All services are located and the relevant service authorities have been consulted and permits obtained
label | REFERENCE DOCUMENTS: DBYD
label | INSPECTION / TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | Construction Works
checkpoint | 2.1 - Site Setout Survey
label | FREQUENCY: At Commencement
label | ACCEPTANCE CRITERIA: Setout of excavation and works to be done by DTP Geotechnical Engineer
label | REFERENCE DOCUMENTS: Design IFC Drawings
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Superintendent/ Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Saw cutting
label | FREQUENCY: Where required
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any saw cutting commencing.
label | ○ Extent and location of cuts to be clearly set out and checked prior to saw cutting
label | REFERENCE DOCUMENTS: Design IFC Drawings
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation Works
label | FREQUENCY: During excavation
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation and always remain within the parameters of the Native Vegetation permit.
label | REFERENCE DOCUMENTS: Exc Permit Native Veg Permit Design Dwg
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Inspection of the Base of the Fill
label | FREQUENCY: Post-Excavation
label | ACCEPTANCE CRITERIA: Floor of layers to be free draining towards face (0.5%) or sub-soil drain installed taken to ends of site outletting below toe of works.
label | ○ The Superintendent and Works Supervisor shall inspect sub-grade material prior to placement of rock in accordance with clause 204.04
label | REFERENCE DOCUMENTS: 204.06 Vicroads Technical advice
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: Project Supervisor, Geo-Technical engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Benching
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Benches to be cut at widths of 0.7m. Maximum overall excavation angle must not exceed 60 degrees (0.6h:1v).
label | REFERENCE DOCUMENTS: Design IFC Drawings
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.5 - Disposal of Material
label | FREQUENCY: All times
label | ACCEPTANCE CRITERIA: Surplus material, debris and demolished material are to be sorted and transported off site. Material to be kept in condition for re-use where possible.
label | REFERENCE DOCUMENTS: Conctract Specification 402.03
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.6 - Placement of Rock Fill & Geotextile
label | FREQUENCY: Per layer
label | ACCEPTANCE CRITERIA: Machinery must be approved weights and only used in staging as detailed for the impact & load assessment. Un-approved machinery cannot be used.
label | ○ Ensure extents of rock fill is wrapped in approved Geotextile layer.
label | REFERENCE DOCUMENTS: Work Methodology
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Test Rolling
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Base of excavation prepared and test rolled in accordance with Section 173 & 204 prior to placement of geotextile and geogrid.
label | REFERENCE DOCUMENTS: Section 173 & 204
label | INSPECTION / TEST METHOD: Proof Roll
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY:
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Placement of 40mm Class 3 Crushed Rock Layers and Geogrid
label | FREQUENCY: Per layer
label | ACCEPTANCE CRITERIA: Density testing each layer as per section 304 at compaction standard C (not less than 98%). Density Test Results for first to layers to be provided to DTP Prior to placement of remaining layors.
label | ○ Placement of approved non-woven geogrid shall be roller out perpendicular to the centreline with no joints parallel to the centreline. The Geogrid shall wrap around each layer as per drawing (refer section 210 and placed at the base of excavation in conjunction with Geotextile fabric.
label | REFERENCE DOCUMENTS: Section 173, 204 & 210
label | INSPECTION / TEST METHOD: Density Testing/ Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed & Test Reports
label | TP
label | RESPONSIBILITY: Site Engineer/ Site Foreman/DPT Geo-Technical Engineer
date | Date Completed:
checkpoint | 2.9 - Placement of Subase layer 20mm Class 3 Crushed Rock Placed in two equal layers
label | FREQUENCY: Per layer
label | ACCEPTANCE CRITERIA: Density testing each layer as per section 304 at compaction standard C (not less than 98%)
label | REFERENCE DOCUMENTS: Section 304
label | INSPECTION / TEST METHOD: Density Testing
label | RECORD OF CONFORMITY: This ITP signed & Test Reports
label | TP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.10 - Placement of Jute Matting
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Place local topsoil 50mm minimum thickness along the batter of the works and place jute matting over extent of works ensuring jute mat is pinned in place.
label | REFERENCE DOCUMENTS: Design IFC Drawings
label | INSPECTION / TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY:
date | Date Completed:
checkpoint | 2.11 - Kerbing
label | FREQUENCY: During Installation
label | ACCEPTANCE CRITERIA: As Per Kerb & Channel ITP_002
label | REFERENCE DOCUMENTS: ITP 002
label | INSPECTION / TEST METHOD: Review
label | RECORD OF CONFORMITY: This ITP signed & Kerb & Channel ITP
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.23 - Guardrail
label | FREQUENCY: During Installation
label | ACCEPTANCE CRITERIA: As Per Guardrail ITP_003
label | REFERENCE DOCUMENTS: ITP 003
label | INSPECTION / TEST METHOD: Review
label | RECORD OF CONFORMITY: This ITP signed & Guardrail ITP
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.13 - Asphalt
label | FREQUENCY: During Installation
label | ACCEPTANCE CRITERIA: As Per Asphalt ITP_004
label | REFERENCE DOCUMENTS: ITP 004
label | INSPECTION / TEST METHOD: Review
label | RECORD OF CONFORMITY: This ITP Signed & Asphalt ITP
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP