## Checklist Template Builder
Component | Name | Values
checklist | Fit-out - Ceiling
section | Prestart
checkpoint | Verify materials on-site comply with specification
checkpoint | Check proper labeling on materials
checkpoint | Check site condition for suitability (e.g. cleanliness, weather)
section | Safety
checkpoint | Ensure all necessary safety equipment (PPE, scaffolding, fall protection)
checkpoint | Ensure the site is clean and ready for installation.
section | Installation
section | 1. Framing & Structure Check:
checkpoint | Ensure steel framing for plasterboard fixing is straight, aligned, and securely fixed​.
checkpoint | Verify fasteners, brackets, and support hardware are in compliance with structural requirements.
section | 2. Plasterboard Installation:
checkpoint | Install 13mm GIB® Standard Plasterboard for ceilings and bulkheads.
checkpoint | In bathrooms/laundries, install GIB® Aqualine for water resistance.
checkpoint | Use GIB® 90-degree corner trims and shadowline beads at all external and ceiling-to-wall junctions​.
section | 3. Bulkhead & Recess Features:
checkpoint | Construct plasterboard bulkheads in living, kitchen, dining, and bedroom areas, following bulkhead design details​
checkpoint | Ensure proper installation of GIB® stopping beads to exposed board edges in recesses​
checkpoint | Use selected tile finishes in areas that extend into ceiling coving​
section | 4. Lighting & Fixtures:
checkpoint | Ensure proper integration of linear LED strip lighting along ceiling edges as per electrical plans​
checkpoint | Verify cutouts for lighting and other fixtures are accurately placed.
section | 5. Finishing Applications:
checkpoint | Apply Level 4 plaster finish for most areas (standard), and Level 5 finish for areas requiring a higher level of smoothness​
checkpoint | Apply selected paint finish over plasterboard​.
section | Post-Installation
checkpoint | Perform a comprehensive walkthrough to identify any defects or issues.
checkpoint | Complete and accurate installation and inspection documentation.
checkpoint | Engineers/Architects and inspectors Sign-off

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty