## Checklist Template Builder
Component | Name | Values
checklist | Fit-out - Floor Finishes - Park & Garden
section | Prestart
checkpoint | Check apartment details (unit numbers)
checkpoint | Confirm specifications and floor plans
checkpoint | Confirm construction materials used in floor finishes
checkpoint | Ensure proper surface Preparation, including cleaning and level
section | Installation
section | Substrate
checkpoint | Verify installation of 19mm hardie Secura floorboard
checkpoint | Verify the concrete slab is primed (e.g., MXS120 Primer) and ready for installation
checkpoint | Confirm installation of batten and cradle systems (e.g., Acoustiflor, ZZ-5438) for raised floors and soundproofing
section | Waterproofing
checkpoint | Verify correct application of membrane (full coverage)
checkpoint | Check for overlaps and sealing around edges and penetrations
checkpoint | Conduct waterproofing tests in all wet areas
section | Tile Installation
checkpoint | Confirm tiles (TL02 Porcelain, etc.) are installed with appropriate tile adhesive over waterproof membranes
checkpoint | Check installation of chrome floor grates and drainage systems at shower waste points
checkpoint | Verify that aluminum angle finishing trims are installed at the edges of tiled areas
checkpoint | Confirm correct grout color and cleanliness
section | Timber Veneer
checkpoint | Verify correct adhesive, and primer ensuring a smooth and even finish
checkpoint | Check for timber quality, consistent colour, grains and quantity
checkpoint | Check expansion requirements and waterproofing in wet area transitions
section | Carpet Installation
checkpoint | Check seams, stretching and alignment
checkpoint | ensure underlay and carpet thickness
section | Shower System Installation
checkpoint | Confirm installation of Newline Profinish shower trays with the specified adhesive
checkpoint | Ensure shower cradles are trimmed and spaced according to the design (37mm height)​
section | Post Installation
checkpoint | Inspect entire flooring surface for defects
checkpoint | Confirm all floor elements are correctly installed
checkpoint | Compile Subcontractors QA
checkpoint | Archi Engineer SignOff

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty