## Checklist Template Builder
Component | Name | Values
checklist | Fitout– internal Windows and Doors
section | Pre-Start Inspection
checkpoint | Confirm that door and window schedules match the approved project drawings.
checkpoint | Ensure the correct types of doors and windows are delivered (refer to provided schedules for specifics)
checkpoint | Verify that all required hardware and accessories are on-site.
checkpoint | Rough opening height and width. (tolerance +- 10mm)
section | Installation Inspection
section | 1. Alignment and Leveling
checkpoint | Check that all windows and doors are installed level and plumb.
checkpoint | Ensure that the gaps around the frames are consistent and within allowable tolerances.
section | 2. Fixing and Fastening
checkpoint | Verify that all doors and windows are securely fixed as per the manufacturer's guide and specs.
checkpoint | Inspect the use of appropriate screws, bolts, and other fasteners as required.
section | 3. Sealing and Insulation
checkpoint | Ensure that all frames are adequately sealed to prevent air and water ingress.
checkpoint | Confirm that any insulation required around the frames is correctly installed.
section | 4. Fire and Smoke Stop
checkpoint | Smoke stop systems and fire-rated windows are installed according to the fire report rqmts.
section | 5. Hardware Installation
checkpoint | Ensure that all hardware (e.g., locks, handles) is installed correctly and operates smoothly.
checkpoint | Check that all roller doors function as intended without obstructions.
section | Post-Installation Inspection
checkpoint | Confirm that all doors and windows open and close smoothly without binding.
checkpoint | Verify that locking mechanisms engage properly and provide secure closure.
checkpoint | Ensure that all installations are free from scratches, dents, and other damages.
checkpoint | Obtain sign-off from the appropriate parties, confirming that all inspections are passed.

## Template Components
checklist |  |  |  | This is where you specify the name of the checklist. It is a required field on all checklist templates
| section |  |  | This breaks your checklist up into collapsible sections. These are not necessary, but when used, each section must contain at least one checkpoint.
|  | checkpoint |  | This is a necessary component, all checklist templates must include at least one checkpoint. A checkpoint is where you can set the status, add comments and attach files.
|  | checkpoint-no-status |  | This can be used the same way as a checkpoint, the only difference is that it does not have a status attached. You might use this when you want to attach photos but not have them linked to a PASS/FAIL
All of the below datapoints must be attached to a checkpoint. You do this by simply making sure there is a checkpoint in your checklist template. The data point will then attach to the above checkpoint.
|  |  | button | You can set specific button values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: 1, 2, 3)
|  |  | date | Provides a date input box with a calendar picker to select a date
|  |  | dropdown | This gives multiple specific answer types, of which only one (or none) can be selected at time. Specify these in the 'values' column, separating each with a comma (e.g: One, Two, Three)
|  |  | signoff | This prompts for a signature to be added, either on site, or a digital request for a signature to be sent via email to someone off site. If required these can be made mandatory.
|  |  | label | This is a text label that shows under the parent checkpoint
|  |  | number | A short text field allowing for only numerical input
|  |  | radio | You can set specific response values, of which only one can be selected at a time. Specify these in the 'values' column, separating each with a comma (e.g: A, B, C)
|  |  | note | A free text input field that allows users to write notes and add comments to the above checkpoint
|  |  | tickbox | Add a single check box that can be checked or left empty