## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Facade - Balustrades
section | Pre-start
checkpoint | Clean work area
checkpoint | Verify site is prepared according to approved design
checkpoint | Glass Panels: Verify thickness, type (laminated/tempered),
checkpoint | Aluminium Panels: Confirm grade (6063 T6), powder-coated finish, and corrosion resistance
checkpoint | Slat Profile Balustrades: Ensure proper slat spacing and use of stainless steel screws (grade 316)
section | Installation
checkpoint | Confirm Handrail height
checkpoint | Confirm Baluster spacing requirements
checkpoint | Ensure proper Anchoring, appropriate screws, botls, connectors.
checkpoint | Ensure sealing with Sikaflex® AT-Facade or equivalent sealant for weather and air protection, as detailed in the specifications.
checkpoint | Architectural Eng inspection report received and close-out
section | Post Installation
checkpoint | Ensure required documentation. (test reports and compliance certifications provided)
checkpoint | Conduct comprehensive walkthrough to verify overall quality and compliance
checklist | Facade - Glazing and Doors
section | Pre-Start
checkpoint | Confirm all relevant drawings, schedules, and specifications are available and reviewed.
checkpoint | Verify glazing and door specifications from the schedule.
checkpoint | Ensure the site is prepared and clear for installation.
checkpoint | Check for adequate access for delivery and installation of glazing and doors.
checkpoint | Verify that all required materials (glazing, doors, frames, seals, etc.) are on-site and match the specifications:
section | Installation
section | 1. Glazing
checkpoint | Check the frame for correct alignment and secure fixing.
checkpoint | Inspect glazing materials for any damage before installation.
checkpoint | Ensure glazing units are installed with appropriate spacers and seals.
checkpoint | Ensure the steel framed fire-rated window system meets fire rating requirements.
checkpoint | Verify the glass type and thickness (e.g., acoustic, fire-rated) is as per the glazing schedule​
section | 2. Doors
checkpoint | Ensure frames are correctly positioned and securely fixed.
checkpoint | Check doors for damage before installation:
checkpoint | Check roller doors for damage before installation.
checkpoint | Confirm that fire-rated doors meet the fire rating requirements
checkpoint | Verify fire-rated and egress doors meet specified requirements.
section | 3. Seals and Flashings
checkpoint | Check that all seals and flashings are installed as per specifications.
checkpoint | Ensure water and air tightness are maintained around all openings.
section | 4. Hardware and Operation
checkpoint | Ensure that all hardware (e.g., locks, handles) is installed correctly and operates smoothly.
checkpoint | Verify that doors open and close smoothly without obstruction.
checkpoint | Ensure locking mechanisms function correctly.
section | Post-Installation Checks
checkpoint | Check for any signs of damage or defects.
checkpoint | Test all doors for proper operation, including roller doors.
checkpoint | Verify that glazing provides the required performance (e.g., thermal, acoustic).
checkpoint | Remove any protective films from glazing.
checkpoint | Installer QA received
checklist | Fit-out - Ceiling
section | Prestart
checkpoint | Verify materials on-site comply with specification
checkpoint | Check proper labeling on materials
checkpoint | Check site condition for suitability (e.g. cleanliness, weather)
section | Safety
checkpoint | Ensure all necessary safety equipment (PPE, scaffolding, fall protection)
checkpoint | Ensure the site is clean and ready for installation.
section | Installation
section | 1. Framing & Structure Check:
checkpoint | Ensure steel framing for plasterboard fixing is straight, aligned, and securely fixed​.
checkpoint | Verify fasteners, brackets, and support hardware are in compliance with structural requirements.
section | 2. Plasterboard Installation:
checkpoint | Install 13mm GIB® Standard Plasterboard for ceilings and bulkheads.
checkpoint | In bathrooms/laundries, install GIB® Aqualine for water resistance.
checkpoint | Use GIB® 90-degree corner trims and shadowline beads at all external and ceiling-to-wall junctions​.
section | 3. Bulkhead & Recess Features:
checkpoint | Construct plasterboard bulkheads in living, kitchen, dining, and bedroom areas, following bulkhead design details​
checkpoint | Ensure proper installation of GIB® stopping beads to exposed board edges in recesses​
checkpoint | Use selected tile finishes in areas that extend into ceiling coving​
section | 4. Lighting & Fixtures:
checkpoint | Ensure proper integration of linear LED strip lighting along ceiling edges as per electrical plans​
checkpoint | Verify cutouts for lighting and other fixtures are accurately placed.
section | 5. Finishing Applications:
checkpoint | Apply Level 4 plaster finish for most areas (standard), and Level 5 finish for areas requiring a higher level of smoothness​
checkpoint | Apply selected paint finish over plasterboard​.
section | Post-Installation
checkpoint | Perform a comprehensive walkthrough to identify any defects or issues.
checkpoint | Complete and accurate installation and inspection documentation.
checkpoint | Engineers/Architects and inspectors Sign-off
checklist | Fit-out - Floor Finishes - Park & Garden
section | Prestart
checkpoint | Check apartment details (unit numbers)
checkpoint | Confirm specifications and floor plans
checkpoint | Confirm construction materials used in floor finishes
checkpoint | Ensure proper surface Preparation, including cleaning and level
section | Installation
section | Substrate
checkpoint | Verify installation of 19mm hardie Secura floorboard
checkpoint | Verify the concrete slab is primed (e.g., MXS120 Primer) and ready for installation
checkpoint | Confirm installation of batten and cradle systems (e.g., Acoustiflor, ZZ-5438) for raised floors and soundproofing
section | Waterproofing
checkpoint | Verify correct application of membrane (full coverage)
checkpoint | Check for overlaps and sealing around edges and penetrations
checkpoint | Conduct waterproofing tests in all wet areas
section | Tile Installation
checkpoint | Confirm tiles (TL02 Porcelain, etc.) are installed with appropriate tile adhesive over waterproof membranes
checkpoint | Check installation of chrome floor grates and drainage systems at shower waste points
checkpoint | Verify that aluminum angle finishing trims are installed at the edges of tiled areas
checkpoint | Confirm correct grout color and cleanliness
section | Timber Veneer
checkpoint | Verify correct adhesive, and primer ensuring a smooth and even finish
checkpoint | Check for timber quality, consistent colour, grains and quantity
checkpoint | Check expansion requirements and waterproofing in wet area transitions
section | Carpet Installation
checkpoint | Check seams, stretching and alignment
checkpoint | Ensure underlay and carpet thickness
section | Shower System Installation
checkpoint | Confirm installation of Newline Profinish shower trays with the specified adhesive
checkpoint | Ensure shower cradles are trimmed and spaced according to the design (37mm height)​
section | Post Installation
checkpoint | Inspect entire flooring surface for defects
checkpoint | Confirm all floor elements are correctly installed
checkpoint | Compile Subcontractors QA
checkpoint | Archi Engineer SignOff
checklist | Fitout – Internal Windows and Doors
section | Pre-Start Inspection
checkpoint | Confirm that door and window schedules match the approved project drawings.
checkpoint | Ensure the correct types of doors and windows are delivered (refer to provided schedules for specifics)
checkpoint | Verify that all required hardware and accessories are on-site.
checkpoint | Rough opening height and width. (tolerance +- 10mm)
section | Installation Inspection
section | 1. Alignment and Leveling
checkpoint | Check that all windows and doors are installed level and plumb.
checkpoint | Ensure that the gaps around the frames are consistent and within allowable tolerances.
section | 2. Fixing and Fastening
checkpoint | Verify that all doors and windows are securely fixed as per the manufacturer's guide and specs.
checkpoint | Inspect the use of appropriate screws, bolts, and other fasteners as required.
section | 3. Sealing and Insulation
checkpoint | Ensure that all frames are adequately sealed to prevent air and water ingress.
checkpoint | Confirm that any insulation required around the frames is correctly installed.
section | 4. Fire and Smoke Stop
checkpoint | Smoke stop systems and fire-rated windows are installed according to the fire report rqmts.
section | 5. Hardware Installation
checkpoint | Ensure that all hardware (e.g., locks, handles) is installed correctly and operates smoothly.
checkpoint | Check that all roller doors function as intended without obstructions.
section | Post-Installation Inspection
checkpoint | Confirm that all doors and windows open and close smoothly without binding.
checkpoint | Verify that locking mechanisms engage properly and provide secure closure.
checkpoint | Ensure that all installations are free from scratches, dents, and other damages.
checkpoint | Obtain sign-off from the appropriate parties, confirming that all inspections are passed.