## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
f045854b-354e-40db-a8f2-e2a000f63931 | checklist | Refurb Checklist |  | Refurb Checklist
a4107dc9-2d6e-4350-b47b-9895691cfa75 | section | Disconnection/Isolation
f5db2670-09f9-4c32-b4ca-6a26bb9aded1 | checkpoint | Current locations of Plates and Cabling (Attach Photos)
ca29c836-74fc-426e-b364-1530377b7803 | checkpoint | Disable Nurse Call in the Edge/ECall System
e6f2b623-3405-47a1-8a8b-f0d3b3baa121 | checkpoint | Area is left clean and tidy (Attach Photos)
31895bd1-ec28-48a1-819e-a02da53793f9 | section | First Fix
6c0137d9-bb90-46dd-ab48-9efef8611cda | checkpoint | Approval to start work is obtained
1731534a-11ca-4ac1-9722-451d733e6697 | checkpoint | Install/Re-route cabling to new positions (Attach Photos)
da4d91e3-d843-4afc-9a57-fbb9b0623789 | checkpoint | Area is left clean and tidy (Attach Photos)
fb234bd9-5e09-45dc-b06f-862971921377 | section | Second Fix
227d13df-1c14-4da5-a6c9-d8e1a654b580 | checkpoint | Approval to start work is obtained
eea7a7bb-43c0-4f24-a248-c432114df2f1 | checkpoint | Install Call Points/TV/Data Plates (Attach Photos)
fbaa23f1-6789-4536-af28-6669d8aa1660 | checkpoint | Nurse Call tested through Edge/Displays and Pagers
8918e30c-c8df-4b0c-a2a6-541ed8e8b306 | checkpoint | Bedroom 1 - Button
98aa720e-5b7e-5d5e-a71e-262f69a334b3 | button | Enabled | Yes,No,N/A
34951df6-1cf7-5d5a-9b41-3772457d8c88 | button | Shows on Edge | Yes,No,N/A
572f3886-6409-5a18-99b8-f0b0c37768c7 | button | Displays Assignments | Yes,No,N/A
e60b9551-9d34-5bb4-ad46-36e0484a2e25 | button | Shows on Pager | Yes,No,N/A
6845fb5d-186f-496a-80cb-cc4ab8439431 | checkpoint | Bedroom 1 - Pendant
384d7b41-2372-5805-a9da-de2d42d939e5 | button | Enabled | Yes,No,N/A
d093058a-4f31-5dda-86fa-e662adcccecb | button | Shows on Edge | Yes,No,N/A
916cac20-c86d-54ca-b990-8a4736bd3464 | button | Displays Assignments | Yes,No,N/A
bc07e39f-d088-500a-a2c0-7e27b67a6b08 | button | Shows on Pager | Yes,No,N/A
4ddc11af-15a2-438f-b97b-9fc4fb01e5d6 | checkpoint | Bedroom 1 - Pullout Alarm
59e1d2d6-c127-53a9-8da2-266341506556 | button | Enabled | Yes,No,N/A
e9fea242-0092-5141-9e0a-4ddf8eeecd85 | button | Shows on Edge | Yes,No,N/A
1af47db3-617a-5ad8-b167-d90a4fc0b726 | button | Displays Assignments | Yes,No,N/A
a5809edd-3e3d-5189-9782-0885cda9756f | button | Shows on Pager | Yes,No,N/A
47f7bf4d-1ea2-4483-975e-c705eb0618fc | checkpoint | Bedroom 2 - Button
d2c139a4-17f9-5415-a24c-26ed29e1c749 | button | Enabled | Yes,No,N/A
e0f6efd2-b6e5-5002-bc56-be53ae64c7bd | button | Shows on Edge | Yes,No,N/A
84a91c86-1b53-52ec-bd2c-d194156ad5b5 | button | Displays Assignments | Yes,No,N/A
1032319f-0974-5781-8dff-87b8789b1cea | button | Shows on Pager | Yes,No,N/A
0f9885d4-b708-4e00-96e7-a36624ea2fe8 | checkpoint | Bedroom 2 - Pendant
4791e866-fcce-5bdd-935e-ff6c2bfe0692 | button | Enabled | Yes,No,N/A
8f00c66d-abcf-538a-a2f1-e066b03a10a2 | button | Shows on Edge | Yes,No,N/A
79a4645e-fccb-51f2-9f0b-7235402fbed6 | button | Displays Assignments | Yes,No,N/A
3855400a-9f0c-5b17-ab64-087449432b21 | button | Shows on Pager | Yes,No,N/A
c7e0afa1-79e4-4356-8633-5135e96de242 | checkpoint | Bedroom 2 - Pullout Alarm
aff5ed42-edb1-52b8-9081-5feb8933d04f | button | Enabled | Yes,No,N/A
8a4a07ff-cc37-518d-b898-2c96123a31de | button | Shows on Edge | Yes,No,N/A
92ead883-5ba4-5f3d-90fc-81482fc0c7bc | button | Displays Assignments | Yes,No,N/A
ab57e668-69f4-5bc8-91ee-fe127c4acada | button | Shows on Pager | Yes,No,N/A
5809a8cc-89ad-4f39-87b7-8395ec889c2f | checkpoint | Bathroom - Toilet Button
607c5954-72b6-526a-97ac-adfeda8310ae | button | Enabled | Yes,No,N/A
a5d39670-c52d-5c83-8f7c-18955f035a25 | button | Shows on Edge | Yes,No,N/A
6f4278bd-c75d-58ea-8f72-889ca2e0e115 | button | Displays Assignments | Yes,No,N/A
b5d3ec63-ee4a-5990-b1ef-85d4f556bab1 | button | Shows on Pager | Yes,No,N/A
80294e3a-ce3d-42e2-91a9-b2fa2f2d32a1 | checkpoint | Bathroom - Pullcord
5349ba61-513c-5b2a-834f-7cc95e9ae4d7 | button | Enabled | Yes,No,N/A
e05e1693-4e58-5996-afec-6cf5dd6fe35f | button | Shows on Edge | Yes,No,N/A
69045564-1b1c-5dc0-97b3-b09d9aa7bf77 | button | Displays Assignments | Yes,No,N/A
a5c919f3-8586-505d-9ada-c837f69c9c23 | button | Shows on Pager | Yes,No,N/A
3dfc13d8-560d-41c4-a248-9a9fbe9b6d89 | checkpoint | Toilet - Button
f984193f-0c51-556f-86cc-25257f6a5c48 | button | Enabled | Yes,No,N/A
3f626770-dc1e-5c6f-9470-cb8cc4e94f63 | button | Shows on Edge | Yes,No,N/A
7af20dde-807e-5044-bdb0-397527f63ea2 | button | Displays Assignments | Yes,No,N/A
70672b92-8fb5-5d3a-aed8-20093a5c5e41 | button | Shows on Pager | Yes,No,N/A
d24ac5ee-c10b-4425-8bc1-1b781b0b2e77 | checkpoint | Kitchen/Living Space - Nurse Presence
a5477d7c-3a58-5aa4-938f-5d2e1055d52c | button | Enabled | Yes,No,N/A
56a5343e-8495-55a7-856f-44d429bddf62 | button | Shows on Edge | Yes,No,N/A
88b8ee94-ef11-5af6-93b9-7facac5a1df9 | button | Displays Assignments | Yes,No,N/A
8dbb0506-e6c0-5014-a9aa-3d34e14952e7 | button | Shows on Pager | Yes,No,N/A
13afb468-bb0e-4a8b-836f-8b407e5ec0e4 | checkpoint | Never Alone PIR
b72e40db-6493-5182-bcea-f9ade0486a03 | button | Enabled | Yes,No,N/A
1b82dea0-7321-5b70-84c2-87b48235883b | button | Shows on Edge | Yes,No,N/A
91318d18-906c-5de2-b03b-74f3503d38a5 | button | Displays Assignments | Yes,No,N/A
8b39ba0e-1539-5283-b700-c631a8ca90e9 | button | Shows on Pager | Yes,No,N/A
3e89a15e-a78c-4ba2-aeb3-21320f5cf5a1 | checkpoint | Additional Call Points - Please note location
4658c1a4-35dc-5408-861d-65400755125d | button | Enabled | Yes,No,N/A
9c32807f-099c-589a-ba84-0f2614fcaed1 | button | Shows on Edge | Yes,No,N/A
3aa8ad36-d81d-5d66-ac10-c23a444aa3ff | button | Displays Assignments | Yes,No,N/A
5234ba43-6576-5a61-8d0e-b1781471edb4 | button | Shows on Pager | Yes,No,N/A
29e6b0c2-3a0e-4290-914e-0aa64c54cf1d | checkpoint | MATV/Data tested and commissioned
236aff3d-e2e3-480c-9c0e-76e475fe6adb | checkpoint | Smoke Alarms installed and tested (Attach Photos)
a2164117-ff14-44df-86fe-f7ad369a4d5c | checkpoint | Area is left clean and tidy (Attach Photos)
1a8ac4c3-b21e-4ae9-bc97-f3b4573800b4 | checklist | Refurb Checklist (Second Fix) |  | Second Fix (Bedroom 1 to Never Alone PIR/Additional Call Points)
c37c4b02-f54c-4ada-945a-04b9e828472f | section | Details
3ef6a7c5-4512-4eae-b270-1b179d55fe5d | checkpoint | Bedroom 1 - Button
cb7c7bd6-3386-5d4e-8014-a2b672395f29 | button | Enabled | Yes,No,N/A
449a129d-b2df-5130-a6d0-8785d1bf2e22 | button | Shows on Edge | Yes,No,N/A
1e7a877d-b31a-5800-81b8-18620d103bab | button | Displays Assignments | Yes,No,N/A
bf12ef45-9fa2-53c6-b96b-91bd67457bfa | button | Shows on Pager | Yes,No,N/A
bface443-2d08-4479-a6b5-431fdb83f2ab | checkpoint | Bedroom 1 - Pendant
4c6c45ab-8efd-51c8-8827-8fe591d0e569 | button | Enabled | Yes,No,N/A
1a6325fe-2b36-595d-b67f-c77048911120 | button | Shows on Edge | Yes,No,N/A
e2573110-4e0e-5588-bdc9-21af249b7881 | button | Displays Assignments | Yes,No,N/A
297c3f5f-80b6-5488-909d-49e7acd8a68a | button | Shows on Pager | Yes,No,N/A
583e228f-2a08-40b0-84a0-c68e9ca7a1cb | checkpoint | Bedroom 1 - Pullout Alarm
a5035fc9-b71b-5634-be90-b16acc9db221 | button | Enabled | Yes,No,N/A
913bb977-a7fb-5b33-8862-4b875659f324 | button | Shows on Edge | Yes,No,N/A
3ca86fbe-5bf5-5777-9f42-5e9aa476fa77 | button | Displays Assignments | Yes,No,N/A
711f3863-4b61-5402-8319-c472446bee8a | button | Shows on Pager | Yes,No,N/A
460fc388-ce07-4b4e-ab8a-144dd75d820f | checkpoint | Bedroom 2 - Button
9f19214e-2216-5997-8d76-c559a0a76b28 | button | Enabled | Yes,No,N/A
34f43868-ca4e-55cc-856c-7ceb79d184bf | button | Shows on Edge | Yes,No,N/A
d19d31e5-eb4c-55e5-b7e0-4c6b72d5c280 | button | Displays Assignments | Yes,No,N/A
0c75fc95-f092-5a4b-b6f4-2427854812c6 | button | Shows on Pager | Yes,No,N/A
846ac083-e026-4bce-9554-43358268b9be | checkpoint | Bedroom 2 - Pendant
42094dd2-2ce6-5e94-8793-1140307323c8 | button | Enabled | Yes,No,N/A
1fe1749a-5494-5273-aa3b-63862585f6a2 | button | Shows on Edge | Yes,No,N/A
c5676d01-9b99-58ef-bb7b-80723c3ea533 | button | Displays Assignments | Yes,No,N/A
88c5ee56-2fcb-5953-b4bc-3e0924e997df | button | Shows on Pager | Yes,No,N/A
65c85768-3115-44da-a491-3a6a979a38ea | checkpoint | Bedroom 2 - Pullout Alarm
7cbbe638-3502-591f-a289-1a08a727c161 | button | Enabled | Yes,No,N/A
c864d612-dcfd-501f-bbce-ee3acf71d43e | button | Shows on Edge | Yes,No,N/A
fac3e67d-192f-50f2-926b-4de9297c87b1 | button | Displays Assignments | Yes,No,N/A
7d6b925b-f29c-5316-ac80-641cf45d07b9 | button | Shows on Pager | Yes,No,N/A
7c64b457-5d93-46be-9fce-9548974835ce | checkpoint | Bathroom - Toilet Button
36edea37-cda6-5326-9945-3ffeae190cfa | button | Enabled | Yes,No,N/A
78622fc9-d034-5baa-9a08-aa98ec3f02b2 | button | Shows on Edge | Yes,No,N/A
499ab0cf-7725-5b1b-81a1-ce12ad09fcf4 | button | Displays Assignments | Yes,No,N/A
3fdb0000-9b28-5fe9-aa50-c6721b0872fb | button | Shows on Pager | Yes,No,N/A
2c2fa87e-b300-4e27-b33a-6c94c441834e | checkpoint | Bathroom - Pullcord
842fd04d-7063-54eb-8906-e39f20fdff32 | button | Enabled | Yes,No,N/A
a2542088-1b9d-5716-9c68-211baaf605c9 | button | Shows on Edge | Yes,No,N/A
4d2fb10c-86bb-50d3-8944-2c592737f725 | button | Displays Assignments | Yes,No,N/A
32b4e2d2-d09b-58ab-af12-32cef57ce9d5 | button | Shows on Pager | Yes,No,N/A
5e9ea78b-0621-4845-8be1-cef481c68835 | checkpoint | Toilet - Button
e491eb7c-bade-5863-aa32-c33d41f3dc13 | button | Enabled | Yes,No,N/A
0e616abe-73b9-511b-b5b3-17236c7d8668 | button | Shows on Edge | Yes,No,N/A
5664c7df-6a8b-5748-89be-24e7ae57d5d9 | button | Displays Assignments | Yes,No,N/A
4b72e323-2917-5bcb-8cc7-1c894b63119d | button | Shows on Pager | Yes,No,N/A
cfbc6d89-5cff-463b-b081-6e3276afb03e | checkpoint | Kitchen/Living Space - Nurse Presence
52ac98a1-9942-5a9e-8e80-33d2f0f4bca5 | button | Enabled | Yes,No,N/A
5876da63-b7ea-5c07-aeba-89127cdf3745 | button | Shows on Edge | Yes,No,N/A
073b8bcf-42a7-52ac-8558-02d9db20e651 | button | Displays Assignments | Yes,No,N/A
327d864b-f4ec-5a87-af5b-6fd2f448c52e | button | Shows on Pager | Yes,No,N/A
1c9f507f-2de2-4629-b1ff-92b1377437d9 | checkpoint | Never Alone PIR
12d6fa4f-c6cb-525c-8cc8-5e79309048b7 | button | Enabled | Yes,No,N/A
9017c62b-98ea-5e79-bdab-7fd5f25682cf | button | Shows on Edge | Yes,No,N/A
b67fcd0a-9548-5b8f-bc2c-9a07f6d60abb | button | Displays Assignments | Yes,No,N/A
49a36552-b0ed-52c8-98eb-356ec26f25e8 | button | Shows on Pager | Yes,No,N/A
f3559f10-c5a5-4e31-be8b-6881a25b02f7 | checkpoint | Additional Call Points - Please note location
3baadaef-7230-5a56-873d-2a2743b2ef53 | button | Enabled | Yes,No,N/A
36011c73-c133-55b8-8881-d5d79813e871 | button | Shows on Edge | Yes,No,N/A
d4b4a555-0d00-5a50-9691-0def9da35083 | button | Displays Assignments | Yes,No,N/A
16e839e7-022b-5dc6-80fb-e795a8902d98 | button | Shows on Pager | Yes,No,N/A
58870fa7-1d13-4e9a-b645-e902199cf84e | checklist | zSYS - Refurb Checklist (old version, 07-03-24) |  | Refurb Checklist
5173db59-4602-49a9-9dab-73d0d58ef68e | section | Disconnection/Isolation
3562b5a0-3482-4ab5-9263-cc5ff2fdf7ae | checkpoint | Current locations of Plates and Cabling (Attach Photos)
41754dfa-e029-4912-aa54-378825f4c5bb | checkpoint | Disable Nurse Call in the Edge/ECall System
3d20a5bc-6693-4054-bd15-c2fe8729f087 | checkpoint | Area is left clean and tidy (Attach Photos)
e937c98d-1c18-41f5-b132-3e424aa248d9 | section | First Fix
b9f757d0-f366-43a5-bb88-6ac80da6fd98 | checkpoint | Approval to start work is obtained
1e92dbda-9c7e-475d-bc6b-7e73c82a3b7b | checkpoint | Install/Re-route cabling to new positions (Attach Photos)
56f8dcc9-46bb-45bf-ab5b-d7443bc4706e | checkpoint | Area is left clean and tidy (Attach Photos)
98e0a017-b6ad-4c55-8333-21a938b5707a | section | Second Fix
5bf467d1-99cb-466b-9758-4131fd9bdccd | checkpoint | Approval to start work is obtained
74c62291-121f-476d-9d6d-1e81ec42bd95 | checkpoint | Install Call Points/TV/Data Plates (Attach Photos)
7c50d736-20d3-4423-b22b-33122aba89ca | checkpoint | Nurse Call tested through Edge/Displays and Pagers
a296aab2-c52c-494e-a96c-74a40e5734d5 | checkpoint | MATV/Data tested and commissioned
c444518b-35b0-4b14-8ec5-0a9878968c93 | checkpoint | Smoke Alarms installed and tested (Attach Photos)
6a98d8ce-68df-4653-86c0-8e6ba880582d | checkpoint | Area is left clean and tidy (Attach Photos)