## Sheet3
Inspection and Test Plan Te Ara o Te Ata Temporary Culverts Installation - ITP - 006
| This ITP has been prepared by |  |  | Reviewed by [as applicable] |  |  | Reviewed by DSR | [6 empty] | Approved by [as applicable]
Rev Number | Name | Signature | Date | Name | Signature | Date | Name |  | Signature |  | Date |  |  | Name |  | Signature |  | Date
Rev 01 | Isaac Dunn | I.Dunn | 22.02.2023 |  |  |  | Danny Beasant (Geotech Site Lead) |  | D.Beasant |  | 22.02.2023
Rev 02
Rev 03
Rev 04
ITP NO: XXX |  | Project: Te Ara o Te Ata | [5 empty] | Method Statement Ref: |  |  | Rev.A
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity/Specification: Drainage and Earthworks | [7 empty] | Area Location / Work Breakdown: Zone 5
Item | Construction Step or Material |  | Specifications and Standards |  | Acceptance criteria and testing |  |  |  | Method (H,I,W,R) |  |  |  | Verifying Records Checklists, Test and Supplier Certificates |  | Site Engineer approved | DSR Engineer verification | Certified Complete (Date, relevant checklist title/lab report number etc)
Responsible [tick]
[5 empty] | Method/ Description | Test frequency |  | Conformance Criteria | Contractor | Hynds | Client | Lab
1.0 Pre-Construction
1.01 | Confirm CWP Signed off |  | MMA-DES-GEO-E1-SPC-3862 |  | Document Review | Prior to Work |  | Approved by Relevant Parties | H | H | H |  | Signed Copy of Method Statement
1.02 | Confirm Compliance against Resource Consent & Management Plans |  | Section 3.0 - MMA-DES-GEO-E1-SPC-3862 |  | Document Review | Prior to Work |  | Approved Management Plans, SCWMP and CWP | H | H | H |  | Signed Management Plans, Approved SCWMP and Approved CWP
1.03 | Confirm Design is in place |  |  |  | Document Review | Prior to Work |  | IFC | H | R |  |  | IFC Drawings
1.04 | Complete Permit To Dig |  | Internal Permit |  | Document Production | Prior to all Excavation works |  | Signed off Permit to Dig | H |  |  |  | Permit to Dig Form
1.05 | Survey |  | N/A |  | Record inlet and outlet heights for the stream diversion. Mark out scope of works | Prior to Work |  | Survey proposed pipe line and set out to confirm levels and grade | H | R |  |  | Survey Heights Survey Mark-out
2.0 Material Compliance
2.01 | PKS pipe (1400mm, 900mm & 800mm) |  | Structural analysis provided by Hynds PKS for pipe |  | Document Review | All PKS pipes |  | Correct Size as per temporary Culvert design Structural Analysis of pipe under backfill loading | R |  |  | H | Delivery Dockets Lab Tests
2.02 | PKS pipe fittings |  | Structural analysis provided by Hynds PKS for pipe fittings |  | Document Review | All Fittings |  | Correct Size as per temporary Culvert design Structural Analysis of fittings under backfill loading | R |  |  | H | Delivery Dockets Lab Tests
2.03 | Subsoil Pipe |  | Section 5.1 - MMA-DES-GEO-E1-SPC-3862 As per relevant Drawing set MMA-DES-GEO-E1-DRG-4006 |  | Ensure Pipes are ordered as per drawing | All Subsoils |  | Ordered Pipes match Design 110 NEXUS HI-WAY | R, I |  |  |  | Delivery Dockets
2.05 | Geotextile |  | TNZ F/5:2000 Bidim-Storage-Installation-Guide-M142-10-14-NZ.pdf |  | Document Review | All Geotextiles |  | Ensure Geotextile ordered meets specification & drawings Non-Woven Strength Class C For Cohesive Soil Type Filtration Class 1 or 3 (BIDIM A29) Stored off ground, under shade, rolls come wrapped | R, I |  |  |  | Delivery Dockets
2.06 | Drainage sand/ aggregate |  | AS/NZS-2566-22002 Appendix C, Tables C1, C2 |  | Laboratory Testing | Embedment material |  | 20-12 drainage aggregate, as per RFI 007 | R |  |  | I | PSD Results Crushing Resistance Test Confirmation of Material acceptance from Designers
3.0 During Construction
3.01 | Trench for PKS |  | AS/NZS-25661.2-2002 |  | Inspection | Prior to BIDIM installation |  | The minimum width/ height for the trench of each pipe is as follows: - DN1400 pipe: W2400mm, H2050mm - DN900: W1740mm, H1390mm - DN800: W1640mm, H1290mm | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.02 | Insitu subgrade (foundation) Compliance |  | As per Earthworks Spec MMA-DES-GEO-E1-SPC-3859 4/08/2022 AS/NZS-25661.2-2002 |  | Inspection | Checksheet filled in for every 100m section of drainage |  | Even Bed and Maintain pipe alignment soft or expansive clays | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.03 | Lay Geotextile (BIDIM A29) |  | MMA-DES-GEO-E1-SPC-3862 TNZ F/6:2003 (Geotextile wrapped aggregate subsoil drain construction) Bidim-Storage-Installation-Guide-M142-10-14-NZ.pdf |  | Inspection | Checksheet filled in for every 100m section of drainage |  | Fabric shall be laid as tight and flat as possible Laid in such a way that there is only one transverse joint. Minimum overlap of 500mm. | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.04 | Install Bedding Material |  | AS/NZS-2566-22002 , Table 4.2 |  | Inspection | Checksheet filled in for every 100m section of drainage |  | For DN1400, DN900 and DN800, the depth of bedding below the bottom of pipe must be a minimum of 150mm | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.05 | Install Nexus Highway novacoil |  |  |  | Inspection | Checksheet filled in for every 100m section of drainage |  | Ensure 110mm nexus highway novacoil is installed below PKS in subsoil layer | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.06 | Survey pick up location and heights |  | N/A |  | Survey pick up | Picked up location minimum every 100m |  | Pick up pipe heights and location for asbuilt | H |  |  |  | Survey record
3.07 | Install PKS pipe |  | AS/NZS-25661.2-2002 |  | Inspection | Checksheet filled in for every 100m section of drainage |  | Grade of pipe between | W, I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.08 | Install side support embedment material |  | AS/NZS-25661.2-2002, Table 4.2 |  | Inspection | Checksheet filled in for every 100m section of drainage |  | The minimum horizontal distance between the exterior of the PKS pipe and the trench wall or permanent trench support (not distance to temporary trench supports) is as follows: - 400mm for DN1400 - 350mm for DN900 and DN800 | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.09 | Install overlay embedment material |  | AS/NZS-25661.2-2002 |  | Inspection | Checksheet filled in for every 100m section of drainage |  | The minimum depth of overlay is as follows: - 300mm for DN1400 - 200mm for DN900 and DN800 | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.1 | Wrap Geotextile |  | Bidim-Storage-Installation-Guide-M142-10-14-NZ.pdf |  | Inspection | Checksheet filled in for every 100m section of drainage |  | Installed in area as per drawings, 300mm minimum lap. CBR over 2 - 300mm Minimum Lap CBR 1-2 - 600mm Minimum Lap CBR 0.5-1 900mm Minimum Lap CBR Less than 900mm report to Designer Engineer | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.11 | Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top |  | AS/NZS-25661.2-2002 |  | Inspection | Checksheet filled in for every 100m section of drainage |  | There must be a minimum of 750mm cover above the top of pipe before vehicle loading is acceptable | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.12 | Spat Rope installation |  | AS/NZS-25661.2-2002 |  | Inspection | Checksheet filled in for every 100m section of drainage |  | 3xRopes, along thebottom of each temporary culvert | I |  |  |  | Visual inspection/ photos Drainage installation Checksheet
3.13 | Construct inlet and Outlet structures |  | AS/NZS-25661.2-2002 |  | Inspection |  |  | TBC | I |  |  |  | Visual inspection/ photos
4.0 Post Construction
4.01 | Install culvert screen to catch debris |  | N/A |  | Inspection | N/A |  | N/A | I
4.02 | Provide Maintenance and Inspection Report/As Built |  | Section 10.0 - MMA-DES-GEO-E1-SPC-3862 |  | Maintenance and Inspection Report Completed | All Temporary culverts |  | Detail location of all drainage outlets, flushing points, and associated features that require maintenance and inspection. Drawings showing locations and extent of drainage. Electronic images (photographs) of outlets and features shall be provided. As Built points every 100m of PKS pipe | I | R |  |  | Maintenance and Inspection Report including As Built Plan & Photographs
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove this line we dont need a subsoil