## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 006 Temporary Culverts Installation | [5 empty] | ITP 006 Temporary Culverts Installation
section | 1.0 Pre-Construction
checkpoint | 1.01 - Confirm CWP Signed off
note | Method/Description - Document Review
note | Test frequency - Prior to Work
note | Contractor - H
note | Hynds - H
note | Verifying Records Checklists, Test and Supplier Certificates - Signed Copy of Method Statement
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Confirm Compliance against Resource Consent & Management Plans
note | Method/Description - Document Review
note | Test frequency - Prior to Work
note | Contractor - H
note | Hynds - H
note | Verifying Records Checklists, Test and Supplier Certificates - Signed Management Plans, Approved SCWMP and Approved CWP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Confirm Design is in place
note | Method/Description - Document Review
note | Test frequency - Prior to Work
note | Contractor - H
note | Hynds - R
note | Verifying Records Checklists, Test and Supplier Certificates - IFC Drawings
checkpoint | 1.04 - Complete Permit To Dig
note | Method/Description - Document Production
note | Test frequency - Prior to all Excavation works
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - Permit to Dig Form
checkpoint | 1.05 - Survey
note | Method/Description - Record inlet and outlet heights for the stream diversion. Mark out scope of works
note | Test frequency - Prior to Work
note | Contractor - H
note | Hynds - R
note | Verifying Records Checklists, Test and Supplier Certificates - Survey Heights, Survey Mark-out
section | 2.0 Material Compliance
checkpoint | 2.01 - PKS pipe (1400mm, 900mm & 800mm)
note | Method/Description - Document Review
note | Test frequency - All PKS pipes
note | Contractor - R
note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
checkpoint | 2.02 - PKS pipe fittings
note | Method/Description - Document Review
note | Test frequency - All Fittings
note | Contractor - R
note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets, Lab Tests
checkpoint | 2.03 - Subsoil Pipe
note | Method/Description - Ensure Pipes are ordered as per drawing
note | Test frequency - All Subsoils
note | Contractor - R, I
note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
checkpoint | 2.05 - Geotextile
note | Method/Description - Document Review
note | Test frequency - All Geotextiles
note | Contractor - R, I
note | Verifying Records Checklists, Test and Supplier Certificates - Delivery Dockets
checkpoint | 2.06 - Drainage sand/ aggregate
note | Method/Description - Laboratory Testing
note | Test frequency - Embedment material
note | Contractor - R
note | Verifying Records Checklists, Test and Supplier Certificates - PSD Results, Crushing Resistance Test, Confirmation of Material acceptance from Designers
section | 3.0 During Construction
checkpoint | 3.01 - Trench for PKS
note | Method/Description - Inspection
note | Test frequency - Prior to BIDIM installation
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.02 - Insitu subgrade (foundation) Compliance
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.03 - Lay Geotextile (BIDIM A29)
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.04 - Install Bedding Material
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.05 - Install Nexus Highway novacoil
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.06 - Survey pick up location and heights
note | Method/Description - Survey pick up
note | Test frequency - Picked up location minimum every 100m
note | Contractor - H
note | Verifying Records Checklists, Test and Supplier Certificates - Survey record
checkpoint | 3.07 - Install PKS pipe
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - W, I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.08 - Install side support embedment material
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.09 - Install overlay embedment material
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.10 - Wrap Geotextile
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.11 - Lay protective Fill Layer over Lapped Geotextile to allow plant to Run over top
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.12 - Spat Rope installation
note | Method/Description - Inspection
note | Test frequency - Checksheet filled in for every 100m section of drainage
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos, Drainage installation Checksheet
checkpoint | 3.13 - Construct inlet and Outlet structures
note | Method/Description - Inspection
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates - Visual inspection/ photos
section | 4.0 Post Construction
checkpoint | 4.01 - Install culvert screen to catch debris
note | Method/Description - Inspection
note | Test frequency - N/A
note | Contractor - I
note | Verifying Records Checklists, Test and Supplier Certificates -
checkpoint | 4.02 - Provide Maintenance and Inspection Report/As Built
note | Method/Description - Maintenance and Inspection Report Completed
note | Test frequency - All Temporary culverts
note | Contractor - I
note | Hynds - R
note | Verifying Records Checklists, Test and Supplier Certificates - Maintenance and Inspection Report including As Built Plan & Photographs