## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | FC - S - Roofing |  |  |  |  | Yes | FC - S - Roofing | 3fd20937-b7aa-4e93-8f8a-88754ba2c3b8
checkpoint-group |  |  | section | Pre-installation checks
checkpoint-status |  |  | checkpoint | Scaffolding in place and tagged
checkpoint-status |  |  | checkpoint | Edge protection and safety nets installed
checkpoint-status |  |  | checkpoint | Correct Purlin / Steelwork heights
checkpoint-status |  |  | checkpoint | Correct Precast wall heights
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Plywood Gutter Substrate
checkpoint-status |  |  | checkpoint | Plywood laid a minimum 0.5 degrees
checkpoint-status |  |  | checkpoint | Plywood surface smooth finish CD minimum 1.75mm H3 no knots
checkpoint-status |  |  | checkpoint | Plywood laid with 2mm gaps
checkpoint-status |  |  | checkpoint | Plywood fastened with stainless steel screws recessed 2mm
checkpoint-status |  |  | checkpoint | Outlets installed correctly 73-75mm above plywood
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Steel Tray Substrate
checkpoint-status |  |  | checkpoint | Metal profile installed upside down with fastenings spaced correctly
checkpoint-status |  |  | checkpoint | Flashings installed on hips and valleys
checkpoint-status |  |  | checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint-status |  |  | checkpoint | Outlets framed and plywood routed out
checkpoint-status |  |  | checkpoint | Unused Roofing Iron Secured
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Insulation panels
checkpoint-status |  |  | checkpoint | Sheets installed in brick-bond pattern
checkpoint-status |  |  | checkpoint | No gaps between sheets
checkpoint-status |  |  | checkpoint | Adhesive applied evenly and at correct amount
checkpoint-status |  |  | checkpoint | Sheets held down for correct length of time
checkpoint-status |  |  | checkpoint | Roof is confirmed uniform and flat
checkpoint-status |  |  | checkpoint | Observations
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Insulation panels are acceptable level of cleanliness
checkpoint-status |  |  | checkpoint | Membrane colour and thickness confirmed correct
checkpoint-status |  |  | checkpoint | Membrane penetrations have been sealed and are watertight
checkpoint-status |  |  | checkpoint | All welded seams and proprietary items to be seam probed
checkpoint-status |  |  | checkpoint | Observations
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Handover Checklist |  |  |  |  | Yes | Handover Checklist | 5538a44c-ecb3-413e-99d7-d105fbcdf3d7
checkpoint-status |  |  | checkpoint | Area 100% completed and waterproof as per specification
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Inform Viking and book completion inspection for FSW
checkpoint-status |  |  | checkpoint | PS3s BCO10324155-2
checkpoint-status |  |  | checkpoint | Record of Building Work
checkpoint-status |  |  | checkpoint | Product Warranty
checklist-flat |  |  | checklist | Pre-commencement checklist |  |  |  |  | Yes | Pre-commencement Checklist | bbf40d41-804c-4e3a-a93c-cc96145cdc08
checkpoint-status |  |  | checkpoint | Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
checkpoint-status |  |  | checkpoint | Conqa Setup & Project Team Trained & Given Access
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Relevant Parties
checkpoint-status |  |  | checkpoint | Matrix/insights Setup (if required)
checklist-flat |  |  | checklist | Membrane Checklist |  |  |  |  | Yes | Membrane Checklist | d7bcf17b-b38c-4356-ab50-45d5e22e11df
checkpoint-status |  |  | checkpoint | Polyiso thoroughly cleaned and checked prior to priming or membrane application
checkpoint-status |  |  | checkpoint | Checked to ensure no dye-batch colour variation
checkpoint-status |  |  | checkpoint | Ensure the specified membrane thickness and colour is used on site
checkpoint-status |  |  | checkpoint | All products installed with a Viking Membrane comply with Viking Specifications e.g. the tested ‘system’ - Drains and accessories supplied by Viking Roofspec
checkpoint-status |  |  | checkpoint | All welded seams and proprietary items to be seam probed
checkpoint-status |  |  | checkpoint | Membrane installed as per spec and complete. Any general observations made
checklist-sectioned |  |  | checklist | Warm Roof Checklist |  |  |  |  | Yes | Warm Roof Checklist | fb2bdb62-aff6-4cb8-874e-128d9fd20b5d
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Area accessible
checkpoint-status |  |  | checkpoint | Edge protection and safety installed
checkpoint-status |  |  | checkpoint | Perimeter support installed if metal deck substrate
checkpoint-status |  |  | checkpoint | Substrate acceptable (clean, dry and stable)
checkpoint-group |  |  | section | Metcom7
checkpoint-status |  |  | checkpoint | Falls deemed acceptable by Council
checkpoint-status |  |  | checkpoint | Purlins and roof structure ready for Metcom 7 and approval given to lay
text | 8b81387f-1ce5-48b9-a054-6624d75f2f6b |  | textbox | Who has given approval to lay
checkpoint-status |  |  | checkpoint | Fix steel to manufacturers specifications in compliance with NZBC
checkpoint-status |  |  | checkpoint | The metal profile installed upside down and the specified fastenings installed in the trough
checkpoint-status |  |  | checkpoint | Flashings installed on hips and valleys
checkpoint-status |  |  | checkpoint | Insulation protected from crushing (edge of gutter, timber edging, etc.)
checkpoint-status |  |  | checkpoint | The timber height is exact height of the insulation and the outside edge of the timber has a generous radius to ensure maximum bond of the membrane when dressed over it
checkpoint-status |  |  | checkpoint | Outlets framed and plywood routed out
checkpoint-status |  |  | checkpoint | Metcom7 installed as per spec and complete. Any general observations made
checkpoint-group |  |  | section | Polyiso
checkpoint-status |  |  | checkpoint | All Polyiso sheets butt jointed - np gaps created
checkpoint-status |  |  | checkpoint | Polyiso Sheets glued down with Viking FAST Adhesive (STP900B) using a proprietary dual cartridge caulking gun
checkpoint-status |  |  | checkpoint | STP900B adhesive applied in sweeping ribbons on every steel rib and then left to ‘foam-up’ over the next few minutes
checkpoint-status |  |  | checkpoint | Polyiso boards laid in a brick-bond pattern.
checkpoint-status |  |  | checkpoint | Butt the polyiso sheets up to the pre-formed timber edging where applicable
checkpoint-status |  |  | checkpoint | Entire roof inspected upon completion to ensure a uniform flat surface
checkpoint-status |  |  | checkpoint | Polyiso installed as per spec and complete. Any general observations made
checkpoint-group |  |  | section | Membrane
checkpoint-status |  |  | checkpoint | Polyiso thoroughly cleaned and checked prior to priming or membrane application
checkpoint-status |  |  | checkpoint | Checked to ensure no dye-batch colour variation
checkpoint-status |  |  | checkpoint | Ensure the specified membrane thickness and colour is used on site
checkpoint-status |  |  | checkpoint | All products installed with a Viking Membrane comply with Viking Specifications e.g. the tested ‘system’ - Drains and accessories supplied by Viking Roofspec
checkpoint-status |  |  | checkpoint | All welded seams and proprietary items to to be seam probed.
checkpoint-status |  |  | checkpoint | Membrane installed as per spec and complete. Any general observations made
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area 100% completed and waterproof as per specification
holdpoint |  |  | signoff | Request Review / Sign Off
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-status |  |  | checkpoint | Area complete and ready for FSW inspection
checkpoint-status |  |  | checkpoint | Report sent through to client