## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - SH33 | itp |  |  |  |  | ITP - SH33
section | SPECIFICATION: 100 (GENERAL FOR PROJECT)
checkpoint | 100.1 - Physically located all utility locations
note | Detail of Activity: Permit to work around services (Gas, Power, Fibre, etc.)
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: as required per section of works
note | Inspection / Test Method: Document Review
note | Acceptance Criteria: All services physically located
note | Record Documents: Permit attached or permit number noted
note | Responsibility: Contractor
checkpoint | 100.2 - Contract Document Signed
note | Detail of Activity: Ensure Contract is signed
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: at the Contract kickoff meeting
note | Inspection / Test Method: Document Issue
note | Acceptance Criteria: N/A
note | Record Documents: Issued with a NTC
note | Responsibility: Safe Roads' Rep.
checkpoint | 100.3 - "For Construction" Drawings Isssued
note | Detail of Activity: Ensure "For Construction" drawings are issued
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: at the Contract kickoff meeting
note | Inspection / Test Method: Document Issue
note | Acceptance Criteria: N/A
note | Record Documents: Issued with a NTC
note | Responsibility: Safe Roads' Rep.
checkpoint | 100.4 - Traffic Management Plan
note | Detail of Activity: Ensure TMP is approved and check that the requirements are fully understood by the STMS
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: every morning and/or when the TMP changes
note | Inspection / Test Method: Document and Physical works review
note | Acceptance Criteria: COPTTM
note | Record Documents: TMP from contractor
note | Responsibility: Contractor
checkpoint | 100.5 - Design
note | Detail of Activity: Ensure that Design is approved and drawings are the latest revision
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to commencement
note | Inspection / Test Method: Document Review
note | Record Documents: Check Drawing register
note | Responsibility: Contractor
note | Comments: Drawing register maintained by Safe Roads and e-mailed to contractor when revised drawings are issued
checkpoint | 100.6 - Approved Consents
note | Detail of Activity: Is a copy of approved consent(s) available on site
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to commencement
note | Inspection / Test Method: Visual Inpection
note | Record Documents: This ITP
note | Responsibility: Safe Roads' Rep.
checkpoint | 100.7 - Pre-start meeting
note | Detail of Activity: Pre-start meeting to confirm work strategy and safety measures
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Before commencing work each day
note | Inspection / Test Method: N/A
note | Acceptance Criteria: 100% attendance
note | Record Documents: Pre-start sign on register / site diary
note | Responsibility: Contractor
checkpoint | 100.8 - Contractor's methodology
note | Detail of Activity: Approval of Contractor's methodology
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to commencement
note | Inspection / Test Method: Document review
note | Acceptance Criteria: Methodology conforms with all relevant specifications
note | Record Documents: Methodology submitted via NTE
note | Responsibility: Safe Roads' Rep.
note | Comments: Methodology submitted min. 7 working days and approval min. 3 working days prior to commencement
checkpoint | 100.9 - Laydown area / stockpile sites
note | Detail of Activity: Site inspection
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to commencement
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Approved by Safe Roads
note | Record Documents: Request for approval (RFA) via NTE
note | Responsibility: Safe Roads' Rep.
note | Comments: RFA submitted min. 7 working days and approval min. 3 working days prior to commencement
checkpoint | 100.10 - Weather
note | Detail of Activity: Assessment of forecast
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Daily prior to and during works
note | Inspection / Test Method: Check local and national weather forcast services
note | Acceptance Criteria: No imminent rain or adverse weather conditions. Consideration of wind and project location/environment
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
checkpoint | 100.11 - Environmental Protection
note | Detail of Activity: Site evaluation
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to commencement
note | Inspection / Test Method: Inspection
note | Acceptance Criteria: Supervisor assessment of conformance
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
section | SPECIFICATION: 302 EARTHWORKS (Widening Works)
checkpoint | 302.1 - Mark out and approve
note | Detail of Activity: Set out and mark up of extent of earthworks
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All earthworks areas
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: N/A
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
checkpoint | 302.2 - Underground services
note | Detail of Activity: Identify and positively locate services
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All earthworks areas
note | Inspection / Test Method: Hydoexcavation
note | Acceptance Criteria: N/A
note | Record Documents: Drawings
note | Responsibility: Contractor
checkpoint | 302.3 - Determine Embankment / Subgrade
note | Detail of Activity: Determine bearing strength of subgrade Strength
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 Scala per 20m
note | Inspection / Test Method: Scala Penetrometer Test NZS 4402.6.5.2
note | Acceptance Criteria: SUBBASE DEPTH WHERE SUBGRADE <6%
note | – – – – – – – – – – – – – – – – – – – – – – – – –
note | CBR ¦¦ DEPTH ¦¦ ADDITIONAL REQUIREMENT
note | – – – – – – – – – – – – – – – – – – – – – – – – –
note | 4% (2blows/100mm) ¦¦ 320mm ¦¦ -
note | 2% (1blows/100mm) ¦¦ 540mm ¦¦ Geotextile (Strength Class C) on excavation floor
note | – – – – – – – – – – – – – – – – – – – – – – – – –
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if appliacable.
checkpoint | 302.4 - GENERAL FILL
note | Detail of Activity: General Fill Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | Inspection / Test Method: Determination of MDD & OMC Compaction to NZS 4402 Part 2P: 1981, Test 14 "Determination of the Dry Density/Water Content Relationship (NZ Standard Compaction)".
note | Acceptance Criteria: Report value only
note | Record Documents: IANZ Report
note | Responsibility: Contractor
checkpoint | 302.5 - GAP65 HARDFILL
note | Detail of Activity: Hardfill Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | Inspection / Test Method: PSD NZS 4407: 1991 Test 3.8.1
note | Acceptance Criteria: Project Spec
note | • GAP65
note | • 100% passing 63mm
note | • 77-90% passing 37.5mm
note | • 55-75% passing 19mm
note | • 40-60% passing 9.5mm
note | • 28-48% passing 4.75mm
note | • 18-25% passing 1.18mm
note | • 6-18% passing 600µm
note | • 3-15% passing 300µm
note | • 2-14% passing 150µm
note | • 0-9% passing 75µm
checkpoint | 302.6 - GAP65 HARDFILL
note | Detail of Activity: Hardfill Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | Inspection / Test Method: Determination of MDD & OMC Compaction to NZS 4402 Part 2P: 1981, Test 14 "Determination of the Dry Density/Water Content Relationship (NZ Standard Compaction)".
note | Acceptance Criteria: Report Value Only
checkpoint | 302.7 - GAP65 HARDFILL
note | Detail of Activity: Hardfill Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | Inspection / Test Method: Weathering Quality Index Test NZS 4407 : 1991, Test 3.11
note | Acceptance Criteria: AA, AB, AC, BA , BB, CB
checkpoint | 302.8 - GAP65 HARDFILL
note | Detail of Activity: Hardfill Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Three tests on samples randomly selected in accordance with NZ 4402 clause 1.6.3 and 1.6.4 from a truck or stockpile at the site of works. The tests shall consist of 4- day soaked CBRs carried out to NZS 4402.
note | Inspection / Test Method: Soaked CBR Compaction to NZS 4402 Part 2P: 1981, Test 14. CBR testing to NZS 4402
note | Acceptance Criteria: Insitu CBR of 40 + 1.3 standard deviation (s) over the three samples
checkpoint | 302.9 - Testing of placed material, Test with a Scala if the material allows it (Pumice etc), or with NDM on material that doesn't allow it (millings etc)
note | Detail of Activity: Strength of placed material (Pumice, sand etc)
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All earthworks areas, 1 Lot < 300m long per 0.5m lift
note | Inspection / Test Method: Scala penetrometer test NZS 4402.6.5.2
note | Acceptance Criteria: 4 blows / 100mm
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
checkpoint | 302.10 - Testing of placed material, Test with a Scala if the material allows it (Pumice etc), or with NDM on material that doesn't allow it (millings etc)
note | Detail of Activity: Compaction (millings etc)
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All earthworks areas, 1 Lot < 300m long per 0.5m lift
note | Inspection / Test Method: Nuclear Density Meter NZS 4407.4.2.1
note | Acceptance Criteria: Minimum field density of 95% of maximum dry density (MDD) obtained by standard compaction
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
checkpoint | 302.11 - Testing of placed material, Test with a Scala if the material allows it (Pumice etc), or with NDM on material that doesn't allow it (millings etc)
note | Detail of Activity: Proof roll of placed material
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All earthworks areas per 0.5m lift
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: No significant visual deformation under the wheel load
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint | 302.12 - Testing of placed material GAP65
note | Detail of Activity: Proof roll of placed material
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All earthworks areas per 0.5m lift
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: No significant visual deformation under the wheel load
note | • =< 7mm for bulk fill
note | • =< 5mm for subgrade fill
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint | 302.13 - Testing of placed material GAP65
note | Detail of Activity: Compaction
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All earthworks areas, 1 Lot < 300m long per 0.5m lift
note | Inspection / Test Method: Nuclear Density Meter NZS 4407.4.2.1
note | Acceptance Criteria: Minimum field density of 95% of maximum dry density (MDD) obtained by standard compaction
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
section | SPECIFICATION: 402 STORMWATER DRAINAGE
checkpoint | 402.1 - Mark out works
note | Detail of Activity: Set out and mark up proposed drainage features
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All drainage features
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: N/A
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
checkpoint | 402.2 - Underground services
note | Detail of Activity: Identify and positively locate services
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All drainage features
note | Inspection / Test Method: Hydoexcavation
note | Acceptance Criteria: N/A
note | Record Documents: Drawings
note | Responsibility: Contractor
checkpoint | 402.3 - Precast tranversable wingwall design
note | Detail of Activity: Contract to provide manufacturer dwgs of the proposed sturcture design for approval
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per wingwall type
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve proposed design
note | Record Documents: NTC / Site instruction
note | Responsibility: Contractor
note | Comments: This requirement acknowledges minor variances in manufacturer design details for precast wingwalls
checkpoint | 402.4 - Determine Embankment / Subgrade Strength
note | Detail of Activity: Determine bearing strength of subgrade
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per 5m length of trench base; or
note | Inspection / Test Method: Scala Penetrometer NZS 4402.6.5.2
note | Acceptance Criteria: 2 blows per 100mm (CBR4%) - increase bedding depth by 100mm 1 blows per 100mm (CBR2%) - increase bedding depth by 300mm
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if applicable.
checkpoint | 402.5 - Trench backfill
note | Detail of Activity: Hardfill Source Properties (as per Specification 302 - Earthworks)
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source
note | Inspection / Test Method: Determination of MDD & OMC NZS 4402: Test 4.1.3
note | Acceptance Criteria: For analysis of DoC
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: By IANZ accredited lab
checkpoint | 402.6 - Trench backfill
note | Detail of Activity: Compaction (trench inside of carrigeway)
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per 5m trench per 1m lift
note | Inspection / Test Method: NDM NZS 4407.4.2.1
note | Acceptance Criteria: NZTA B02: DoC ≥ 95%
note | Record Documents: IANZ Report
note | Responsibility: Contractor
checkpoint | 402.7 - Trench backfill
note | Detail of Activity: Compaction (trench more than 1m outside of carrigeway)
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per 5m trench per 1m lift
note | Inspection / Test Method: Clegg Hammer
note | Acceptance Criteria: Need to issue NTE to confirm this
checkpoint | 402.8 - Structures (manholes, head walls etc.)
note | Detail of Activity: Visual inspection of completed structure
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per structure
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: No visible leakage through joints
note | Record Documents: NTC / Site instruction
note | Responsibility: Contractor
checkpoint | 402.9 - CCTV Inspection
note | Detail of Activity: Visual record of completed works
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All drainage pipelines
note | Inspection / Test Method: CCTV Inspection
note | Acceptance Criteria: No significant cracks, level deformation, faulty joints
note | Record Documents: CCTV Footage
note | Responsibility: Contractor
note | Comments: CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction
section | SPECIFICATION: 406 STONE RIPRAP
checkpoint | 406.1 - Mark out and approve
note | Detail of Activity: Set out and mark up of scour protection area
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All locations scour protection is required
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Engineer to confirm
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
checkpoint | 406.2 - Confirm filter material
note | Detail of Activity: Contract to provide manufacture specifications proposed filter materials
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per material type
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve proposed material in accordance with TNZ F/7
note | Record Documents: NTC / Site instruction
note | Responsibility: Contractor
note | Comments: Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if appliacable.
checkpoint | 406.3 - Confirm rip rap material
note | Detail of Activity: RipRap Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per material type
note | Inspection / Test Method: PSD
note | • Grading: Individual stones shall be approximately cubical or spherical with a nominal dimension of 300mm, with no stone less than 100mm nor greater than 400mm. Grading shall be confirmed by weighing a sample of 100 stones. The average weight shall be in the range 35 to 40 kg, with no stone less than 5kg and no stone greater than 90kg (machine placed).
note | • Crushing Resistance Test NZS 4407 : 1991, Test 3.10
note | • Weathering Quality Index Test NZS 4407 : 1991, Test 3.11
note | • Solid Density NZS 4407 : 1991, Test 3.7
note | • Abrasion Resistance
note | Acceptance Criteria: d50 = 250mm riprap 100% passing 400mm
note | • 84-72% passing 300mm
note | • 50-30% passing 250mm
note | • 20-8% passing 150mm
note | • 7-3% passing 80mm
note | • Not less than 150kN when tested in accordance with NZS4407
note | • AA, AB, AC, BA or BB
note | • => 2.6T/m³
note | • Abrasion resistance (using the Los Angeles Test): With less than 25% loss of weight after 500 revolutions in accordance with NZS4407.
note | Record Documents: Laboratory Test Results
note | • Issue NTE to confirm this is not necessary due to location of riprap placement
note | Responsibility: Contractor
note | Comments: Laboratory test may be substitued for a visual inspection (if instructed by the Engineer)
checkpoint | 406.4 - Final Inspection
note | Detail of Activity: Engineer to inspect the final works
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All locations scour protection is required
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: No significant visual deformation under the wheel load
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Witnessed by Engineers Representative and signed off in daily diary
section | SPECIFICATION: 506 GRANULAR PAVEMENT (Widening Works)
checkpoint | 506.1 - Mark out and approve
note | Detail of Activity: Set out and mark up of treatment area
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All areas of shoulder top-up.
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: N/A
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
checkpoint | 506.2 - Determine Embankment / Subgrade Strength (Shoulder Top-up)
note | Detail of Activity: Proof Roll the excavated area (bottom of 100mm topup horizon)
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All areas of shoulder top-up. 1 Lot < 300m long.
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: No significant visual deformation under the wheel load
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Witnessed by Engineers Representative and signed off in daily diary
checkpoint | 506.3 - Determine Embankment / Subgrade Strength (Pavement Widening)
note | Detail of Activity: Determine bearing strength of subgrade
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 Scala per 20m
note | Inspection / Test Method: NZS 4402.6.5.2
note | Acceptance Criteria: SUBBASE DEPTH WHERE SUBGRADE <6%
note | – – – – – – – – – – – – – – – – – – – – – – – – –
note | CBR ¦¦ DEPTH ¦¦ ADDITIONAL REQUIREMENT
note | – – – – – – – – – – – – – – – – – – – – – – – – –
note | 4% (2blows/100mm) ¦¦ 320mm ¦¦ -
note | 2% (1blows/100mm) ¦¦ 540mm ¦¦ Geotextile (Strength Class C) on excavation floor
note | – – – – – – – – – – – – – – – – – – – – – – – – –
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if appliacable.
checkpoint | 506.4 - Confirm pavement thickness design
note | Detail of Activity: Confirm Pavement thickness
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per section
note | Inspection / Test Method: AGPT Part2: Fig.8.4 if widening area is trafficked
note | Acceptance Criteria: Pavement thickness is minimum of adjacent existing pavement (to ensure drainage) and Figure 8.4 (if widening area is trafficked)
note | Record Documents: NTC
note | Responsibility: SR Designer
checkpoint | 506.5 - Confirm Subbase Material
note | Detail of Activity: Subbase Aggregate (Hardfill) Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | • Three tests on samples randomly selected in accordance with NZ 4402 clause 1.6.3 and 1.6.4 from a truck or stockpile at the site of works. The tests shall consist of 4- day soaked CBRs carried out to NZS 4402.
note | Inspection / Test Method: PSD NZS 4407: 1991 Test 3.8.1
note | • Determination of MDD & OMC Compaction to NZS 4402 Part 2P: 1981, Test 14 "Determination of the Dry Density/Water Content Relationship (NZ Standard Compaction)".
note | • Soaked CBR Compaction to NZS 4402 Part 2P: 1981, Test 14. CBR testing to NZS 4402
note | • Weathering Quality Index Test NZS 4407 : 1991, Test 3.11
note | Acceptance Criteria: Project Spec
note | • GAP65
note | • 100% passing 63mm
note | • 77-90% passing 37.5mm
note | • 55-75% passing 19mm
note | • 40-60% passing 9.5mm
note | • 28-48% passing 4.75mm
note | • 18-25% passing 1.18mm
note | • 6-18% passing 600µm
note | • 3-15% passing 300µm
note | • 2-14% passing 150µm
note | • 0-9% passing 75µm
note | • Report Value Only
note | • Insitu CBR of 40 + 1.3 x s (where s=standard deviation) over the three samples
note | • AA, AB, AC, BA , BB, CB
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 506.6 -
note | Inspection / Test Method: PSD NZS 4407: 1991 Test 3.8.1
note | Acceptance Criteria: NZTA M04 / Project Spec
note | ○ AP40
note | • 100% passing 37.5mm
note | • 66 - 81% passing 19mm
note | • 43 - 57 passing 9.5mm
note | • 28 - 43 passing 4.75mm
note | • 19 - 33 passing 2.36mm
note | • 12 - 25 passing 1.18mm
note | • 7 - 19 passing 600μm
note | • 3 - 14 passing 300μm
note | • 0 - 10 passing 150μm
note | • 0 - 7 passing 75μm
note | ○ AP20
note | • 100% passing 19mm
note | • 55 - 75% passing 9.5mm
note | • 33 - 55 passing 4.75mm
note | • 22 - 42 passing 2.36mm
note | • 14 - 31 passing 1.18mm
note | • 8 - 23 passing 600μm
note | • 5 - 16 passing 300μm
note | • 0 - 12 passing 150μm
note | • 0 - 8 passing 75μm
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 506.7 - Confirm Basecourse Material
note | Detail of Activity: Basecourse Aggregates Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | Inspection / Test Method: Atterburg Limit (Plastisity Index) NZS 4407:1991, Test 3.4
note | • Determination of MDD & OMC NZS 4402: Test 4.1.3
note | • Soaked CBR Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
note | • Solid Density NZS 4407 : 1991, Test 3.7
note | Acceptance Criteria: Report value only
note | • TNZ M/4 3.3.3 ≥ 80%
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 506.8 - Confirm Basecourse Material
note | Detail of Activity: Basecourse Aggregates Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | Inspection / Test Method: Crushing Resistance Test NZS 4407 : 1991, Test 3.10
note | Acceptance Criteria: TNZ M/4 3.3.1 <10% fines passing 2.36mm under 130 KN load
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
checkpoint | 506.9 - Confirm Basecourse Material
note | Detail of Activity: Basecourse Aggregates Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per source stockpile (1 test per 10,000m³)
note | Inspection / Test Method: Weathering Quality Index Test NZS 4407 : 1991, Test 3.11
note | Acceptance Criteria: TNZ M/4 3.3.2 AA, AB, AC, BA, BB or CA
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
checkpoint | 506.10 - Confirm Basecourse Material
note | Detail of Activity: Basecourse Aggregates Production
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 0-400m3 = 2 tests
note | • 400-1500m3 = 3 tests
note | • 1500-4000m3 = 4 tests
note | • >4000m3 = 1 test/1000m3
note | Inspection / Test Method: PSD NZS 4407 : 1991, Test 3.8.1
note | Acceptance Criteria: NZTA M04 / Project Spec 100% passing 37.5mm
note | • 66 - 81% passing 19mm
note | • 43 - 57 passing 9.5mm
note | • 28 - 43 passing 4.75mm
note | • 19 - 33 passing 2.36mm
note | • 12 - 25 passing 1.18mm
note | • 7 - 19 passing 600μm
note | • 3 - 14 passing 300μm
note | • 0 - 10 passing 150μm
note | • 0 - 7 passing 75μm
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 506.11 - Confirm Basecourse Material
note | Detail of Activity: Basecourse Aggregates Production
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 0-400m3 = 2 tests
note | • 400-1500m3 = 3 tests
note | • 1500-4000m3 = 4 tests
note | • >4000m3 = 1 test/1000m3
note | Inspection / Test Method: Sand equivalent NZS4407 : 1991, Test 3.6
note | Acceptance Criteria: TNZ M/4 4.2.1.1 >= 40
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 506.12 - Shoulder Top-Up
note | Detail of Activity: Proof Roll top of topup area (finished shoulder)
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All areas of shoulder top-up
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: No significant visual deformation under the wheel load
note | • =< 7mm for bulk fill
note | • =< 5mm for subgrade fill
note | Record Documents: Contractor's site diary
note | Responsibility: Contractor
note | Comments: Witnessed by Engineers Representative and signed off in contractor's daily diary
checkpoint | 506.13 - Shoulder Top-Up
note | Detail of Activity: Clegg Hammer
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 CIV per 20 m2
note | Inspection / Test Method: Clegg Impact Value Test
note | Acceptance Criteria: Average CIV > 40 Min. CIV > 35
note | Record Documents: Contractor's CIV form appended to Contractor's daily diary
note | Responsibility: Contractor
checkpoint | 506.14 - Subbase
note | Detail of Activity: Determine bearing strength of subgrade
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Confirm that subbase strength (Scala) has been completed and within spec
note | Inspection / Test Method: Confirm that subbase strength (Scala) has been completed and within spec
note | Acceptance Criteria: Confirm that subbase strength (Scala) has been completed and within spec
note | Record Documents: Confirm that subbase strength (Scala) has been completed and within spec
checkpoint | 506.15 - Subbase
note | Detail of Activity: Target Maximum Dry Density (Determination of MDD & OMC)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per 5,000m2 of material laid
note | Inspection / Test Method: Determination of MDD & OMC NZS 4402: Test 4.1.3
note | Acceptance Criteria: report value only
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: By IANZ accredited lab
checkpoint | 506.16 - Subbase
note | Detail of Activity: Compaction
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 9 per Lot
note | Inspection / Test Method: NDM NZS 4407.4.2.1
note | Acceptance Criteria: NZTA B02: DoC ≥ 95%
note | Record Documents: IANZ Report
note | Responsibility: Contractor
checkpoint | 506.17 - Basecourse
note | Detail of Activity: Target Maximum Dry Density (Determination of MDD & OMC)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: One per 5,000m2 of material laid
note | Inspection / Test Method: Determination of MDD & OMC NZS 4402: Test 4.1.3
note | Acceptance Criteria: report value only
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: By IANZ accredited lab
checkpoint | 506.18 - Basecourse
note | Detail of Activity: Compaction
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 9 per Lot
note | Inspection / Test Method: NDM NZS 4407.4.2.1
note | Acceptance Criteria: NZTA B02: DoC ≥ 98%
note | Record Documents: IANZ Report
note | Responsibility: Contractor
section | SPECIFICATION:507 TNZ M4: 2006 NZTA B/07:2012, Specification for the Manufacture and Construction on Plant Mix Modified Pavement Layers.
checkpoint | 507.1 - Setout
note | Detail of Activity: Install offset pegs; record centreline, edgeline or mark out stabilisation extents from existing line marking
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to works
note | Inspection / Test Method: Measurement
note | Acceptance Criteria: Document existing furniture
note | Record Documents: ITP
note | Responsibility: Contractor
checkpoint | 507.2 - Check raw materials
note | Detail of Activity: Cement
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Per Batch
note | Inspection / Test Method: NZS 3122
note | Acceptance Criteria: For design input
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Check prior to arrival on site
checkpoint | 507.3 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Production before the addition of cement
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 0-400m3 = 2 tests
note | • 400-1500m3 = 3 tests
note | • 1500-4000m3 = 4 tests
note | • >4000m3 = 1 test/1000m3
note | Inspection / Test Method: PSD NZS 4407 : 1991, Test 3.8.1
note | Acceptance Criteria: NZTA M04 / Project Spec 100% passing 37.5mm
note | • 66 - 81% passing 19mm
note | • 43 - 57 passing 9.5mm
note | • 28 - 43 passing 4.75mm
note | • 19 - 33 passing 2.36mm
note | • 12 - 25 passing 1.18mm
note | • 7 - 19 passing 600μm
note | • 3 - 14 passing 300μm
note | • 0 - 10 passing 150μm
note | • 0 - 7 passing 75μm
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 507.4 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Production before the addition of cement
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 0-400m3 = 2 tests
note | • 400-1500m3 = 3 tests
note | • 1500-4000m3 = 4 tests
note | • >4000m3 = 1 test/1000m3
note | Inspection / Test Method: Sand equivalent NZS4407 : 1991, Test 3.6
note | Acceptance Criteria: TNZ M/4 4.2.1.1 >= 40
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 507.5 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Source Testing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Atterburg Limit ( Plastisity Index) NZS 4407:1991, Test 3.4
note | Acceptance Criteria: TNZ M/4 4.2.1.3 = <5
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 507.6 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Source Testing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Determination of MDD & OMC NZS 4402: Test 4.1.3
note | Acceptance Criteria: Report Value Only
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 507.7 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Source Testing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Crushing Resistance Test NZS 4407 : 1991, Test 3.10
note | Acceptance Criteria: TNZ M/4 3.3.1 <10% fines passing 2.36mm under 130 KN load
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 507.8 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Source Testing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Weathering Quality Index Test NZS 4407 : 1991, Test 3.11
note | Acceptance Criteria: TNZ M/4 3.3.2 AA, AB, AC, BA, BB or CA
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 507.9 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Source Testing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Soaked CBR Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
note | Acceptance Criteria: TNZ M/4 3.3.3 ≥ 80%
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 507.10 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Source Testing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Solid Density NZS 4407 : 1991, Test 3.7
note | Acceptance Criteria: Report Value Only
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
note | Comments: Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
checkpoint | 507.11 - Check raw materials AP40
note | Detail of Activity: Basecourse Aggregates Source Testing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Broken Faces Content NZS 4407 : 1991, Test 3.14
note | Acceptance Criteria: TNZ M/4 4.2.2
note | • 19mm-37.5mm
note | • 9.5mm-19.mm
note | • acceptance criteria = none >= 70% retained 4.75mm-9.5mm
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 507.12 - Site plan
note | Detail of Activity: Daily Production Plan
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: NZTA B/7 7.2.3, Before the commencement of the day’s work
note | Inspection / Test Method: Report
note | Acceptance Criteria: Report only
note | Record Documents: Report
note | Responsibility: Contractor
checkpoint | 507.13 - Cement
note | Detail of Activity: Cement Feed
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: NZTA B/7 7.3.2, Record Plant Display Reading
note | Inspection / Test Method: weight of cement
note | Acceptance Criteria: Plant Display Reading +/- 5% of specified rate
note | Record Documents: Supplier quality representative
note | Responsibility: Contractor
checkpoint | 507.14 - Cement
note | Detail of Activity: Cement Feed
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: NZTA B/7 7.3.2, Average usage test upon emptying the bulk tanker
note | Inspection / Test Method: weight of cement
note | Acceptance Criteria: compare tonnes used with measured qty +/- 5% of specified rate
note | Record Documents: Supplier quality representative
note | Responsibility: Contractor
checkpoint | 507.15 - Production AP40 2% CMB
note | Detail of Activity: Particle size distribution lab to take sufficient material to perform Dry back Moisture Content Analysis (modified material)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 3 per Lot (completed within 4 hours of mixing to ensure all particle sizes can be washed off prior to cementing)
note | • *1 lot = 1000m³ or 250lm (whichever is least) as per B/07
note | Inspection / Test Method: Wet sieving test NZS 4407 : 1991, Test 3.8.1
note | Acceptance Criteria: TNZ M/04
note | • 100% passing 37.5mm
note | • 66 - 81% passing 19mm
note | • 43 - 57 passing 9.5mm
note | • 28 - 43 passing 4.75mm
note | • 19 - 33 passing 2.36mm
note | • 12 - 25 passing 1.18mm
note | • 7 - 19 passing 600μm
note | • 3 - 14 passing 300μm
note | • 0 - 10 passing 150μm
note | • 0 - 7 passing 75μm
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 507.16 - Production AP40 2% CMB
note | Detail of Activity: Determination of MDD & OMC (modified material)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per 5000m² laid
note | Inspection / Test Method: Determination of MDD & OMC NZS 4402: Test 4.1.3
note | Acceptance Criteria: report value only
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 507.17 - Production AP40 2% CMB
note | Detail of Activity: Compaction
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 9 per Lot
note | • *1 lot = 1000m³ or 250lm (whichever is least)
note | Inspection / Test Method: NDM TNZ B/2 7.6 & B/7 8.1
note | Acceptance Criteria: RC ≥ 98%
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 507.18 - Production AP40 2% CMB
note | Detail of Activity: Plateau Density Test (3 tests) (as part of this 3 NDM readings are taken and then 3 samples are taken and dried back in the lab to determine actual moisture content of material placed)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: TNZ B/2 7.5(b)
note | Inspection / Test Method: NDM
note | Acceptance Criteria: report value only, Used for moisture contect correction
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 507.19 -
note | Detail of Activity: Indirect tensile strength testing - on mixed stockpiled material if B/7 time limits not met
note | S
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Day 1: Two (2) soaked & two (2) dry ITS
note | • All subsequent days: One (1) soaked & one (1) dry ITS from the spreader truck, prior to addition of compaction water, within 2 hours of completion of primary compaction of lift
note | Inspection / Test Method: NZTA T/19
note | Acceptance Criteria: Dry ITS > 250 Kpa Soaked ITS >150 Kpa
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
checkpoint | 507.20 -
note | Detail of Activity: Dry back Moisture Content (Degree of Saturation)
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 9 per Lot
note | • *1 lot = 1000m³ or 250lm (whichever is least)
note | Inspection / Test Method: NDM NZS 4407.4.2.1
note | Acceptance Criteria: TNZ B/7 8.5 DOS ≤ 80% preferably ≤ 70%
note | Record Documents: IANZ accredited laboratory
note | Responsibility: Contractor
note | Comments: Only required if pavement widening extends into trafficked lane
checkpoint | 507.21 - Surface conformity
note | Detail of Activity: Layer Width
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: every 20m
note | Inspection / Test Method: Measurement
note | Acceptance Criteria: ±100 mm, -20mm
note | Record Documents: Survey
note | Responsibility: Contractor
checkpoint | 507.22 - Surface conformity
note | Detail of Activity: Surface Shape
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: every 20m
note | Inspection / Test Method: Measurement
note | Acceptance Criteria: < 6mm using 3m straight edge
note | Record Documents: Work sheet
note | Responsibility: Contractor
checkpoint | 507.23 - Surface conformity
note | Detail of Activity: Surface Levels
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: every 20m
note | Inspection / Test Method: Measurement
note | Acceptance Criteria: -5mm, +15mm
note | Record Documents: Survey
note | Responsibility: Contractor
checkpoint | 507.24 - Surface conformity
note | Detail of Activity: Assessment of all test results for conformity
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Each Lot
note | Inspection / Test Method: Site Inspection
note | Acceptance Criteria: Reporting of any non-conforming results to Designer via NCR.
note | Record Documents: NCR
note | Responsibility: Safe Roads
section | SPECIFICATION 522: BITUMINOUS SEAL COAT
checkpoint | 522.1 - Pre-seal inspection
note | Detail of Activity: Visual inspection of surface to be sealed
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: per sealing schedule. 1 Lot = 1 day's production and < 1500m2
note | Inspection / Test Method: Visual inspection
note | Acceptance Criteria: NZTA B/02
note | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
note | • The large aggregate is
note | • exposed to the surface;
note | • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material;
note | • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter
note | Record Documents: Seal inspection record
note | Responsibility: Safe Roads' Rep.
note | Comments: The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
checkpoint | 522.2 - Seal Design
note | Detail of Activity: Seal design outling all design assumptions
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per seal application type
note | Inspection / Test Method: Review
note | Acceptance Criteria: New Zealand Chip Sealing Handbook
note | Record Documents: Seal design in contractor's site folder
note | Responsibility: Contractor
checkpoint | 522.3 - Check raw materials
note | Detail of Activity: Sealing Aggregates Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: 1. Polished Stone Value
note | 2. Crushing Resistance
note | 3. Weathering Quality Index
note | 1. BS 812: Part 114
note | 2. NZS 4407:1991, Test 3.10
note | 3. NZS 4407:1991, Test 3.11
note | Acceptance Criteria: TNZ M06 / RNZ 9805:2009
note | 1. Polished Stone Value Required = 45
note | 2. Crushing Resistance: <10% fines p[assing 2.36 under 230 KN load
note | 3. Weathering Quality Index: AA or BA
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
checkpoint | 522.4 - Check raw materials
note | Detail of Activity: Sealing Aggregates Source Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per source, 1 test per 10,000m3 (min 1 per source)
note | Inspection / Test Method: Broken Faces NZS 4407:1991, Test 3.14
note | Acceptance Criteria: TNZ M/6 4.1.2, 98% with minimum two broken faces
note | Record Documents: IANZ Report
note | Responsibility: Contractor
checkpoint | 522.5 - Check raw materials
note | Detail of Activity: Sealing Aggregates Production
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per 500m³
note | Inspection / Test Method: Size & Shape NZS 4407:1991, Test 3.13
note | Acceptance Criteria: TNZ M/6 4.1.2
note | • Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD
note | • Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD
note | • Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm
note | Record Documents: IANZ Report
note | Responsibility: Contractor
checkpoint | 522.6 - Check raw materials
note | Detail of Activity: Sealing Aggregates Production
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per 500m³
note | Inspection / Test Method: Cleanliness NZS 4407:1991, Test 3.9
note | Acceptance Criteria: TNZ M/6 4.2.3
note | • G2 chip: 89
note | • G3 chip: 87
note | • G4 chip: 85
note | • G5 chip: Report only G5 chip: Report Only
note | Record Documents: IANZ Report
note | Responsibility: Contractor
checkpoint | 522.7 - Check raw materials
note | Detail of Activity: Sealing Aggregates Production
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per 500m³
note | Inspection / Test Method: PSD NZS 4407:1991, Test 3.8
note | Acceptance Criteria: NZTA M/06
note | ○ Grade 5: 100% passing 13.2mm
note | • 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300μm
note | ○ Grade 6:
note | • 100% passing 9.5mm
note | • 95-100% max passing 6.7mm 15% max passing
note | • 2.36mm
note | • 8% max passing 300μm
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: Test certificates issued to the Engineers Rep at least 10 days prior to sealing
checkpoint | 522.8 - Check raw materials
note | Inspection / Test Method: Penetration ASTM D5
note | • Penetration of residue, at 25°C, 100g, five seconds, % of original
checkpoint | 522.9 - Check raw materials
note | Inspection / Test Method: Viscosity
note | • AS 2341.2 or ASM D2171
note | • Viscosity PaS at 60°C
checkpoint | 522.10 -
note | Detail of Activity: Bitumen Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test
note | Inspection / Test Method: Viscosity
note | • AS 2341.3 or ASM D2170
note | • Viscosity mm2/s at 135°C
note | Acceptance Criteria: Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint | 522.11 -
note | Detail of Activity: Bitumen Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test
note | Inspection / Test Method: Flash point ASTM D92
note | • Flash point (Cleveland open cup), °C
note | Acceptance Criteria: Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint | 522.12 -
note | Detail of Activity: Bitumen Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test
note | Inspection / Test Method: Solubility
note | • ASTM D2042, AS 2341.8
note | • Solubility in Trichloroethylene, % or Solubility in Toluene, %
note | Acceptance Criteria: Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint | 522.13 -
note | Detail of Activity: Bitumen Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test
note | Inspection / Test Method: Rolling Thin Film
note | • ASTM D2872 or AS 2341.10
note | • Rolling Thin Film Oven Test
note | Acceptance Criteria: Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint | 522.14 -
note | Detail of Activity: Bitumen Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 2 samples per distributor
note | Inspection / Test Method: Durability
note | • NZTA M01 - Table 5
note | Acceptance Criteria: Complies with requirements for penetration grade as per TNZ M/01 Table 1
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Refer notes in clause 5 of NZTA M01
checkpoint | 522.15 -
note | Detail of Activity: Bitumen Properties
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test
note | Inspection / Test Method: Ductility ASTM D113
note | • Ductility of residue, at 25°C, (metres)
note | Acceptance Criteria: Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint | 522.16 -
note | Detail of Activity: Adhesion Agents
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to use
note | Acceptance Criteria: NZTA M06 / NZTA M13
note | Record Documents: Certificate in contractor's site folder
note | Responsibility: Contractor
note | Comments: Retain for testing if required
checkpoint | 522.17 -
note | Detail of Activity: Audit samples
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 20 kg per stockpile
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Stored in a sealed plastic bag in a covered environment
note | Record Documents: ITP
note | Responsibility: Contractor
note | Comments: Retain for testing if required
checkpoint | 522.18 - Confirm surface for sealing
note | Detail of Activity: Dry back Moisture Content (Degree of Saturation)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Confirm testing has been completed and surface has not been saturated after testing and before sealing.
note | Inspection / Test Method: Confirm testing has been completed and surface has not been saturated after testing and before sealing.
note | Acceptance Criteria: Confirm testing has been completed and surface has not been saturated after testing and before sealing.
note | Record Documents: Confirm testing has been completed and surface has not been saturated after testing and before sealing.
note | Responsibility: Confirm testing has been completed and surface has not been saturated after testing and before sealing.
checkpoint | 522.19 - Chipseal Production
note | Detail of Activity: Spraying Temperature
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Ongoing with non-going heat sensing gauge
note | Inspection / Test Method: Non-contact heat sensing gun
note | Acceptance Criteria: NZTA P03 - Table 2
note | Record Documents: ITP
note | Responsibility: Contractor
checkpoint | 522.20 - Chipseal Production
note | Detail of Activity: Spray sheets
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: On day of seal
note | Inspection / Test Method: Report
note | Acceptance Criteria: Report value only
note | Record Documents: Surfacing Subcontractor's Quality Representative
section | SPECIFICATION 580: SAFETY BARRIERS
checkpoint | 800.1 - Ground conditions testing
note | Detail of Activity: Bearing strength of foundation depth
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 Scala every 20m, All leading and terminal ends Or as directed by the Engineer
note | Inspection / Test Method: NZS 4402.6.5.2
note | Acceptance Criteria: For design input
note | Record Documents: Scalar test sheet
note | Responsibility: Contractor
note | Comments: Test results provided to Eng.Rep.. for analysis. Safe Roads provides foundation size details
checkpoint | 800.2 - Ground conditions testing
note | Detail of Activity: Linear Shrinkage (LS)
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test every 250m, All leading and terminal ends Or as directed by the Engineer
note | Inspection / Test Method: NZS 4402.2.6
note | Acceptance Criteria: For design input
note | Record Documents: IANZ Report
note | Responsibility: Contractor
note | Comments: Test results provided to Eng.Rep.. for analysis. Safe Roads provides foundation size details
checkpoint | 800.3 - Ground conditions testing
note | Detail of Activity: Shear Vane (SV)
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test every 250m, All leading and terminal ends Or as directed by the Engineer
note | Inspection / Test Method: NZ Geotechnical Society Guide (Aug 2001)
note | Acceptance Criteria: For design input
note | Record Documents: Shear Vane test sheet
note | Responsibility: Contractor
note | Comments: Test results provided to Eng.Rep.. for analysis. Safe Roads provides foundation size details
checkpoint | 800.4 - WRSB Pile Excavation
note | Detail of Activity: Excavation size and shape
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All excavations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Ground is level
note | Record Documents: Check sheet
note | Responsibility: Safe Roads
checkpoint | 800.5 - WRSB Pile Excavation
note | Detail of Activity: Excavation size and shape
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All excavations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Excavated depth as specified
note | Record Documents: Check sheet
note | Responsibility: Safe Roads
checkpoint | 800.6 - WRSB Pile Excavation
note | Detail of Activity: Excavation size and shape
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All excavations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Sides of excavation parallel and not collapsing
note | Record Documents: Check sheet
note | Responsibility: Safe Roads
checkpoint | 800.7 - WRSB Pile inspection before casting concrete
note | Detail of Activity: Pile specifics
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Plastic socket in correct position and well secured
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.8 - WRSB Pile inspection before casting concrete
note | Detail of Activity: Pile specifics
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Rebar ring position in correct position
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.9 - WRSB Pile inspection before casting concrete
note | Detail of Activity: Pile specifics
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Rebar position in correct position (type B to type E)
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.10 - Pile position
note | Detail of Activity: Pile position
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Sufficient supporting slope outside the line of the posts in relation to pile size
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.11 - Pile position
note | Detail of Activity: Pile spacing
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Post spacing's as per the Construction Drawings or NTCs
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.12 - Pile position
note | Detail of Activity: Post orientation
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Slot orientation consistent for the entire length of the barrier
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.13 - Cast WRSB Pile
note | Detail of Activity: Check condition of finished pile
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All Piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Top of pile is level and Flush with ground at front face of pile
note | Record Documents: Check sheet
note | Responsibility: Safe Roads
checkpoint | 800.14 - Cast WRSB Pile
note | Detail of Activity: Check condition of finished pile
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All Piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Top of pile is formed to specified diameter (+50mm, -0mm)
note | Record Documents: Check sheet
note | Responsibility: Safe Roads
checkpoint | 800.15 - Cast WRSB Pile
note | Detail of Activity: Excess concrete removed from site
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All Piles
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: No signs of concrete
note | Record Documents: Check sheet
note | Responsibility: Safe Roads
checkpoint | 800.16 -
note | Detail of Activity: Cables at correct position as per manufacturer's installation manual
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All posts
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Cables are in or on the seating position
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.17 - Installed WRSB system
note | Detail of Activity: O' ring seal is positioned on all posts at the top of socket (if applicable for system)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All posts
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: 100%
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.18 - Installed WRSB system
note | Detail of Activity: All posts have plastic cap inserted into the post (if applicable for system)
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All posts
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: 100%
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.19 - Installed WRSB system
note | Detail of Activity: All cables are tensioned correctly
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All barrier lengths
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: As per manufacturer's installation manual
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.20 - On-site post testing
note | Detail of Activity: Pull test as per manufacturer's instruction
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 per 100m of barrier length
note | Inspection / Test Method: Manufacturer's instructions
note | Acceptance Criteria: As per manufacturer's installation manual
note | Record Documents: Test Certificate
note | Responsibility: Contractor
checkpoint | 800.21 - Installed WSB system
note | Detail of Activity: Barrier section at correct position as per manufacturer's installation manual
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All posts
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Barrier is at correct height and secured correctly
note | Record Documents: Check sheet
note | Responsibility: Contractor
checkpoint | 800.22 -
note | Detail of Activity: All cables are tensioned correctly
note | M
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All barrier lengths
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: As per manufacturer's installation manual
note | Record Documents: Check sheet
note | Responsibility: Contractor
section | SPECIFICATION 810: ROAD SIGNS
checkpoint | 810.1 - Mark out works
note | Detail of Activity: Set out new roadmarkings, RRPMS, delineators and any associated removal works
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All roadmarking and delination installations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: N/A
note | Record Documents: NTC / Site instruction
note | Responsibility: Contractor
checkpoint | 810.2 - Retro-reflective sheeting supplier
note | Detail of Activity: Evidence of a quality assurance system that has been certified by a Joint Accreditation System Australia and New Zealand (JAS-ANZ) accredited agency.
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Six weeks prior to the construction of any sign.
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve
note | Record Documents: Compliance information
note | Responsibility: Contractor
checkpoint | 810.3 - Retro-reflective sheeting supplier
note | Detail of Activity: Evidence of technical representation in New Zealand.
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to construction.
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve
note | Record Documents: Compliance information
note | Responsibility: Contractor
checkpoint | 810.4 - Retro-reflective sheeting supplier
note | Detail of Activity: Evidence of a formal technical qualification programme with the sign manufacturers using their material.
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to construction.
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve
note | Record Documents: Certificate
note | Responsibility: Contractor
checkpoint | 810.5 - Retro-reflective sheeting supplier
note | Detail of Activity: Proof that an approved quality system is in place.
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Within 48 hours of request.
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve
note | Record Documents: Compliance information
note | Responsibility: Contractor
checkpoint | 810.6 - Retro-reflective sheeting supplier
note | Detail of Activity: An original certificate written and issued by the retro-reflective sheeting manufacturer that the sign manufacturer has a formal technical qualification for using their material.
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Within 48 hours of request.
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve
note | Record Documents: Certificate
note | Responsibility: Contractor
checkpoint | 810.7 - Retro-reflective sheeting supplier
note | Detail of Activity: A compliance certificate issued by an independent qualified testing laboratory.
note | W
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Within 48 hours of request.
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve
note | Record Documents: Certificate
note | Responsibility: Contractor
checkpoint | 810.8 - Retro-reflective sheeting supplier
note | Detail of Activity: Visual inspection of completed traffic signs
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All traffic sign installations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Compliance with project specifications
note | Record Documents: NTC / Site instruction
note | Responsibility: Contractor
section | SPECIFICATION 820: PAVEMENT MARKING AND DELINEATION
checkpoint | 820.1 - Mark out works
note | Detail of Activity: Set out new roadmarkings, RRPMS, delineators and any associated removal works
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All roadmarking and delination installations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: N/A
note | Record Documents: NTC/ Site instruction
note | Responsibility: Contractor
checkpoint | 820.2 - Pavement marking material informations and certification
note | Detail of Activity: Contractor to provide Certification of Compliance of Application Machine
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to commencing works
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve
note | Record Documents: NTC/ Site instruction
note | Responsibility: Contractor
checkpoint | 820.3 - Pavement marking material informations and certification
note | Detail of Activity: Contractor to provide brand and type of high perfomance marking to be used
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: Prior to commencing works
note | Inspection / Test Method: N/A
note | Acceptance Criteria: Engineer to review and approve proposed lighting columns and luminaries
note | Record Documents: NTC/ Site instruction
note | Responsibility: Contractor
checkpoint | 820.4 - Application Testing
note | Detail of Activity: Reflectivity
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per line type
note | Inspection / Test Method: TNZ M/20
note | Acceptance Criteria: Engineer to review in accordance with TNZ P/30
note | Record Documents: Test Results
note | Responsibility: Contactor
note | Comments: Needs review to meet current specifications
checkpoint | 820.5 - Application Testing
note | Detail of Activity: Skid resistance
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: 1 test per line type
note | Inspection / Test Method: TNZ M/20
note | Acceptance Criteria: Engineer to review in accordance with TNZ P/30
note | Record Documents: Test Results
note | Responsibility: Contactor
note | Comments: Needs review to meet current specifications
checkpoint | 820.6 - Complete road marking
note | Detail of Activity: Visual inspection of completed road marking installations
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All roadmarking installations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Compliance with project specifications
note | Record Documents: NTC/ Site instruction
note | Responsibility: Contactor
checkpoint | 820.7 - Completed raised reflectoristed pavement markings
note | Detail of Activity: Visual inspection of completed raised reflectorised pavement markings
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All roadmarking installations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Compliance with project specifications
note | Record Documents: NTC/ Site instruction
note | Responsibility: Contractor
checkpoint | 820.8 - Completed delineators
note | Detail of Activity: Visual insoection of completed road delineators
note | H
note | Minimum Test Frequency (Lot = 1 day’s production or 2,500m2) or as specified in the frequency: All delineators installations
note | Inspection / Test Method: Visual Inspection
note | Acceptance Criteria: Compliance with project specifications
note | Record Documents: NTC/ Site instruction
note | Responsibility: Contractor