## Table 1
Item | Task/Activity/Description | Inspection/Test |  |  |  | Acceptance Criteria | Record documents | Responsibility | Comments | Checked by |  |  | QA Pack Reference
|  | Detail of Activity | Action | Minimum Test Frequency | Inspection / Test method |  |  |  |  | Saferoads | Contractor | Date
|  |  | (Hold, | (Lot = 1 day’s production or 2,500m2) or as specified in the frequency
Monitor,
Witness)
SPECIFICATION: 100 (GENERAL FOR PROJECT)
100.1 | Physically located all utility locations | Permit to work around services (Gas, Power, Fibre, etc.) | H | as required per section of works | Document Review | All services physically located | Permit attached or permit number noted | Contractor
100.2 | Contract Document Signed | Ensure Contract is signed | H | at the Contract kickoff meeting | Document Issue | N/A | Issued with a NTC | Safe Roads' Rep.
100.3 | "For Construction" Drawings Isssued | Ensure "For Construction" drawings are issued | H | at the Contract kickoff meeting | Document Issue | N/A | Issued with a NTC | Safe Roads' Rep.
100.4 | Traffic Management Plan | Ensure TMP is approved and check that the requirements are fully understood by the STMS | H | every morning and/or when the TMP changes | Document and Physical works review | COPTTM | TMP from contractor | Contractor
100.5 | Design | Ensure that Design is approved and drawings are the latest revision | H | Prior to commencement | Document Review |  | Check Drawing register | Contractor | Drawing register maintained by Safe Roads and e- mailed to contractor when revised drawings are issued
100.6 | Approved Consents | Is a copy of approved consent(s) available on site | H | Prior to commencement | Visual Inpection |  | This ITP | Safe Roads' Rep.
100.7 | Pre-start meeting | Pre-start meeting to confirm work strategy and safety measures | H | Before commencing work each day | N/A | 100% attendance | Pre-start sign on register / site diary | Contractor
100.8 | Contractor's methodology | Approval of Contractor's methodology | H | Prior to commencement | Document review | Methodology conforms with all relevant specifications | Methodology submitted via NTE | Safe Roads' Rep. | Methodology submitted min. 7 working days and approval min. 3 working days prior to commencement
100.9 | Laydown area / stockpile sites | Site inspection | M | Prior to commencement | Visual Inspection | Approved by Safe Roads | Request for approval (RFA) via NTE | Safe Roads' Rep. | RFA submitted min. 7 working days and approval min. 3 working days prior to commencement
100.1 | Weather | Assessment of forecast | H | Daily prior to and during works | Check local and national weather forcast services | No imminent rain or adverse weather conditions. Consideration of wind and project location/environment | Contractor's site diary | Contractor
100.11 | Environmental Protection | Site evaluation | M | Prior to commencement | Inspection | Supervisor assessment of conformance | Contractor's site diary | Contractor
SPECIFICATION: 302 EARTHWORKS (Widening Works)
Setout, Materials and Preparation
302.1 | Mark out and approve | Set out and mark up of extent of earthworks | H | All earthworks areas | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
302.2 | Underground services | Identify and positively locate services | H | All earthworks areas | Hydoexcavation | N/A | Drawings | Contractor
302.3 | Determine Embankment / Subgrade | Determine bearing strength of subgrade Strength | H | 1 Scala per 20m | Scala Penetrometer Test NZS 4402.6.5.2 | SUBBASE DEPTH WHERE SUBGRADE <6% CBR DEPTH ADDITIONAL REQUIREMENT 4% (2blows/100mm) 320mm - 2% (1blows/100mm) 540mm Geotextile (Strength Class C) on excavation floor | IANZ Report | Contractor | Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if appliacable.
302.4 | GENERAL FILL | General Fill Source Properties | M | 1 per source stockpile (1 test per 10,000m³) | Determination of MDD & OMC Compaction to NZS 4402 Part 2P: 1981, Test 14 "Determination of the Dry Density/Water Content Relationship (NZ Standard Compaction)". | Report value only | IANZ Report | Contractor
302.5 | GAP65 HARDFILL | Hardfill Source Properties | M | 1 per source stockpile (1 test per 10,000m³) | PSD NZS 4407: 1991 Test 3.8.1 | Project Spec GAP65 100% passing 63mm 77-90% passing 37.5mm 55-75% passing 19mm 40-60% passing 9.5mm 28-48% passing 4.75mm 18-25% passing 1.18mm 6-18% passing 600µm 3-15% passing 300µm 2-14% passing 150µm 0-9% passing 75µm
302.6 |  |  | M | 1 per source stockpile (1 test per 10,000m³) | Determination of MDD & OMC Compaction to NZS 4402 Part 2P: 1981, Test 14 "Determination of the Dry Density/Water Content Relationship (NZ Standard Compaction)". | Report Value Only
302.7 |  |  | M | 1 per source stockpile (1 test per 10,000m³) | Weathering Quality Index Test NZS 4407 : 1991, Test 3.11 | AA, AB, AC, BA , BB, CB
302.8 |  |  | M | Three tests on samples randomly selected in accordance with NZ 4402 clause 1.6.3 and 1.6.4 from a truck or stockpile at the site of works. The tests shall consist of 4- day soaked CBRs carried out to NZS 4402. | Soaked CBR Compaction to NZS 4402 Part 2P: 1981, Test 14. CBR testing to NZS 4402 | Insitu CBR of 40 + 1.3 standard deviation (s) over the three samples
Construction and Finshing
GENERAL FILL
302.9 | Testing of placed material Test with a Scala if the material allows it (Pumice etc), or with NDM on material that doesn't allow it (millings etc) | Strength of placed material (Pumice, sand etc) | W | All earthworks areas 1 Lot < 300m long per 0.5m lift | Scala penetrometer test NZS 4402.6.5.2 | 4 blows / 100mm | Contractor's site diary | Contractor
302.1 |  | Compaction (millings etc) | W | All earthworks areas 1 Lot < 300m long per 0.5m lift | Nuclear Density Meter NZS 4407.4.2.1 | Minimum field density of 95% of maximum dry density (MDD) obtained by standard compaction | Contractor's site diary | Contractor
302.11 |  | Proof roll of placed material | M | All earthworks areas per 0.5m lift | Visual Inspection | No significant visual deformation under the wheel load | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
Construction and Finshing (Hardfill)
HARDFILL (Granular material)
302.12 | Testing of placed material GAP65 | Proof roll of placed material | W | All earthworks areas per 0.5m lift | Visual Inspection | No significant visual deformation under the wheel load =< 7mm for bulk fill =< 5mm for subgrade fill | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
302.13 |  | Compaction | M | All earthworks areas 1 Lot < 300m long per 0.5m lift | Nuclear Density Meter NZS 4407.4.2.1 | Minimum field density of 95% of maximum dry density (MDD) obtained by standard compaction | Contractor's site diary | Contractor
SPECIFICATION: 402 STORMWATER DRAINAGE
402 | Setout, Materials and Preparation
402.1 | Mark out works | Set out and mark up proposed drainage features | H | All drainage features | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
402.2 | Underground services | Identify and positively locate services | H | All drainage features | Hydoexcavation | N/A | Drawings | Contractor
402.3 | Precast tranversable wingwall design | Contract to provide manufacturer dwgs of the proposed sturcture design for approval | H | 1 per wingwall type | N/A | Engineer to review and approve proposed design | NTC / Site instruction | Contractor | This requirement acknowledges minor variances in manufacturer design details for precast wingwalls
402.4 | Determine Embankment / Subgrade Strength | Determine bearing strength of subgrade | H | 1 per 5m length of trench base; or | Scala Penetrometer NZS 4402.6.5.2 | 2 blows per 100mm (CBR4%) - increase bedding depth by 100mm 1 blows per 100mm (CBR2%) - increase bedding depth by 300mm | IANZ Report | Contractor | Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if appliacable.
402.5 | Trench backfill | Hardfill Source Properties (as per Specification 302 - Earthworks) | W | 1 per source | Determination of MDD & OMC NZS 4402: Test 4.1.3 | For analysis of DoC | IANZ Report | Contractor | By IANZ accredited lab
Construction and Finshing
402.6 | Trench backfill | Compaction (trench inside of carrigeway) | H | 1 per 5m trench per 1m lift | NDM NZS 4407.4.2.1 | NZTA B02: DoC ≥ 95% | IANZ Report | Contractor
402.7 | Trench backfill | Compaction (trench more than 1m outside of carrigeway) | H | 1 per 5m trench per 1m lift | Clegg Hammer | Need to issue NTE to confirm this
402.8 | Structures (manholes, head walls etc.) | Visual inspection of completed structure | H | 1 per structure | Visual Inspection | No visible leakage through joints | NTC / Site instruction | Contractor
402.9 | CCTV Inspection | Visual record of completed works | W | All drainage pipelines | CCTV Inspection | No significant cracks, level deformation, faulty joints | CCTV Footage | Contractor | CCTV footage to be reviewed by Engineers Representative and signed off via NTC / Site Instruction
SPECIFICATION: 406 STONE RIPRAP
406 | Setout, Materials and Preparation
406.1 | Mark out and approve | Set out and mark up of scour protection area | H | All locations scour protection is required | Visual Inspection | Engineer to confirm | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
406.2 | Confirm filter material | Contract to provide manufacture specifications proposed filter materials | H | 1 per material type | N/A | Engineer to review and approve proposed material in accordance with TNZ F/7 | NTC / Site instruction | Contractor | Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if appliacable.
406.3 | Confirm rip rap material | RipRap Source Properties | M | 1 per material type | PSD Grading: Individual stones shall be approximately cubical or spherical with a nominal dimension of 300mm, with no stone less than 100mm nor greater than 400mm. Grading shall be confirmed by weighing a sample of 100 stones. The average weight shall be in the range 35 to 40 kg, with no stone less than 5kg and no stone greater than 90kg (machine placed). | d50 = 250mm riprap 100% passing 400mm 84-72% passing 300mm 50-30% passing 250mm 20-8% passing 150mm 7-3% passing 80mm | Laboratory Test Results | Contractor | Laboratory test may be substitued for a visual inspection (if instructed by the Engineer)
[5 empty] | Crushing Resistance Test NZS 4407 : 1991, Test 3.10 | Not less than 150kN when tested in accordance with NZS4407
[5 empty] | Weathering Quality Index Test NZS 4407 : 1991, Test 3.11 | AA, AB, AC, BA or BB
[5 empty] | Solid Density NZS 4407 : 1991, Test 3.7 | => 2.6T/m³ | Issue NTE to confirm this is not nessesary due to location of riprap placement
[5 empty] | Abrasion Resistance | Abrasion resistance (using the Los Angeles Test): With less than 25% loss of weight after 500 revolutions in accordance with NZS4407. | Issue NTE to confirm this is not nessesary due to location of riprap placement
Construction and Finshing
406.4 | Final Inspection | Engineer to inspect the final works | H | All locations scour protection is required | Visual Inspection | No significant visual deformation under the wheel load | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
SPECIFICATION: 410 VEHICLE CROSSING AND FOOTPATHS
SPECIFICATION: 506 GRANULAR PAVEMENT (Widening Works)
506 | Setout, Materials and Preparation
506.1 | Mark out and approve | Set out and mark up of treatment area | H | All areas of shoulder top-up. | Visual Inspection | N/A | Contractor's site diary | Contractor | Treatment area marked up jointly by Contractor and Eng.Rep. Approved by Designer
506.2 | Determine Embankment / Subgrade Strength (Shoulder Top-up) | Proof Roll the excavated area (bottom of 100mm topup horizon) | H | All areas of shoulder top-up. 1 Lot < 300m long. | Visual Inspection | No significant visual deformation under the wheel load | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in daily diary
506.3 | Determine Embankment / Subgrade Strength (Pavement Widening) | Determine bearing strength of subgrade | H | 1 Scala per 20m | NZS 4402.6.5.2 | SUBBASE DEPTH WHERE SUBGRADE <6% CBR DEPTH ADDITIONAL REQUIREMENT 4% (2blows/100mm) 320mm - 2% (1blows/100mm) 540mm Geotextile (Strength Class C) on excavation floor | IANZ Report | Contractor | Refer to Barrier Installation section - these scalas can be used for the design of WRSB foundation design if appliacable.
506.4 | Confirm pavement thickness design | Confirm Pavement thickness | H | 1 per section | AGPT Part2: Fig.8.4 if widening area is trafficked | Pavement thickness is minimum of adjacent existing pavement (to ensure drainage) and Figure 8.4 (if widening area is trafficked) | NTC | SR Designer
506.5 | Confirm Subbase Material | Subbase Aggregate (Hardfill) Source Properties | M | 1 per source stockpile (1 test per 10,000m³) | PSD NZS 4407: 1991 Test 3.8.1 | Project Spec GAP65 100% passing 63mm 77-90% passing 37.5mm 55-75% passing 19mm 40-60% passing 9.5mm 28-48% passing 4.75mm 18-25% passing 1.18mm 6-18% passing 600µm 3-15% passing 300µm 2-14% passing 150µm 0-9% passing 75µm | Certificate in contractor's site folder | Contractor | Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
|  |  | M | 1 per source stockpile (1 test per 10,000m³) | Determination of MDD & OMC Compaction to NZS 4402 Part 2P: 1981, Test 14 "Determination of the Dry Density/Water Content Relationship (NZ Standard Compaction)". | Report Value Only
|  |  | M | Three tests on samples randomly selected in accordance with NZ 4402 clause 1.6.3 and 1.6.4 from a truck or stockpile at the site of works. The tests shall consist of 4- day soaked CBRs carried out to NZS 4402. | Soaked CBR Compaction to NZS 4402 Part 2P: 1981, Test 14. CBR testing to NZS 4402 | Insitu CBR of 40 + 1.3 x s (where s=standard deviation) over the three samples
|  |  | M | 1 per source stockpile (1 test per 10,000m³) | Weathering Quality Index Test NZS 4407 : 1991, Test 3.11 | AA, AB, AC, BA , BB, CB
506.6 |  |  |  |  | PSD NZS 4407: 1991 Test 3.8.1 | NZTA M04 / Project Spec AP40 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600μm 3 - 14 passing 300μm 0 - 10 passing 150μm 0 - 7 passing 75μm AP20 100% passing 19mm 55 - 75% passing 9.5mm 33 - 55 passing 4.75mm 22 - 42 passing 2.36mm 14 - 31 passing 1.18mm 8 - 23 passing 600μm 5 - 16 passing 300μm 0 - 12 passing 150μm 0 - 8 passing 75μm | Certificate in contractor's site folder | Contractor | Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
506.7 | Confirm Basecourse Material | Basecourse Aggregates Source Properties | M | 1 per source stockpile (1 test per 10,000m³) | Atterburg Limit ( Plastisity Index) NZS 4407:1991, Test 3.4 | Report value only
[5 empty] | Determination of MDD & OMC NZS 4402: Test 4.1.3 | Report value only
[5 empty] | Soaked CBR Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15 | TNZ M/4 3.3.3 ≥ 80%
[5 empty] | Solid Density NZS 4407 : 1991, Test 3.7 | Report Value Only | IANZ accredited laboratory | Contractor
506.8 |  |  |  |  | Crushing Resistance Test NZS 4407 : 1991, Test 3.10 | TNZ M/4 3.3.1 <10% fines passing 2.36mm under 130 KN load | Certificate in contractor's site folder | Contractor
506.9 |  |  |  |  | Weathering Quality Index Test NZS 4407 : 1991, Test 3.11 | TNZ M/4 3.3.2 AA, AB, AC, BA, BB or CA | Certificate in contractor's site folder | Contractor
506.1 |  | Basecourse Aggregates Production | M | 0-400m3=2 tests 400-1500m3=3 tests 1500-4000m3=4 tests >4000m3=1 test/1000m3 | PSD NZS 4407 : 1991, Test 3.8.1 | NZTA M04 / Project Spec 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600μm 3 - 14 passing 300μm 0 - 10 passing 150μm 0 - 7 passing 75μm | Certificate in contractor's site folder | Contractor | Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
506.11 |  |  | M |  | Sand equivalent NZS4407 : 1991, Test 3.6 | TNZ M/4 4.2.1.1 >= 40 | IANZ accredited laboratory | Contractor
Construction and Finshing
SHOULDER TOP-UP CONSTRUCTION
506.12 | Shoulder Top-Up | Proof Roll top of topup area (finished shoulder) | W | All areas of shoulder top-up | Visual Inspection | No significant visual deformation under the wheel load =< 7mm for bulk fill =< 5mm for subgrade fill | Contractor's site diary | Contractor | Witnessed by Engineers Representative and signed off in contractor's daily diary
506.13 |  | Clegg Hammer | M | 1 CIV per 20 m2 | Clegg Impact Value Test | Average CIV > 40 Min. CIV > 35 | Contractor's CIV form appended to Contractor's daily diary | Contractor
SUBBASE CONSTRUCTION
506.14 | Subbase | Determine bearing strength of subgrade | M | Confirm that subbase strength (Scala) has been completed and within spec
506.15 |  | Target Maximum Dry Density (Determination of MDD & OMC) | M | 1 per 5,000m2 of material laid | Determination of MDD & OMC NZS 4402: Test 4.1.3 | report value only | IANZ Report | Contractor | By IANZ accredited lab
506.16 |  | Compaction | H | 9 per Lot | NDM NZS 4407.4.2.1 | NZTA B02: DoC ≥ 95% | IANZ Report | Contractor
BASECOURSE CONSTRUCTION
506.17 | Basecourse | Target Maximum Dry Density (Determination of MDD & OMC) | M | One per 5,000m2 of material laid | Determination of MDD & OMC NZS 4402: Test 4.1.3 | report value only | IANZ Report | Contractor | By IANZ accredited lab
506.18 |  | Compaction | H | 9 per Lot | NDM NZS 4407.4.2.1 | NZTA B02: DoC ≥ 98% | IANZ Report | Contractor
SPECIFICATION:507 TNZ M4: 2006 NZTA B/07:2012, Specification for the Manufacture and Construction on Plant Mix Modified Pavement Layers.
507 | Setout, Materials and Preparation
507.1 | Setout | Install offset pegs; record centreline, edgeline or mark out stabilisation extents from existing line marking | M | Prior to works | Measurement | Document existing furniture | ITP | Contractor
507.2 | Check raw materials | Cement | M | Per Batch | NZS 3122 | For design input | Certificate in contractor's site folder | Contractor | Check prior to arrival on site
507.3 | Check raw materials AP40 | Basecourse Aggregates Production before the addition of cement | M | 0-400m3=2 tests 400-1500m3=3 tests 1500-4000m3=4 tests >4000m3=1 test/1000m3 | PSD NZS 4407 : 1991, Test 3.8.1 | NZTA M04 / Project Spec 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600μm 3 - 14 passing 300μm 0 - 10 passing 150μm 0 - 7 passing 75μm | Certificate in contractor's site folder | Contractor | Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
507.4 |  |  | M |  | Sand equivalent NZS4407 : 1991, Test 3.6 | TNZ M/4 4.2.1.1 >= 40 | IANZ accredited laboratory | Contractor
507.5 |  | Basecourse Aggregates Source Testing | M | 1 test per source 1 test per 10,000m3 (min 1 per source) | Atterburg Limit ( Plastisity Index) NZS 4407:1991, Test 3.4 | TNZ M/4 4.2.1.3 =<5 | IANZ accredited laboratory | Contractor | Test certificate(s) to include PSD, Atterberg Limits, MDD, OMC on material sampled from the loaded stockpile and not more than 2 months old
507.6 |  |  | M |  | Determination of MDD & OMC NZS 4402: Test 4.1.3 | Report Value Only | IANZ accredited laboratory | Contractor
507.7 |  |  | M |  | Crushing Resistance Test NZS 4407 : 1991, Test 3.10 | TNZ M/4 3.3.1 <10% fines passing 2.36mm under 130 KN load | Certificate in contractor's site folder | Contractor
507.8 |  |  | M |  | Weathering Quality Index Test NZS 4407 : 1991, Test 3.11 | TNZ M/4 3.3.2 AA, AB, AC, BA, BB or CA | Certificate in contractor's site folder | Contractor
507.9 |  |  | M |  | Soaked CBR Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15 | TNZ M/4 3.3.3 ≥ 80% | Certificate in contractor's site folder | Contractor
507.1 |  |  | M |  | Solid Density NZS 4407 : 1991, Test 3.7 | Report Value Only | IANZ accredited laboratory | Contractor
507.11 |  |  | M |  | Broken Faces Content NZS 4407 : 1991, Test 3.14 | TNZ M/4 4.2.2 19mm-37.5mm 9.5mm-19.mm acceptance criteria = none >= 70% retained 4.75mm-9.5mm | IANZ accredited laboratory | Contractor
Construction and Finshing
TNZ M4 - AP40 2% CMB CONSTRUCTION
507.12 | Site plan | Daily Production Plan | M | NZTA B/7 7.2.3 Before the commencement of the day’s work | Report | Report only | Report | Contractor
507.13 | Cement | Cement Feed | M | NZTA B/7 7.3.2 Record Plant Display Reading | weight of cement | Plant Display Reading +/- 5% of specified rate | Supplier quality representative | Contractor
507.14 |  | Cement Feed | M | NZTA B/7 7.3.2 Average usage test upon emptying the bulk tanker | weight of cement | compare tonnes used with measured qty +/- 5% of specified rate | Supplier quality representative | Contractor
507.15 | Production AP40 2% CMB | Particle size distribution lab to take sufficient material to perform Dry back Moisture Content Analysis (modified material) | M | 3 per Lot (completed within 4 hours of mixing to ensure all particle sizes can be washed off prior to cementing) *1 lot = 1000m³ or 250lm (whichever is least) as per B/07 | Wet sieving test NZS 4407 : 1991, Test 3.8.1 | TNZ M/04 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600μm 3 - 14 passing 300μm 0 - 10 passing 150μm 0 - 7 passing 75μm | IANZ accredited laboratory | Contractor
507.16 |  | Determination of MDD & OMC (modified material) | M | 1 test per 5000m² laid | Determination of MDD & OMC NZS 4402: Test 4.1.3 | report value only | IANZ accredited laboratory | Contractor
507.17 |  | Compaction | H | 9 per Lot *1 lot = 1000m³ or 250lm (whichever is least) | NDM TNZ B/2 7.6 & B/7 8.1 | RC ≥ 98% | IANZ accredited laboratory | Contractor
507.18 |  | Plateau Density Test (3 tests) (as part of this 3 NDM readings are taken and then 3 samples are taken and dried back in the lab to determine actual moisture content of material placed) | M | TNZ B/2 7.5(b) | NDM | report value only Used for moisture contect correction | IANZ accredited laboratory | Contractor
507.19 |  | Indirect tensile strength testing - on mixed stockpiled material if B/7 time limits not met | S | Day 1: Two (2) soaked & two (2) dry ITS All subsequent days: One (1) soaked & one (1) dry ITS from the spreader truck, prior to addition of compaction water, within 2 hours of completion of primary compaction of lift | NZTA T/19 | Dry ITS > 250 Kpa Soaked ITS >150 Kpa | IANZ accredited laboratory | Contractor
507.2 |  | Dry back Moisture Content (Degree of Saturation) | H | 9 per Lot *1 lot = 1000m³ or 250lm (whichever is least) | NDM NZS 4407.4.2.1 | TNZ B/7 8.5 DOS ≤ 80% preferably ≤ 70% | IANZ accredited laboratory | Contractor | Only required if pavement widening extends into trafficked lane
507.21 | Surface conformity | Layer Width | H | every 20m | Measurement | ± 100 mm -20mm | Survey | Contractor
507.22 |  | Surface Shape | H | every 20m | Measurement | < 6mm using 3m straight edge | Work sheet | Contractor
507.23 |  | Surface Levels | H | every 20m | Measurement | - 5mm, + 15mm | Survey | Contractor
507.24 | Non-conforming results | Assessment of all test results for conformity | H | Each Lot | Site Inspection | Reporting of any non-conforming results to Designer via NCR. | NCR | Safe Roads
SPECIFICATION 520: BITUMINOUS PRIME COAT
SPECIFICATION 522: BITUMINOUS SEAL COAT
Setout, Materials and Preparation
522.1 | Pre-seal inspection | Visual inspection of surface to be sealed | H | per sealing schedule. 1 Lot = 1 day's production and < 1500m2 | Visual inspection | NZTA B/02 The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which; • The large aggregate is• exposed to the surface; • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material; • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter | Seal inspection record | Safe Roads' Rep. | The surface finish, line and level is checked by Engineer's Rep. immediately prior to sealing
522.2 | Seal Design | Seal design outling all design assumptions | H | 1 per seal application type | Review | New Zealand Chip Sealing Handbook | Seal design in contractor's site folder | Contractor
522.3 | Check raw materials | Sealing Aggregates Source Properties | M | 1 test per source 1 test per 10,000m3 (min 1 per source) | 1. Polished Stone Value 2. Crushing Resistance 3. Weathering Quality Index 1. BS 812: Part 114 2. NZS 4407:1991, Test 3.10 3. NZS 4407:1991, Test 3.11 | TNZ M06 / RNZ 9805:2009 1. Polished Stone Value Required = 45 2. Crushing Resistance: <10% fines p[assing 2.36 under 230 KN load 3. Weathering Quality Index: AA or BA | Certificate in contractor's site folder | Contractor
522.4 |  |  | M | 1 test per source 1 test per 10,000m3 (min 1 per source) | Broken Faces NZS 4407:1991, Test 3.14 | TNZ M/6 4.1.2 98% with minimum two broken faces | IANZ Report | Contractor
522.5 |  | Sealing Aggregates Production | M | 1 test per 500m³ | Size & Shape NZS 4407:1991, Test 3.13 | TNZ M/6 4.1.2 Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm | IANZ Report | Contractor
522.6 |  |  | M | 1 test per 500m³ | Cleanliness NZS 4407:1991, Test 3.9 | TNZ M/6 4.2.3 G2 chip: 89 G3 chip: 87 G4 chip: 85 G5 chip: Report only G5 chip: Report Only | IANZ Report | Contractor
522.7 |  |  | M | 1 test per 500m³ | PSD NZS 4407:1991, Test 3.8 | NZTA M/06 Grade 5: 100% passing 13.2mm 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300μm Grade 6: 100% passing 9.5mm 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300μm | IANZ Report | Contractor | Test certificates issued to the Engineers Rep at least 10 days prior to sealing
522.8 |  |  |  |  | Penetration ASTM D5 Penetration of residue, at 25°C, 100g, five seconds, % of original
522.9 |  |  |  |  | Viscosity AS 2341.2 or ASM D2171 Viscosity PaS at 60°C
522.1 |  | Bitumen Properties | M | 1 test | Viscosity AS 2341.3 or ASM D2170 Viscosity mm2/s at 135°C | Complies with requirements for penetration grade as per TNZ M/01 Table 1
522.11 |  |  |  |  | Flash point ASTM D92 Flash point (Cleveland open cup), °C
522.12 |  |  |  |  | Solubility ASTM D2042, AS 2341.8 Solubility in Trichloroethylene, % or Solubility in Toluene, %
522.13 |  |  |  |  | Rolling Thin Film ASTM D2872 or AS 2341.10 Rolling Thin Film Oven Test
522.14 |  |  |  | 2 samples per distributor | Durability NZTA M01 - Table 5 |  | Certificate in contractor's site folder | Contractor | Refer notes in clause 5 of NZTA M01
522.15 |  |  |  | 1 test | Ductility ASTM D113 Ductility of residue, at 25°C, (metres)
522.16 |  | Adhesion Agents | M | Prior to use |  | NZTA M06 / NZTA M13 | Certificate in contractor's site folder | Contractor | Retain for testing if required
522.17 |  | Audit samples | M | 20 kg per stockpile | N/A | Stored in a sealed plastic bag in a covered environment | ITP | Contractor | Retain for testing if required
Construction and Finshing
522.18 | Confirm surface for sealing | Dry back Moisture Content (Degree of Saturation) | M | Confirm testing has been completed and surface has not been saturated after testing and before sealing.
522.19 | Chipseal Production | Spraying Temperature | W | Ongoing with non-going heat sensing gauge | Non-contact heat sensing gun | NZTA P03 - Table 2 | ITP | Contractor
522.2 |  | Spray sheets | W | On day of seal | Report | Report value only | Surfacing Subcontractor's Quality Representative
SPECIFICATION 523: ASPHALTIC CONCRETE
SPECIFICATION 524: Open Graded Porous Asphalt
SPECIFICATION 580: SAFETY BARRIERS
Setout, Materials and Preparation
800.1 | Ground conditions testing | Bearing strength of foundation depth | H | 1 Scala every 20m All leading and terminal ends Or as directed by the Engineer | NZS 4402.6.5.2 | For design input | Scalar test sheet | Contractor | Test results provided to Eng.Rep.. for analysis. Safe Roads provides foundation size details
800.2 |  | Linear Shrinkage (LS) | H | 1 test every 250m All leading and terminal ends Or as directed by the Engineer | NZS 4402.2.6 | For design input | IANZ Report | Contractor | Test results provided to Eng.Rep.. for analysis. Safe Roads provides foundation size details
800.3 |  | Shear Vane (SV) | H |  | NZ Geotechnical Society Guide (Aug 2001) |  | Shear Vane test sheet
800.4 | WRSB Pile Excavation | Excavation size and shape | W | All excavations | Visual Inspection | Ground is level | Check sheet | Safe Roads
800.5 |  | Excavation size and shape | W | All excavations | Visual Inspection | Excavated depth as specified | Check sheet | Safe Roads
800.6 |  | Excavation size and shape | W | All excavations | Visual Inspection | Sides of excavation parallel and not collapsing | Check sheet | Safe Roads
800.7 | WRSB Pile inspection before casting concrete | Pile specifics | M | All piles | Visual Inspection | Plastic socket in correct position and well secured | Check sheet | Contractor
800.8 |  | Pile specifics | M | All piles | Visual Inspection | Rebar ring position in correct position | Check sheet | Contractor
800.9 |  | Pile specifics | M | All piles | Visual Inspection | Rebar position in correct position (type B to type E) | Check sheet | Contractor
800.1 | Pile position | Pile position | M | All piles | Visual Inspection | Sufficient supporting slope outside the line of the posts in relation to pile size | Check sheet | Contractor
800.11 |  | Pile spacing | M | All piles | Visual Inspection | Post spacing's as per the Construction Drawings or NTCs | Check sheet | Contractor
800.12 |  | Post orientation | M | All piles | Visual Inspection | Slot orientation consistent for the entire length of the barrier | Check sheet | Contractor
800.13 | Cast WRSB Pile | Check condition of finished pile | M | All Piles | Visual Inspection | Top of pile is level and Flush with ground at front face of pile | Check sheet | Safe Roads
800.14 |  | Check condition of finished pile | M | All Piles | Visual Inspection | Top of pile is formed to specified diameter (+50mm, -0mm) | Check sheet | Safe Roads
800.15 |  | Excess concrete removed from site | M | All Piles | Visual Inspection | No signs of concrete | Check sheet | Safe Roads
800.16 |  | Cables at correct position as per manufacturer's installation manual | M | All posts | Visual Inspection | Cables are in or on the seating position | Check sheet | Contractor
800.17 | Installed WRSB system | O' ring seal is positioned on all posts at the top of socket (if applicable for system) | M | All posts | Visual Inspection | 100% | Check sheet | Contractor
800.18 |  | All posts have plastic cap inserted into the post (if applicable for system) | M | All posts | Visual Inspection | 100% | Check sheet | Contractor
800.19 |  | All cables are tensioned correctly | M | All barrier lengths | Visual Inspection | As per manufacturer's installation manual | Check sheet | Contractor
800.2 | On-site post testing | Pull test as per manufacturer's instruction | M | 1 per 100m of barrier length | Manufacturer's instructions | As per manufacturer's installation manual | Test Certificate | Contractor
Construction and Finshing (W-Section/Thrie Beam Barriers)
800.21 | Installed WSB system | Barrier section at correct position as per manufacturer's installation manual | M | All posts | Visual Inspection | Barrier is at correct height and secured correctly | Check sheet | Contractor
Setout, Materials and Preparation
800.22 |  | All cables are tensioned correctly | M | All barrier lengths | Visual Inspection | As per manufacturer's installation manual | Check sheet | Contractor
SPECIFICATION 810: ROAD SIGNS
810 | Setout, Materials and Preparation
810.1 | Mark out works | Set out new roadmarkings, RRPMS, delineators and any associated removal works | H | All roadmarking and delination installations | Visual Inspection | N/A | NTC / Site instruction | Contractor
810.2 | Retro-reflective sheeting supplier | Evidence of a quality assurance system that has been certified by a Joint Accreditation System Australia and New Zealand (JAS-ANZ) accredited agency. | W | Six weeks prior to the construction of any sign. | N/A | Engineer to review and approve | Compliance information | Contractor
810.3 |  | Evidence of technical representation in New Zealand. | W | Prior to construction. | N/A | Engineer to review and approve | Compliance information | Contractor
810.4 |  | Evidence of a formal technical qualification programme with the sign manufacturers using their material. | W | Prior to construction. | N/A | Engineer to review and approve | Certificate | Contractor
810.5 |  | Proof that an approved quality system is in place. | W | Within 48 hours of request. | N/A | Engineer to review and approve | Compliance information | Contractor
810.6 |  | An original certificate written and issued by the retro-reflective sheeting manufacturer that the sign manufacturer has a formal technical qualification for using their material. | W | Within 48 hours of request. | N/A | Engineer to review and approve | Certificate | Contractor
810.7 |  | A compliance certificate issued by an independent qualified testing laboratory. | W | Within 48 hours of request. | N/A | Engineer to review and approve | Certificate | Contractor
Construction and Finshing
810.8 | Completed traffic signs | Visual inspection of completed traffic signs | H | All traffic sign installations | Visual Inspection | Compliance with project specifications | NTC / Site instruction | Contractor
SPECIFICATION 820: PAVEMENT MARKING AND DELINEATION
820 | Setout, Materials and Preparation
820.1 | Mark out works | Set out new roadmarkings, RRPMS, delineators and any associated removal works | H | All roadmarking and delination installations | Visual Inspection | N/A | NTC/ Site instruction | Contractor
820.2 | Pavement marking material informations and certification | Contractor to provide Certification of Compliance of Application Machine | H | Prior to commencing works | N/A | Engineer to review and approve | NTC/ Site instruction | Contractor
820.3 |  | Contractor to provide brand and type of high perfomance marking to be used | H | Prior to commencing works | N/A | Engineer to review and approve proposed lighting columns and luminaries | NTC/ Site instruction | Contractor
Construction and Finshing
820.4 | Application Testing | Reflectivity | H | 1 test per line type | TNZ M/20 | Engineer to review in accordance with TNZ P/30 | Test Results | Contactor | Needs review to meet current specifications
820.5 |  | Skid resistance | H | 1 test per line type | TNZ M/20 | Engineer to review in accordance with TNZ P/30 | Test Results | Contactor
820.6 | Complete road marking | Visual inspection of completed road marking installations | H | All roadmarking installations | Visual Inspection | Compliance with project specifications | NTC/ Site instruction | Contactor
Construction and Finishing (raise reflectorised pavement markers)
820.7 | Completed raised reflectoristed pavement markings | Visual inspection of completed raised reflectorised pavement markings | H | All roadmarking installations | Visual Inspection | Compliance with project specifications | NTC/ Site instruction | Contractor
Construction and Finishing (Delineators)
820.8 | Completed delineators | Visual insoection of completed road delineators | H | All delineators installations | Visual Inspection | Compliance with project specifications | NTC/ Site instruction | Contractor
SPECIFICATION 840: ROAD LIGHTING
SPECIFICATION 880: BOUNDARY FENCING