## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e07db9bf-6c2c-40bb-b7f9-537d19e8222d | checklist | Document Upload |  | Document Upload
937349c9-3e01-4fea-bac7-1c68c6da1a4a | section | Document Upload
12ca371b-b3fc-426d-9df6-6aa8a008cf18 | checkpoint-no-value | Upload Documents
91284eb0-5b2c-4a5d-abd8-662162636ea3 | checklist | Final Handover |  | Final Handover
e12e7701-1f6d-46ab-ac79-e1ecd00b211d | section | Final Handover
69de7bc2-2c7f-4279-91de-130fb21fd91a | checkpoint | All works Complete
930d746d-5b0a-4986-aaf5-ed37cffdd641 | checkpoint | List Outstanding Work, if any
4b49f53b-c4d8-4e79-ba68-81c1eadf722d | checkpoint | Handover Sent to CMP
ae5994b2-4843-4558-9f95-4194b06a0362 | checkpoint | Handover confirmation Received from CMP
42ff8d6f-be89-407a-9bdf-f775252afd8e | checklist | Floor Handover |  | Floor Handover
c8aa5541-d08c-4c0b-912c-3da6493fca97 | section | Main Contractor Handover
669a4f91-3cf4-4fdd-8018-f75be9894149 | checkpoint | CMP Handover Doc Recd
506e3ad1-d9f7-412e-9f4a-4b7cfbf7ebe8 | checkpoint | CMP Opening Survey Recd
5db503f5-cad9-453d-b5ce-0c27a60c7a56 | checkpoint | Opening position within tolerance
41c4f8de-9d2d-4c0c-9141-a729ba5e9ef3 | checkpoint | Grid Line clearly marked on floor
456d15d0-b7da-4829-92ef-5068a48f938f | checkpoint | Master RL Provided
7a90e131-1ac6-435c-a295-3975ce7814a9 | checkpoint | All timber framing completed and waterproofed
053d4b34-c334-46f9-8c29-73118afc6070 | checkpoint | Concrete opening completed and waterproofed
280b97d1-e955-40e9-b624-f37e48ce47bb | checkpoint | Has Allwin team checked and accepted against received marked up floor plan?
1d857822-8084-43c4-ad56-11afade8adfb | checklist | QA - Alum. Cladding Panel / Flashing |  | Alum. Cladding Panel / Flashing
0cd1bdec-274f-4b4f-8d86-0b5adf444510 | section | Pre-Installation QA Check
dd144180-737b-4a83-b918-1498800ea797 | checkpoint | Have the aluminum panels / flashing been received without damages?
f4f34bc9-422d-4e46-864c-022187ceb1ba | checkpoint | Has the aluminum panels / flashing received in the correct color, sizes and quantity based on the fabrication drawing and TAG drawings?
d7c6f888-899a-4d29-9c2f-edbda2dfe160 | section | Pre-Installation QA Check
633e2452-7329-4f58-bce7-597e39b0e69c | checkpoint | Is The Structure Handed Over
c155f67f-b9da-404b-8839-556a03343b4f | checkpoint | EPDM membranes/under flashings installed and sealed?
3546cff3-6517-4c51-b224-c58bb05ecf16 | checkpoint | Alum cladding installed line and leveled
ecd9b566-6e68-42ce-b96e-72f4af1a37a3 | checkpoint | Has the PEF rod installed as per the standard
fa733dcc-1bd2-46e1-a13f-9a2f68ec411f | checkpoint | Has the silicon applied without bubbles and sealed neatly
2d7c60e3-9289-4bed-bdc7-5a956b61b83a | checklist | QA - CW Panels |  | CW Panel
2ab80a32-3118-42bb-b0f4-ae29b6b9de92 | section | Panel Installation QA Check
42fe4f7e-1ea8-4c30-ae75-5f149611eb8a | checkpoint | Glass and alum panels installed line and leveled
ee34dbd1-fb33-4cd7-9fb9-2596c33c08ee | checkpoint | Are all beads installed and have wedge rubber
d64a9327-536a-40c8-82cd-1b9c833c0f61 | checkpoint | Back Of Mullion silicone seal in place
8ec214f0-0f34-4b43-950c-bede4becf25b | checklist | QA - Doors - Hinged |  | Hinge Door
357a53a8-25e4-4b9d-934c-4606b3866202 | section | Hinged Door QA Check
29616701-92b7-467c-b454-e9be24dc73a7 | checkpoint | Are all beads installed and have wedge rubber
0062a529-cde6-48a2-80df-125a8f9b73ff | checkpoint | Door frame installed in-line & leveled
bc56bf7d-6a6d-43bf-9f21-a6ebd0fc3403 | checkpoint | Door installed with 3 hinges per side
31c818d6-0eb6-4d38-b682-d0dbededfc53 | checkpoint | Door closing smoothly without scratching floors and head.
96bc0d7b-7b08-42fd-b678-562a2b341699 | checkpoint | Door Handle Installed and Tight
f04ff692-987a-499e-807f-d0d6e0c37b88 | checkpoint | Door Lock installed and working
7e03e5ef-187f-4d60-bb1e-c83c58665a2a | checkpoint | Shoot Bolts Working Correctly
78473030-ec65-4908-940c-26a60ec9f37b | checkpoint | Door closure installed and functioning
57421e56-a7f7-411c-a3d9-68f12d8e07a8 | checklist | QA - Louver Fins |  | Louver Fins
3082d88e-1e03-4dac-905b-7ce2b7c72e88 | section | Pre-Installation QA Check
b12d8155-d898-4a38-9a54-b8c89ea1c767 | checkpoint | Handover Recd
40bebffe-907c-4385-b87c-7aca95ad00ed | checkpoint | Have the aluminum fins & Brackets been received without damage?
832d0f2d-e40a-4591-b20e-42f31b31dc4a | checkpoint | Are the aluminum fins received in the correct color, size, and quantity based on the fabrication and TAG drawings?
77ded1c2-1b89-428e-bd49-c0a863034113 | section | Installation QA Check
5ff73554-492d-480a-b75e-db711052c219 | checkpoint | Has the bracket been installed with correct Anchors bolts?
eacb591f-29ca-4cf4-8b03-3985bec7be63 | checkpoint | Has The EDPM Seperator been Installed
3a9b47cc-7dd1-416b-87ca-3b8d92c3bd97 | checkpoint | Has the Fin been installed with the correct nuts, bolts and washers per the drawing?
ecaad462-b548-4344-8262-624a28504d5a | checkpoint | Has the bolt been tightened.
6182fe96-9ad5-4c2d-8d73-e3f1f77511f8 | checkpoint | Have the fins been installed, line, and leveled?
5261688d-a031-4f13-9fa7-ba2726bf27c8 | checklist | QA - Sash Window |  | Sash Window
242bd7d0-2e61-4477-98d9-5475fb69ef0a | section | Sash Window QA Check
7628db21-56b0-4712-ad18-5ad10181ea69 | checkpoint | Are all beads installed and have wedge rubber
e99d679e-fac5-4226-a0ea-13da085e5626 | checkpoint | Sash frame installed in-line & leveled
e131c670-51e8-4b16-bd62-4a1a8a931edd | checkpoint | Sash Hinges installed
8cd49bcc-e3ac-43fd-bcf3-d5b7377c0f17 | checkpoint | Sash Stay Installed with 100mm gap
92b255c8-800a-4d92-bee9-90d792502c04 | checkpoint | Sash Handle Installed and Tight
25f26e33-d3c8-4776-b643-930af5e5d489 | checkpoint | Sash Lock Working Correctly
fd1b3e23-3a11-4ee9-85ea-82c53f618488 | checklist | QA - Seismic Frame |  | Seismic Frame
ce9f256e-3188-44b0-b6a0-d4584ab7b597 | section | Pre-Installation QA Check
2d0065c4-c8ba-4f1d-934a-d0f787c753f7 | checkpoint | Is the seismic frame the correct size and quantity?
33a97c93-d9d5-4095-9c07-87583f23385f | checkpoint | Does the seismic frame have the correct gaskets and mohair.
80c9e065-af98-4cc8-8f51-b62e5129241e | checkpoint | Have you got sufficient sleeves
811aa0e6-88ef-47ec-9ace-94a095e2474a | section | Installation QA Check
33044811-7a68-4d1b-9fb6-3433d4f1a1ef | checkpoint | Sill Tray bolts sealed to Structure
cdba8a23-f2c1-480e-9359-54e11abe8f68 | checkpoint | Sill tray packers Installed around all bolts.
6ca39f8e-0933-429a-9646-0dbdf075fad9 | checkpoint | Sill Tray splices sealed
aa12dc77-c59d-4481-8ae4-4fef67bd01af | checkpoint | Sill tray end dams fitted and sealed
aed691d9-7a64-4c0b-b0d1-79c24cdc111a | checkpoint | Have all the bolt/ screw heads been sealed
d14fa04f-0f04-42fa-afe8-39f5e0071931 | checkpoint | Is sill installed level
47395889-0ca5-4bee-a538-bc55f47c42bf | checkpoint | Is Head and Jamb Installed Level
f106135f-9abb-4ad5-bf05-165c056a9c5a | checkpoint | Are Head/Jamb fixing heads sealed
b8ca146e-3a0c-455a-b500-a12883a564d2 | checkpoint | Are Head/Jamb sleeves fitted and sealed
f84283d2-2aa7-4858-a636-de593d88d0a6 | checkpoint | Are Head/Jamb corner splice fitted.
e3d34955-9f9a-494d-8a54-4ad34f7a007d | checkpoint | Is Head/Jamb face of Mitre sealed
486f2261-0c70-4c9b-b5e9-bb91fbebc292 | checkpoint | Is Head/Sill/Jamb External Backing rod installed
f36ec973-7e34-485d-bca9-7c41c09d3f70 | checkpoint | Is Head/Sill/Jamb external seal 6mm- 20mm
f0f02f4e-5533-4905-b668-5a44e03391e4 | checkpoint | Is Head/Sill/Jamb Internal seal 6mm- 20mm
1728eb9b-4abe-4231-a8d7-2117b0b5273a | checkpoint | Is Head/Jamb External Rainshield fitted
6b164a83-25c6-40e8-93f9-3aeca36d43fc | checkpoint | Is internal sill cover fitted
969d6b29-4416-415a-aa86-5f229d36eba8 | checklist | QA - Sliding Windows |  | Sliding Window
37108a74-a750-46e4-babb-9baacb6d2244 | section | Sash Window QA Check
261c436e-36a6-4dc3-832b-da970b29f489 | checkpoint | Are all beads installed and have wedge rubber
4b888c94-7b99-4525-948e-0b658f70be6e | checkpoint | Sliding Window frame installed In-line & leveled
612affab-3dee-4b66-8a9e-86112979c2d9 | checkpoint | Fixed Panel wedge gasket installed
691ebe5b-ca27-4161-a1b4-90c5feb5e83e | checkpoint | Wheels installed and adjusted to height
c30ea305-68fc-4dd1-a1d3-77a08168967e | checkpoint | Sliding Window Stopper Installed
7c94cac0-911b-4ad9-8362-bdfe19dd0fcc | checkpoint | Infill Sliding window stopper installed
aeaf8503-4d88-4d38-b06f-b7d04eb2a21a | checkpoint | Handle Installed and Tight
c25e3ce1-807b-410f-b1d6-547de522a74f | checkpoint | Lock Installed and Working
551e57a9-6912-4c95-b05b-dd89dcf3473d | checkpoint | Infills installed