## Sero Apartments break down
Sero Apartments
Installation QA Breakdown
Levels | Façade Systems | Location | Checksheets
General | Testing
|  | Water test | NO CHECK SHEETS, WE ONLY UPLOAD PHOTOS, REPORTS
Pull Test
Embedment Test
Flood Test
Bolt Torque Test
Site sealant peel & adhesion test
Lower Ground Floor | Floor Handover
| South Eastern Elevation | DT-E1 | Seismic Frame
Hinge Door
Final Handover
Ground Floor | Floor Handover
| South Western Elevation | W0.01 | Seismic Frame
Hinge Door
Final Handover
|  | W0.02 | Seismic Frame
CW Panel
Final Handover
|  | W0.03 | Seismic Frame
CW Panel
Final Handover
|  | W0.04 | Seismic Frame
CW Panel
Hinge Door
Final Handover
|  | W0.05 | Seismic Frame
CW Panel
Final Handover
|  | W0.06 | Seismic Frame
CW Panel
Final Handover
|  | W0.07 | Seismic Frame
CW Panel
Final Handover
|  | W0.08 | Seismic Frame
CW Panel
Hinge Door
Final Handover
| South Eastern Elevation | W0.09 | Seismic Frame
CW Panel
Final Handover
|  | W0.10 | Seismic Frame
CW Panel
Final Handover
|  | W0.11 | Seismic Frame
CW Panel
Hinge Door
Final Handover
|  | W0.12 | Seismic Frame
CW Panel
Final Handover
Level 1 | Floor Handover
| South Western Elevation | W1.01 | Seismic Frame
CW Panel
Fin Install
Sliding Window
Final Handover
|  | W1.02 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W1.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W1.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W1.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W1.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W1.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W1.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W1.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W1.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W1.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.15 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W1.16 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W1.17 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W1.18 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W1.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.21 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
| North Eastern Elevation | W1.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W1.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W1.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 2 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 3 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 4 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 5 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 6 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 7 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Sash Window
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Sash Window
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Sash Window
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 8 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Fin Install
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 9 | Floor Handover
| South Western Elevation | W.01 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Fin Install
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Final Handover
| South Eastern Elevation | W.09 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.10 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sliding Window
Fin Install
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Fin Install
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.24 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.25 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.31 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Western Elevation | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.28 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.29 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 10 | Floor Handover
| South Western Elevation | W10.24 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W10.02 | Seismic Frame
CW Panel
Final Handover
|  | W10.03 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W10.04 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W10.05 | Seismic Frame
CW Panel
Final Handover
| South Eastern Elevation | W10.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.08 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W10.09 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.11 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.14 | Seismic Frame
CW Panel
Sash Window
Sliding Window
Final Handover
| North Eastern Elevation | W10.10 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.16 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W10.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W10.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.21 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W10.23 | Seismic Frame
CW Panel
Final Handover
|  | W10.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 11 | Floor Handover
| South Western Elevation | W.24 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Final Handover
| South Eastern Elevation | W.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.09 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Sliding Window
Final Handover
| North Eastern Elevation | W.10 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.23 | Seismic Frame
CW Panel
Final Handover
|  | W.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 12 | Floor Handover
| South Western Elevation | W.24 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.04 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Final Handover
| South Eastern Elevation | W.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.08 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.09 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.14 | Seismic Frame
CW Panel
Sash Window
Sliding Window
Final Handover
| North Eastern Elevation | W.10 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.20 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.21 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.22 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.23 | Seismic Frame
CW Panel
Final Handover
|  | W.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 13 | Floor Handover
| South Western Elevation | W.19 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
| South Eastern Elevation | W.04 | Seismic Frame
CW Panel
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.8 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.9 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.10 | Seismic Frame
CW Panel
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 14 | Floor Handover
| South Western Elevation | W.19 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
| South Eastern Elevation | W.04 | Seismic Frame
CW Panel
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.8 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.9 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.10 | Seismic Frame
CW Panel
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 15 | Floor Handover
| South Western Elevation | W.19 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
| South Eastern Elevation | W.04 | Seismic Frame
CW Panel
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.8 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.9 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.10 | Seismic Frame
CW Panel
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 16 | Floor Handover
| South Western Elevation | W.19 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
| South Eastern Elevation | W.04 | Seismic Frame
CW Panel
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.8 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.9 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.10 | Seismic Frame
CW Panel
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install
Level 17 | Floor Handover
| South Western Elevation | W.19 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.01 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.02 | Seismic Frame
CW Panel
Sliding Window
Final Handover
|  | W.03 | Seismic Frame
CW Panel
Sash Window
Final Handover
| South Eastern Elevation | W.04 | Seismic Frame
CW Panel
Final Handover
|  | W.05 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.06 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.07 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.8 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.9 | Seismic Frame
CW Panel
Sliding Window
Final Handover
| North Eastern Elevation | W.10 | Seismic Frame
CW Panel
Final Handover
|  | W.11 | Seismic Frame
CW Panel
Final Handover
|  | W.12 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.13 | Seismic Frame
CW Panel
Sash Window
Final Handover
| North Western Elevation | W.19 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.15 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.16 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.17 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | W.18 | Seismic Frame
CW Panel
Sash Window
Final Handover
|  | Fin Grid 5 | Fin Install