## ITP Cover Page (Tactiles)
[16 empty] | Tactiles | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 145 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 145 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Tactiles |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 2780,2781,2782,2783,2784&2785
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Approval | 2025-07-29 |  | Nicky Turner/Gurmeet Singh |  | First Revision for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
A | Draft for Approval | 2025-08-13 |  | Nicky Turner/Gurmeet Singh |  | Second Revision for Review and Approval |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
A | Approved | [8 empty] | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Tactiles ITP
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.01 | Site Requirements
1.01.01 | Setout | The Contractor shall set out position of TGSI per RTS 14 and RITS | IFC Drawing & RTS 14, RITS D3.6.3 | Survey Records | Prior to Works | H | PE
1.01.02 | Approved Construction Drawings | Drawings are IFC and latest version including TGSI layout details. | Approved IFC Drawings | IFC Drawings | Prior to works start | M | PE
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.01
2.01.01 | Materail Approval | BBO approved TGSI Product | BBO apporval | In-Eight Correspondence | Prior to ordering | HP | ENG
2.01.02 | Walkover | Walkover and agree postioning with BBO MSQA/Engineer | IFC Drawing | Email/ Record of Conversation | Each Walkover | HP | ENG
SECTION 4 – CONSTRUCTION ACTIVITY
4.01
4.01.01 | Warning Tactile Placement | Located minimum 300mm and maximum 1m from kerb, 600mm depth or agreed with BBO | RTS 14 Fig 7.1 / RITS D3.6.3 | Photos | Random | V | PE
4.01.02 | Directional Tactile Placement | As agreed with BBO | RTS 14 Section 6.1 / RITS D3.6.3 | Photos | Random | V | PE
SECTION 5 – POST CONSTRUCTION
5.01 | Site Post Construction Activities
5.01.01 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines & As-builts | Post construction | H | SE/PE
5.01.02 | Installers Warantee | Completed and signed warantee by CMT (Haptix) | CMT | Warantee Doc | Once | H | S