## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 145 - Tactiles | itp |  |  |  |  | ITP - 145 - Tactiles Rev A
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.01.01 - Setout
label | Acceptance / Conformance Criteria - The Contractor shall set out position of TGSI per RTS 14 and RITS
label | Standard / Specification - IFC Drawing & RTS 14, RITS D3.6.3
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 1.01.02 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Drawings are IFC and latest version including TGSI layout details.
label | Standard / Specification - Approved IFC Drawings
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - M
label | Verification Activity: By - PE
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.01.01 - Material Approval
label | Acceptance / Conformance Criteria - BBO approved TGSI Product
label | Standard / Specification - BBO approval
label | Verifying Document - In-Eight Correspondence
label | Frequency - Prior to ordering
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.01.02 - Walkover
label | Acceptance / Conformance Criteria - Walkover and agree postioning with BBO MSQA/Engineer
label | Standard / Specification - IFC Drawing
label | Verifying Document - Email/ Record of Conversation
label | Frequency - Each Walkover
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – CONSTRUCTION ACTIVITY
checkpoint | 4.01.01 - Warning Tactile Placement
label | Acceptance / Conformance Criteria - Located minimum 300mm and maximum 1m from kerb, 600mm depth or agreed with BBO
label | Standard / Specification - RTS 14 Fig 7.1 / RITS D3.6.3
label | Verifying Document - Photos
label | Frequency - Random
label | Verification Activity: Activity - V
label | Verification Activity: By - PE
checkpoint | 4.01.02 - Directional Tactile Placement
label | Acceptance / Conformance Criteria - As agreed with BBO
label | Standard / Specification - RTS 14 Section 6.1 / RITS D3.6.3
label | Verifying Document - Photos
label | Frequency - Random
label | Verification Activity: Activity - V
label | Verification Activity: By - PE
section | SECTION 5 – POST CONSTRUCTION
checkpoint | 5.01.01 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines & As-builts
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE/PE
checkpoint | 5.01.02 - Installers Warantee
label | Acceptance / Conformance Criteria - Completed and signed warantee by CMT (Haptix)
label | Standard / Specification - CMT
label | Verifying Document - Warantee Doc
label | Frequency - Once
label | Verification Activity: Activity - H
label | Verification Activity: By - S
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature