## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
298c170a-53f5-4df2-af76-cbed8e04a7a1 | checklist | LQS-QA-6000 - ITP - Compliance Record | itp | LQS-QA-6000 - ITP - Compliance Record
9c04caa9-479b-43e4-a236-42eb493a239a | section | Compliance Record
018af20e-4fcd-46df-bb49-ea84f641debc | checkpoint | 1 - Pre-construction sign-offs
bb51969f-50b7-515c-9fcd-ecc2b2a655a1 | note | ACTION (Hold, Monitor, Witness) - H
fa16c327-3fa3-5294-a603-4ac980fc8734 | note | DETAIL - Is there a Safe Work Method Statement for this task?
a5f020a1-5b04-5bcd-9fb6-805800d62260 | note | FREQUENCY - Prior to commencement
7f6fc341-31e9-5251-a738-13bf1730802a | note | INSPECTION - Document Review, Submission
e6f9da4f-480f-5b18-a2d7-e29ee319c5b3 | note | CONFORMANCE CRITERIA - Relevant parties to review, Note Method statement in the Comments
fb40e489-fa2d-527f-a069-561c0d6e0a23 | note | RECORDS - Sign off this task
edbf2dc9-04b2-412e-bf2e-a825341f9a0d | signoff | AUTHORITY HOLDPOINT
c34bedad-1d12-4923-963a-c134189a76ba | checkpoint | 2 - Design
bbc88d4e-5667-5c94-bcba-922c9f51ee86 | note | ACTION (Hold, Monitor, Witness) - H
ac022abf-3411-5db1-9427-9cb95d4b21fa | note | DETAIL - Review relevent design / task characteristics and identify hold points
17659988-bd4d-5056-b31d-8869ca4dc6b3 | note | FREQUENCY - Prior to commencement
7448a319-7ae6-5fc6-af49-41668cdacbe1 | note | INSPECTION - Document Review
6164d4d5-4049-565e-8fb6-99beec08a43e | note | CONFORMANCE CRITERIA - All design requirements are met
63766c09-40bc-5a8a-8946-6169b2bde6ca | note | RECORDS - Sign off this task
46f8f1f5-8fa3-4772-a694-bf6f7c98a7f8 | signoff | AUTHORITY HOLDPOINT
153c5e63-3a7f-4dc7-8679-20e9432f99b6 | checkpoint | 2.1 - Design
89c37157-7cd3-5a3e-bf27-e51a269f3d8b | note | ACTION (Hold, Monitor, Witness) - H
18164620-eb62-5bc4-ba54-6747e3e1696e | note | DETAIL - Is a temporary works design required for this task?
d1c29574-8fb3-5766-8573-5dcf6dd2bae4 | note | FREQUENCY - Prior to commencement
a8669517-9c7f-5b4d-ab2a-9b58eeef29f5 | note | INSPECTION - Document Review, Submission
0ab58c8d-5095-5b03-83bf-e8349ecd346d | note | CONFORMANCE CRITERIA - Temporary Works design completed and attached
b8fcb388-42e2-5807-86ea-7f6f82c5f986 | note | RECORDS - TW design, Sign off this task
5a846a9a-adf2-452d-8b51-2b2686c14fbc | signoff | AUTHORITY HOLDPOINT
645751ab-b961-4616-95cb-90cffb358e5b | checkpoint | 3 - Technical Reports
d52fb51b-42cc-56f3-b60b-3f7e5de54c61 | note | ACTION (Hold, Monitor, Witness) - H
10187dfc-e2a9-5d1e-9f50-f68cf28376c2 | note | DETAIL - If relevant attach technical reports
8e585762-df8f-5791-bbfe-e6f735c737ec | note | FREQUENCY - Prior to commencement
eed7b0e5-71aa-58ff-8ecb-50b32e97ba7d | note | INSPECTION - Document Review
ec6e8160-dedb-5bd1-b5ea-056b113b6cb2 | note | CONFORMANCE CRITERIA - All related reports attached
34e08768-87fd-56a9-8208-5238e8236478 | note | RECORDS - Sign off this task
833af6fc-8c35-42fc-ab51-e4fe280622c8 | signoff | AUTHORITY HOLDPOINT
64f5e652-3673-418d-b47a-a4f0e75d4f22 | checkpoint | 4 - Materials
96fcfdea-0b96-58b5-98a7-60740da3301d | note | ACTION (Hold, Monitor, Witness) - W
61d21138-897f-5926-a34d-028c847252aa | note | DETAIL - If required provide required laboratory testing reports, material designs and attach i.e. grading curves, concrete design, steel certs etc.
b8448982-8a3f-545a-ac79-da93320ac03d | note | FREQUENCY - Prior to commencement
15c936f3-3c73-563f-a2bf-19ebd8895dca | note | INSPECTION - Document Review, submission
f5c84937-564e-5134-a44c-9603a11d59d1 | note | CONFORMANCE CRITERIA - All related reports are attached
1cd14996-aa9a-5fdb-8e4e-cbb1a812e237 | note | RECORDS - Laboratory test results, Sign off this task
8a77f777-f310-4c39-bcad-d8cbbafd0500 | checkpoint | 5 - Field Compliance
2908e6bc-9b0f-5946-8d0c-009a19d98389 | note | ACTION (Hold, Monitor, Witness) - W
4a56e68b-ce02-5052-8dd6-280b013e7e01 | note | DETAIL - Complete any field testing and Checksheets required by permanent design or temporary works design
8d7c2e03-9966-5647-b152-2d0e4fafd9bf | note | FREQUENCY - During construction
64573f4c-af8b-5503-a24c-9d34b248b65f | note | INSPECTION - Testing
af485475-a520-53f4-adb3-9d26ba57ac93 | note | CONFORMANCE CRITERIA - All related reports are attached
b63b2f84-37b2-5061-b8c1-f64821bb721c | note | RECORDS - Field Test, Sign off this task
9af5a458-122c-49cb-a1b9-74635eb48067 | checkpoint | 6 - Photo Records
024254de-9bd6-59ce-9668-f220573906ef | note | ACTION (Hold, Monitor, Witness) - H
e80d7a3c-797a-5fed-b94a-d364eeba2e1a | note | DETAIL - Attach photo records
36265952-2aed-5846-b013-6bc43ebe3031 | note | FREQUENCY - As completed
9983b837-2f0c-534f-9053-2d3ba9f1b3e9 | note | INSPECTION - Document Review
8d10bb2b-7644-5d4b-9e14-e0253b55ec59 | note | CONFORMANCE CRITERIA - All related photos are attached
e60703ca-b9a9-55f1-8efb-350d861f4a85 | note | RECORDS - Photo records, Sign off this task
e2f5f53c-7098-4c12-a153-29304e00cf37 | signoff | AUTHORITY HOLDPOINT
59d53fd8-083c-48dd-bc30-c28b96ff192e | checkpoint | Final Inspection
e0b18875-fece-5224-a603-8340269a93a0 | textbox | QA Compiled By:
e6d4d4b1-65fe-523a-b28e-77ab2add878d | textbox | QA checked By Project Manager:
8be1ecb6-921c-5ed8-8fff-46ba8f89749e | textbox | Accepted By Design Engineer:
681479aa-ffc8-4f1b-bf1c-ce00882c69bb | signoff | Sign ITP
16246b65-87c4-4785-b2a5-e692d582dfc5 | checklist | LQS-QA-6007 - ITP - Drainage Installation | itp | LQS-QA-6007 - ITP - Drainage Installation
52665069-0767-4134-b945-7d4a4a97d9d3 | section | Drainage Installation
92252b9b-bc05-4ba1-939a-d53da2aafb63 | checkpoint | 1 - Permits
3f12399e-d2fb-5543-a68a-27bd6044f92b | note | ACTION (Hold, Monitor, Witness) - H
45d7a5ed-0fdb-5107-a157-0532b4b45f58 | note | DETAIL - Obtain Permits
5ef99924-b3d7-5dfd-8c78-6a6913112df7 | note | FREQUENCY - As required
0818e69f-704b-5be2-a2a8-10607d50d4c2 | note | INSPECTION - Document Review
983e2f32-ef36-5992-82e1-6769b2bee096 | note | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), PTW #2 Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
4857494e-0640-5dd6-a3c4-31b1cb75f1fd | note | RECORDS - Permit attached or permit number noted
6ce67414-4dcb-47da-b839-097fc12bb156 | signoff | AUTHORITY HOLDPOINT
6b62f117-9cb9-4830-9f43-4f74e23c9703 | checkpoint | 2 - Design
f6e1e912-eb0e-5057-8bc9-fc0c12081e90 | note | ACTION (Hold, Monitor, Witness) - H
3b5279bc-e1f7-5d1d-a6b2-6aa56e88c743 | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
0183de00-4de6-5f82-af41-7332f7c6d80f | note | FREQUENCY - Prior to commencement
3884a7ac-f1f4-51e6-8eef-3eeff82cefdb | note | INSPECTION - Document Review
eeb4ad1b-34ce-548a-8f4a-7a6a11b7f67d | note | CONFORMANCE CRITERIA - IFC Drawings
cd14e854-340f-515c-8b26-aee23e39c915 | note | RECORDS - Check Drawing Register
1a5a8b35-6001-4224-aac5-4e9035c90388 | signoff | AUTHORITY HOLDPOINT
62c0817f-9c72-44a1-b943-f6756e87178f | checkpoint | 3 - Survey Setout
7c9b492e-d307-56f3-a2e0-41a072184bd6 | note | ACTION (Hold, Monitor, Witness) - H
211b03d1-aaa2-5882-b490-6af754025cbb | note | DETAIL - Setout inlet & outlet points with inverts as required by Contractor to construct to design
4070852d-27bf-5a48-97b9-20d4ebc8d18f | note | FREQUENCY - Prior to commencement
02d66e28-2994-5f40-83b7-ba2191a90ba1 | note | INSPECTION - Survey
29bf8782-9a27-5302-87e9-d0ab0041cca5 | note | CONFORMANCE CRITERIA - Survey is correct and consistent with plans
04a2fdcc-d25e-518c-9d2e-67cca0ef6bff | note | RECORDS - Photo
c6ae9def-6e71-4b23-bbdb-6bde9716680e | signoff | AUTHORITY HOLDPOINT
5226b91b-1906-4505-998e-6138d50f7d3f | checkpoint | 4 - Fill Material Compliance
774976d1-9133-5944-b5e1-a49d6ba41efb | note | ACTION (Hold, Monitor, Witness) - H
258054f6-0ce0-537d-b066-0856265263e0 | note | DETAIL - Bedding, Side support and Overlay materials tested in accordance with Specifications
e3725b8f-352c-5229-a237-dcb4e8c1642f | note | FREQUENCY - Prior to Installation
41f888a2-9947-56e6-9921-d75824a19604 | note | INSPECTION - Document review, Lab Testing
75ce7328-bb2d-577c-ab0a-ce657e3e13c2 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
1ef8f39b-709d-5bae-b734-88cf30247f7b | note | RECORDS - Lab Test results
7a076022-5779-4e03-b033-f8196cf15f84 | signoff | AUTHORITY HOLDPOINT
ee76dee1-b091-4144-9480-0ef342eb58cd | checkpoint | 5 - Pipes and Precast Units (1)
78ac8e66-e713-5542-acc5-f221b2e34af6 | note | ACTION (Hold, Monitor, Witness) - H
fad43d0d-10d7-5c95-a8fc-847e1c2d480e | note | DETAIL - Confirm pipes diameter, class & jointing type, as well as manholes, are as shown on the drawings, and that the pipes/pre-cast units are correct and in good condition.
d5202497-e0f8-5b88-a27a-27cee89686c7 | note | FREQUENCY - Each delivery to site
b492c3cc-346d-5397-8e8e-8b85e66d12a5 | note | INSPECTION - Certification
1ccc6e5f-77dd-5228-9a06-5c54fbd61ccf | note | CONFORMANCE CRITERIA - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
cabd03e5-8dcb-5176-abb0-7379d972d6f4 | note | RECORDS - Delivery Dockets
d4fff4d0-87db-492f-83a2-822a4ee7a95a | signoff | AUTHORITY HOLDPOINT
811de8c0-87e3-42db-8a5e-12edcb871b6e | checkpoint | 5 - Pipes and Precast Units (2)
010b0ea3-aa83-5e8b-a5ff-66189e2b52b6 | note | ACTION (Hold, Monitor, Witness) - H
473324bf-e88e-50ee-a971-570fe57ba3f5 | note | DETAIL - Flanges, Valve boxes, Fire Hydrants, bolts, nuts, washers shall be as in accordance with the Specifications
8aa43a4e-a463-518c-ba6c-dbe346e947dc | note | FREQUENCY - Prior to Installation
58576700-3bab-566a-8c25-fd8fbc1f69b1 | note | INSPECTION - Document review
f3c17b92-11f1-575a-b49e-c9c7dd8d811d | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
8604a0f5-969d-54d0-a732-97ef78394fb2 | note | RECORDS - Delivery Dockets
ca13890f-7573-4022-aa02-819cbb4fb0f7 | signoff | AUTHORITY HOLDPOINT
db6de711-9229-4ba0-b97b-c5c878d665a8 | checkpoint | 6 - Trenching (1)
ef15ba5e-ee45-5e19-bdc7-7d655ab0c38c | note | ACTION (Hold, Monitor, Witness) - W
21e579b6-3ce4-54e8-9a1d-6d05d28232f1 | note | DETAIL - Inspect trench profile and ensure it is correct to lines and levels to design. Ensure trench width is sufficient to provide enough space on either side of the pipe for compaction
bc05ff0c-925c-5615-9a6b-7374126aa7c8 | note | FREQUENCY - Prior to Installation
35bfd1b8-aa21-516e-ad2f-78daf5fe6374 | note | INSPECTION - Visual/Inspection
0c31c6f5-d6fd-56f8-ae1f-45b34bf9f9ff | note | CONFORMANCE CRITERIA - 350mm for external dia >900. DN900 for SW1, Line and level is correct
1b298376-540f-5fd9-8b02-086579053c69 | note | RECORDS - LQS-CS-4025
a7654020-4dad-4ced-81c5-d6f8ab11cd5e | checkpoint | 6 - Trenching (2)
a2c0476d-1837-5f3d-ae12-af24d8521c3e | note | ACTION (Hold, Monitor, Witness) - H
ca5cbb0a-2140-50bc-87fd-262d92e41cc8 | note | DETAIL - Base of trenching to be inspected by Design Engineer. If undercutting required or excess water encountered, backfill material and method to be agreed before proceeding
6251919c-a730-5c83-ba13-cff50be12f28 | note | FREQUENCY - Scalar 1/20m length of trench
d3653059-1e59-5f56-95d1-93af1cb05708 | note | INSPECTION - Visual Inspection
efbe2fad-9e78-5ecd-b9b8-da074c382845 | note | CONFORMANCE CRITERIA - Review Inferred CBRs with Design Engineer to sign-off
3e269463-2a5a-504c-842c-9302e9fd800d | note | RECORDS - LQS-CS-4003 Scala Record
52462691-2f4b-45be-8422-5ee3e6e0a4d0 | signoff | AUTHORITY HOLDPOINT
5b13b6a7-d44b-4f46-81e5-c0a7fbd9a99c | checkpoint | 7 - Pipe Installation (1)
c63b319e-03de-597d-9efd-3150d38ebeb9 | note | ACTION (Hold, Monitor, Witness) - W
04b5cd86-bdb5-5f37-b371-bcef31e01f02 | note | DETAIL - Bedding to be placed and compacted 150mm thick bedding for pipe dia between 450 to 1500
0b7738a6-2949-517d-ab94-e60b5c2afa43 | note | FREQUENCY - Prior to backfilling
cd71ed33-2fa1-5bac-b6db-69df7cdbcafc | note | INSPECTION - Lab Testing
bcdffa12-f0f5-58c8-a288-dda339e300ec | note | CONFORMANCE CRITERIA - AP20 Bedding
6a57c3fb-71f9-5130-969f-1f823f476e5a | note | ○ Clegg hammer CIV = >25 in engineered fill, and within berm (if req'd) CIV = >20
59ef4b27-597f-51a8-b110-855a4098d6c6 | note | ○ Pea Metal Bedding
3a985a09-d426-5b87-bcab-e4c0eeb7f686 | note | ○ Photo record of bedding.
496d6de8-17eb-5c5b-8e29-94428e86f405 | note | RECORDS - LQS-CS-4025
502c42d3-d5a7-41df-a4cf-d04f675e7847 | checkpoint | 7 - Pipe Installation (2)
57513da4-e812-5bdd-adea-e6467d914864 | note | ACTION (Hold, Monitor, Witness) - W
be86003a-0115-50f0-8882-c02c01a6f6d0 | note | DETAIL - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
6e8fbac8-5444-5ac4-b556-86f4517d69ca | note | FREQUENCY - Prior to backfilling
16c7f009-8075-5903-bb46-e541dc81d04b | note | INSPECTION - Survey
bc14ed18-f0a6-58fe-a67c-c62c886a1430 | note | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm, unless approved by eng rep
5bcfd970-f7c5-53d3-a268-e181534421f5 | note | RECORDS - LQS-CS-4025
d10a8c7d-4204-4bc1-9858-655dd9b06fd8 | checkpoint | 7 - Pipe Installation (3)
7d8869b5-cc09-5011-9adb-2073b22a18e1 | note | ACTION (Hold, Monitor, Witness) - W
3090cd7a-45e6-55a5-9d07-8d619cb2f81c | note | DETAIL - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
f5705570-acfe-56a4-9ac0-55475fdd352d | note | FREQUENCY - Prior to backfilling
f6625fd9-26ed-566d-b8c0-b6a56b043340 | note | INSPECTION - Survey
9fc27730-1b15-5e3e-b99a-c57737f87a84 | note | CONFORMANCE CRITERIA - Vertical tolerance +/- 5mm, unless approved by eng rep
627d3e91-d4a7-54a6-8cd0-791f022a4837 | note | RECORDS - LQS-CS-4025
7ae622b8-801e-48d7-943f-8508e90c36c3 | checkpoint | 7 - Pipe Installation (4)
c4eb23c0-1a4f-55a1-be64-ca9740dbb920 | note | ACTION (Hold, Monitor, Witness) - W
b84aa94e-e477-5b82-85db-5a27a158f418 | note | DETAIL - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
8fb7c31c-8be5-5774-b206-815f419ace1f | note | FREQUENCY - Prior to backfilling
5944a984-c8e6-5c6a-81f0-3ea81793e164 | note | INSPECTION - Visual/Inspection
e5b7ca5e-292e-5e8d-94d3-21d385c8531b | note | CONFORMANCE CRITERIA - No defects/ gaps / pipes are aligned correctly
028448f4-997d-54fb-b50b-ac776e5f2de5 | note | RECORDS - Photos
97debb05-f4ab-4cad-8ebb-a7444ca806f1 | checkpoint | 7 - Pipe Installation (5)
971c169c-2104-556c-a5b5-8f7594d7a5b3 | note | ACTION (Hold, Monitor, Witness) - W
980f7716-e8f6-55c8-814d-ed80b9dbe91c | note | DETAIL - Backfill compacted and tested in 200mm thick layers
7c5d60cd-8ce7-560a-99ad-0efed627fb09 | note | FREQUENCY - 1/20m length of pipe
369bfd4e-d26f-58e7-a9bd-9a692f304482 | note | INSPECTION - Measure/Testing
427d87cb-677c-5995-8a68-42333ff36c14 | note | CONFORMANCE CRITERIA - <Subbase Layer
27eb0178-89f4-5240-991f-e49541864e7a | note | — Clegg CIV >25 for engineered fill. In berms, Photo record.
b69e26b5-9e2b-5675-a464-e14533397ced | note | ○ Subbase Layer
ff61bcd9-3d38-52c1-9928-717d59fcef2c | note | — 95% MDD under carriageway for engineered fill. In berms, Photo record
3fd816dd-19fe-56ab-b215-73ba28d0b671 | note | ○ Basecourse Layer
70c22087-1baf-50aa-8dff-a585f729e0b7 | note | — 98% MDD for engineered fill. In berms, Photo record
c85357ac-3cb5-57ba-a9c0-e6aa12a47dd1 | note | RECORDS - Lab test Results/Photo/Clegg Sheet
9957fb02-049a-4c60-979f-15ed0efd7113 | checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (1)
4552ff4d-2bda-5270-a161-f1c5b73e289b | note | ACTION (Hold, Monitor, Witness) - W
31166e15-9995-5b94-b58f-04e1ff6677eb | note | DETAIL - Base of structure to be tested. Scala's to be minimum of 3 blows per 100mm
e27142c1-e283-56d7-88cc-77575fbf4ffb | note | FREQUENCY - 1 test per structure
601724bb-688a-5146-9f1f-38f3ee5853c8 | note | INSPECTION - Testing
17d80549-9580-5733-9c03-d2770c60ac98 | note | CONFORMANCE CRITERIA - Scala minimum 3 blows/100mm
f3a90d9d-13fd-571a-b9ba-eea38fd5eddf | note | RECORDS - LQS-LA-4003
1fdcaca4-7265-4693-ba7f-592cf047c449 | checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (2)
563cb95e-eb7d-59de-92a0-0fd9a275b5a9 | note | ACTION (Hold, Monitor, Witness) - W
5d462085-c141-5094-a85c-b4ee2a62b6ec | note | DETAIL - Structures to be installed to the design survey location and level
6d0e8d11-add9-558f-9a03-49e3da23aec0 | note | FREQUENCY - During structure construction
642c38e9-f7ff-5898-b809-9fb1f114af98 | note | INSPECTION - Visual/Inspection
ddb0f21d-b75a-59ad-9e00-50f3fea422ef | note | CONFORMANCE CRITERIA - As-Built Survey
21f80c6e-b061-5fe6-b44f-8a15da1e874c | note | RECORDS - LQS-CS-4006, As-Builts
9754dc11-cc27-4937-b990-6b159fb21a7e | checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (3)
01645ea3-43be-5898-aee6-9e4d8e7e7d0b | note | ACTION (Hold, Monitor, Witness) - W
7c19fcd8-b75f-5513-a460-d2987805ed62 | note | DETAIL - Corbals to be poured around each connection to a manhole structure
e4d237d4-74d9-5be6-9b89-a628f2d5aee2 | note | FREQUENCY - During structure construction
163d3955-f670-5f83-a42a-c4d6bda930c0 | note | INSPECTION - Visual/Inspection
bdc04580-a20e-5b04-9e8a-110b36a49472 | note | CONFORMANCE CRITERIA - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
fe8b1c3a-40e3-5fca-b47f-a3386748ce15 | note | RECORDS - LQS-CS-4006
dfb3a6ff-97a9-49ca-92c6-4940f0cc5936 | checkpoint | 8 - Structure installation (Manhole, Catchpit, Wingwall) (4)
8dbfec4e-c3e1-5c64-af9e-fe0f4fcd4bf4 | note | ACTION (Hold, Monitor, Witness) - W
4ef9c5e8-2151-56ee-9956-88a3b7f012cc | note | DETAIL - As-built survey of the structure and all invert levels
009065b9-6a8d-51f0-b871-65eb37f0f3b3 | note | FREQUENCY - Once installed
53e4782c-a60f-51c8-ab23-6fad0ff0c470 | note | INSPECTION - Survey
a216fa60-b4c6-5e71-8f01-1f11515828f2 | note | CONFORMANCE CRITERIA - As Built Survey
89f29af6-a9a0-5408-ba9f-0234ed65b062 | note | RECORDS - As builts
2f0e1edb-dce0-48dc-9528-b78702f217ce | checkpoint | 9 - CCTV
3f2d49c3-38b1-5a6e-9f92-443439e1921d | note | ACTION (Hold, Monitor, Witness) - H
62449f5a-5bc1-5f47-8649-171a1891562f | note | DETAIL - For pipes <900mm a CCTV inspection must be completed. Pipes >900mm must be visually inspected
067bfbf8-621d-5065-ba9e-d562ad6b016e | note | FREQUENCY - At completion of the works
c37b3f68-22ad-5d1a-aab0-454dd365def4 | note | INSPECTION - Visual Inspection/ CCTV inspection
8f6b56df-1e6e-514c-bdcc-2b6ea5621dcc | note | CONFORMANCE CRITERIA - No Defects
2e410cb2-62b8-5a33-8d8a-740ea684f789 | note | RECORDS - Inspection Report CCTV DVD
a2893d0f-0f49-48c8-aca1-353a2b6924a0 | signoff | AUTHORITY HOLDPOINT
6ab5bc44-9278-438f-869d-6c37c84895ca | checkpoint | 10 - Testing of Manholes & Pipelines
7dd0ce12-c8aa-5e18-9bba-9ac16fb92191 | note | ACTION (Hold, Monitor, Witness) - H
ceb0e5d0-7f33-5e87-b11f-f31652345d63 | note | DETAIL - If required, testing for water tightness in the structures and low pressure air testing of the pipelines is to be carried out - test sheets to be filling in where required
ba72c083-cb52-57d6-b5d3-2d3c41ec91dc | note | FREQUENCY - One per line/structure
54fb258b-ade1-5415-960f-cef9d810d3eb | note | INSPECTION - Measurement
6529ef38-8e62-5978-956c-47070cfbc477 | note | CONFORMANCE CRITERIA - Drainage Structure Water Tightness Test Record & Low Pressure Air Test Record
2280f535-527c-5619-9f5a-105dd78a6e54 | note | RECORDS - LQS-CS-4073 & FHIMS-CS-4074
4ef083aa-a5e5-492d-b44c-9b1ece745ab4 | signoff | AUTHORITY HOLDPOINT
d9a2e5f1-e298-4d7f-9075-f88bd38ed077 | checkpoint | 11 - Survey As Built
36aa1cac-e338-5111-8a4c-4d86938fe25a | note | ACTION (Hold, Monitor, Witness) - H
1d4ad847-59ab-516c-ae91-924ccad8d1e2 | note | DETAIL - Ensure all drainage lines comply with design prior to carrying on with next construction process
5d083ce3-7897-53ee-9e97-fe4422425377 | note | FREQUENCY - At completion of drainage line
5e84f845-ca2a-5042-a089-517275668632 | note | INSPECTION - Measurement
6b6d64f0-e7fd-5a76-ba2a-d6576167ec4b | note | RECORDS - Survey receipt
d2c6ebf7-c77d-4249-8189-de6139829377 | signoff | AUTHORITY HOLDPOINT
574cca2c-7d93-432f-a10e-99ace67ee4e1 | checkpoint | 12 - As-builts
12d38561-8d88-5ee8-8b67-b2ab3e9a8812 | note | ACTION (Hold, Monitor, Witness) - H
179a4473-a9cb-5006-9d83-7e56169c5a1a | note | DETAIL - Updated drawings to be submitted with As-built line and levels recorded
09b6fd58-03e8-524a-b629-6fd6f96866e5 | note | FREQUENCY - At the completion of the Lot of work
09e71374-9d05-58d1-a9bf-0e8e4961a9e3 | note | INSPECTION - Drawings
befdc820-f738-5a27-b44d-0a7140c9ecd5 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
2843c98e-3843-53e1-839e-15f1ae586826 | note | RECORDS - Asbuilt Drawing
bfa980ad-6eb8-4503-9983-9f0b004a31d2 | signoff | AUTHORITY HOLDPOINT
7798f415-bd37-4ef2-86a1-07f7d0cc1279 | checkpoint | Final Inspection
954d8352-2ceb-576a-916b-2bf3032a12e3 | textbox | QA Compiled By:
34258375-b6ad-514c-a177-8083460ea30d | textbox | QA checked By Project Manager:
1eb89aa4-a481-5c5e-bd91-a15412dd9d36 | textbox | Accepted By Design Engineer:
bdb63e22-67e2-46d0-b432-ed15ebbb48d5 | signoff | Sign ITP
5dbbdfa2-45e6-415d-a3e2-4761a2e424e7 | checklist | LQS-QA-6090 - ITP - Service Installation | itp | LQS-QA-6090 - ITP - Service Installation
ac55603c-3f2e-474f-8ec4-f9eaf9816039 | section | Service Installation
e4aed450-fe7e-4d2f-9d30-0f577329358c | checkpoint | 1 - Permits
f0a09317-71e8-5937-a4fd-3b0d8faad583 | note | ACTION (Hold, Monitor, Witness) - H
6b034d75-328b-5b73-b8d1-e65b7c1b4748 | note | DETAIL - Obtain Permits
33ba6d04-ec75-5a38-9a57-099153e5f17c | note | FREQUENCY - As required
483e56da-c2ad-5430-8e14-5d256e1e51bb | note | INSPECTION - Document Review
709682b3-b2cd-53ec-906d-40cbca0e2d98 | note | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), PTW #1 - Confined Space, PTW #2 - Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
7d845bbd-189a-56e2-a72f-fd154c1d53ee | note | RECORDS - Permit attached or permit number noted
ecd55f01-c65c-4dab-ba86-220c0dd5061d | signoff | AUTHORITY HOLDPOINT
c31c5c7c-aa07-4e74-aa81-549c51002ca1 | checkpoint | 2 - Design
c6e382b9-5767-51bc-b2f5-7aaf64d56f95 | note | ACTION (Hold, Monitor, Witness) - H
5a5a88a8-a735-5ca9-a1da-bad6a9336295 | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
cd747f57-36a3-5b0a-8cd0-b2e0ca4d1d1e | note | FREQUENCY - Prior to commencement
8b418792-c973-5b6d-b3d9-76f86e8b6683 | note | INSPECTION - Document Review
46e5d17e-844d-5538-9282-635ed04fd44e | note | CONFORMANCE CRITERIA - IFC Drawings
8b16d324-e6b2-5746-a411-0623b9868a00 | note | RECORDS - Check Drawing Register
5b4d1d85-5237-4a03-a6ac-6b19f89cdfb0 | signoff | AUTHORITY HOLDPOINT
d4b1bf74-7d5e-4c53-a5fe-a974433fc4e5 | checkpoint | 3 - Survey Setout
5ea38586-bf15-584d-90b8-415f847870b9 | note | ACTION (Hold, Monitor, Witness) - H
529fffa0-6478-58f2-9d3a-d92090edef5e | note | DETAIL - Set out utiliy service alignment, and depths per construction drawings
3e721f9f-df8e-539b-b0ca-ec9ce174019e | note | FREQUENCY - Prior to commencement
6fef7c01-7550-5fb0-9370-1f90a09223c7 | note | INSPECTION - Survey
70c1e03d-edfd-56be-aeee-63e7c6729bda | note | CONFORMANCE CRITERIA - Survey is correct and consistent with plans
765e9558-8958-5617-816e-289dafc33321 | note | RECORDS - Photo
aa527887-1075-4390-b135-5d980145fb9e | signoff | AUTHORITY HOLDPOINT
a86d80a5-c8e8-4b32-88d5-0fe02b12b744 | checkpoint | 5 - Material Compliance (1)
62b8bdeb-faab-5f5d-9a95-83f81a183864 | note | ACTION (Hold, Monitor, Witness) - H
475afc9d-e72f-5cde-9637-2bb37c7c5bfd | note | DETAIL - PVC ducting shall be of approved material and/or supplied by service provider
b2906752-bad4-5dcd-b57b-a9d6576165bb | note | FREQUENCY - Prior to instalment
a3692274-4967-5e4b-93df-4ab732dea27f | note | INSPECTION - Document/Visual
ec3411ad-187f-5cc4-ae16-d5019eaef1fd | note | CONFORMANCE CRITERIA - Ducts are acceptable to the service providers standards
5bff3be4-664b-52b0-a76b-b489f2e2a758 | note | RECORDS - Delivery Docket/ Service Provider acceptance
a1207c84-2250-4746-8c80-e161208af70b | signoff | AUTHORITY HOLDPOINT
f3caf393-4510-48d7-8034-56a37389b3d1 | checkpoint | 5 - Material Compliance (2)
3749c1d2-0042-564a-adf5-3e5e9eb84b84 | note | ACTION (Hold, Monitor, Witness) - H
3d689cc6-8e35-586b-9ca4-e57f0b9447ba | note | DETAIL - Ensure cables, transformers and ring main units are to (service Providers) specifications
33834238-ad55-5c08-b19d-91a47f690bbb | note | FREQUENCY - Prior to installation
fbf91982-30fd-5d39-b94b-74a2d6139d28 | note | INSPECTION - Document review
8a2d5546-6d82-5409-977c-0234bba43a5d | note | CONFORMANCE CRITERIA - As per (Power Providers) specifications
155b785f-0b9d-5320-99b8-9e80b59a6227 | note | RECORDS - Delivery Dockets
7f03a72f-4417-41ae-a004-0c7cc3ecbc37 | signoff | AUTHORITY HOLDPOINT
25b28ac0-d536-48ef-8fef-e9ac04d58c90 | checkpoint | 5 - Material Compliance (3)
f3169bd9-465c-5643-87b4-4950f719e4e3 | note | ACTION (Hold, Monitor, Witness) - H
4715c4e1-73c6-5705-a0df-996f1c090dc0 | note | DETAIL - Bedding material/backfill shall meet the specifications of the service provider/Specifications
d77aea5a-fdd3-5da1-af92-0a0e0831b105 | note | FREQUENCY - Prior to installation
32a92b38-0683-5fb9-90df-e3b8bbb1a295 | note | INSPECTION - Document review
101eab2f-fd15-5e28-b63c-133a69207592 | note | CONFORMANCE CRITERIA - As per (Power Providers) specifications, NTLDM
e5110119-a2b7-51df-b68f-6fda0d7e1ebe | note | RECORDS - Delivery dockets, Lab Material testing
21c6f457-4b60-4db2-90c5-ffee0de51893 | signoff | AUTHORITY HOLDPOINT
117fc9e9-36fb-4e98-a546-4acc1ca2f40f | checkpoint | 6 - Trenching & Service Installation (1)
6f140cfa-54c3-5e96-84d5-b31d2487f531 | note | ACTION (Hold, Monitor, Witness) - W
b2230d0a-0f08-5bbc-a9b2-75e34f0239df | note | DETAIL - Inspect trench profile and ensure it is correct to lines and levels set out by survey
290bc5cd-a0b8-5178-8f66-9e51ae89e9a1 | note | FREQUENCY - Daily
c873c352-cb36-5cac-8363-ec343efc2ec8 | note | INSPECTION - Visual
d04d48ca-e508-5e84-a82f-415761dc312c | note | CONFORMANCE CRITERIA - Depth and line is correct as per for construction drawings
9f9b54a5-df50-522f-a0ce-b0ef800f6054 | note | RECORDS - FHIMS-CS-4010
bae83485-f893-4ac9-b35d-7b3b72a09145 | checkpoint | 6 - Trenching & Service Installation (2)
1a3c13c3-d5b1-52af-a628-fe9ec4b27bbb | note | ACTION (Hold, Monitor, Witness) - W
3ee3194f-d335-58dd-8a66-7d1dc61f6d1c | note | DETAIL - 100mm thick bedding to be placed and compacted and cable laid (by other)
653c73dc-8d72-52d7-acd1-4da836d92749 | note | FREQUENCY - Prior to backfilling
2d501efc-b6b7-5ca8-92f5-37d6b582385b | note | INSPECTION - Visual
55bd3319-4e63-54de-b3fa-9713ef88a784 | note | CONFORMANCE CRITERIA - >100mm of clean sand bedding
5b0f1e38-6e4b-5147-8728-8a5962dcd53a | note | RECORDS - FHIMS-CS-4010
86f6e1f7-1088-4282-8ce7-cc1b3c367f3e | checkpoint | 6 - Trenching & Service Installation (3)
9ed806dd-0d93-5f1f-81ca-91f405de8ada | note | ACTION (Hold, Monitor, Witness) - W
918e533a-de1a-52ca-9a6e-00aa32769cc8 | note | DETAIL - As built survey at intervals of no more than 20m and at each change in direction
c80ff893-4b17-5cac-bed5-e01250c0314c | note | FREQUENCY - Prior to backfilling
4de80ae5-2a2f-57f6-bd38-b6ce269b74df | note | INSPECTION - Survey
68d6470d-4687-56a6-b149-253b519ea4b7 | note | CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times
de0818cb-5bf3-59ba-be27-54e1637c6d03 | note | RECORDS - As-Builts
d87945a2-339e-4b34-a052-60e67771c771 | checkpoint | 6 - Trenching & Service Installation (4)
218926ec-d8b2-5e7d-8daf-7b04c16cbfdd | note | ACTION (Hold, Monitor, Witness) - W
4042f47c-b17f-5a4f-bc6b-3a3099229200 | note | DETAIL - If required, Mag slab to be installed 300mm above the cable
fac812ec-1a5b-5c72-9fd0-3c9fcfcd560f | note | FREQUENCY - Prior to backfilling
e2061882-f237-561c-82ea-89bf22beff50 | note | INSPECTION - Visual
b7accdd8-38bd-5223-acae-be5a2cd7585d | note | CONFORMANCE CRITERIA - Mag slab to be laid on top of clean sand layer
54a65935-1844-54db-846a-972cadccc0f2 | note | RECORDS - FHIMS-CS-4010
20281288-67fc-44a5-be72-04fee280b69e | checkpoint | 6 - Trenching & Service Installation (5)
ff651dbb-2c11-5738-bc66-c38a5996812f | note | ACTION (Hold, Monitor, Witness) - W
cc08c75e-5c38-500b-aa61-0d5cbf15f455 | note | DETAIL - Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet (Power Providers) specification.
6af9cc14-eccb-525b-84d2-16fa23819f5e | note | FREQUENCY - Every 300mm lift
94f00213-f390-54be-83b5-01ef2c93530a | note | INSPECTION - Visual
65117886-071d-5bd8-b90b-dc558579faa4 | note | CONFORMANCE CRITERIA - <Subbase Layer
b7f97e70-9ad9-57cd-b09c-469ffab24682 | note | — Clegg CIV >25 for engineered fill. In berms, Photo record.
1a553cda-6244-51e4-b764-796ecf63cea9 | note | ○ Subbase Layer
08c8e574-4e97-5315-9dce-1b885e4a52c9 | note | — 95% MDD under carriageway for engineered fill. In berms, Photo record
a9f11d54-c71e-52a1-ba93-71c39c4a0340 | note | ○ Basecourse Layer
9ee25afb-0351-5789-b60e-021a5d9d475f | note | — 98% MDD for engineered fill. In berms, Photo record
5bd8b406-eceb-5f60-97aa-7953d997117b | note | RECORDS - Lab Test results, Clegg Hammer Checksheet
9b8fefd4-0be0-49ab-a050-5314e5decb6d | checkpoint | 7 - Directional Drilling (1)
d9ba5baf-9438-5c6c-bb65-9edf9b2d2972 | note | ACTION (Hold, Monitor, Witness) - W
30f60c64-5251-5ce6-aa53-b601138e45e3 | note | DETAIL - PE Pipe installed by drilling to survey setout, draw wire/draw rope installed and cable pulled through pipe
0487a7f4-f3e8-5a08-9155-ffd0d15b5968 | note | FREQUENCY - Daily
ca567f6f-d0ae-5212-9200-115c3aae6c90 | note | INSPECTION - Visual
804a1889-f857-5f4c-b06d-cb85e6e5d9f2 | note | CONFORMANCE CRITERIA - Line and depth consistent with for construction drawings
c54c6533-9af8-5ae3-9224-89a2f085d0c1 | note | RECORDS - Survey receipt
c039d28d-8fc7-46e3-89a7-300df1c1aa5a | checkpoint | 7 - Directional Drilling (2)
64935ecf-43ba-54f1-a154-7c895cf36561 | note | ACTION (Hold, Monitor, Witness) - W
a448b507-8f9e-5753-ae14-93982c158539 | note | DETAIL - As built survey of the PE pipe installed including depth using depths marked by drilling contractors
00691caa-3fb2-50a6-aab7-d4bdfd4c1702 | note | FREQUENCY - After duct has been installed
2c5460ce-862d-5247-bc6e-a97ba2505b63 | note | INSPECTION - Survey
5d813525-ae3d-51d2-9432-a1c9f0f922ec | note | CONFORMANCE CRITERIA - As-built points spacing to be less than 20m at all times
f17f192d-23fa-5bbd-be05-c1c5b2c7eeed | note | RECORDS - As-Builts
d420dcd6-9b6a-407b-8143-4040ca41602c | checkpoint | 7 - Directional Drilling (3)
572b5e83-51e3-576e-8a3b-ccd7233e3c55 | note | ACTION (Hold, Monitor, Witness) - W
d9ae33c1-0536-560f-9ee4-1b8668e26e61 | note | DETAIL - Backfill connection pits, Sand placed to bed cabling. Clean Insitu backfill material to be placed and compacted in 300mm lifts to meet power providers specification.
92323ec9-cd00-5805-917f-e727a2617d18 | note | FREQUENCY - As required by specification
c61e8f34-d805-5a7a-8054-2ca32414d53f | note | INSPECTION - Visual
a82d5013-9bc3-576f-a33a-a8b0680bb738 | note | CONFORMANCE CRITERIA - <Subbase Layer
bde64ce1-d900-5540-b999-4f44f319f91d | note | — Clegg CIV >25 for engineered fill. In berms, Photo record.
5d82d2c4-8bc0-53ba-a467-efe58c4c7d7c | note | ○ Subbase Layer
6247a08e-ff5a-51e5-ae21-4ada7b88b005 | note | — 95% MDD under carriageway for engineered fill. In berms, Photo record
f727589c-411e-5124-ad4c-ef0e842464b4 | note | ○ Basecourse Layer
89d21d45-f3fd-53bb-954e-e6ef4715242b | note | — 98% MDD for engineered fill. In berms, Photo record
4a12af75-c945-5413-b24b-f7ad30bb45c6 | note | RECORDS - Lab Test results,Photo
295a6e81-6627-4823-b6ab-486b1cd9b250 | checkpoint | 8 - Feature installation (1)
cc3811b5-4e32-5be8-af7e-43615499f336 | note | ACTION (Hold, Monitor, Witness) - W
c26944d6-2097-5b4f-a52d-70263ac4cff6 | note | DETAIL - Feature such as poles, transformers, distribution pillars installed as per IFC drawings
1a0b363f-666f-5902-92ee-69abff3bf9e5 | note | FREQUENCY - Daily checks
690ad139-ff86-5036-a08e-181726a919af | note | INSPECTION - Visual
94cddb80-d02d-5bb2-b55a-b71fd5023973 | note | CONFORMANCE CRITERIA - Location of feature consistent with for construction drawings
882ff800-0a9f-566c-8faa-c4dbfd08a6ae | note | RECORDS - Survey receipt
3c7c7445-c59a-402f-a433-54a42456c41b | checkpoint | 8 - Feature installation (2)
9e558c47-bc59-5069-a441-3bee9990f6bd | note | ACTION (Hold, Monitor, Witness) - W
d4bb63ca-cb22-54e7-b13e-b41ce50ba4e9 | note | DETAIL - Install overhead lines to the locations shown on the drawings
465ffb37-edf6-5c55-9d92-c4993c0de177 | note | FREQUENCY - Daily checks
9ec85bcf-1eed-5146-8497-a7d185746fa2 | note | INSPECTION - Visual
c13ac3f7-627d-52bd-b51c-d452979f1394 | note | CONFORMANCE CRITERIA - Consistent with for construction drawings
956092f0-f381-5a89-9b90-42c1f4c9ae75 | note | RECORDS - Certificate of acceptance
6cb9ca40-fd06-4a62-8333-0a9a84e80879 | checkpoint | 9 - Connection
1da37c89-c4c0-587f-8a2f-aa4a7434c1a0 | note | ACTION (Hold, Monitor, Witness) - W
0b6f1440-6dde-5d26-b902-026ba6f18d93 | note | DETAIL - Complete all jointing and carry out testing
fd2124e3-e2ea-5b08-bce2-589aa0c6dbe6 | note | FREQUENCY - After instalment of Cable/Ducts
b834c67b-b749-5e62-a4de-109be9f4e4b7 | note | INSPECTION - Visual
f8fe5db4-7e51-5ad7-89c4-d739851a9135 | note | CONFORMANCE CRITERIA - Commissioning tests all pass
94486bf4-82e3-5f2e-bea8-9854ebb8f169 | note | RECORDS - Confirmation Note
f9a43f30-ac7b-46cf-a18e-8d62e015bdde | checkpoint | 10 - Service handover
a7230f8b-6761-5126-ac43-14ec8adb5219 | note | ACTION (Hold, Monitor, Witness) - W
5a44aa8c-b6f9-5234-b827-d7fd673e0105 | note | DETAIL - Service accepted by the service provider
76e63bfe-14d1-52e3-8cfd-456c2265422f | note | FREQUENCY - Completion of works
5a115ef9-d699-5fb9-8407-251b239f915c | note | INSPECTION - Document
fc367414-3266-5d15-b478-6a4cfbb88348 | note | CONFORMANCE CRITERIA - Service provider approval
6df210a5-8329-588e-9210-a618e2ab949a | note | RECORDS - Certificate of acceptance
9df1b347-0cc0-46f3-941d-3a6ed8df65fb | checkpoint | 11 - Abandonment (1)
c980aef4-03f4-51b3-89f7-89cf65defe74 | note | ACTION (Hold, Monitor, Witness) - W
691cd51a-b9f4-5fbf-8d8e-21e4ef079b09 | note | DETAIL - Once the existing power line is taken out of service it shall be capped and sealed in the locations on the IFC drawings
4d56ad29-2951-5561-baa9-9806636e2cab | note | FREQUENCY - Completion of works
9bf13560-a13d-50af-93f3-5342bd1f6af0 | note | INSPECTION - Visual
e838c3cb-7ed7-5d21-b8e1-f76ddf22abb1 | note | CONFORMANCE CRITERIA - Consistent with for construction drawings
24346e1d-1c45-518e-8b15-969b64558b45 | note | RECORDS - As-built drawings
a5983b6c-ddf3-41a5-b054-a51007fc9647 | checkpoint | 11 - Abandonment (2)
88c3010a-3a7d-5268-8782-c23d27bbeabb | note | ACTION (Hold, Monitor, Witness) - W
88f8295f-8437-584b-8aa1-a62bd2e1cb37 | note | DETAIL - Remove all other redundant items such as redundant poles, pillar boxes, overhead lines etc.
adfaff40-ca69-531f-bbb3-fd6375ae65c2 | note | FREQUENCY - Completion of works
5296848f-eb1d-59db-bbf6-4cd96dc93c3a | note | INSPECTION - Visual
76bf6994-136d-5312-857b-92542a42c206 | note | CONFORMANCE CRITERIA - Site clear of redundant items
b838c4e8-0877-5268-aaaf-d1ec6842816d | note | RECORDS - As-built drawings
35cf8661-0857-4ebc-a496-eb6a68543d1d | checkpoint | 12 - As-builts
fb86fb4c-8ce1-58b0-a247-1f3ee52834d5 | note | ACTION (Hold, Monitor, Witness) - H
22e78613-4afd-5025-9e16-0dd3c48175c8 | note | DETAIL - Updated drawings to be submitted with As-built line and levels recorded
5f61e3cd-9d01-5fab-a009-71e891343559 | note | FREQUENCY - At the completion of the Lot of work
8e155b2c-ed74-5eac-b245-a0841c8cf9e5 | note | INSPECTION - Drawings
bb95c5d5-ab27-5951-b8e4-8a165d0ffdfd | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, service provider secification
522b329c-2692-56bf-b505-cbb9889d61c4 | note | RECORDS - Asbuilt Drawing
3031dc96-cb16-4394-aa32-07f61341a186 | signoff | AUTHORITY HOLDPOINT
2d7a6a0e-160b-463f-86f1-8057462259a6 | checkpoint | Final Inspection
42ca45c1-7bbf-58c1-8834-8669c3696801 | textbox | QA Compiled By:
aab05c39-beef-5c11-9007-3032258d2059 | textbox | QA checked By Project Manager:
a11d49ab-f867-5ccd-84ac-8b1bed7ae06a | textbox | Accepted By Design Engineer:
5cc8ef1e-ba48-4da6-9abf-fccbc5b29261 | signoff | Sign ITP
0b0045b1-f3dd-4538-b0ee-12555f7e5be4 | checklist | LQS-QA-6092 - ITP - Water Services | itp | LQS-QA-6092 - ITP - Water Services
ab94cc40-c069-47d4-b4bd-3b1e61936b54 | section | Water Services
8a103069-69b5-456e-ae09-9790b5041cce | checkpoint | 1 - Permits
3495bde2-f949-594b-84f8-14cdc20e7d55 | note | ACTION (Hold, Monitor, Witness) - H
63de7df3-75c3-502b-b67f-e8f6a82e4dce | note | DETAIL - Obtain Permits
fe921714-8181-52d9-98ef-2179444f3863 | note | FREQUENCY - As required
6a44ff1f-5585-561d-98fc-9116caff5a14 | note | INSPECTION - Document Review
8b7998eb-6721-551d-a66d-1be673de430b | note | CONFORMANCE CRITERIA - Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), PTW #2 Trench Excavation Inspection, Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
8bea1728-9c6b-5961-9f0d-92db1c297714 | note | RECORDS - Permit attached or permit number noted
419ff225-fb24-4b21-851c-3b3f0ad6d394 | signoff | AUTHORITY HOLDPOINT
9a97f187-1e1e-4f21-a021-6798231c8409 | checkpoint | 2 - Design
531d6ac1-915c-57d0-9114-50c9a2d81103 | note | ACTION (Hold, Monitor, Witness) - H
183c49da-87f1-5fab-ab14-aebff9817686 | note | DETAIL - Ensure that Design is approved and Drawings are of the latest revision
995109f2-48bb-579b-aae1-a5b0c2b3b522 | note | FREQUENCY - Prior to commencement
5453849b-aee6-54de-b6fa-fa8f4bd7976a | note | INSPECTION - Document Review
921ec380-2f30-5885-b9f0-c4e52690fc09 | note | CONFORMANCE CRITERIA - IFC Drawings
22a42176-aded-5c4d-9674-8ad96ccbeb4d | note | RECORDS - Check Drawing Register
6fd5d511-4b92-4d44-bd31-d6cab0fcbe1c | signoff | AUTHORITY HOLDPOINT
95168eec-79e5-4511-9785-436263c92b6d | checkpoint | 3 - Survey Setout
e26783ba-2c09-50cd-996e-195b4be38f7e | note | ACTION (Hold, Monitor, Witness) - H
0f2644b6-ae28-5d15-9d16-68361e2f45e3 | note | DETAIL - Set out watermain alignment, design features and depths per construction drawings
c22e486a-5e16-548c-9263-ade859339d74 | note | FREQUENCY - Prior to commencement
59d81785-bb1d-5a56-9b01-4645550ae889 | note | INSPECTION - Survey
69f9df35-554f-5085-b9ef-2139389b17aa | note | CONFORMANCE CRITERIA - Survey is correct and consistent with plans
f7ef344f-ec94-5586-910b-c78bb4f910bc | note | RECORDS - Photo
dce6b22f-aa93-4a62-92fb-787bd58229ce | signoff | AUTHORITY HOLDPOINT
f4912cbb-50d8-4dc7-8674-cc97aad51f2f | checkpoint | 5 - Material Compliance (1)
c50ac607-0596-5361-97a5-40b15e302242 | note | ACTION (Hold, Monitor, Witness) - H
e2f961de-c327-5c3b-9ae2-62208512e2c2 | note | DETAIL - Bedding, Side support and Overlay materials tested in accordance with Specifications
4c8ae5ec-8000-5324-bd3a-63e99138dd27 | note | FREQUENCY - Baseline test
cb80a80c-3e94-5b8c-96a7-a586d3510b17 | note | INSPECTION - Document review Lab Testing
9bc44eaf-1f7f-5f15-ac3c-fc28f29d6bb2 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
5da4a5d6-2b2d-5845-b2e8-46c5889f7e61 | note | RECORDS - Lab Test results
0632e64e-d572-4045-93a4-087555cc64bb | signoff | AUTHORITY HOLDPOINT
10887624-998f-42a9-8933-84d2f56324e4 | checkpoint | 5 - Material Compliance (2)
508690af-471b-5789-bf0a-e1487aa3b10c | note | ACTION (Hold, Monitor, Witness) - H
e554d5b0-4631-5dde-9e58-170fa6d9c85a | note | DETAIL - HDPE pipe is in accordance with specifications. If Butt welded, this has been completed in accordance with Specifications and correct number of test welds completed
cf73524c-8b4e-5f97-9446-ed2f2f9e8623 | note | FREQUENCY - Prior to Installation
9dee83c1-1aa3-557b-9198-b686e07f33ba | note | INSPECTION - Document review
e8edae1f-159d-5b30-bc4e-44e12c1dfdea | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, Project specification
a8ee59ec-4cb8-58df-9b14-156126e9b658 | note | RECORDS - PE welder Record, Delivery Dockets, Test weld cert
558ea7f0-07bb-4468-8c2d-0471fa1e20ba | signoff | AUTHORITY HOLDPOINT
349ef228-8915-4f7e-a810-56b2edfa12e9 | checkpoint | 5 - Material Compliance (3)
d322ad5e-d73c-5cac-b1aa-2a2c36a60f9f | note | ACTION (Hold, Monitor, Witness) - H
d2566ebe-8e9e-5828-9dcb-62cf37d868e6 | note | DETAIL - PVC pipe is in accordance with specifications. Joins shall have spigot and socket joints with rubber rings
81593238-f058-575d-9d26-cd8738bc2ed4 | note | FREQUENCY - Prior to Installation
f2b1c4f1-268a-5db0-8822-e49ceca6f146 | note | INSPECTION - Document review
ecc4a5d2-516a-5b79-ac5b-aeaba376a396 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, Project specification
b8e05667-ed9a-51e4-b3ca-49e5d788ebf6 | note | RECORDS - Photo, Delivery Dockets
751d813c-2c36-4a86-9d73-0dd131f517ad | signoff | AUTHORITY HOLDPOINT
53e014b3-f6fa-460f-bb07-da3f4e42272a | checkpoint | 5 - Material Compliance (4)
942cfa2f-f756-56ed-9623-0780c8b0bd96 | note | ACTION (Hold, Monitor, Witness) - H
b96a8498-e782-5abc-9409-4ab9a4c8ceeb | note | DETAIL - Flanges, Valve boxes, Fire Hydrants, bolts, nuts, washers shall be as in accordance with the Specifications
9be2d827-e58f-5663-806c-a2e52b4c7eb4 | note | FREQUENCY - Prior to Installation
6683cd5e-3e5a-5234-8bd2-4e2aacf40e3a | note | INSPECTION - Document review
49bb0e66-2a48-5fec-90ad-f5655f1ebd4e | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
cc4ff1a4-85ae-5ea1-96ab-6c4b6cac8e66 | note | RECORDS - Delivery Dockets
1c446ca5-c91e-472c-8799-e071f2e91028 | signoff | AUTHORITY HOLDPOINT
9844c782-5951-480f-8c41-c4d0cd2af788 | checkpoint | 5 - Material Compliance (5)
87d30818-bbf3-596b-96c9-242f659c6bc7 | note | DETAIL - Concrete - ensure its in accordance with the Specifications
0bf07903-2ecf-53ef-b022-68bb40e24000 | note | FREQUENCY - Prior to Installation
c900e2f1-574d-5ffd-a866-de8684ce21e4 | note | INSPECTION - Document review
595d1a51-b568-511d-ac8d-0e79a2cf557c | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
0fa9ab92-1c42-5790-9385-1419a00e8a60 | note | RECORDS - Delivery Dockets
3e4b697b-8c8b-47cc-99ac-e2bce125b1e3 | checkpoint | 6 - Trenching (1)
1959658e-6828-5115-b697-f5dbef507e2c | note | ACTION (Hold, Monitor, Witness) - W
7b0a5589-c176-5c01-9d15-1427356836d9 | note | DETAIL - Inspect trench profile and ensure it is correct to lines and levels set out by survey
1ba41e06-8fe6-5cbe-b235-adf49e1dfeb8 | note | FREQUENCY - Daily
c9e8cd93-62b5-5522-ab7f-8e0665776a36 | note | INSPECTION - Visual
102a23a0-6986-523b-84b2-515cf8ae3969 | note | CONFORMANCE CRITERIA - Depth and line is correct as per for construction drawings
28480859-8fa9-56e4-9101-c40cee891898 | note | RECORDS - LQS-CS-4101
b4de32ba-0ffb-4dc0-8233-16db8a023e9e | checkpoint | 6 - Trenching (2)
ff623b60-9a40-5846-aa8b-c64ff3f42a7c | note | ACTION (Hold, Monitor, Witness) - H
ae854826-7c38-592a-b1e1-eb50b7db40ec | note | DETAIL - Base of trenching to be inspected by Design Engineer. If underctting required, backfill material and method to be agreed before proceeding
45f0aa8a-20b8-5d92-9d8b-a1650627dbc6 | note | FREQUENCY - Scalar 1/20m length of trench
e24d7341-4a87-5292-b390-418f1bc01827 | note | INSPECTION - Visual Inspection
30d8a755-67b1-5137-9929-d578a83658bd | note | CONFORMANCE CRITERIA - Review Inferred CBRs with Design Engineer to sign-off
0d989bf4-28ad-531f-a1c1-c2a3fb1a432f | note | RECORDS - LQS-CS-4003 Scala Record
a9833387-11d4-49e8-9272-e5fab5e50a76 | signoff | AUTHORITY HOLDPOINT
15de9766-507d-4618-b722-87842f7e37e2 | checkpoint | 7 - Pipe Installation (1)
ff58a723-3abd-59bd-9535-56e112813078 | note | ACTION (Hold, Monitor, Witness) - W
0ea45864-7a23-50c3-8a11-3a1a03e2fbd8 | note | DETAIL - 100mm thick bedding to be placed and compacted
b2310397-2ce3-5361-82b2-5ce33bbbad0a | note | FREQUENCY - Prior to backfilling
e3974527-3937-5dc5-bce7-055e79845b6b | note | INSPECTION - Lab Testing
1860d6b5-faa7-5e5b-a13b-0b7d41ce352f | note | CONFORMANCE CRITERIA - AP20 Bedding
2745a81a-2ef8-5ca5-af01-efdb6a281b67 | note | ○ Clegg hammer CIV = >35 in engineered fill, and within berm (if req'd) CIV = >25
1cfdbf1a-a7cb-5a2e-91b6-6e9b8e03fb0c | note | ○ Pea Metal Bedding
38e3d674-674f-5a72-9047-617d96ac5d77 | note | ○ Photo record of bedding.
749e2fc1-17a7-595f-babf-cc20eae947d0 | note | ○ NTLDM 7.8.7
3d1d11f5-728e-5ac3-88e4-4986afac1698 | note | RECORDS - LQS-CS-4101
a726f56b-31d0-4f21-a111-0a88f3620471 | checkpoint | 7 - Pipe Installation (2)
fdc9c085-adcd-5efb-95bb-a8d65b6f4980 | note | ACTION (Hold, Monitor, Witness) - W
61c06f69-6b18-5718-89e9-af903a01a195 | note | DETAIL - The pipe and fittings will be laid to within tolerance/specification.
30dee085-c876-524b-bd5d-074a5d1ef609 | note | FREQUENCY - Prior to backfilling
bb28bf3c-6b84-5243-8cf5-526592020600 | note | INSPECTION - Visual Inspection
48f5c770-f7fe-5a97-a7de-6402a263f593 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
72cb4a36-1183-5bed-b86d-184b50bf838f | note | RECORDS - As-Built
1251479b-d764-4094-893b-285b59a89d94 | checkpoint | 7 - Pipe Installation (3)
e205557d-23df-5558-b747-c35e54ac2c65 | note | ACTION (Hold, Monitor, Witness) - W
60f79a4f-7a58-57b2-96c1-4dff240390b5 | note | DETAIL - Pipe bends installed in the locations as per the drawings
4402f650-3250-5454-8593-155fd6a3f079 | note | FREQUENCY - Prior to backfilling
81530c38-e30e-5e18-b1e1-ca3313501e14 | note | INSPECTION - Visual Inspection
319bc403-32db-51b2-b405-d8edf18c7f1b | note | CONFORMANCE CRITERIA - Consistency with Construction Drawing
89bfe47b-a15c-5e97-889a-e0d618f0227b | note | RECORDS - Photo/As-Built
0959ca5b-d506-4214-a351-2ae0dec306b6 | checkpoint | 7 - Pipe Installation (4)
56ca0c5f-3107-5016-a716-062ab9a34f72 | note | ACTION (Hold, Monitor, Witness) - W
67aa5004-4176-5118-b8eb-306bbc2b6fa0 | note | DETAIL - Thrust blocks installed as required and per drawings
23cfbb75-c4df-5ea5-9d82-994f3ca68ebf | note | FREQUENCY - Prior to backfilling
c509ea9d-d6eb-5a4d-ab39-762c40e30cfb | note | INSPECTION - Visual Inspection
3f117427-9f48-5083-8730-aa759b303d43 | note | CONFORMANCE CRITERIA - 25 Mpa concrete unless otherwise stated, per design drawings
8c9fc191-8862-5861-916f-1bbc3629bfe3 | note | RECORDS - Delivery dockets
5cda91a3-923d-415b-984c-2ad7d44b9dba | checkpoint | 7 - Pipe Installation (5)
8f85493b-d9c4-5cf7-b759-48b389f53696 | note | ACTION (Hold, Monitor, Witness) - W
b8eefe19-5192-5267-866a-b6b7908cb93e | note | DETAIL - Denso to be applied to all steel fittings, bolts, nuts and washers
a37a6308-72a1-57d5-8e6b-26d26feecb7a | note | FREQUENCY - Prior to backfilling
469e1564-0ed7-5622-a1b5-060c83b0c1bc | note | INSPECTION - Visual Inspection
721a238e-ed79-5009-bc0a-670bdc336018 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
c6210f63-2217-5aab-ac1f-acf74c711876 | note | RECORDS - Photo
dee980af-34f7-41cf-a59c-63b86478a8ee | checkpoint | 7 - Pipe Installation (6)
297e39f1-833a-539a-b01d-263fa9f90faa | note | ACTION (Hold, Monitor, Witness) - W
605ab89f-e551-50c7-8352-0325835f0a34 | note | DETAIL - As built survey at 20m intervals and at each change in direction, and butt weld/EF
860b805a-8b4f-5d56-8afc-e28a15c70693 | note | FREQUENCY - Prior to backfilling
e30cdff4-6e35-5527-b856-72c65b10b861 | note | INSPECTION - Survey
e778c78e-23f3-5bdd-9dad-59156c3f5298 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
3fb81850-a10a-5761-96d0-7ef33a32a8c7 | note | RECORDS - As-Built
8252e543-f1f1-4664-9263-32e4e1979625 | checkpoint | 7 - Pipe Installation (7)
efe59203-aa0d-59a6-9036-8d215da06c7f | note | ACTION (Hold, Monitor, Witness) - W
88a057ae-b7d4-5ff6-bee0-b67101e09a48 | note | DETAIL - Approved Detector tape for Watermain to be installed 300mm above the pipe
34c9c245-bd9f-52e3-b568-90fc3be92b30 | note | FREQUENCY - Prior to backfilling
cd2575fa-1e10-5675-92ad-38a8f012fbe5 | note | INSPECTION - Visual
129ccc4f-dd43-5d9f-8c9c-a31e2958b7a4 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, SD702
509f401d-d54e-56f4-b71f-41bc87a9f3dd | note | RECORDS - LQS-CS-4101
d173a5c1-8ace-4305-b6cf-3204c0063b32 | checkpoint | 7 - Pipe Installation (8)
090c24f7-3626-5ada-8ef1-a9ee3d93c200 | note | ACTION (Hold, Monitor, Witness) - W
d7655a9f-4498-51f0-9a7b-b6a40da1c614 | note | DETAIL - Backfill compacted and tested in 200mm thick layers
c9663003-50de-58b1-8ac4-12ae1b6171ad | note | FREQUENCY - 1/20m length of pipe
26f5f803-9066-59a4-8bbd-fcfed96d6e11 | note | INSPECTION - Measure/Testing
05ebcd96-6b1f-50de-80b9-c54ad4ff675e | note | CONFORMANCE CRITERIA - <Subbase Layer
212c859e-fcd0-59a8-a7dd-6ea5fa3a16a3 | note | — Clegg CIV >25 for engineered fill. In berms, Photo record.
5ead0560-d41a-5606-be4a-3cc7bc209c5f | note | ○ Subbase Layer
32fbb55c-4aa7-5fcc-98a6-9a2f0ea2f123 | note | — 95% MDD under carriageway for engineered fill. In berms, Photo record
ecc0a581-4574-52d2-8449-d3ec4dcd8ca6 | note | ○ Basecourse Layer
5a95ee76-10fe-5601-b654-ad8c19183358 | note | — 98% MDD for engineered fill. In berms, Photo record
61ff4fdb-2b36-543f-9e06-2e8f22493c45 | note | RECORDS - Lab test Results/Photo/Clegg Sheet
fbca9770-6fdf-4e98-9dff-841c988eea7d | checkpoint | 8 - Hydrants and Valves (1)
bb754c2a-0a07-50b3-8a8d-365835196e3e | note | ACTION (Hold, Monitor, Witness) - H
5fd50804-2fc0-5ea8-8b2f-d2bbc694c724 | note | DETAIL - Fire Hydrant Lids shall be painted golden yellow. A yellow triangle shall be painted on or near the centre line of the road and RRPM. A yellow circle encircling the hydrant shall be painted if its location can be obscured by parked vehicles.
05f29f4c-a5d8-5960-b504-dbb748dd7216 | note | FREQUENCY - All fire hydrants
d5d1a2e7-c212-5751-be44-487e3b6c5a34 | note | INSPECTION - Painting
77761f5b-92ee-50b4-a344-10a215131122 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, SD709
1ce31c2d-8ced-5e51-bb8d-ec9f539fa28a | note | RECORDS - Photo
5604d88b-f44e-48fc-b994-4052f2f84eb7 | signoff | AUTHORITY HOLDPOINT
face18cb-552c-47ae-b88c-2118ed220a8d | checkpoint | 8 - Hydrants and Valves (2)
4508d964-4143-5485-b691-2bf37451de5e | note | ACTION (Hold, Monitor, Witness) - H
8255f8fe-d657-50bb-8a8e-edb170aca8ca | note | DETAIL - Marker plates on posts shall be installed near all watermain valves, if required. Valves to be painted to sepcification
8382227d-c514-5c0a-92c6-272248eaa0ba | note | FREQUENCY - All valves
6e957287-f1cc-542d-bffd-4913a69e298d | note | INSPECTION - Post installation
b87d4874-ad90-5f55-aac9-e8cbc1097f30 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM, SD709
29348265-d0e3-5f79-a67d-d0a8319adc84 | note | RECORDS - Photo
fe68a7c7-0874-4d57-bb15-635a76ef33a5 | signoff | AUTHORITY HOLDPOINT
2a4b52f4-b55b-4bae-9789-6c963520f33b | checkpoint | 9 - Inspection and Pretesting
7ed3e1c1-bf74-5b67-bbd1-1abf5cc189b4 | note | ACTION (Hold, Monitor, Witness) - H
0ebb7d4c-0586-54c4-b7b1-52aff3e4c1a1 | note | DETAIL - Watermain, service connections and fittings shall be flushed before testing
9061f828-aa00-512d-9825-aeb8210fb4da | note | FREQUENCY - Prior to Testing
26a12f43-df98-5fd9-aeba-cb79665e9452 | note | INSPECTION - Visual Inspection
87236dd7-b08b-5efc-82bf-cc24058834b2 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
fa0746ab-3e50-5279-9db5-514e6f91f183 | note | RECORDS - LQS-CS-4101
483040fc-10f9-4899-8b3c-0fa348c88d3f | signoff | AUTHORITY HOLDPOINT
4ede1148-5eac-41c5-8daa-6437ae3997e9 | checkpoint | 10 - Pre-commissioning (1)
10993c10-320d-59d2-b627-0392f3b743cd | note | ACTION (Hold, Monitor, Witness) - H
c1665434-45bd-5784-b3c2-5022668a2752 | note | DETAIL - All mains, service connections and fittings shall be pressure tested
ab64ec73-fe20-53df-8267-9d6158e9cdc3 | note | FREQUENCY - Prior to Pre-Commissioning
529826e0-88ad-5094-98a0-cf855aedbc43 | note | INSPECTION - Rebound Testing
e90cdf3b-8421-521b-b6d8-5c7521e35faf | note | CONFORMANCE CRITERIA - 1200kPa for treated water mains
aa8ef627-64b8-53aa-8b82-66340431b3eb | note | — 540kPa for DN375 raw water
8e2bccac-e430-5945-9a99-41f6f6c05088 | note | — 645kPa for DN450 raw water pipe
2fdf8848-ea9d-59a1-84b9-1f5d7da0676b | note | — 1350 kPa Wasterwater pipe
5bd7d80b-ab3c-59e5-ba6c-e5f43242ca79 | note | (1.5 x operating pressure rule of thumb)
4f38075e-edad-5e81-81f9-7e993e3c530f | note | RECORDS - Test results
511d5bd9-df97-4eeb-8fa7-abdec83001b5 | signoff | AUTHORITY HOLDPOINT
a250aafe-4922-4eed-9c2c-28bb32cd21db | checkpoint | 10 - Pre-commissioning (2)
46fc3320-1669-58e3-8d9a-1b1e0af1ab26 | note | ACTION (Hold, Monitor, Witness) - H
71ceb27b-bdab-58b4-88a3-f0244737e1e7 | note | DETAIL - Pipe sterilisation testing for the whole length. Once completed Chorinated water to be discharged
3099e816-0151-536e-9c94-c1db72ac2c7b | note | FREQUENCY - Prior to Commissioning
b8bc8e1d-172d-5748-af51-19b2423227a9 | note | INSPECTION - Residual Chlorine Test
9c4d1794-0eb6-5fe1-894a-cde034431f68 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
a3caf608-13bf-596c-a054-9c9fbb0a27dd | note | RECORDS - Test results
aec97447-466e-465d-a4ea-f988f5ed2c95 | signoff | AUTHORITY HOLDPOINT
b919e516-7568-42a7-b8d6-fc06a7758bbb | checkpoint | 10 - Pre-commissioning (3)
14572582-74ac-540a-afe3-655f781ef615 | note | ACTION (Hold, Monitor, Witness) - H
1a24733d-03f5-56d0-a5e5-48ac5a0ff29f | note | DETAIL - Bacteriological Test
a388796b-81a0-5e6a-ac0f-f2926c965e78 | note | FREQUENCY - Prior to Commissioning
10a68e10-7f4d-5f81-b4aa-8ec072f0a0f1 | note | INSPECTION - Tests
3480c5cf-e3d3-501f-b5a3-dd8f988c7dcc | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM. 0 E.coli present in pipe
529579fe-3cb5-59f2-8d11-50bf07496070 | note | RECORDS - Test results
b52ac991-83ca-404b-972f-357a76fb15e6 | signoff | AUTHORITY HOLDPOINT
f4a93107-3c17-425e-88b9-5fec3b6005fa | checkpoint | 11 - Shutdown
efcd4fda-c18f-5d14-b589-a825de06a082 | note | ACTION (Hold, Monitor, Witness) - H
beae9d79-f623-587b-8e22-765b3ef73f43 | note | DETAIL - Apply for Shutdown of Mains with diagram, site preparation plan and duration. Notify Council of Shutdown Commencement, carry out required work, notify Council of completion of works.
c464e3bd-de7e-5c1d-a1fd-4becb550df39 | note | FREQUENCY - Prior to programmed work
9b177898-bcb1-5a30-9fd6-3cb5e172a8ac | note | INSPECTION - Liaise with Council
9430f650-5673-5122-bfd1-730f34c8800a | note | CONFORMANCE CRITERIA - Completed shutdown plan approved by council
21116bb8-3418-589a-ab33-1ab3ff664a71 | note | RECORDS - Written approval from the Council
c686ada0-6298-40e0-b2ae-106923ffb531 | signoff | AUTHORITY HOLDPOINT
650a1cde-42cc-4580-bc11-e3cc3a0f7d8e | checkpoint | 12 - Tie-in and commissioning (1)
0a210045-919a-54a7-8fef-1e7115c1bae1 | note | ACTION (Hold, Monitor, Witness) - H
1a638bc8-b261-5c41-9604-a9353cfbd591 | note | DETAIL - Connection to existing water reticulation per specifiction
53a81ac2-a6a8-5e4f-8d67-2a7bdad0010a | note | FREQUENCY - During shutdown
77ea9741-d1ca-50a8-8267-ca8bc7b98254 | note | INSPECTION - Document review
d63f6112-587a-5228-95d5-eb3454377069 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
8a7991c3-b3b5-58de-9164-c71c6721a33f | note | RECORDS - Photos
65eeafdb-6192-4e7c-91ad-94a26d67342b | signoff | AUTHORITY HOLDPOINT
4ef5c0e0-1698-47d7-a3ed-42c20f57a204 | checkpoint | 12 - Tie-in and commissioning (2)
5c6f4178-fe49-50cc-a449-6232383b237f | note | ACTION (Hold, Monitor, Witness) - W
464da359-1d26-58b6-a6e2-27324822e915 | note | DETAIL - Post connection inspection
2e909913-ca6c-5841-980f-61c576a3ef81 | note | FREQUENCY - Completion of works
3f4c29ae-8a0a-5095-9d54-72637cab0e81 | note | INSPECTION - Visual
4c2eb171-836d-5842-8946-ec0a7d428570 | note | CONFORMANCE CRITERIA - Inspection
66dfebaf-d7d5-5494-9b77-94c0a3268f61 | note | RECORDS - Site confimation
dd0c1844-eab2-4dbf-a231-65096172e56a | checkpoint | 13 - Abandonment
cda30e3f-52e1-5851-b230-1a2ef41c0380 | note | ACTION (Hold, Monitor, Witness) - W
b7ec3b8b-2896-576c-9c8d-eee18abcfcc1 | note | DETAIL - Remove all fittings from disused watermains if required. Capping of ends of abandoned pipes
7dc8f63e-0aa3-558f-ba3f-d4e94db87b8a | note | FREQUENCY - After Tie-in
8db70651-d1c4-52ba-9222-8f98b6850f30 | note | INSPECTION - Document review
1c365721-982a-5f90-a0ec-8768bb04ea14 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
614cae6e-1874-5c4e-b279-505f4df5dd5d | note | RECORDS - Photos
802e4c50-00c6-46b0-8e48-d29d9f6eb636 | checkpoint | 14 - As-builts
db9d57f5-5b4b-5c04-9bf2-7a7f90d8530f | note | ACTION (Hold, Monitor, Witness) - H
3353cb65-affe-5569-87dc-bce6aba35d35 | note | DETAIL - Updated drawings to be submitted with As-built line and levels recorded
3751d159-79cb-51b7-bcb3-81c2a6058c2a | note | FREQUENCY - At the completion of the Lot of work
7fd21f39-110b-5d1e-9399-19c6e5ca19f8 | note | INSPECTION - Drawings
bd9672e5-081a-5e18-b9b6-4b87c4745878 | note | CONFORMANCE CRITERIA - Council Water Main Specification - NTLDM
6c4610c2-0ed6-5652-b18a-167a49f6e42b | note | RECORDS - Asbuilt Drawing
82206c32-d961-410e-99ba-cf796005ce8a | signoff | AUTHORITY HOLDPOINT
609986f8-a1be-4b5a-9d88-0a95e4cab8f7 | checkpoint | Final Inspection
c65c62df-06a4-5a97-b6c2-5a34a58a67b0 | textbox | QA Compiled By:
1b2b69bc-44b1-5df9-bb3d-eca991fc1265 | textbox | QA checked By Project Manager:
a6d416c2-a5e0-5602-a07b-e6da8a3cdb02 | textbox | Accepted By Design Engineer:
4b2641b4-996c-4cf3-ab74-65cd4c51073f | signoff | Sign ITP