## Bored Pile
|  |  |  | Process Control Plan |  | FHIMS-QA-6031 | Approved |  | Signature
|  |  |  | Contract Name: | Lower Queen St - Bridge Redevelopment |  | FH Engineer
|  |  |  | Procedure: | Bored Pile |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | LQS-CS-7031 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits | W | Obtain Permits | As required | Document Review | Control Checklist - Digging / Excavating (incl. marking out & potholing existing services), Notify Worksafe NZ if req. Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
2 | Pre-construction sign offs | W | Ensure that Sub-Contract and Supplier Agreements are signed, TMP is approved all Sub-Contractors and Suppliers are inducted to site | Prior to commencement | Document Review | Signed Subcontract and Supplier Agreements, TMP on M-Files and Induction Register updated | Subcontract and Supplier Agreements, Approved TMP & Updated Induction Register on sharefile | Site Engineer
3 | Design | W | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | — | Check Drawing Register | Site Engineer
4 | Survey Setout (1) | W | Set out grid around pile location. As per contract drawings and specification. | Prior to commencement | Survey | Consistency with Construction Drawing | As-built, photos | Site Engineer
4 | Survey Setout (2) | W | Verification of pile set-out by surveyor | Prior to commencement | Survey | Consistency with setout | As-built, photos | Site Engineer
5 | Material Compliance (1) | H | Concrete mix design(s) shall be submitted to the Design Engineer in writing at least 2 weeks prior to placing concrete and approved before placing concrete | Prior to commencement | Document review | — | Design Engineer Approval | Site Engineer | Design Engineer
5 | Material Compliance (2) | W | All concrete delivered to site shall be produced strictly in accordance with the approved mix design | Prior to pouring concrete | Concrete Delivery Dockets | — | Concrete Delivery Dockets | Site Engineer
5 | Material Compliance (3) | W | Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade called up on the drawings | Prior to ordering steel | Document review | AS/NZS4671&NZS3109 | Detail Sheets and Mill Certificates | Site Engineer
5 | Material Compliance (4) | H | Any welding or mechanical splicing to be approved in writing by the Design Engineer | Prior to welding or splicing | Document review | — | Mark Up As Built Drawings | Site Engineer | Design Engineer
5 | Material Compliance (5) | H | Any reinforcement requiring cutting or bending on site to be approved in writing by the Design Engineer | Prior to cutting or bending on site | Document review | — | Mark Up As Built Drawings | Site Engineer | Design Engineer
6 | Pile Line | H | Check if the bench has been excavated/filled can accommodate the entire pile line | Prior to Commencement | Visual Inspection | Relevant Drawing | LQS-CS-4011 | Site Engineer
7 | Permanent Steel Liners (If required) (1) | W | Check fabrication of casings | Prior to Commencement | Visual Inspection | Piling Specification | Photos | Site Engineer
7 | Permanent Steel Liners (If required) (2) | W | Check installation of casings | Each Pile | Visual Inspection | Piling Specification | Photos, As-Built | Site Engineer
8 | Drill Rig Set Up | W | Check drilling performance, verticality and position | Each Pile | Visual Inspection | Piling Specification, Relevant Drawings | LQS-CS-4011 & LQS-CS-4083 | Site Engineer
9 | Pile Bore Condition & Logs | H | Inspect pile bore condition, pile depth, rock socket length and toe level | Each Pile | Measure | Checklist completed | LQS-CS-4011 & LQS-CS-4083 | Site Engineer | Design Engineer
10 | Plug Driving Operations | H | Check driving performance, verticality and position | Each Pile | Checksheet | Piling Specification, Relevant Drawings | LQS-CS-4099 | Site Engineer | Design Engineer
11 | Reinforcement Cage (1) | W | Check supply and installation of reinforcement cage | Each Cage | Document Review & Visual Inspection | Relevant Drawings | LQS-CS-4011, Photos | Site Engineer
11 | Reinforcement Cage (2) | W | Arrange for inspection of installed reinforcement cage | Min 48 hours prior to pour | Visual Inspection | — | LQS-CS-4011 | Site Engineer | Design Engineer
12 | Concreting (1) | H | The Design Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required | Prior to concrete pour | Visual inspection | — | LQS-CS-4011 | Site Engineer | Design Engineer
12 | Concreting (2) | w | Concrete dockets checked for correct mix and concrete site testing undertaken if applicable | Prior to concrete pour | Test Results | Concrete Dockets | LQS-CS-4090 | Site Engineer
13 | As Builts | H | Survey final position and R.L. of each pile, produce As-Built drawings. Any other documentation provided per contract requirements | Each Pile | Measurement / Survey/As-built Diagram | As-Built Drawing uploaded into CONQA | Pile As-Built | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: