## Precast Installation
|  |  |  | Inpesction Test Plan |  | LQS-QA-6007 | Approved |  | Signature
|  |  |  | Contract Name: | Lower Queen St - Bridge Redevelopment |  | FH Engineer
|  |  |  | Procedure: | Precast Installation |  | FH Project Manager
Inspection & Test Plan / Checklist
Lot No: |  |  |  | Corresponding Work Instruction: |  | LQS-CS-7040 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | FH Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Permits (1) | W | Obtain Permits | As required | Document Review | Ensure all necessary Permit to Works & Controlled Checklists are in place | Permit attached or permit number noted | Site Engineer
1 | Permits (2) | W | Permit to Lift &/or Lift Study to be carried out | Prior to commencement | Document Review | Approval given by Project Manager | Permit to Lift | Site Engineer
2 | Design | W | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | — | Check Drawing Register | Site Engineer
3 | Survey Setout | W | Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations) | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
4 | Precast Installation (1) | H | No Precast Components are to be installed until FHIMS-QA-6049 has been completed and signed off for that item | Prior to commencement | Document Review | Process Control Plan, Checksheets & any other associated documentation is provided | LQS-QA-6049 | Site Engineer | Engineer Rep
4 | Precast Installation (2) | W | Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial to be done by the manufacturer onsite & an OFI to be completed | Prior to unloading | Visual | No Damage | Delivery Dockets | Site Engineer
4 | Precast Installation (3) | H | Ensure that other components are installed correctly (Rubber Pad etc.) and are approval given from Designer team before precast components are lifted into their final positions | Prior to commencement | Visual | Pads installed correctly | Photos | Site Engineer | Engineer Rep
4 | Precast Installation (4) | W | Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the risk control plan | Prior to commencement | Document Review | — | RCP | Site Engineer
5 | As-builts | H | As-built documentation provided per contract requirements | At the completion of the Lot of work | Drawings | — | Asbuilt Drawing | Site Engineer
Comments:
`
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/OFIs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Project Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: